## Findings and Actions
Topic | Source | Finding | Required action
Tender date sequence | TBOextension050526.pdf p1;250526 p1;090626 p1 | Submission:6 May→26 May→9 June→23 June2026,15:00IST. Unpriced opening:7 May→27 May→10 June→24 June2026,15:30IST. These notices share Tender ID2026_ONGC_273234_1. | Use23/24June as the latest dates evidenced by these supplied notices only. Actual opening, subsequent extensions and award are not independently confirmed.
SCC revision remains unresolved | Four Technical_SCC PDFs; SHA inventory | All four SCC uploads are byte-identical and match the earlier15-page SCC. No newly distinguishable revised SCC is established by this batch. | Keep the revised-SCC issue open; reconcile the controlled issue/transmittal against the23April addendum announcement. Do not infer revision from filename suffix.
A-3 revision remains unresolved | A-3 PRICE SCHEDULE sheet; SHA inventory | A-3 is byte-identical to the earlier supplied workbook. It is not proof of the announced revised A-3 version. | Maintain base workbook plus amendment overlays, including AddendumtoA3. Require positive version/issue mapping before final pricing and cash-flow approval.
A-10 obsolete lines require overlay | A-10 Milestone Payment Formula rows30-35,53-54; previous general Addendum | Uploaded A-10 still contains3% Mob and3% Demob lines. Previous general amendment deletes items12/13 and changes the repair-material-arrival milestone20%→25%. | Do not count those deleted separate payments in forecast receipts. Reconcile the entire amended milestone allocation and governing price base; do not assume rental/marine schedule lines are also deleted.
Completion and marine criteria | SCC p2 clauses2,3 | 12months from NOA. Monsoon16May–15October inclusive: conditional time relief for inability to work due to adverse weather, without extra mob/demob cost. Minimum60 special-personnel accommodation; minimum5tonne crane is for transfers, not proof of bridge lifting capability. | Use actual award, approved weather records and extension decisions. Engineer lift capacity at working radius using verified module/rigging weight, COG and marine conditions.
Marine compliance timing | SCC p3 clauses5.1–5.5 | Company predeployment and periodic audits apply. DGS phased lifeboat compliance in this source lists70% through15May2027 and100% beyond, with prior ONGC approval of phased compliance and additional provisions. | Check applicable current statutory requirements and company approvals at mobilisation; do not treat historical table as unconditional permission for a noncompliant vessel.
Painting and PPE acceptance | SCC p3 clause6; p9 clause8.5.3 | Paint applicator/manufacturer MOU and continuous manufacturer representative during platform maintenance painting are specified. PPE issue evidence is a work-start gate; non-use can cause stoppage and penalties as stated. | Include manufacturer attendance, joint-guarantee documentation, PPE issue/verification and replacement records in readiness and cost plans; reconcile P9 PPE list.
Delay records and e-measurement | SCC p13 clauses11,12 | Quarterly joint delay/progress analysis and monthly critical/near-critical activity logs are required. Daily measurements must enter digital e-MB; billing is linked to e-MB validation and approvals. | Add monthly signed logs, quarterly delay-review deliverables and e-MB/SES billing predecessors. Offline spreadsheets do not replace the required portal record; no portal entries were made.
LD and scrap disposal | SCC pp14-15 clauses13,14 | Progressive weekly LD slabs0.1/0.2/0.3/0.4%, capped as stated, include monsoon-rate provisions distinct from clause2 relief. Scrap handling, sea fastening, transport and handover at Nhava/Pipavav are contractor scope. | Model LD only against governing dates, scope bases and approved relief. Include scrap manifests, cargo capacity, port handling and handover evidence; reconcile A-10 named-port condition before claiming payment.
Technical qualification route | Technical BEC pp3-8 clauses5.1–5.4; original scanned11pages OCRed | Steel experience route explicitly states110MT in one project; marine route requires1000GT/GRT and6months/one construction season. Clauses5.3A/B specify consortium requirements unless the bidder also establishes the complementary experience. PM and qualifying main activities must be retained as specified. | Reconcile A-9 legacy350MT wording against these specific BEC clauses and amendments; record discrepancy formally. Qualification needs the full route and evidence, not110MT alone. No Shivansh eligibility determination made.
Deleted yard criterion versus execution capacity | Technical BEC p8 clause5.5; previous general Addendum | The original scanned BEC still contains yard-adequacy clause5.5; earlier general amendment deletes it. | Apply the deletion in bid evaluation. Continue execution-stage yard/resource capacity checks without presenting the deleted criterion as mandatory tender qualification.
TPI authentication | Technical BEC pp8,10-11 clause5.6 | Specified technical-BEC documents require empanelled TPI verification, original-authenticity wording and certificate; ONGC-issued experience documents and bidder self-undertakings have specified exclusions. Accreditation must be valid at verification date. | Check actual NABCB TypeA ISO/IEC17020 status and empanelment when appointing. Printed list includes expired dates; listing alone is not proof of current validity. Source is OCR; verify decisive wording against scans.
Financial qualification | General BEC DOCX paragraphs99,106 and surrounding financial section | Base financial section states turnover INR3,65,38,82,460 (365.388246crore) and working capital INR1,09,61,64,738 (109.6164738crore), with net-worth and evidence provisions. | Confirm amended applicability, financial-year rules, support/JV route and auditor certification using the complete financial section. These thresholds are eligibility criteria, not project budget or available funding.
Response forms and amendments | BRS workbook; BidderGTE workbook; ITB/GCC; P9 corrigenda | BRS and BidderGTE contents have no exact prior local hash match in this audit; this does not establish a new issued revision. Base forms must be read with corrigenda on45-day bid security, validity anchor, performance security and steel-origin evidence. | Complete clause-to-form matrix without fabricating confirmations. Cross-check BRS versus A-3 and actual priced/unpriced cover requirements; preserve base documents and amendment precedence.
Scope and source reuse | Specification Combined257pages; SOW/Bridge Report506pages; inventory | These are exact matches to prior local sources. Two SOW filenames are identical. Prior bridge geometry, source MTO discrepancies and design issues are not closed by re-upload. | Reuse prior analyses and retain references. Do not relabel tender GAs AFC or claim member/joint checks completed because the source set is repeated.

## File Inventory
Name | Bytes | SHA256 | Prior exact copies | Duplicate of | PDF pages
Specification Combined.pdf | 7076751 | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 3 |  | 257
TBOextension050526.pdf | 87134 | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 0 |  | 1
SOW & Bridge Report Combined (3).pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 2 |  | 506
TBOextension090626.pdf | 87471 | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 1 |  | 1
TBOextension250526.pdf | 285407 | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 0 |  | 1
SOW & Bridge Report Combined.pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 2 | SOW & Bridge Report Combined (3).pdf | 506
Technical_SCC (1).pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 4 |  | 15
Technical_SCC (2).pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 4 | Technical_SCC (1).pdf | 15
Technical_SCC (3).pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 4 | Technical_SCC (1).pdf | 15
Technical_SCC.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 4 | Technical_SCC (1).pdf | 15
Tendernotice_1 (1).pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 1 |  | 8
Tendernotice_1.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 1 | Tendernotice_1 (1).pdf | 8
Vol I _PartV_Appendix A-3 Price Schedule.xlsx | 480905 | 7b4e2c5849fc2b293e4de333dd3bb7b9893702fce99f93d01d637308b1d397a6 | 1
Vol I _PartVA_BRS.xlsx | 480805 | 872ba27d634dc202597837a32971bafa19c0eb54ac151f7c86f64bccd1d5d897 | 0
Vol I_ Part III Appendices.docx | 315676 | c1ef1672214f304f856d1a3bdb5f1a3c4d685f00e484907e5bc826d46155ca7f | 1
Vol I_PartIV_BEC.docx | 78107 | df1674f7946d9f62bfc169251d43ad05ee75549001c0d460408055e43b9818b2 | 1
Vol I _PartV_Appendix A-10 MPF.xlsx | 463605 | 3e1398fa91d52a60c14f78ba4aaccd1e2a3b90b8cc5046dc980561a45e712aa9 | 1
Vol I_PartIVA_BidderGTE.xlsx | 20715 | 73b9c45b583b3612ee2b8bcb5a0f95cfad5392979d3d697c8f9ff3c1664d5e02 | 0
Vol-I I ITB.docx | 208982 | 61033c9e7a297215977bdbf88dd81b3bca8073d17e7ae88f2ae7b57ce1fd58ae | 1
Vol_I_PartIV_ Technical BEC.pdf | 1654179 | d5548eb59f55cf6504d770c44e2dcd42b42392eb71541f36a742df9b089e3a7c | 1 |  | 11
Vol-I-II GCC.docx | 341696 | 78d8130c8aab9b96e9dad2584cb6c30be370c72dd71f154df103eb238b08f4a1 | 1
Vol I_PartIV_BEC - Copy.docx | 78107 | df1674f7946d9f62bfc169251d43ad05ee75549001c0d460408055e43b9818b2 | 1 | Vol I_PartIV_BEC.docx
Vol I_PartIVA_BidderGTE - Copy.xlsx | 20715 | 73b9c45b583b3612ee2b8bcb5a0f95cfad5392979d3d697c8f9ff3c1664d5e02 | 0 | Vol I_PartIVA_BidderGTE.xlsx
Vol-I I ITB - Copy.docx | 208982 | 61033c9e7a297215977bdbf88dd81b3bca8073d17e7ae88f2ae7b57ce1fd58ae | 1 | Vol-I I ITB.docx
Vol-I-II GCC - Copy.docx | 341696 | 78d8130c8aab9b96e9dad2584cb6c30be370c72dd71f154df103eb238b08f4a1 | 1 | Vol-I-II GCC.docx
Vol_I_PartIV_ Technical BEC - Copy.pdf | 1654179 | d5548eb59f55cf6504d770c44e2dcd42b42392eb71541f36a742df9b089e3a7c | 1 | Vol_I_PartIV_ Technical BEC.pdf | 11

## Extension Chronology
Notice | Submission IST | Unpriced opening IST | Status
050526 | 26May2026 15:00 | 27May2026 15:30 | Superseded by next supplied notice
250526 | 9June2026 15:00 | 10June2026 15:30 | Superseded by next supplied notice
090626 | 23June2026 15:00 | 24June2026 15:30 | Latest in supplied notice set; actual event unverified