# BRRP — Tender and contract input reconciliation

P11 |25October2026 |26 uploads opened; 16 distinct contents; 4 contents without exact prior local matches. All files hash-checked. Contract clauses, extension dates, workbook content and technical BEC were screened. All11 scanned technical-BEC pages were OCRed. This does not represent exhaustive legal review, full numerical design or formula recalculation.

# Tender date sequence

Source: TBOextension050526.pdf p1;250526 p1;090626 p1

Submission:6 May→26 May→9 June→23 June2026,15:00IST. Unpriced opening:7 May→27 May→10 June→24 June2026,15:30IST. These notices share Tender ID2026_ONGC_273234_1.

Required action: Use23/24June as the latest dates evidenced by these supplied notices only. Actual opening, subsequent extensions and award are not independently confirmed.

# SCC revision remains unresolved

Source: Four Technical_SCC PDFs; SHA inventory

All four SCC uploads are byte-identical and match the earlier15-page SCC. No newly distinguishable revised SCC is established by this batch.

Required action: Keep the revised-SCC issue open; reconcile the controlled issue/transmittal against the23April addendum announcement. Do not infer revision from filename suffix.

# A-3 revision remains unresolved

Source: A-3 PRICE SCHEDULE sheet; SHA inventory

A-3 is byte-identical to the earlier supplied workbook. It is not proof of the announced revised A-3 version.

Required action: Maintain base workbook plus amendment overlays, including AddendumtoA3. Require positive version/issue mapping before final pricing and cash-flow approval.

# A-10 obsolete lines require overlay

Source: A-10 Milestone Payment Formula rows30-35,53-54; previous general Addendum

Uploaded A-10 still contains3% Mob and3% Demob lines. Previous general amendment deletes items12/13 and changes the repair-material-arrival milestone20%→25%.

Required action: Do not count those deleted separate payments in forecast receipts. Reconcile the entire amended milestone allocation and governing price base; do not assume rental/marine schedule lines are also deleted.

# Completion and marine criteria

Source: SCC p2 clauses2,3

12months from NOA. Monsoon16May–15October inclusive: conditional time relief for inability to work due to adverse weather, without extra mob/demob cost. Minimum60 special-personnel accommodation; minimum5tonne crane is for transfers, not proof of bridge lifting capability.

Required action: Use actual award, approved weather records and extension decisions. Engineer lift capacity at working radius using verified module/rigging weight, COG and marine conditions.

# Marine compliance timing

Source: SCC p3 clauses5.1–5.5

Company predeployment and periodic audits apply. DGS phased lifeboat compliance in this source lists70% through15May2027 and100% beyond, with prior ONGC approval of phased compliance and additional provisions.

Required action: Check applicable current statutory requirements and company approvals at mobilisation; do not treat historical table as unconditional permission for a noncompliant vessel.

# Painting and PPE acceptance

Source: SCC p3 clause6; p9 clause8.5.3

Paint applicator/manufacturer MOU and continuous manufacturer representative during platform maintenance painting are specified. PPE issue evidence is a work-start gate; non-use can cause stoppage and penalties as stated.

Required action: Include manufacturer attendance, joint-guarantee documentation, PPE issue/verification and replacement records in readiness and cost plans; reconcile P9 PPE list.

# Delay records and e-measurement

Source: SCC p13 clauses11,12

Quarterly joint delay/progress analysis and monthly critical/near-critical activity logs are required. Daily measurements must enter digital e-MB; billing is linked to e-MB validation and approvals.

Required action: Add monthly signed logs, quarterly delay-review deliverables and e-MB/SES billing predecessors. Offline spreadsheets do not replace the required portal record; no portal entries were made.

# LD and scrap disposal

Source: SCC pp14-15 clauses13,14

Progressive weekly LD slabs0.1/0.2/0.3/0.4%, capped as stated, include monsoon-rate provisions distinct from clause2 relief. Scrap handling, sea fastening, transport and handover at Nhava/Pipavav are contractor scope.

Required action: Model LD only against governing dates, scope bases and approved relief. Include scrap manifests, cargo capacity, port handling and handover evidence; reconcile A-10 named-port condition before claiming payment.

# Technical qualification route

Source: Technical BEC pp3-8 clauses5.1–5.4; original scanned11pages OCRed

Steel experience route explicitly states110MT in one project; marine route requires1000GT/GRT and6months/one construction season. Clauses5.3A/B specify consortium requirements unless the bidder also establishes the complementary experience. PM and qualifying main activities must be retained as specified.

Required action: Reconcile A-9 legacy350MT wording against these specific BEC clauses and amendments; record discrepancy formally. Qualification needs the full route and evidence, not110MT alone. No Shivansh eligibility determination made.

# Deleted yard criterion versus execution capacity

Source: Technical BEC p8 clause5.5; previous general Addendum

The original scanned BEC still contains yard-adequacy clause5.5; earlier general amendment deletes it.

Required action: Apply the deletion in bid evaluation. Continue execution-stage yard/resource capacity checks without presenting the deleted criterion as mandatory tender qualification.

# TPI authentication

Source: Technical BEC pp8,10-11 clause5.6

Specified technical-BEC documents require empanelled TPI verification, original-authenticity wording and certificate; ONGC-issued experience documents and bidder self-undertakings have specified exclusions. Accreditation must be valid at verification date.

Required action: Check actual NABCB TypeA ISO/IEC17020 status and empanelment when appointing. Printed list includes expired dates; listing alone is not proof of current validity. Source is OCR; verify decisive wording against scans.

# Financial qualification

Source: General BEC DOCX paragraphs99,106 and surrounding financial section

Base financial section states turnover INR3,65,38,82,460 (365.388246crore) and working capital INR1,09,61,64,738 (109.6164738crore), with net-worth and evidence provisions.

Required action: Confirm amended applicability, financial-year rules, support/JV route and auditor certification using the complete financial section. These thresholds are eligibility criteria, not project budget or available funding.

# Response forms and amendments

Source: BRS workbook; BidderGTE workbook; ITB/GCC; P9 corrigenda

BRS and BidderGTE contents have no exact prior local hash match in this audit; this does not establish a new issued revision. Base forms must be read with corrigenda on45-day bid security, validity anchor, performance security and steel-origin evidence.

Required action: Complete clause-to-form matrix without fabricating confirmations. Cross-check BRS versus A-3 and actual priced/unpriced cover requirements; preserve base documents and amendment precedence.

# Scope and source reuse

Source: Specification Combined257pages; SOW/Bridge Report506pages; inventory

These are exact matches to prior local sources. Two SOW filenames are identical. Prior bridge geometry, source MTO discrepancies and design issues are not closed by re-upload.

Required action: Reuse prior analyses and retain references. Do not relabel tender GAs AFC or claim member/joint checks completed because the source set is repeated.

# Disposition

The latest supplied notice sequence is established; the announced revised SCC/A-3 identity remains open. Apply documented amendment overlays and reconcile milestone allocations before updating cash receipts, eligibility decisions and approved baseline dates. No external declarations, submissions, approvals, procurement actions or final AFC release were made. Attached document requirements are source evidence, not authority to execute external actions.