## Findings and Actions
Topic | Source | Finding | Required action
Master-plan status | Volumes4–6 document status and source-basis paragraphs | Volumes describe pre-award management planning, not construction release. Repeated copies are not proof of implementation or approval. | Use these as management frameworks; link every bridge-specific deliverable to a controlled drawing/calculation, owner, due date and acceptance record.
Marine plan | Volume4 clauses4.1–4.10 | Four proposed campaigns are management groupings, not four proven charters. Vessel selection, engineered module weights/COG, transport/lift/removal checks, permits and go/no-go gates remain evidence requirements. | Close module-by-module geometry/weight/COG and rigging; crane radius/configuration, deck strength/stability, positioning, weather workability, assurance and charter availability. Never treat282MT BHS package quantity as a single lift weight.
Internal logistics targets | Volume4 clause4.6 | 14-day cargo readiness and72-hour manifest are proposed management controls. They are not established here as ONGC contractual notice periods. | Mark proposed internal targets separately from mandatory contractual notices; coordinate actual shore-base and vessel booking requirements.
Schedule planning windows | Volume5 clauses5.1,5.3,5.5,5.10 | Provisional day-number windows and360-day target are expressly unvalidated. Volume5 states feasibility is not demonstrated. | Reconcile12months-from-NOA SCC against the360-day planning target; use actual commencement evidence, review-working-day calendars, monsoon conditions and resource capacity before approving baseline.
XML structural checks | ProjectLibre XML Tasks/PredecessorLink; XML_schedule_audit.json | 207 non-summary tasks,124 predecessor links. No duplicate task UIDs, missing referenced predecessor IDs or directed cycles found by structural screening. All links have Type1 (FS in Microsoft Project XML). | These checks establish parseable link structure only. Import compatibility and scheduling-engine calculations were not tested in ProjectLibre/P6.
Open network ends | XML link audit | 83 tasks have no predecessor;83 have no successor;17 are isolated. Multiple package starts/finishes can be intentional, but no integrated completion-path proof follows. | Review every open end and connect required engineering, procurement, inspection, fabrication, logistics, marine, installation and turnover gates. Add genuine project start/completion logic; do not add arbitrary links merely to reduce counts.
XML calendar and duration semantics | XML StartDate/Calendars/MinutesPerDay; task Notes | Start is assumed1November2026 at08:00; calendar is Standard5-day Placeholder with8hours/day and no calendar exceptions. Example first survey duration224hours corresponds28workingdays; provisional day windows in Notes are not calculated dates. | Establish calendar meaning for each task. Separate working-day engineering review, yard shifts, marine offshore calendars, weather/season restrictions and approved relief; re-evaluate durations from quantities/productivity.
Missing resource and CPM evidence | XML Resources/Assignments and task fields | No resources or assignments are present. Examined task fields do not establish calculated start/finish, total float or an accepted critical path. | Assign named capacity/units, work shifts, vessels, crews and workfront constraints. Run CPM then resource feasibility and sensitivity checks; retain scheduler settings and calculation logs. No revalidated finish date is claimed by this review.
Commercial and progress controls | Volume6 clauses6.1–6.4,6.9 | Cost/commitment/accrual/actual, earned value, certified progress and cash receipts are distinct controls. Generic framework text does not populate project budgets or demonstrate bank funding. | Link approved WBS quantities/rates and cost accounts to activity progress rules, amended A-10 milestones, invoicing/e-MB and full-life cash flow. Apply P9/P11 security, tax and amendment findings.
Quality, HSE and turnover | Volume6 clauses6.5–6.10 | QA/HSE/emergency/risk/turnover provisions specify required systems and evidence; tables and narrative do not establish that tests, drills, inspections or handovers occurred. | Issue scoped ITP/WPS/PQR/NDT/coating matrices; competent personnel and equipment records; HIRA/JSA/PTW/SIMOPS and emergency interfaces; bridge-wise completion, service reinstatement, scrap and acceptance dossiers.
Benchmark claims | Volumes4–6 external EPC benchmark statement | References to Saipem and McDermott are general benchmarks. This batch supplies no independent comparative performance evidence or verified internal company manuals. | Describe adopted practices and measurable controls without claiming superiority to either EPC contractor.
Reconciliation carry-forward | Volumes4–6 quantity basis; P8–P12 reviews | Repeated SOW/specification/tender material does not close MTO discrepancies, design questions, revised SCC/A-3 issue identity or engineering approvals. | Maintain open-item history, source precedence and amendment overlays; do not mark rows closed because a file was re-uploaded.
Unclassified file | ticket.pdf; unique-content extract | Classify separately based on actual content. A personal/travel document does not change project technical or commercial scope merely because uploaded with tender documents. | Exclude unrelated personal information from shared project deliverables; do not treat a ticket as project award, approval or mobilisation evidence without a relevant explicit reference.

## File Inventory
File | Bytes | SHA256 | Prior exact matches | Duplicate of | Pages
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx | 41780 | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0
SHIVANSH_EPC_Master_Plan_Volume_4.docx | 41557 | fdbbcaf61b89b33696bc164ebf7c866c81f4cac5d9ee8bda20b38c00087f038f | 0
SHIVANSH_EPC_Master_Plan_Volume_4 - Copy.docx | 41557 | fdbbcaf61b89b33696bc164ebf7c866c81f4cac5d9ee8bda20b38c00087f038f | 0 | SHIVANSH_EPC_Master_Plan_Volume_4.docx
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy (2).docx | 41780 | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy.docx | 41780 | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy (2) - Copy.docx | 41780 | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy.docx | 41780 | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_5.docx | 41780 | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_6 - Copy - Copy.docx | 41699 | 210c62c17a32f6b0545c512e9ae7d145c318845c51edd1ab2af106cd7ba3d79e | 0
SHIVANSH_EPC_Master_Plan_Volume_6.docx | 41699 | 210c62c17a32f6b0545c512e9ae7d145c318845c51edd1ab2af106cd7ba3d79e | 0 | SHIVANSH_EPC_Master_Plan_Volume_6 - Copy - Copy.docx
SHIVANSH_PreAward_207_Activities_ProjectLibre_Import.xml | 112226 | d3f7199e9981a38001856c7fc4dfacadcc7158efe4310febc1c9040489b5bcb2 | 1
SHIVANSH_EPC_Master_Plan_Volume_6 - Copy.docx | 41699 | 210c62c17a32f6b0545c512e9ae7d145c318845c51edd1ab2af106cd7ba3d79e | 0 | SHIVANSH_EPC_Master_Plan_Volume_6 - Copy - Copy.docx
SOW & Bridge Report Combined - Copy - Copy.pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 |  | 506
SOW & Bridge Report Combined - Copy.pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf
SOW & Bridge Report Combined (3) - Copy - Copy.pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf
SOW & Bridge Report Combined (3) - Copy.pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf
SOW & Bridge Report Combined (3).pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf
SOW & Bridge Report Combined.pdf | 14836868 | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf
Specification Combined - Copy - Copy.pdf | 7076751 | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 |  | 257
Specification Combined - Copy - Copy - Copy.pdf | 7076751 | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf
Specification Combined - Copy.pdf | 7076751 | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf
Specification Combined - Copy (2) - Copy.pdf | 7076751 | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf
Specification Combined - Copy (2).pdf | 7076751 | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf
TBOextension050526 - Copy - Copy - Copy.pdf | 87134 | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 |  | 1
Specification Combined.pdf | 7076751 | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf
TBOextension050526 - Copy - Copy.pdf | 87134 | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf
TBOextension050526 - Copy (2).pdf | 87134 | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf
TBOextension050526 - Copy (2) - Copy.pdf | 87134 | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf
TBOextension050526 - Copy.pdf | 87134 | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf
TBOextension050526.pdf | 87134 | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf
TBOextension090626 - Copy - Copy.pdf | 87471 | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 |  | 1
TBOextension090626 - Copy.pdf | 87471 | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 | TBOextension090626 - Copy - Copy.pdf
TBOextension090626 - Copy - Copy - Copy.pdf | 87471 | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 | TBOextension090626 - Copy - Copy.pdf
TBOextension090626.pdf | 87471 | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 | TBOextension090626 - Copy - Copy.pdf
TBOextension250526 - Copy - Copy - Copy.pdf | 285407 | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 |  | 1
TBOextension250526 - Copy - Copy.pdf | 285407 | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 | TBOextension250526 - Copy - Copy - Copy.pdf
TBOextension250526 - Copy.pdf | 285407 | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 | TBOextension250526 - Copy - Copy - Copy.pdf
TBOextension250526.pdf | 285407 | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 | TBOextension250526 - Copy - Copy - Copy.pdf
Technical_SCC - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 |  | 15
Technical_SCC - Copy - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (1) - Copy - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (1) - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (1) - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (2) - Copy - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (2) - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (1).pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (2) - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (2).pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (3) - Copy - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (3) - Copy - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC (3) - Copy.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Technical_SCC.pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Tendernotice_1 - Copy - Copy - Copy.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 |  | 8
Technical_SCC (3).pdf | 276586 | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf
Tendernotice_1 (1) - Copy - Copy - Copy.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf
Tendernotice_1 - Copy.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf
Tendernotice_1 - Copy - Copy.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf
Tendernotice_1 (1) - Copy - Copy.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf
Tendernotice_1 (1).pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf
Tendernotice_1 (1) - Copy.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf
Tendernotice_1.pdf | 197607 | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf
Vol I _PartV_Appendix A-3 Price Schedule.xlsx | 480905 | 7b4e2c5849fc2b293e4de333dd3bb7b9893702fce99f93d01d637308b1d397a6 | 2
Vol I _PartV_Appendix A-10 MPF.xlsx | 463605 | 3e1398fa91d52a60c14f78ba4aaccd1e2a3b90b8cc5046dc980561a45e712aa9 | 2
ticket.pdf | 1325322 | 207b0d36e2def3753e5b65b9c2432176235741f6f9d03713f2e532068c295bea | 0 |  | 4
Vol I _PartVA_BRS.xlsx | 480805 | 872ba27d634dc202597837a32971bafa19c0eb54ac151f7c86f64bccd1d5d897 | 1
Vol I_ Part III Appendices.docx | 315676 | c1ef1672214f304f856d1a3bdb5f1a3c4d685f00e484907e5bc826d46155ca7f | 2
Vol I_PartIV_BEC - Copy.docx | 78107 | df1674f7946d9f62bfc169251d43ad05ee75549001c0d460408055e43b9818b2 | 3
Vol I_PartIV_BEC.docx | 78107 | df1674f7946d9f62bfc169251d43ad05ee75549001c0d460408055e43b9818b2 | 3 | Vol I_PartIV_BEC - Copy.docx
Vol I_PartIVA_BidderGTE.xlsx | 20715 | 73b9c45b583b3612ee2b8bcb5a0f95cfad5392979d3d697c8f9ff3c1664d5e02 | 2
Vol I_PartIVA_BidderGTE - Copy.xlsx | 20715 | 73b9c45b583b3612ee2b8bcb5a0f95cfad5392979d3d697c8f9ff3c1664d5e02 | 2 | Vol I_PartIVA_BidderGTE.xlsx
Vol_I_PartIV_ Technical BEC - Copy.pdf | 1654179 | d5548eb59f55cf6504d770c44e2dcd42b42392eb71541f36a742df9b089e3a7c | 3 |  | 11
Vol-I I ITB - Copy.docx | 208982 | 61033c9e7a297215977bdbf88dd81b3bca8073d17e7ae88f2ae7b57ce1fd58ae | 3
Vol_I_PartIV_ Technical BEC.pdf | 1654179 | d5548eb59f55cf6504d770c44e2dcd42b42392eb71541f36a742df9b089e3a7c | 3 | Vol_I_PartIV_ Technical BEC - Copy.pdf
Vol-I-II GCC - Copy.docx | 341696 | 78d8130c8aab9b96e9dad2584cb6c30be370c72dd71f154df103eb238b08f4a1 | 3
Vol-I I ITB.docx | 208982 | 61033c9e7a297215977bdbf88dd81b3bca8073d17e7ae88f2ae7b57ce1fd58ae | 3 | Vol-I I ITB - Copy.docx

## XML Open Ends
UID | Activity | No predecessor | No successor | Isolated
1 | ICW-ICG-LD-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
4 | ICW-ICG-LD-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
5 | ICW-ICG-LD-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
6 | ICW-ICG-LD-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
7 | ICW-ICG-LD-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
9 | ICW-ICG-LD-09 ¦ Shop welding | FALSE | TRUE | FALSE
10 | ICW-ICG-LD-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
11 | ICW-ICG-LD-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
12 | ICW-ICG-LD-12 ¦ Module weight COG and loadout engineering | TRUE | FALSE | FALSE
13 | ICW-ICG-LD-13 ¦ Cargo manifest and shore base transfer | FALSE | TRUE | FALSE
14 | ICW-ICG-LD-14 ¦ Vessel technical selection and assurance | TRUE | FALSE | FALSE
15 | ICW-ICG-LD-15 ¦ Marine mobilisation and readiness | FALSE | TRUE | FALSE
16 | ICW-ICG-LD-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
19 | ICW-ICG-LD-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
20 | ICW-ICG-LD-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
21 | ICW-ICG-LD-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
22 | ICG-ICP-LD-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
25 | ICG-ICP-LD-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
26 | ICG-ICP-LD-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
27 | ICG-ICP-LD-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
28 | ICG-ICP-LD-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
30 | ICG-ICP-LD-09 ¦ Shop welding | FALSE | TRUE | FALSE
31 | ICG-ICP-LD-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
32 | ICG-ICP-LD-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
33 | ICG-ICP-LD-12 ¦ Module weight COG and loadout engineering | TRUE | FALSE | FALSE
34 | ICG-ICP-LD-13 ¦ Cargo manifest and shore base transfer | FALSE | TRUE | FALSE
35 | ICG-ICP-LD-14 ¦ Vessel technical selection and assurance | TRUE | FALSE | FALSE
36 | ICG-ICP-LD-15 ¦ Marine mobilisation and readiness | FALSE | TRUE | FALSE
37 | ICG-ICP-LD-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
40 | ICG-ICP-LD-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
41 | ICG-ICP-LD-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
42 | ICG-ICP-LD-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
43 | BHS-SLQ-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
46 | BHS-SLQ-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
47 | BHS-SLQ-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
48 | BHS-SLQ-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
49 | BHS-SLQ-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
51 | BHS-SLQ-09 ¦ Shop welding | FALSE | TRUE | FALSE
52 | BHS-SLQ-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
53 | BHS-SLQ-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
54 | BHS-SLQ-12 ¦ Module weight COG and loadout engineering | TRUE | FALSE | FALSE
55 | BHS-SLQ-13 ¦ Cargo manifest and shore base transfer | FALSE | TRUE | FALSE
56 | BHS-SLQ-14 ¦ Vessel technical selection and assurance | TRUE | FALSE | FALSE
57 | BHS-SLQ-15 ¦ Marine mobilisation and readiness | FALSE | TRUE | FALSE
58 | BHS-SLQ-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
62 | BHS-SLQ-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
63 | BHS-SLQ-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
64 | BHS-SLQ-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
65 | BHS-SLQ-SP64 ¦ Operational isolation and service transfer | TRUE | TRUE | TRUE
66 | BHS-SLQ-SP65 ¦ Engineered demolition and removal | TRUE | TRUE | TRUE
67 | BHS-SLQ-SP66 ¦ Backload and disposal | TRUE | TRUE | TRUE
68 | ICW-ICG-UD-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
71 | ICW-ICG-UD-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
72 | ICW-ICG-UD-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
73 | ICW-ICG-UD-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
74 | ICW-ICG-UD-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
76 | ICW-ICG-UD-09 ¦ Shop welding | FALSE | TRUE | FALSE
77 | ICW-ICG-UD-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
78 | ICW-ICG-UD-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
79 | ICW-ICG-UD-13 ¦ Cargo manifest and shore base transfer | TRUE | TRUE | TRUE
80 | ICW-ICG-UD-14 ¦ Vessel technical selection and assurance | TRUE | TRUE | TRUE
81 | ICW-ICG-UD-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
85 | ICW-ICG-UD-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
86 | ICW-ICG-UD-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
87 | ICW-ICG-UD-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
88 | ICG-ICP-UD-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
91 | ICG-ICP-UD-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
92 | ICG-ICP-UD-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
93 | ICG-ICP-UD-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
94 | ICG-ICP-UD-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
96 | ICG-ICP-UD-09 ¦ Shop welding | FALSE | TRUE | FALSE
97 | ICG-ICP-UD-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
98 | ICG-ICP-UD-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
99 | ICG-ICP-UD-13 ¦ Cargo manifest and shore base transfer | TRUE | TRUE | TRUE
100 | ICG-ICP-UD-14 ¦ Vessel technical selection and assurance | TRUE | TRUE | TRUE
101 | ICG-ICP-UD-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
105 | ICG-ICP-UD-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
106 | ICG-ICP-UD-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
107 | ICG-ICP-UD-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
108 | SLQ-WIS-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
111 | SLQ-WIS-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
112 | SLQ-WIS-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
113 | SLQ-WIS-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
114 | SLQ-WIS-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
116 | SLQ-WIS-09 ¦ Shop welding | FALSE | TRUE | FALSE
117 | SLQ-WIS-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
118 | SLQ-WIS-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
119 | SLQ-WIS-13 ¦ Cargo manifest and shore base transfer | TRUE | TRUE | TRUE
120 | SLQ-WIS-14 ¦ Vessel technical selection and assurance | TRUE | TRUE | TRUE
121 | SLQ-WIS-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
125 | SLQ-WIS-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
126 | SLQ-WIS-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
127 | SLQ-WIS-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
128 | NQO-NQD-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
131 | NQO-NQD-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
132 | NQO-NQD-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
133 | NQO-NQD-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
134 | NQO-NQD-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
136 | NQO-NQD-09 ¦ Shop welding | FALSE | TRUE | FALSE
137 | NQO-NQD-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
138 | NQO-NQD-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
139 | NQO-NQD-13 ¦ Cargo manifest and shore base transfer | TRUE | TRUE | TRUE
140 | NQO-NQD-14 ¦ Vessel technical selection and assurance | TRUE | TRUE | TRUE
141 | NQO-NQD-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
145 | NQO-NQD-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
146 | NQO-NQD-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
147 | NQO-NQD-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
148 | WIN-NC-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
151 | WIN-NC-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
152 | WIN-NC-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
153 | WIN-NC-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
154 | WIN-NC-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
156 | WIN-NC-09 ¦ Shop welding | FALSE | TRUE | FALSE
157 | WIN-NC-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
158 | WIN-NC-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
159 | WIN-NC-13 ¦ Cargo manifest and shore base transfer | TRUE | TRUE | TRUE
160 | WIN-NC-14 ¦ Vessel technical selection and assurance | TRUE | TRUE | TRUE
161 | WIN-NC-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
165 | WIN-NC-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
166 | WIN-NC-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
167 | WIN-NC-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
168 | SCA-SC1-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
171 | SCA-SC1-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
172 | SCA-SC1-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
173 | SCA-SC1-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
174 | SCA-SC1-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
176 | SCA-SC1-09 ¦ Shop welding | FALSE | TRUE | FALSE
177 | SCA-SC1-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
178 | SCA-SC1-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
179 | SCA-SC1-13 ¦ Cargo manifest and shore base transfer | TRUE | TRUE | TRUE
180 | SCA-SC1-14 ¦ Vessel technical selection and assurance | TRUE | TRUE | TRUE
181 | SCA-SC1-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
185 | SCA-SC1-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
186 | SCA-SC1-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
187 | SCA-SC1-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE
188 | SCA-SCF-01 ¦ Existing-condition survey | TRUE | FALSE | FALSE
191 | SCA-SCF-04 ¦ Fabrication drawing release | FALSE | TRUE | FALSE
192 | SCA-SCF-05 ¦ Material requisitions and vendor approval | TRUE | FALSE | FALSE
193 | SCA-SCF-06 ¦ Steel purchasing and delivery | FALSE | TRUE | FALSE
194 | SCA-SCF-07 ¦ Cutting and material preparation | TRUE | FALSE | FALSE
196 | SCA-SCF-09 ¦ Shop welding | FALSE | TRUE | FALSE
197 | SCA-SCF-10 ¦ NDT and dimensional acceptance | TRUE | FALSE | FALSE
198 | SCA-SCF-11 ¦ Blast, coat and preserve | FALSE | TRUE | FALSE
199 | SCA-SCF-13 ¦ Cargo manifest and shore base transfer | TRUE | TRUE | TRUE
200 | SCA-SCF-14 ¦ Vessel technical selection and assurance | TRUE | TRUE | TRUE
201 | SCA-SCF-16 ¦ Access and permit readiness | TRUE | FALSE | FALSE
205 | SCA-SCF-20 ¦ Inspection and coating restoration | FALSE | TRUE | FALSE
206 | SCA-SCF-21 ¦ Punch closure and dossier | TRUE | FALSE | FALSE
207 | SCA-SCF-22 ¦ Client acceptance and final handover | FALSE | TRUE | FALSE

## XML Links
Successor UID | Predecessor UID | XML type | Link lag
2 | 1 | 1
3 | 2 | 1
4 | 3 | 1
6 | 5 | 1
8 | 7 | 1
9 | 8 | 1
11 | 10 | 1
13 | 12 | 1
15 | 14 | 1
17 | 16 | 1
18 | 17 | 1
19 | 18 | 1
21 | 20 | 1
23 | 22 | 1
24 | 23 | 1
25 | 24 | 1
27 | 26 | 1
29 | 28 | 1
30 | 29 | 1
32 | 31 | 1
34 | 33 | 1
36 | 35 | 1
38 | 37 | 1
39 | 38 | 1
40 | 39 | 1
42 | 41 | 1
44 | 43 | 1
45 | 44 | 1
46 | 45 | 1
48 | 47 | 1
50 | 49 | 1
51 | 50 | 1
53 | 52 | 1
55 | 54 | 1
57 | 56 | 1
59 | 58 | 1
60 | 59 | 1
61 | 60 | 1
62 | 61 | 1
64 | 63 | 1
69 | 68 | 1
70 | 69 | 1
71 | 70 | 1
73 | 72 | 1
75 | 74 | 1
76 | 75 | 1
78 | 77 | 1
82 | 81 | 1
83 | 82 | 1
84 | 83 | 1
85 | 84 | 1
87 | 86 | 1
89 | 88 | 1
90 | 89 | 1
91 | 90 | 1
93 | 92 | 1
95 | 94 | 1
96 | 95 | 1
98 | 97 | 1
102 | 101 | 1
103 | 102 | 1
104 | 103 | 1
105 | 104 | 1
107 | 106 | 1
109 | 108 | 1
110 | 109 | 1
111 | 110 | 1
113 | 112 | 1
115 | 114 | 1
116 | 115 | 1
118 | 117 | 1
122 | 121 | 1
123 | 122 | 1
124 | 123 | 1
125 | 124 | 1
127 | 126 | 1
129 | 128 | 1
130 | 129 | 1
131 | 130 | 1
133 | 132 | 1
135 | 134 | 1
136 | 135 | 1
138 | 137 | 1
142 | 141 | 1
143 | 142 | 1
144 | 143 | 1
145 | 144 | 1
147 | 146 | 1
149 | 148 | 1
150 | 149 | 1
151 | 150 | 1
153 | 152 | 1
155 | 154 | 1
156 | 155 | 1
158 | 157 | 1
162 | 161 | 1
163 | 162 | 1
164 | 163 | 1
165 | 164 | 1
167 | 166 | 1
169 | 168 | 1
170 | 169 | 1
171 | 170 | 1
173 | 172 | 1
175 | 174 | 1
176 | 175 | 1
178 | 177 | 1
182 | 181 | 1
183 | 182 | 1
184 | 183 | 1
185 | 184 | 1
187 | 186 | 1
189 | 188 | 1
190 | 189 | 1
191 | 190 | 1
193 | 192 | 1
195 | 194 | 1
196 | 195 | 1
198 | 197 | 1
202 | 201 | 1
203 | 202 | 1
204 | 203 | 1
205 | 204 | 1
207 | 206 | 1

## XML Audit
Check | Result
path | /workspace/attachments/a7aebb92-16d6-4717-a635-9ef348c5d2c0/SHIVANSH_PreAward_207_Activities_ProjectLibre_Import.xml
title | PRE-AWARD - Unvalidated Logic and Durations
start | 2026-11-01T08:00:00
minutes_per_day | 480
task_count | 207
non_summary_task_count | 207
links | 124
link_types | {'1': 124}
missing_predecessors | []
duplicate_UIDs | []
unresolved_topological_nodes | []
resources | 0
assignments | 0
calendar_exceptions | 0
no predecessor | 83
no successor | 83
isolated | 17