## START HERE
Control | Current disposition
Issue | P14 Rev0 ¦25October2026 ¦ Consolidated management-development package
Baseline status | NOT APPROVED; no actual NOA/progress/capacity or funding independently established
Latest batch | 68 supplied;67 opened;52 distinct contents;7 distinct contents without prior local hash match
Transfer exception | SHIVANSH ONGC Offshore Bridges - PRELIMINARY.pdf exceeds32MiB; not reviewed
Prior batch | P13:76 opened;21 distinct; XML207tasks/124links screened
Authoritative use | Management requirements/registers implemented here; technical design, actual execution and external approvals require their evidence
Planning scenario | 285activities,1Nov2026 assumed start; base finish6Apr2028, not an approved forecast
Scenario meaning | Explicit named resource sequencing; office/yard/offshore calendars; unverified engineering/productivity/supply inputs
Financial use | Blank inputs mean missing; no completed funding or EAC claim
Source controls | P8–P13 remain source evidence; P14 is consolidated management index and scenario, not a superseding contract
Progress | No actual work performed inferred from planning spreadsheets
Revision | Preserve uploaded originals; update P14 under change control

## CEO Decisions
Priority | Decision | Owner | Required evidence | Trigger | Status
P1 | Confirm NOA/start, governing SCC/A3 and applicability | Contracts | Controlled issue list and actual award | Before baseline | OPEN
P1 | Freeze bridge scope and resolve MTO/bearing/load conflicts | Engineering | Survey, corrected MTO and design queries | Before affected PO/AFC | OPEN
P1 | Validate target feasibility and seasonal strategy | Project Director | Approved dates, capacity and supplier/vessel offers | Before completion commitment | OPEN
P1 | Fund full execution and commercial exposure | Finance | Priced estimate, term sheet and cash stress | Before commitments | OPEN
P1 | Nominate and verify delivery capacity | Project Director | People, design teams, fabrication/NDT/coating and marine commitments | Before mobilisation | OPEN
P1 | Approve stage-specific design/marine assurance | Engineering/Marine | Independent checked calculations and accepted procedures | Before field release | OPEN
P2 | Adopt progress/e-MB and completion boundaries | Controls | Contract weights, signed rules and turnover matrix | Before first progress claim | OPEN
P2 | Resolve large-file transfer exception | Document Control | Readable split PDF or equivalent verified source | Before claiming complete source review | OPEN

## A-Z Execution Plan
Code | Workstream | Accountable role | Inputs | Required procedure | Acceptance evidence | Control measure | Source
A | Accountability and authority | Project Director | NOA/contract, scope split and corporate delegation | Appoint named managers and deputies; record availability and competing commitments; establish RACI; set spending/change/technical-release authority; chair weekly integration review. | Signed organisation/RACI and delegated-authority register | Named accountable owner for each control; no unidentified release authority | SCC1; Technical BEC5.2–5.4
B | Baseline and requirements | Contracts Manager | Tender, addenda/corrigenda, source drawing register | Maintain clause-to-deliverable matrix; resolve SCC/GCC precedence using B-4; link revisions and deletions; isolate S&SRP references; freeze controlled scope by bridge and retain open discrepancies. | Approved requirements and scope baseline; assumption/change log | Every requirement has source, owner, verification and disposition | P8–P12; CQ replies; B-4
C | Contract, qualification and compliance | Contracts Manager | Actual bidding route, experience evidence and amendments | Check110MT/marine route and consortium exceptions; retain PM/qualifying main activity; obtain subcontract commitments; verify TPI authentication and valid accreditation; reconcile financial evidence; manage securities and integrity-pact disclosures. | Qualification/compliance matrix and evidence bundle | No unsupported bidder confirmations or expired verification evidence | Technical BEC5; P9/P11
D | Design basis and survey | Engineering Manager | BRRP criteria, tender GAs and survey access | Verify coordinates, elevations, spans, clearances, member sizes/thickness/loss, support movement, piping/cable loads and NDT; create controlled datums; close bearing/camber/load discrepancies; record later company instructions under change control. | Accepted survey dossier and bridge-specific design basis | Survey-derived geometry and load status visible on every engineering package | CriteriaPartII; Corrigendum3 GCC2.3.6
E | Engineering and independent checking | Engineering Manager | Accepted survey, criteria, scope and discipline interfaces | Analyse bridge and supporting platforms, members/joints, bearings, fatigue/VIV, preservice lifts/transport and temporary stages; iterate piping reactions; detail connections; perform independent check and comment closure; submit through controlled DCI. | Checked calculations, interface reactions, design reports and accepted drawings | No source-study utilisation ratio represented as new design proof | C8; Combined1Annexure1; DesignCriteria
F | Fabrication drawings and AFC release | Lead Structural Engineer | Accepted mother analysis and verified geometry | Issue source-to-detail mapping, shop GAs, member/cut lists, joint/weld maps, bearing/guides, padeyes/supports and temporary-stability details; apply source revisions and CRS; independent check then company/CA release as applicable. | Signed bridge-specific release index with matching drawing/MTO/procedure revisions | AFC status requires actual authorised approval and field-copy control | C8 mother documents; Combined1 pp27–41
G | Geometry, MTO and weight control | Quantity/Weight Engineer | Released model/drawings and field verification | Separate new bridge, strengthening, new landing, existing landing, demolition and finish quantities; resolve1MT/2m/1m² discrepancies; calculate member-length/plate/bolt/weld/coating MTO and wastage explicitly; track module dry/wet/rigging weights and COG. | Traceable MTO revisions, reconciliation and verified module weight report | No bulk tonnage substituted for lift weight, member BOM or coating area | SOW quantity table; MTOIRT; Criteria weight/COG trigger
H | HSE and SIMOPS | HSE Manager | Workfront hazards, operating platform and vessel requirements | Complete HIRA/JSA/PTW, isolation/LOTO, hot work, gas testing, work-at-height/rescue, dropped objects, scaffold/access, marine transfers, occupational exposure and emergency interfaces; train staff; issue certified PPE and validate work-start clearance. | Approved HSE/SIMOPS plan, personnel matrix and permit packs | Zero work starts without applicable permits, isolation and readiness evidence | SCC7/8; PPElist; OISD155 applicability
I | Interface and operations management | Interface Manager | Platform operations, engineering and contractors | Register structural/piping/electrical/instrument/telecom/firewater interfaces; agree outage and transfer sequence; assign tie-in owners; confirm access and emergency routes; track support reactions and dimensional tolerances; resolve NQO/NOQ naming. | Signed interface agreements, outage windows and battery-limit register | No unowned interface on lookahead or lift plan | SCC1.7; Combined1/2/3
J | Joint inspections and quality assurance | QA/QC Manager | Project quality plan, codes, specifications and approved ITP | Set inspection/hold/witness points; qualify welding and personnel; control heat/consumable traceability; calibrate instruments; inspect fit-up/weld/NDT/coating/dimensions; repair and close NCRs; issue releases and indexed records. | ITP, qualification dossiers, inspection releases and NCR closure | No concealed work or next-stage release through an unresolved hold point | FS2009F; FS2005Rev9; C8
K | Key suppliers and procurement | Procurement Manager | Approved requisition, MTO, PS and compliant sources | Package25 procurement scopes; RFQ and technical/commercial evaluation; verify SVL12.3 status/product/location, steel melt/pour/DVA and traceability; obtain PS approvals, place authorised PO, expedite and inspect; preserve vendor-data dependencies. | PO/delivery/inspection register with quoted dates and evidence | No unpriced allowance treated as commitment; no silent substitution | SVL12.3 Combined3 pp261–341; Corr3; C8
L | Logistics, loadout and preservation | Logistics Manager | Released modules, lifting/transport studies and cargo slots | Verify shore-base storage/load capacity, route permits, lifting gear and packing/preservation; produce cargo ID/weight/COG/manifests; sea fasten and inspect loadout; monitor voyage/receipt and backload; segregate quarantine and accepted stock. | Approved loadout/transport pack, manifests and receipt reports | Cargo release ties to exact module/drawing/weight revision | SCC14; C9/C10; applicable marine assurance
M | Marine engineering and assurance | Marine Manager | Module envelope, vessel particulars and environmental data | Verify actual-radius crane charts, dynamics/rigging/padeyes, deck strength/stability, seafastening/voyage, positioning/mooring/DP, subsea hazards, access/POB and certificates; obtain applicable MWS/company clearances and predeployment audit. | Accepted vessel/operation assurance pack and go/no-go record | SCC5tonne transfer crane is not a bridge-lift selection criterion | SCC3/5; C9/C10; C8 starred requirements
N | Network schedule and calendars | Planning Manager | Scope/quantities, approvals, capacity and supplier dates | Use one logic network with source/assumption status; model office/yard/offshore calendars, approval states and PS stages; link shared resources and completion dossiers; calculate forward/backward paths, target shortfalls and sensitivities; freeze only after validation. | Approved baseline and update narrative with calculation settings | No day-number bar chart or register labelled approved CPM | SCC2/11; C8; P14 scenario
O | Offshore installation and temporary stability | Construction Manager | Approved IWP, design, loadout and operating windows | Complete preconstruction survey/access; strengthen supports before new bridge placement where required; verify temporary load paths and restraint removal order; authorise lifts, landing alignment/bearing travel and permanent connection; inspect before transfer and removal. | Signed workfront release, installation survey and inspection dossier | No bridge removal until alternate support/service sequence accepted | StructuralSOW addendum; bridge-specific approved methods
P | Production and fabrication control | Fabrication Manager | Released shop packs, material, qualified personnel and capacity | Validate bay dimensions/cranes and shifts; material receipt/heat mapping; cut/form/fit/weld with distortion/camber controls; NDT/repair; dimensional survey/trial fit; coating/curing; preserve and release modules by accepted quantities. | Daily accepted output, resource hours and module release | Separate installed structural MT from purchased stock and rework | MasterPlanV3; FS2009F/2005
Q | Quantity, progress and earned value | Project Controls Manager | Approved work quantities, budget and progress rules | Measure installed and accepted quantities by workpack; distinguish fabrication/install completion, certification, invoice and cash; apply C8 engineering/MCI status weights only to their contractual bases; retain e-MB/SES traceability; do not earn budget twice. | Signed measurement, progress-rule and cost-code reconciliation | EV/SPI/CPI blank where BAC/PV/AC or accepted quantities absent | SCC12; C8 review/progress rules
R | Risk, contingency and recovery | Risk/Planning Manager | Risk register, driving path and resource limits | Identify causes/events/effects; score ownership and early-warning; quantify actual schedule/cost exposures when data exist; test material delays, re-reviews, vessel failure and workability; price recovery options and seek authorised decisions. | Owned mitigations, contingency and recovery decision log | No probability or P80 claim without a risk model and evidence | SCC11; P14 alternatives
S | Subcontracts and retained responsibilities | Contracts Manager | BEC route, agency scope and signed commitments | Define battery limits and deliverables; retain required PM/main activities; obtain capacity/commitment letters and flow down QA/HSE/integrity obligations; manage approved agencies, claims and performance; prohibit unauthorised whole-works pass-through. | Approved responsibility split and signed subcontract evidence | Agency listing alone is not signed capacity or eligibility | A16/A17/B6; TechnicalBEC5
T | Treasury, cost and cash flow | Finance Manager | Priced estimate, signed terms and actual milestones | Track budget/commitment/accrual/actual/ETC/EAC; schedule taxes, wages, charters, vendor payments, BG margins/fees/releases, certification/payment lags, retention/advance recovery and financing; extend through final account/warranty releases. | Priced control budget and funded cash forecast | Unknown inputs remain unknown; no zero-cost feasibility conclusion | P9/P11 securities; A3/A10; SCC
U | Utilities and service reinstatement | Commissioning Manager | Approved tie-ins, isolations and test requirements | List every piping/cable/instrument/lighting/earthing/firewater service; verify temporary bypasses; isolate, transfer, inspect/test and restore under operations control; close pressure/leak, continuity/IR/earthing and functional tests as applicable. | System-wise reinstatement/test sheets and operations acceptance | No energisation or hydrotest without approved test boundary and procedure | Combined1/2/3 discipline specifications
V | Variations, delay and claims records | Contracts Manager | Written instruction, baseline and contemporaneous records | Log notices and contractual time bars; maintain monthly joint critical-event logs and quarterly delay reports; substantiate quantities/invoices/man/barge days; apply SCC9 positive/negative valuation and avoid duplicate fees; document relief decisions. | Notices, joint statements, approved variations and final-account evidence | No assumed entitlement from a schedule overrun alone | SCC9/11; Corr3 clause2.3.6; GCC8
W | Weather and workability | Marine/Planning Manager | Field metocean, forecast and vessel limits | Set engineered operating/abort limits by operation; agree forecast/lookback records and weather standby attribution; plan refuge/demob/remob and emergency triggers; preserve contemporaneous proof for qualifying monsoon relief. | Weather logs, operational decisions and seasonal resource plan | Planning blackout is not automatic contractual extension | SCC2/4; C9/C10
X | Execution readiness and daily control | Construction Manager | IWP, crew/tools, quantities, materials, permits and assurance | Run6week constraint removal,14day lookahead and daily permit/readiness meetings; verify all gates and evidence IDs; record planned/accepted output and crew-hours; escalate blockers and resource clashes without bypassing safety gates. | Released daily work list, production/constraint records | Readiness requires evidence and verified scope, not eight unchecked Yes labels | Stages30–35; HSE/QA project controls
Y | Yard-to-field completion and handover | Completion Manager | ITRs, drawings, tests, systems and punch categories | Create bridge/system turnover boundaries at design stage; collect manufacturing records progressively; inspect structural/bearing alignment and reinstated services; close blocking punch items; deliver as-builts/native files/vendor dossiers and scrap receipts; obtain formal acceptance. | Accepted turnover dossier and handover certificate | No completion earned solely by physical steel placement | A10; C8; SCC14; GCC completion clauses
Z | Warranty, final account and lessons | Project Director | Acceptance terms, outstanding obligations and final payments | Track defect liability/warranty and insurance/security releases; resolve claims and subcontract final accounts; retain integrity-pact/record obligations; archive controlled native/PDF data and access; close lessons and verify promised performance against outcomes. | Contract closure certificate, release schedule and retained records | Physical completion, financial closure and obligation expiry are separate dates | IntegrityPact9; GCC/SCC governing periods

## Source Coverage
File | SHA256 | Prior exact matches | Duplicate in batch | Review disposition | Local source
Addendum.pdf | 1742ad4dd672858b1ee148ba6e82b5d4594b3205a8db344d7631408e582a26fb | 5 |  | Hash/open checked; prior review reused | /workspace/attachments/71d9446a-9284-4152-923c-f5c85a23c0f1/Addendum.pdf
Addendum (1).pdf | 1742ad4dd672858b1ee148ba6e82b5d4594b3205a8db344d7631408e582a26fb | 5 | Addendum.pdf | Hash/open checked; prior review reused | /workspace/attachments/62e4fd39-6c8f-4f77-88c2-7fbc71905567/Addendum (1).pdf
Addendum_Structure_SOW.pdf | 9720ca8546c67ef9cc4f44a8b4fb480de23da3eed38a6ca5dae2879de8c1485a | 4 |  | Hash/open checked; prior review reused | /workspace/attachments/652f34f3-904c-4733-84f5-3badb6e94c6e/Addendum_Structure_SOW.pdf
AddendumtoA3.pdf | 191ca9ccafb391c57652a1e4b5831484c2a53765cf6d813b8bdc87dc1de3ce07 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/b9a9de3b-b77d-49f1-8ff1-a0c7d55ca00b/AddendumtoA3.pdf
Appendix A-9.pdf | fea757b0e53dd170dbe9c645a10ddfe62eec08e2cfe6f151bbd0adf0bd4ed5e4 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/67595e2c-856c-401e-833f-825f1401ae1e/Appendix A-9.pdf
Appendix A-16 List of Agencies.pdf | 09a642f2eb6a23c02a735be3d51b57db316f4d5697aff8e1db8c1ee7bacaa50a | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/2d2bfd9d-58b4-45b5-9b23-013e947fac6f/Appendix A-16 List of Agencies.pdf
Appendix A-17.pdf | 5d5cde215d0959b2e8126df4a2daf7edb4f91a7fc428146dda9d905c4aad6d6a | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/0cc90703-59ca-4d42-87f6-a21665d44d80/Appendix A-17.pdf
Appendix A-11 Offshore SVL Revision 12.1.pdf | 86d3ab9001388087d63075d5cde421a51a6d1f4c5857fda8e18f7459637f5381 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/53ebe58d-28b5-4afe-a534-d4e5e90c0768/Appendix A-11 Offshore SVL Revision 12.1.pdf
Appendix B-5.pdf | 82222c4cdca2f142d619e139280c264c68085cca7444ad0f1152204a91f1bf3e | 3 |  | Hash/open checked; prior review reused | /workspace/attachments/0f6b6e5d-3512-48b3-b967-7e0b5e54488c/Appendix B-5.pdf
Appendix B-6.pdf | dd4ce8688af1b3976c4fc752c9a19e4e14d43984c0e25733d11c6703d9919858 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/4bee04c0-bc1c-43e2-9067-bf305f40553e/Appendix B-6.pdf
Appendix C-9.pdf | f20a85ca3a13c08e62bb18a41838d9e32910cd4f0d7c6b0ab0623df4ca9aeec5 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/253ac71f-d176-432c-911f-60a8f984d59d/Appendix C-9.pdf
Appendix C-8 DCI MCI.pdf | 086b2f7837d09bc6320e2e0794f5b73fc7788b2cb9ecb5a08fa76836e2c97944 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/5e260e43-5134-4a2f-a8df-817300abf68d/Appendix C-8 DCI MCI.pdf
Appendix C-10.pdf | 8f0b1be35e96cc0e953e8614b751f08a987dca4a9060c54319b231f113d7d2d7 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/0c0ae9b7-787b-400e-bb17-d6a1c1a58cb8/Appendix C-10.pdf
chart.pdf | 30e8cf255d41edc9930b28ee4a2bea2c82dcd033222333c9a5e914ba0cb16b00 | 0 |  | Distinct content screened; discipline detail still required | /workspace/attachments/790dcc2a-429d-42e1-9aa9-b5fc913b3310/chart.pdf
Combined_Addendum_2.pdf | f251ecb31a55528c700e82a095c36459b3b84610385d490fd492cc1ce1b9a6b4 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/13283f00-2c75-40f7-9ce4-22e8724d624a/Combined_Addendum_2.pdf
Combined_Addendum_1 (1).pdf | dfda0877c74c0745763a6d8eb0e8894014d27b22ec72c8f44955c933cadf1d65 | 4 |  | Hash/open checked; prior review reused | /workspace/attachments/042f23bd-8110-4235-96d8-8673e520ea0d/Combined_Addendum_1 (1).pdf
Corrigendum.pdf | 02142550f5d609a6a2ffe4ed64d441eaa00540663cee661ed318446e6e19dea6 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/a569298e-9b51-4a0a-865f-1a4350827b47/Corrigendum.pdf
Combined_Addendum_1.pdf | dfda0877c74c0745763a6d8eb0e8894014d27b22ec72c8f44955c933cadf1d65 | 4 | Combined_Addendum_1 (1).pdf | Hash/open checked; prior review reused | /workspace/attachments/24075e12-e392-4681-ac05-3e4aa60baea8/Combined_Addendum_1.pdf
Corrigendum_1_BRRP.pdf | 54977537e10a8249587ad2965eca04a057eaa45f932e6a229959bc3fa30ab7c4 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/ce432d19-ef2c-4984-9b8f-1061008c14af/Corrigendum_1_BRRP.pdf
Corrigendum_2.pdf | cb996ec5837ec4dcfab1a55e4ffcb56248919a73d70cd53492d64d39a2a7b435 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/6f519900-18e2-4842-a3a4-47eab8f9279c/Corrigendum_2.pdf
Corrigendum_3.pdf | e8a07f4059dcb9b81c1cc45b2ae60154c0c142999955b347d2c60133619656d7 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/7932c206-c79d-4425-99a1-c83f9e788608/Corrigendum_3.pdf
Corrigendum_4.pdf | 623614acba28baadc68c22229c039399e9b4385c0945b787197b2dedaaa4acf4 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/e3752b17-cf9c-472e-a3f1-cdcfb97319d9/Corrigendum_4.pdf
CQ_replies_BRRP.pdf | b006f3d20e7ae10d9800b1b9fabfb3104091b09878fcd6bb83b2f328e926df4a | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/dfc717ae-169c-4f98-a676-e4f9135968bb/CQ_replies_BRRP.pdf
IP (1).pdf | 8692fb4bca724408df3fe1ec8377faa678e6238f3fe14bb55fbc6ca4b8cdcf50 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/86b20843-c858-4bbc-ba34-1eb21ae00511/IP (1).pdf
Combined_Addendum_3.pdf | 6d6369b880718f0b84da0776adc723d99eae59b591c8b5d45f1f0b2596b9d5b6 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/1bc81107-8f35-4cbf-9221-83ba100de6ba/Combined_Addendum_3.pdf
Design Criteria & Execution Methodology.pdf | 179b05dabdb90971b5132d38f2a1aa755ce091b640b4e844fa7b0c9cc4a7e706 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/88e427dd-3a5a-4b8d-bdbd-b42e46560820/Design Criteria & Execution Methodology.pdf
IP.pdf | 8692fb4bca724408df3fe1ec8377faa678e6238f3fe14bb55fbc6ca4b8cdcf50 | 2 | IP (1).pdf | Hash/open checked; prior review reused | /workspace/attachments/e09fff9b-4787-43dc-9837-32803d295090/IP.pdf
Kits PPE List-BRRP.pdf | 44e2e5f2214d741c15380702504a73ae00076ab5954bb6ce96011a1e06aed841 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/fd490052-5a1c-457b-8b21-f994277ea8ec/Kits PPE List-BRRP.pdf
Section 1.pdf | 4396fb90c823805128145920d1348e69942a65e501773d80457a3b671e0f3641 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/8da610f6-1801-4fe3-823d-e61a9d261607/Section 1.pdf
Section 2.pdf | 1d6c9da72ce45156e95586056c6d96a06da9563a9a27817dc77935d6fa470a7f | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/42bc04a5-aa70-4b68-8f62-6aa20791774b/Section 2.pdf
MTO Drawings IRT.pdf | 0a8a008d8bc139d05c75f83c52ba23d637c1f78926b7a19e4007297ac52485cb | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/6ac405c9-4cf3-4694-b74c-4bf32ee762e0/MTO Drawings IRT.pdf
SHIVANSH ONGC Offshore Bridges - PRELIMINARY.xlsx | caba714d2cc9b32ddf723228a57797a6e588463c0554ced81701982fcd7f7f20 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/d9e9d456-d843-439f-9b8b-ba2073e00690/SHIVANSH ONGC Offshore Bridges - PRELIMINARY.xlsx
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | a4545c34bc3bfdf771c5918e9335e6b288626e024a5f517e4eb0ca7f6fe870ee | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/9d725d18-b225-48ae-b2c7-08bfdae07e20/SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | 2c64809e2cbab409c9897e19ee5b46768287708a1adb9f923457d03177f24c36 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/e26488ad-6288-488e-9a57-e805e58d373d/Shivansh_BRRPP_Integrated_Execution_Control.xlsx
Section 3.pdf | 64146db7c46ea30fc3e5161cea2ce94bdb3435e4aefe05a81cfac0174c141108 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/e8998ddd-f666-4184-8a06-cfe98fcee70d/Section 3.pdf
Shivansh_BRRPP_Level3_P6_Preparation.xlsx | 186a4f446d7691b5c726f32e8600482c7abde182ef9bbc7d11c07729e4706074 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/5cd8d5fa-208f-4c83-8634-cc48ce45f232/Shivansh_BRRPP_Level3_P6_Preparation.xlsx
Shivansh_BRRPP_P6_Activity_Import.csv | cd3865f25e6d42bccc800bd4344e38816fdcf68c6dbbe63c26a0e76096f358d7 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/93fa0f79-840c-4179-a70c-0453a58a772a/Shivansh_BRRPP_P6_Activity_Import.csv
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | 88adcd75ff58317d0215801c0cee35b3f8aa03b024e8acbd45382e8138db56f0 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/7dc15993-36a3-4025-9400-43b50a6634fa/Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | ac85c7dec0f9db25e971b0795623e465a92732bcc873ba6234bd21f485cc2036 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/d26e8648-ae53-4e11-9b9e-462a8c2d2bf2/Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | 44df6c84070a16804ad83487e7575ba1e99569a53e267c8e3da83ac9cfd59621 | 3 |  | Hash/open checked; prior review reused | /workspace/attachments/eb12ce0c-0f11-4e8b-8f79-44bee2a5c743/Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | 44df6c84070a16804ad83487e7575ba1e99569a53e267c8e3da83ac9cfd59621 | 3 | Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Hash/open checked; prior review reused | /workspace/attachments/af8b4024-34f5-445c-bf5a-6a9bdfb92b31/Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx
Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx | a46229faa98cf1d94ebad3412394eda944398ea5f209b3da5b3fce3af1c0a7d6 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/b862be55-df27-453e-abe6-771340b8533c/Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | 9627644802f34de8ab9f44420ab6b7bad0437a6dbd5ea2a8dc0228d6f53bc422 | 2 |  | Hash/open checked; prior review reused | /workspace/attachments/ecfd871a-db42-4242-b752-7c413a1065c2/Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital.xlsx | 9627644802f34de8ab9f44420ab6b7bad0437a6dbd5ea2a8dc0228d6f53bc422 | 2 | Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | Hash/open checked; prior review reused | /workspace/attachments/f5e8b898-0da0-4e8c-a489-363b2fc2e689/Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital.xlsx
Shivansh_BRRPP_Stage27_Integrated_EPC_Control.xlsx | eaf6f3d25ff076225065d995c586af645d046c87ddc6bd205845e630ede8b4ef | 0 |  | Distinct content screened; discipline detail still required | /workspace/attachments/c1f134e0-4c2b-483e-837f-7666380a5b4d/Shivansh_BRRPP_Stage27_Integrated_EPC_Control.xlsx
Shivansh_BRRPP_Stage28_Level4_Execution_Schedule.xlsx | 9614bca82b60f80b1f746d826905e951351c8630aed6ec1009a194b83f5fb747 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/b5a48b69-16ae-4076-a4c5-9cf21de00369/Shivansh_BRRPP_Stage28_Level4_Execution_Schedule.xlsx
Shivansh_BRRPP_Stage29_Resource_Recovery_Model.xlsx | df1667a6a69dff2106ff4befae034044ceaf70a2876e448ba6561901adaa6f59 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/5295e035-9004-4880-a5d5-8d42ef7d3efc/Shivansh_BRRPP_Stage29_Resource_Recovery_Model.xlsx
Shivansh_BRRPP_Stage30_Workpack_Productivity_Control.xlsx | cb59fab7d9a995acde11a16d7ab6a90dcc9c9c8b1b9f399439c8522dad76f678 | 0 |  | Distinct content screened; discipline detail still required | /workspace/attachments/b58cc7bd-094f-4859-bbd6-71c815d50643/Shivansh_BRRPP_Stage30_Workpack_Productivity_Control.xlsx
Shivansh_BRRPP_Stage31_Daily_Readiness_Production_System.xlsx | 8b3de0f36bc9a4109bb5d9163df942dab56258ed44ae9b708e8308d1bc16cc5b | 0 |  | Distinct content screened; discipline detail still required | /workspace/attachments/af5f377a-ecb4-4cc9-99de-17190c087166/Shivansh_BRRPP_Stage31_Daily_Readiness_Production_System.xlsx
Shivansh_BRRPP_Stage32_Productivity_Forecast_Control (1).xlsx | ac040e820fafb1c9806f6840331bf5c1272ba1df89f7b0ae87292b7aec99b7a0 | 0 |  | Distinct content screened; discipline detail still required | /workspace/attachments/406d956f-fdc8-4096-8ed2-57dfdb944f4c/Shivansh_BRRPP_Stage32_Productivity_Forecast_Control (1).xlsx
Shivansh_BRRPP_Stage33_Early_Warning_Recovery_Dashboard.xlsx | 5bdcdaf794159caa61180384c6cdc30c01ff9485836f7c9b0693ea7e42f9b7cd | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/d957c5a5-a5e2-43c2-9ee2-d27b00e087ef/Shivansh_BRRPP_Stage33_Early_Warning_Recovery_Dashboard.xlsx
Shivansh_BRRPP_Stage32_Productivity_Forecast_Control.xlsx | ac040e820fafb1c9806f6840331bf5c1272ba1df89f7b0ae87292b7aec99b7a0 | 0 | Shivansh_BRRPP_Stage32_Productivity_Forecast_Control (1).xlsx | Distinct content screened; discipline detail still required | /workspace/attachments/87831bc1-2707-4555-8297-b539759e21d3/Shivansh_BRRPP_Stage32_Productivity_Forecast_Control.xlsx
Shivansh_BRRPP_Stage35_90_Day_Mobilisation_Command_Plan.xlsx | 5f19dcee0c81c6931459a5972763e6339eb036ac386518074246b415d1fc5be8 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/f9408db4-29b9-482e-8e94-de2213453ddf/Shivansh_BRRPP_Stage35_90_Day_Mobilisation_Command_Plan.xlsx
Shivansh_BRRPP_Stage34_Integrated_EPC_Control_Centre.xlsx | bc4b4615629759d31ccc86ba1e4ecf532ee00d38596caad9a0da760c945362d6 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/eb68b3fc-f253-47a2-b220-ff21f3834259/Shivansh_BRRPP_Stage34_Integrated_EPC_Control_Centre.xlsx
SHIVANSH_EPC_Master_Plan_All_6_Volumes.zip | d3d3ec37f51bb3dae0e4e52ff8af94dd9735bfcd341f12fb8debdb33c1354dd1 | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/37c20864-f5e3-4a94-85c7-cc94db455b87/SHIVANSH_EPC_Master_Plan_All_6_Volumes.zip
SHIVANSH_EPC_Master_Plan_Volume_1 - Copy.docx | 9b5eb6c4f99d251e612ffcc5acd598f69427282d0d12a4a1cf7a5c933ab3af6f | 1 |  | Hash/open checked; prior review reused | /workspace/attachments/0518acf9-e4f9-4e04-8b74-c94b26366252/SHIVANSH_EPC_Master_Plan_Volume_1 - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_1.docx | 9b5eb6c4f99d251e612ffcc5acd598f69427282d0d12a4a1cf7a5c933ab3af6f | 1 | SHIVANSH_EPC_Master_Plan_Volume_1 - Copy.docx | Hash/open checked; prior review reused | /workspace/attachments/27497066-85c1-47c6-93db-8c616fd503c6/SHIVANSH_EPC_Master_Plan_Volume_1.docx
SHIVANSH_EPC_Master_Plan_Volume_2 - Copy (2) - Copy.docx | ce3642b042ad5b0013de702d9361b1759e5c8e3fbd12839ba2a65de97cf17533 | 0 |  | Distinct content screened; discipline detail still required | /workspace/attachments/44c92e4b-5800-43ac-97df-48e11ac8d63b/SHIVANSH_EPC_Master_Plan_Volume_2 - Copy (2) - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_2 - Copy (2).docx | ce3642b042ad5b0013de702d9361b1759e5c8e3fbd12839ba2a65de97cf17533 | 0 | SHIVANSH_EPC_Master_Plan_Volume_2 - Copy (2) - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/4448d91b-75d1-4b69-99e3-1c2b1a86b75c/SHIVANSH_EPC_Master_Plan_Volume_2 - Copy (2).docx
SHIVANSH_EPC_Master_Plan_Volume_2 - Copy.docx | ce3642b042ad5b0013de702d9361b1759e5c8e3fbd12839ba2a65de97cf17533 | 0 | SHIVANSH_EPC_Master_Plan_Volume_2 - Copy (2) - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/64000d7c-788f-4100-8ae7-a2015a09c0d2/SHIVANSH_EPC_Master_Plan_Volume_2 - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy - Copy.docx | c477c827f9aa7be3bb8ee77c5e4ae906d13836dac27daee468518f4ff869c526 | 0 |  | Distinct content screened; discipline detail still required | /workspace/attachments/8a6d78e8-4db2-4f46-96a6-9eae1c917653/SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy (2).docx | c477c827f9aa7be3bb8ee77c5e4ae906d13836dac27daee468518f4ff869c526 | 0 | SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/3e570754-b37e-4c16-a5f3-5fefb1847ca2/SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy (2).docx
SHIVANSH_EPC_Master_Plan_Volume_2.docx | ce3642b042ad5b0013de702d9361b1759e5c8e3fbd12839ba2a65de97cf17533 | 0 | SHIVANSH_EPC_Master_Plan_Volume_2 - Copy (2) - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/f8a5dc0c-f647-4318-be98-22b2f8f4b7a6/SHIVANSH_EPC_Master_Plan_Volume_2.docx
SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy.docx | c477c827f9aa7be3bb8ee77c5e4ae906d13836dac27daee468518f4ff869c526 | 0 | SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/ee92c4a0-d95c-41b3-a1cc-8581af1ee023/SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_3 - Copy (2) - Copy.docx | c477c827f9aa7be3bb8ee77c5e4ae906d13836dac27daee468518f4ff869c526 | 0 | SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/7a21c556-65d6-482c-a802-ed369b4d4df9/SHIVANSH_EPC_Master_Plan_Volume_3 - Copy (2) - Copy.docx
SHIVANSH_EPC_Master_Plan_Volume_3 - Copy (2).docx | c477c827f9aa7be3bb8ee77c5e4ae906d13836dac27daee468518f4ff869c526 | 0 | SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/6ad32486-2ba2-4baf-a610-d11053809828/SHIVANSH_EPC_Master_Plan_Volume_3 - Copy (2).docx
SHIVANSH_EPC_Master_Plan_Volume_3 - Copy (3).docx | c477c827f9aa7be3bb8ee77c5e4ae906d13836dac27daee468518f4ff869c526 | 0 | SHIVANSH_EPC_Master_Plan_Volume_3 - Copy - Copy - Copy.docx | Distinct content screened; discipline detail still required | /workspace/attachments/cde4c99b-9f2d-43d9-bef9-3fdd909b5310/SHIVANSH_EPC_Master_Plan_Volume_3 - Copy (3).docx
PRELIMINARY.pdf |  | 0 |  | file exceeds the executor transfer limit of 32 MiB

## Earlier P13 Coverage
File | SHA256 | Prior exact matches | Duplicate | Disposition
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 |  | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_4.docx | fdbbcaf61b89b33696bc164ebf7c866c81f4cac5d9ee8bda20b38c00087f038f | 0 |  | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_4 - Copy.docx | fdbbcaf61b89b33696bc164ebf7c866c81f4cac5d9ee8bda20b38c00087f038f | 0 | SHIVANSH_EPC_Master_Plan_Volume_4.docx | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy (2).docx | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy.docx | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy (2) - Copy.docx | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_5 - Copy.docx | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_5.docx | 780b6b86fcd5d34d71bf2cc18548d62a298cee1a296ad7636365ee10c2ff9226 | 0 | SHIVANSH_EPC_Master_Plan_Volume_5 - Copy - Copy - Copy.docx | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_6 - Copy - Copy.docx | 210c62c17a32f6b0545c512e9ae7d145c318845c51edd1ab2af106cd7ba3d79e | 0 |  | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_6.docx | 210c62c17a32f6b0545c512e9ae7d145c318845c51edd1ab2af106cd7ba3d79e | 0 | SHIVANSH_EPC_Master_Plan_Volume_6 - Copy - Copy.docx | Duplicate comparison; P13 content/XML screening
SHIVANSH_PreAward_207_Activities_ProjectLibre_Import.xml | d3f7199e9981a38001856c7fc4dfacadcc7158efe4310febc1c9040489b5bcb2 | 1 |  | Duplicate comparison; P13 content/XML screening
SHIVANSH_EPC_Master_Plan_Volume_6 - Copy.docx | 210c62c17a32f6b0545c512e9ae7d145c318845c51edd1ab2af106cd7ba3d79e | 0 | SHIVANSH_EPC_Master_Plan_Volume_6 - Copy - Copy.docx | Duplicate comparison; P13 content/XML screening
SOW & Bridge Report Combined - Copy - Copy.pdf | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 |  | Duplicate comparison; P13 content/XML screening
SOW & Bridge Report Combined - Copy.pdf | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
SOW & Bridge Report Combined (3) - Copy - Copy.pdf | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
SOW & Bridge Report Combined (3) - Copy.pdf | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
SOW & Bridge Report Combined (3).pdf | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
SOW & Bridge Report Combined.pdf | 1dd8c329d410a7ea7f6b497d8c0fb230e23feaeabcd80964503bdb530236770a | 4 | SOW & Bridge Report Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Specification Combined - Copy - Copy.pdf | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 |  | Duplicate comparison; P13 content/XML screening
Specification Combined - Copy - Copy - Copy.pdf | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Specification Combined - Copy.pdf | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Specification Combined - Copy (2) - Copy.pdf | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Specification Combined - Copy (2).pdf | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension050526 - Copy - Copy - Copy.pdf | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 |  | Duplicate comparison; P13 content/XML screening
Specification Combined.pdf | fcb66cef439b04510b11d0225c2c7327e70a7aeaa8476651e9adc4329a5095eb | 4 | Specification Combined - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension050526 - Copy - Copy.pdf | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension050526 - Copy (2).pdf | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension050526 - Copy (2) - Copy.pdf | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension050526 - Copy.pdf | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension050526.pdf | 9b7cf7505a87a3743ad2da609f7cd2357ad0717a20aefae32c1baf4196876011 | 1 | TBOextension050526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension090626 - Copy - Copy.pdf | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 |  | Duplicate comparison; P13 content/XML screening
TBOextension090626 - Copy.pdf | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 | TBOextension090626 - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension090626 - Copy - Copy - Copy.pdf | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 | TBOextension090626 - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension090626.pdf | 916fdbeecc51c1c44bb20aa3cbc1a8ef3a246fbb0e7c38d605007f72d24021a1 | 2 | TBOextension090626 - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension250526 - Copy - Copy - Copy.pdf | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 |  | Duplicate comparison; P13 content/XML screening
TBOextension250526 - Copy - Copy.pdf | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 | TBOextension250526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension250526 - Copy.pdf | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 | TBOextension250526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
TBOextension250526.pdf | c74098b236b0b059fe9cd539b814bf6838c586cd3a2701d63f41a0d579b7494b | 1 | TBOextension250526 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 |  | Duplicate comparison; P13 content/XML screening
Technical_SCC - Copy - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (1) - Copy - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (1) - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (1) - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (2) - Copy - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (2) - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (1).pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (2) - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (2).pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (3) - Copy - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (3) - Copy - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC (3) - Copy.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Technical_SCC.pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1 - Copy - Copy - Copy.pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 |  | Duplicate comparison; P13 content/XML screening
Technical_SCC (3).pdf | c954759fb14588581784c894f9ffe949760a608217a75f73809b4eefa937ee17 | 9 | Technical_SCC - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1 (1) - Copy - Copy - Copy.pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1 - Copy.pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1 - Copy - Copy.pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1 (1) - Copy - Copy.pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1 (1).pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1 (1) - Copy.pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Tendernotice_1.pdf | 97463997491227dbddeffd8bdd92d82f3d497b88b99227b05a55b03111dda78d | 11 | Tendernotice_1 - Copy - Copy - Copy.pdf | Duplicate comparison; P13 content/XML screening
Vol I _PartV_Appendix A-3 Price Schedule.xlsx | 7b4e2c5849fc2b293e4de333dd3bb7b9893702fce99f93d01d637308b1d397a6 | 2 |  | Duplicate comparison; P13 content/XML screening
Vol I _PartV_Appendix A-10 MPF.xlsx | 3e1398fa91d52a60c14f78ba4aaccd1e2a3b90b8cc5046dc980561a45e712aa9 | 2 |  | Duplicate comparison; P13 content/XML screening
ticket.pdf | 207b0d36e2def3753e5b65b9c2432176235741f6f9d03713f2e532068c295bea | 0 |  | Duplicate comparison; P13 content/XML screening
Vol I _PartVA_BRS.xlsx | 872ba27d634dc202597837a32971bafa19c0eb54ac151f7c86f64bccd1d5d897 | 1 |  | Duplicate comparison; P13 content/XML screening
Vol I_ Part III Appendices.docx | c1ef1672214f304f856d1a3bdb5f1a3c4d685f00e484907e5bc826d46155ca7f | 2 |  | Duplicate comparison; P13 content/XML screening
Vol I_PartIV_BEC - Copy.docx | df1674f7946d9f62bfc169251d43ad05ee75549001c0d460408055e43b9818b2 | 3 |  | Duplicate comparison; P13 content/XML screening
Vol I_PartIV_BEC.docx | df1674f7946d9f62bfc169251d43ad05ee75549001c0d460408055e43b9818b2 | 3 | Vol I_PartIV_BEC - Copy.docx | Duplicate comparison; P13 content/XML screening
Vol I_PartIVA_BidderGTE.xlsx | 73b9c45b583b3612ee2b8bcb5a0f95cfad5392979d3d697c8f9ff3c1664d5e02 | 2 |  | Duplicate comparison; P13 content/XML screening
Vol I_PartIVA_BidderGTE - Copy.xlsx | 73b9c45b583b3612ee2b8bcb5a0f95cfad5392979d3d697c8f9ff3c1664d5e02 | 2 | Vol I_PartIVA_BidderGTE.xlsx | Duplicate comparison; P13 content/XML screening
Vol_I_PartIV_ Technical BEC - Copy.pdf | d5548eb59f55cf6504d770c44e2dcd42b42392eb71541f36a742df9b089e3a7c | 3 |  | Duplicate comparison; P13 content/XML screening
Vol-I I ITB - Copy.docx | 61033c9e7a297215977bdbf88dd81b3bca8073d17e7ae88f2ae7b57ce1fd58ae | 3 |  | Duplicate comparison; P13 content/XML screening
Vol_I_PartIV_ Technical BEC.pdf | d5548eb59f55cf6504d770c44e2dcd42b42392eb71541f36a742df9b089e3a7c | 3 | Vol_I_PartIV_ Technical BEC - Copy.pdf | Duplicate comparison; P13 content/XML screening
Vol-I-II GCC - Copy.docx | 78d8130c8aab9b96e9dad2584cb6c30be370c72dd71f154df103eb238b08f4a1 | 3 |  | Duplicate comparison; P13 content/XML screening
Vol-I I ITB.docx | 61033c9e7a297215977bdbf88dd81b3bca8073d17e7ae88f2ae7b57ce1fd58ae | 3 | Vol-I I ITB - Copy.docx | Duplicate comparison; P13 content/XML screening

## Requirements
ID | Requirement topic | Source | Requirement | Owner | Verification evidence | Status
P9-01 | Bid security | Corrigendum.pdf p1 | Any e-BG must be executed on NeSL before the tender closing deadline; later execution is liable to rejection. | Treasury / Bid Manager | Record portal execution timestamp and evidence; reconcile actual closing date with all extension notices. | OPEN — source requirement; execution not evidenced
P9-02 | Bid validity | Corrigendum_2.pdf pp1-2,5; Corrigendum_4.pdf p1; CQ_replies_BRRP.pdf pp2-3 | Bid security extends 45 days beyond bid validity or extended validity. Bid validity is 120 days after opening of unpriced techno-contractual bids; do not anchor it to submission closing. | Treasury / Contracts | Use actual opening date; diarise bid and security expiry separately. Surety claim-period provisions remain distinct. | OPEN — source requirement; execution not evidenced
P9-03 | Performance security | Corrigendum_1_BRRP.pdf p1 | The quoted ITB 28.1 option for 3% initial security plus 7% progressive deductions is deleted. | Contracts / Finance | Remove that financing assumption; reconcile remaining ITB 28.1, IFB and B-3 for governing amounts, submission and validity. Do not infer replacement wording from deletion alone. | OPEN — source requirement; execution not evidenced
P9-04 | Supporting-company guarantees | Corrigendum_2.pdf pp2-5 | B-19/B-20/B-22 specified guarantee deadlines change from 15 to 30 days from NOA. Applicable supporting/JV guarantee provisions include delayed-submission recovery wording. | Contracts / Treasury | Set separate applicable-route milestones. Review 1.5% of performance-security amount per month or part-month recovery wording; do not apply indiscriminately to every guarantee. | OPEN — source requirement; execution not evidenced
P9-05 | Setting out and changes | Corrigendum_3.pdf p1, GCC 2.3.6 | Modified column reinstates setting-out responsibility. Contractor corrects its positioning errors; company checking does not relieve it. Later company data/instructions after pre-engineering survey causing scope changes are dealt with under Clause 8.0. | Survey / Engineering / Contracts | Establish controlled datums, coordinates, survey acceptance and independent dimensional checks; preserve instruction/change evidence. This clause is not deleted. | OPEN — source requirement; execution not evidenced
P9-06 | Domestic steel compliance | Corrigendum_3.pdf pp1-8 | DMI&SP policy reference changes to notification dated 17 December 2025, G.S.R.904(E). All bidders submit Form-1; item-specific Melt & Pour and domestic-value-addition provisions apply. | Procurement / QA / Contracts | Classify items under policy Appendix A/B and HS code. Obtain heat/mill origin records, Form-1, authorisations and applicable auditor certificates; maintain traceability. Do not confuse these policy appendices with tender appendices. | OPEN — source requirement; execution not evidenced
P9-07 | MSE and local content | CQ_replies_BRRP.pdf p5 | ONGC reply says PPP-MSE exemption/purchase-preference benefits do not apply to this LSTK works tender. PP-MII is referred to ITB23.6.2(b). | Bid / Procurement | Remove assumed MSE EMD exemption; verify PP-MII separately, including current amendments. | OPEN — source requirement; execution not evidenced
P9-08 | Bid content | CQ_replies_BRRP.pdf p6 | ONGC reply requires only BRS Part V-A with Quoted/Not Quoted confirmations in the unpriced bid; price manner follows the actual price format. | Bid Manager | Keep prices in the correct cover; reconcile all A-3 line items and BRS. This reply does not waive separate subcontractor commitment requirements. | OPEN — source requirement; execution not evidenced
P9-09 | Tax and precedence | CQ_replies_BRRP.pdf pp7-9 | Beyond-12NM works are not declared tax-exempt: prevailing GST applies; offshore GSTIN may be used. SCC overrides GCC for conflicts; complete priority is referred to B-4. Liability reduction request was rejected. | Tax / Contracts | Prepare transaction-specific GST, customs and withholding matrix; use B-4 for full hierarchy. Do not adopt the bidder-proposed document hierarchy or 15% liability cap. | OPEN — source requirement; execution not evidenced
P9-10 | Pre-bid and extension requests | Corrigendum_1_BRRP.pdf p1; CQ_replies_BRRP.pdf pp7,9 | Pre-bid conference was physical only, 8 April 2026. Six-week bid extension request was called premature at PBC stage. | Document Control / Bid | Record historical event; use issued extension notices for actual deadline. This reply is not a six-week extension grant. | OPEN — source requirement; execution not evidenced
P9-11 | Integrity pact | IP (1).pdf pp2,4-6; IP.pdf identical | Disclose intermediaries and relevant transgressions, obtain subcontractor adoption undertakings, retain records for IEM access. Contractor pact duration extends 12 months beyond last payment; other bidders six months after award, subject to outstanding claims. | Compliance / Contracts | Maintain signed pact, partner/consortium signatures as applicable, declarations and subcontract flow-down; extend compliance retention beyond physical completion. No signed compliance evidence established by blank form. | OPEN — source requirement; execution not evidenced
P9-12 | PPE | Kits PPE List-BRRP.pdf p1 | Per person: 2 cotton overalls; 2 FR overalls; 2 pairs industrial shoes; 2 pairs electrical-hazard shoes for electrical personnel; 2 helmets; 2 clear goggles; 2 pairs ear muffs; 4 pairs impact/cut gloves; 2 pairs reusable ear plugs; 2 pairs rubber electrical gloves. Each construction season OR condition-based replacement. | HSE / Procurement | Cost against actual personnel and seasons; certified BIS/EN/ANSI items; issue before work, track replacement. Add task-specific PPE from HIRA/JSA/PTW and OISD-STD-155. Do not use 60 accommodation places as total workforce. | OPEN — source requirement; execution not evidenced
P9-13 | Vendor revision gap closed | Combined_Addendum_3.pdf pp261-341 | Offshore Suggested Vendor List Rev12.3, as on 27 March 2026, now located. Prior missing-version finding is closed for this list. | Procurement / Document Control | Use Rev12.3 for revision reconciliation with the reference-only-list amendment. Product/location/status checks remain necessary; current external status not verified. | OPEN — source requirement; execution not evidenced
P9-14 | Vendor restrictions | Combined_Addendum_3.pdf p262 | B1 quotation permitted subject to resolving hold reasons at PS submission; B3 and banned product entries prohibit order placement as stated. B2 rules and manufacturer-location undertakings also apply. | Procurement / QA | Record product, manufacturing location, hold category, evidence and disposition before PO release. Reference-only lists do not erase explicit bans. | OPEN — source requirement; execution not evidenced
P9-15 | Piping material selection | Combined_Addendum_3.pdf pp1-124; material specification 2008 Rev3 | Piping material classes and component schedules are supplied. Index requires missing class sheets needed by approved P&IDs to be prepared using FS2004A for company approval. | Piping / Procurement | Develop surveyed line list, fluid/design pressure-temperature, material class and corrosion allowance; approve PMS, stress/support loads, isometrics and MTO before purchase. Do not apply every class to BRRP. | OPEN — source requirement; execution not evidenced
P9-16 | Welding and NDT | Combined_Addendum_3.pdf pp125-167; FS2009F Rev8 plus Duplex Annex1 Rev1 | Welding/NDT specification and seven scanned duplex annex pages supplied; scanned annex OCR reviewed. Material- and joint-specific applicability is essential. | Welding Engineer / QA | Prepare applicability matrix, approved WPS/PQR and welder qualifications, NDT procedures/personnel/calibration, weld maps, consumable traceability and repair controls. Duplex qualification/testing can be a procurement predecessor where applicable; no blanket structural NDT percentage asserted. | OPEN — source requirement; execution not evidenced
P9-17 | Protective coating | Combined_Addendum_3.pdf pp168-245; FS2005 Rev9 dated12 December2022 | Protective-coating specification is supplied. Selection depends on substrate, exposure, service temperature and approved system. | Coating / QA / Planning | Prepare coating-system schedule, surface preparation/inspection, environmental logs, application/DFT/curing and repair records. Quantify areas from verified MTO; allow curing and inspection before transport. Full system-by-system numerical compliance review remains open. | OPEN — source requirement; execution not evidenced
P9-18 | Bridge piping flexibility | Combined_Addendum_3.pdf pp246-260, piping criteria Rev4; clause5.3 p260 | Bridge piping must account for differential platform movement under extreme storm conditions; assess temperature-range flexibility and required loops/supports. | Piping Stress / Structural | Coordinate bearing movements, piping forces, support stiffness and bridge/platform analyses; close iterative reactions before design release. Generic fire-system text is not proof every system is additional bridge scope. | OPEN — source requirement; execution not evidenced
P9-19 | Schedule impact | P9-03 to P9-18; Appendix C-8 previously reviewed | These inputs create real predecessors for security, material-origin evidence, PS/vendor disposition, qualification, coating and survey/change control. Prior illustrative network is not revalidated by this audit. | Planning Manager | Update package-specific procurement and DCI/MCI review logic, working-day calendars and offshore windows; recalculate CPM only after durations/resources are evidenced. Do not reuse earlier float as an approved forecast. | OPEN — source requirement; execution not evidenced
P9-20 | Remaining version controls | Combined_Addendum_1.pdf p1; P8 and P9 inventories | SVL12.3 found, but positive identification of the announced revised Technical SCC and revised A-3 still requires controlled-document reconciliation. | Document Control / Contracts | Link each governing revision to actual source and issue notice; preserve unresolved drawing revision conflicts and MTO discrepancies. Do not mark all historical inputs fully reconciled. | OPEN — source requirement; execution not evidenced
P14-A | Accountability and authority | SCC1; Technical BEC5.2–5.4 | Appoint named managers and deputies; record availability and competing commitments; establish RACI; set spending/change/technical-release authority; chair weekly integration review. | Project Director | Signed organisation/RACI and delegated-authority register | OPEN — requires named owner and evidence
P14-B | Baseline and requirements | P8–P12; CQ replies; B-4 | Maintain clause-to-deliverable matrix; resolve SCC/GCC precedence using B-4; link revisions and deletions; isolate S&SRP references; freeze controlled scope by bridge and retain open discrepancies. | Contracts Manager | Approved requirements and scope baseline; assumption/change log | OPEN — requires named owner and evidence
P14-C | Contract, qualification and compliance | Technical BEC5; P9/P11 | Check110MT/marine route and consortium exceptions; retain PM/qualifying main activity; obtain subcontract commitments; verify TPI authentication and valid accreditation; reconcile financial evidence; manage securities and integrity-pact disclosures. | Contracts Manager | Qualification/compliance matrix and evidence bundle | OPEN — requires named owner and evidence
P14-D | Design basis and survey | CriteriaPartII; Corrigendum3 GCC2.3.6 | Verify coordinates, elevations, spans, clearances, member sizes/thickness/loss, support movement, piping/cable loads and NDT; create controlled datums; close bearing/camber/load discrepancies; record later company instructions under change control. | Engineering Manager | Accepted survey dossier and bridge-specific design basis | OPEN — requires named owner and evidence
P14-E | Engineering and independent checking | C8; Combined1Annexure1; DesignCriteria | Analyse bridge and supporting platforms, members/joints, bearings, fatigue/VIV, preservice lifts/transport and temporary stages; iterate piping reactions; detail connections; perform independent check and comment closure; submit through controlled DCI. | Engineering Manager | Checked calculations, interface reactions, design reports and accepted drawings | OPEN — requires named owner and evidence
P14-F | Fabrication drawings and AFC release | C8 mother documents; Combined1 pp27–41 | Issue source-to-detail mapping, shop GAs, member/cut lists, joint/weld maps, bearing/guides, padeyes/supports and temporary-stability details; apply source revisions and CRS; independent check then company/CA release as applicable. | Lead Structural Engineer | Signed bridge-specific release index with matching drawing/MTO/procedure revisions | OPEN — requires named owner and evidence
P14-G | Geometry, MTO and weight control | SOW quantity table; MTOIRT; Criteria weight/COG trigger | Separate new bridge, strengthening, new landing, existing landing, demolition and finish quantities; resolve1MT/2m/1m² discrepancies; calculate member-length/plate/bolt/weld/coating MTO and wastage explicitly; track module dry/wet/rigging weights and COG. | Quantity/Weight Engineer | Traceable MTO revisions, reconciliation and verified module weight report | OPEN — requires named owner and evidence
P14-H | HSE and SIMOPS | SCC7/8; PPElist; OISD155 applicability | Complete HIRA/JSA/PTW, isolation/LOTO, hot work, gas testing, work-at-height/rescue, dropped objects, scaffold/access, marine transfers, occupational exposure and emergency interfaces; train staff; issue certified PPE and validate work-start clearance. | HSE Manager | Approved HSE/SIMOPS plan, personnel matrix and permit packs | OPEN — requires named owner and evidence
P14-I | Interface and operations management | SCC1.7; Combined1/2/3 | Register structural/piping/electrical/instrument/telecom/firewater interfaces; agree outage and transfer sequence; assign tie-in owners; confirm access and emergency routes; track support reactions and dimensional tolerances; resolve NQO/NOQ naming. | Interface Manager | Signed interface agreements, outage windows and battery-limit register | OPEN — requires named owner and evidence
P14-J | Joint inspections and quality assurance | FS2009F; FS2005Rev9; C8 | Set inspection/hold/witness points; qualify welding and personnel; control heat/consumable traceability; calibrate instruments; inspect fit-up/weld/NDT/coating/dimensions; repair and close NCRs; issue releases and indexed records. | QA/QC Manager | ITP, qualification dossiers, inspection releases and NCR closure | OPEN — requires named owner and evidence
P14-K | Key suppliers and procurement | SVL12.3 Combined3 pp261–341; Corr3; C8 | Package25 procurement scopes; RFQ and technical/commercial evaluation; verify SVL12.3 status/product/location, steel melt/pour/DVA and traceability; obtain PS approvals, place authorised PO, expedite and inspect; preserve vendor-data dependencies. | Procurement Manager | PO/delivery/inspection register with quoted dates and evidence | OPEN — requires named owner and evidence
P14-L | Logistics, loadout and preservation | SCC14; C9/C10; applicable marine assurance | Verify shore-base storage/load capacity, route permits, lifting gear and packing/preservation; produce cargo ID/weight/COG/manifests; sea fasten and inspect loadout; monitor voyage/receipt and backload; segregate quarantine and accepted stock. | Logistics Manager | Approved loadout/transport pack, manifests and receipt reports | OPEN — requires named owner and evidence
P14-M | Marine engineering and assurance | SCC3/5; C9/C10; C8 starred requirements | Verify actual-radius crane charts, dynamics/rigging/padeyes, deck strength/stability, seafastening/voyage, positioning/mooring/DP, subsea hazards, access/POB and certificates; obtain applicable MWS/company clearances and predeployment audit. | Marine Manager | Accepted vessel/operation assurance pack and go/no-go record | OPEN — requires named owner and evidence
P14-N | Network schedule and calendars | SCC2/11; C8; P14 scenario | Use one logic network with source/assumption status; model office/yard/offshore calendars, approval states and PS stages; link shared resources and completion dossiers; calculate forward/backward paths, target shortfalls and sensitivities; freeze only after validation. | Planning Manager | Approved baseline and update narrative with calculation settings | OPEN — requires named owner and evidence
P14-O | Offshore installation and temporary stability | StructuralSOW addendum; bridge-specific approved methods | Complete preconstruction survey/access; strengthen supports before new bridge placement where required; verify temporary load paths and restraint removal order; authorise lifts, landing alignment/bearing travel and permanent connection; inspect before transfer and removal. | Construction Manager | Signed workfront release, installation survey and inspection dossier | OPEN — requires named owner and evidence
P14-P | Production and fabrication control | MasterPlanV3; FS2009F/2005 | Validate bay dimensions/cranes and shifts; material receipt/heat mapping; cut/form/fit/weld with distortion/camber controls; NDT/repair; dimensional survey/trial fit; coating/curing; preserve and release modules by accepted quantities. | Fabrication Manager | Daily accepted output, resource hours and module release | OPEN — requires named owner and evidence
P14-Q | Quantity, progress and earned value | SCC12; C8 review/progress rules | Measure installed and accepted quantities by workpack; distinguish fabrication/install completion, certification, invoice and cash; apply C8 engineering/MCI status weights only to their contractual bases; retain e-MB/SES traceability; do not earn budget twice. | Project Controls Manager | Signed measurement, progress-rule and cost-code reconciliation | OPEN — requires named owner and evidence
P14-R | Risk, contingency and recovery | SCC11; P14 alternatives | Identify causes/events/effects; score ownership and early-warning; quantify actual schedule/cost exposures when data exist; test material delays, re-reviews, vessel failure and workability; price recovery options and seek authorised decisions. | Risk/Planning Manager | Owned mitigations, contingency and recovery decision log | OPEN — requires named owner and evidence
P14-S | Subcontracts and retained responsibilities | A16/A17/B6; TechnicalBEC5 | Define battery limits and deliverables; retain required PM/main activities; obtain capacity/commitment letters and flow down QA/HSE/integrity obligations; manage approved agencies, claims and performance; prohibit unauthorised whole-works pass-through. | Contracts Manager | Approved responsibility split and signed subcontract evidence | OPEN — requires named owner and evidence
P14-T | Treasury, cost and cash flow | P9/P11 securities; A3/A10; SCC | Track budget/commitment/accrual/actual/ETC/EAC; schedule taxes, wages, charters, vendor payments, BG margins/fees/releases, certification/payment lags, retention/advance recovery and financing; extend through final account/warranty releases. | Finance Manager | Priced control budget and funded cash forecast | OPEN — requires named owner and evidence
P14-U | Utilities and service reinstatement | Combined1/2/3 discipline specifications | List every piping/cable/instrument/lighting/earthing/firewater service; verify temporary bypasses; isolate, transfer, inspect/test and restore under operations control; close pressure/leak, continuity/IR/earthing and functional tests as applicable. | Commissioning Manager | System-wise reinstatement/test sheets and operations acceptance | OPEN — requires named owner and evidence
P14-V | Variations, delay and claims records | SCC9/11; Corr3 clause2.3.6; GCC8 | Log notices and contractual time bars; maintain monthly joint critical-event logs and quarterly delay reports; substantiate quantities/invoices/man/barge days; apply SCC9 positive/negative valuation and avoid duplicate fees; document relief decisions. | Contracts Manager | Notices, joint statements, approved variations and final-account evidence | OPEN — requires named owner and evidence
P14-W | Weather and workability | SCC2/4; C9/C10 | Set engineered operating/abort limits by operation; agree forecast/lookback records and weather standby attribution; plan refuge/demob/remob and emergency triggers; preserve contemporaneous proof for qualifying monsoon relief. | Marine/Planning Manager | Weather logs, operational decisions and seasonal resource plan | OPEN — requires named owner and evidence
P14-X | Execution readiness and daily control | Stages30–35; HSE/QA project controls | Run6week constraint removal,14day lookahead and daily permit/readiness meetings; verify all gates and evidence IDs; record planned/accepted output and crew-hours; escalate blockers and resource clashes without bypassing safety gates. | Construction Manager | Released daily work list, production/constraint records | OPEN — requires named owner and evidence
P14-Y | Yard-to-field completion and handover | A10; C8; SCC14; GCC completion clauses | Create bridge/system turnover boundaries at design stage; collect manufacturing records progressively; inspect structural/bearing alignment and reinstated services; close blocking punch items; deliver as-builts/native files/vendor dossiers and scrap receipts; obtain formal acceptance. | Completion Manager | Accepted turnover dossier and handover certificate | OPEN — requires named owner and evidence
P14-Z | Warranty, final account and lessons | IntegrityPact9; GCC/SCC governing periods | Track defect liability/warranty and insurance/security releases; resolve claims and subcontract final accounts; retain integrity-pact/record obligations; archive controlled native/PDF data and access; close lessons and verify promised performance against outcomes. | Project Director | Contract closure certificate, release schedule and retained records | OPEN — requires named owner and evidence
P8-F01 | SOURCE GAP CLOSED | Combined_Addendum_1 (1).pdf PDF page 27 | B774-101-83-43-0001 ICW-ICG lower-deck dimensioned GA/details is supplied. | Engineering / Document Control | Replace prior missing-GA status with SOURCE RECEIVED / TENDER / VERIFY; update design-input register. | Historical finding; later P9/P11 disposition governs
P8-F02 | SOURCE GAP CLOSED | Combined_Addendum_1 (1).pdf PDF page 31-32 | B774-102-83-43-0001 ICP-ICG lower-deck two-sheet GA/details is supplied. | Engineering | Register both sheets; develop model/member/connection input from source subject to survey and checking. | Historical finding; later P9/P11 disposition governs
P8-F03 | SOURCE GAP CLOSED | Combined_Addendum_1 (1).pdf PDF page 36-41 | BHS-SLQ new GA, landing modifications/extensions and demolition drawing are supplied. | Engineering / Offshore | Map actual103series to BHS installation/service-transfer/demolition engineering; source is not AFC approval. | Historical finding; later P9/P11 disposition governs
P8-F04 | ENGINEERING SCOPE EXPANDED/CLARIFIED | Combined_Addendum_1 (1).pdf PDF page 2 | Annexure specifies10bridge analysis scopes;globaldeckinplace forICP/ICG/ICW/BHS/SLQ;localdeckinplace forWIS/NOQ/NQD/WIN/NC/SC1/SCA/SCF. | Engineering / Planning | Create explicit calculation/deliverable/predecessor rows; verifyNOQ naming againstNQO; do not treat allplatformchecks as one generic activity. | Historical finding; later P9/P11 disposition governs
P8-F05 | APPROVAL/RECORD CLASSIFICATION | Combined_Addendum_1 (1).pdf PDF page 2 | Design basis/methods, reports and AFC drawings show approval;fabrication/as-built columns show records; matrix saysnotexhaustive. | Engineering / QA / Document Control | Revise101itemdraftregister and authority/evidence fields; separate perbridge/landingmethodology submissions. | Historical finding; later P9/P11 disposition governs
P8-F06 | REVIEW CALENDAR CORRECTION | Appendix C-8 DCI MCI.pdf PDF page 2-4;14-18 | ProjectDCI/MCI must befinalised/approved;generally10workingdays review,listedcomplexfirstreviews longer,and subsequentreviews10workingdays. | Planning / Engineering | Replace4calendardayplaceholder engineering review; build working-day calendars, reviewer capacity, staggered submissions and rework loops; recompute forecasts. | Historical finding; later P9/P11 disposition governs
P8-F07 | PREDECESSOR STATE CONTROL | Appendix C-8 DCI MCI.pdf PDF page 3;17-18 | DocumentcategoryA/I/R differs from predecessor stateS/R/A; out-of-sequence documents can be returned withoutreview. | Document Control / Engineering | Map mother documents and required predecessor status; enforce release conditions and preserve baseline revision history. | Historical finding; later P9/P11 disposition governs
P8-F08 | PROGRESS RULE CORRECTION | Appendix C-8 DCI MCI.pdf PDF page 4 | ReviewCatC:noengineeringprogress;CatB:60%engineeringprogress onsubmission perwording;CatA:100%. MCI first/secondstage PS approval earns5%+5%of itemprocurementweight. | Project Controls / Contracts | Reconcile/supersede earlierproposedinternal engineering/procurementcredit rules for contractual reporting; do not interpret as wholeprojectprogress or duplicate A-10billing. | Historical finding; later P9/P11 disposition governs
P8-F09 | PRE-ACTIVITY SUBMISSION/MWS | Appendix C-8 DCI MCI.pdf PDF page 17-18;otherapplicablerows | Starred notes call for30dayadvance submission;double-starred items requireMWS approval whereapplicable. | Marine / Planning | Add submission/assurance milestones and review buffers to relevant operation logic; check row applicability,notblanketassumeallitems. | Historical finding; later P9/P11 disposition governs
P8-F10 | MARINE AUDIT GATES | Appendix C-9.pdf;Appendix C-10.pdf PDF page C9pp1-21 especially20;C10pp1-19 | Vessel particulars, POB, class/statutory/crew/equipment evidence and criticalpre-sail documents are prescribed. | Marine / HSE / Assurance | Create candidate-vessel audit dossiers; schedule inspections/observationclosure/clearances before mobilisation or sail-away as applicable. | Historical finding; later P9/P11 disposition governs
P8-F11 | SUBCONTRACTING CONSTRAINT | Appendix B-6.pdf;Appendix A-9.pdf PDF page B6p1;A9pp4-7 | Work division/locations/commitments and retainedbidderPM/qualifyingmainactivity requirements apply; wholeworksback-to-backsubcontract notallowed. | Contracts / Project Director | Map retained and subcontracted scope against actualBEC route; validate bidder/consortium/subcontractor evidence before commitments. | Historical finding; later P9/P11 disposition governs
P8-F12 | VENDOR REVISION CHECK OPEN | Combined_Addendum_1 (1).pdf;Appendix A-11 Offshore SVL Revision 12.1.pdf PDF page Coverp1;A11pp1-3 | CoverreferencesSVL12.3;separately uploadedlist is12.1. Generaladdendum makeslists reference-only subjecttechnical/tenderrequirements. | Procurement / Contracts | Do notlabel12.1latest; confirm12.3/currentapplicability while retainingqualification/exclusion and technical controls. | Historical finding; later P9/P11 disposition governs
P8-F13 | REVISED SCC/A3 ATTACHMENT MATCH OPEN | Combined_Addendum_1 (1).pdf PDF page Coverp1 | Coverannounces revisedSCC/A3; corresponding full revised attachments are not positivelyidentified inside thetwo combined PDFs. | Contracts / Document Control | Match against earlier/later separatelysuppliedfiles and officialrevision evidence; filename/metadataalone is not precedence proof. Do not freeze commercial/date basis from cover alone. | Historical finding; later P9/P11 disposition governs
P8-F14 | DRAWING REGISTER RECONCILIATION | Combined_Addendum_1 (1).pdf PDF page 3-5;27 | Revisedregister omits some olderstandalone0005references;101GA registershowsRev0 while sheettitleblockshowsA and revisionhistory0. | Document Control / Engineering | Resolve sheet/revision identity; mapold/newreferences; do not keep requesting omittedold0005sheets as definite gaps or assume workdeleted. | Historical finding; later P9/P11 disposition governs
P8-F15 | DISCIPLINE COMPLETENESS | Combined_Addendum_1 (1).pdf;Combined_Addendum_2.pdf PDF page C1pp42-285;C2pp1-250 | Substantial electrical, instrumentation and piping specifications/ITPs/standards are now available. | Discipline Leads / Procurement / QA | Build scope-specific specification/MTO/vendor/test matrix; piping stress reactions must feed structure; attached genericstandards do not automatically create additional facilities. | Historical finding; later P9/P11 disposition governs
P8-F16 | FORM/VERSION COMPLIANCE | Appendix A-9.pdf;Addendum (1).pdf;Appendix B-5.pdf PDF page A9pp4-5;Addendump1;B5p1 | OriginalA9item13 yard-information provision is deleted byaddendum;experienceforms and qualifyingthresholdreferences requireBEC cross-check. | Contracts / Bid Compliance | Maintain amendedcompliance matrix; do notapplydeletedclause ordeclareeligibilityfromaformalone. | Historical finding; later P9/P11 disposition governs
P10-01 | Scope applicability | Section1.pdf pp1,6-8; Section2.pdf p1; Section3.pdf p1 | All three Sections identify S&SRP (Sump Caisson and SWLP Casing Replacement Project). Section1 describes SWLP casings, vent booms, heaters, PBIV, caissons and RS-21 repairs. Shared platform names do not prove BRRP scope. | Workstream accountable owner | Prepare an applicability matrix linking any adopted requirement to BRRP incorporation/contract reference. Retain these sources separately until applicability is established. | Carry-forward action; requires actual evidence
P10-02 | New source contents | inventory.json | Section1, the CSV, Stage4 and Stage5 are four distinct contents without exact prior local matches. Ten successfully transferred uploads match earlier local files; Stage10 variants are also identical to one another. | Workstream accountable owner | Do not assume no prior hash match proves a later revision; reconcile cell-level changes and issuance before superseding earlier plans. | Carry-forward action; requires actual evidence
P10-03 | Network logic | CSV BR0002, BR0003, BR0005, BR0007, BR0008; complete exceptions sheet | 87 activity records. Screening finds54 FS-linked successors starting on or before their predecessor finish day, using the supplied day numbers and assuming no lag because no lag field is present. BR0002 starts day5 after BR0001 finishing day10; BR0007 starts76 after BR0006 finishing99. Same-day cases depend on timing convention. | Workstream accountable owner | Resolve intended FS/SS relations, lags and inclusive-day conventions; validate calendars and import mapping. Do not call these dates a calculated CPM baseline or change relations merely to preserve target dates. | Carry-forward action; requires actual evidence
P10-04 | Resource feasibility | Stage4 Resource Estimates C2:I11; Stage5 Yard Production C2:J11 | Productivity and crew/vessel inputs are unfilled in the sampled resource tables. Stage5 yard allocations are TBD and release gates pending; Ready for loadout is NO. | Workstream accountable owner | Obtain yard outputs, working shifts, named crews, crane charts, vessel availability and shutdown windows; then calculate durations and resource-level the network. | Carry-forward action; requires actual evidence
P10-05 | Spreadsheet calculation state | Workbook sheet inventory | Some Stage4/5 formulas have no stored calculated value; many deliberately return blank for missing inputs. Stage25 also has uncached formula outputs. This does not establish an Excel error; Python inspection does not recalculate formulas. | Workstream accountable owner | Distinguish missing input, blank formula result and stale/missing cache. Recalculate an editable copy in Excel after verified inputs and perform checks; no recalculation claim is made here. | Carry-forward action; requires actual evidence
P10-06 | Cost estimate completeness | Stage25 READ ME B2:B9; Stage26 Commercial Inputs B3:B13 and Controls and Caveats | Financial models explicitly remain illustrative/unpriced. Zero contract value and zero cost inputs mean unknown, not zero exposure. Tonnage allocation is provisional. | Workstream accountable owner | Build priced WBS estimates from quotations, quantities, marine spread days, overheads, risk and taxes; reconcile to signed terms and actual commercial status. | Carry-forward action; requires actual evidence
P10-07 | Funding horizon | Stage26 Controls and Caveats rows5-9; CEO Decision Dashboard C5 | 29-week scenario excludes part of contract life. The workbook states retention is withheld but eventual release is not added; advance recovery needs verification; proposed certification/payment lags require confirmation. | Workstream accountable owner | Extend cash flow through completion, payment delays, retention/warranty/security release and final account. Add explicit advance recovery, BG margin release, tax and financing events and reconcile against milestones; then recalculate peak funding. | Carry-forward action; requires actual evidence
P10-08 | Contract duration | Stage25 READ ME B3:B4; earlier Technical SCC completion provision | 1 November2026 and360 days are planning assumptions. Earlier reviewed SCC states12 months from NOA;360 days is not automatically equivalent to12 months. | Workstream accountable owner | Use controlled governing SCC/award, actual commencement evidence, monsoon rules and approved extensions; align all workbooks to one date/calendar basis. | Carry-forward action; requires actual evidence
P10-09 | MTO reconciliation | Stage25 READ ME B5:B7; Stage10 CEO Decisions row3 | Printed structural total1142MT versus detailed rows1141MT remains acknowledged and unresolved. Labels such as Verified MTO are not approval evidence. | Workstream accountable owner | Maintain discrepancy register and obtain detailed engineering quantity reconciliation before procurement commitments; retain other prior handrail/grating discrepancies. | Carry-forward action; requires actual evidence
P10-10 | Baseline gates | Level3 P6 Preparation, Baseline Readiness rows2-13; Stage10 360D Logic | Workbooks identify award, survey, lift/COG, vessels, shutdowns, productivity, DCI/MCI and CPM as open. Target-day gates are proposals. | Workstream accountable owner | Connect each gate to an evidence owner, due date, document and acceptance; do not promote planned day360 completion or dashboard labels to proof of readiness. | Carry-forward action; requires actual evidence
P10-11 | Newer tender amendments | P9 impact report; C8 DCI/MCI previously reviewed | This upload does not itself demonstrate integration of revised security, steel-origin, vendor12.3, review-working-day, welding/coating and PPE requirements. | Workstream accountable owner | Cross-reference P9 findings into procurement, engineering review, QA, financing and schedule predecessors before the next consolidated baseline issue. | Carry-forward action; requires actual evidence
P10-12 | Unreviewed large PDF | SHIVANSH ONGC Offshore Bridges - PRELIMINARY.pdf | Transfer failed: file exceeds the executor32MiB limit. Its content was not opened or reviewed. The similarly named Excel was opened but equivalence cannot be assumed. | Workstream accountable owner | Keep PDF explicitly pending. The other14 successfully transferred files have been inventoried without requiring this PDF. | Carry-forward action; requires actual evidence
P11-01 | Tender date sequence | TBOextension050526.pdf p1;250526 p1;090626 p1 | Submission:6 May→26 May→9 June→23 June2026,15:00IST. Unpriced opening:7 May→27 May→10 June→24 June2026,15:30IST. These notices share Tender ID2026_ONGC_273234_1. | Workstream accountable owner | Use23/24June as the latest dates evidenced by these supplied notices only. Actual opening, subsequent extensions and award are not independently confirmed. | Carry-forward action; requires actual evidence
P11-02 | SCC revision remains unresolved | Four Technical_SCC PDFs; SHA inventory | All four SCC uploads are byte-identical and match the earlier15-page SCC. No newly distinguishable revised SCC is established by this batch. | Workstream accountable owner | Keep the revised-SCC issue open; reconcile the controlled issue/transmittal against the23April addendum announcement. Do not infer revision from filename suffix. | Carry-forward action; requires actual evidence
P11-03 | A-3 revision remains unresolved | A-3 PRICE SCHEDULE sheet; SHA inventory | A-3 is byte-identical to the earlier supplied workbook. It is not proof of the announced revised A-3 version. | Workstream accountable owner | Maintain base workbook plus amendment overlays, including AddendumtoA3. Require positive version/issue mapping before final pricing and cash-flow approval. | Carry-forward action; requires actual evidence
P11-04 | A-10 obsolete lines require overlay | A-10 Milestone Payment Formula rows30-35,53-54; previous general Addendum | Uploaded A-10 still contains3% Mob and3% Demob lines. Previous general amendment deletes items12/13 and changes the repair-material-arrival milestone20%→25%. | Workstream accountable owner | Do not count those deleted separate payments in forecast receipts. Reconcile the entire amended milestone allocation and governing price base; do not assume rental/marine schedule lines are also deleted. | Carry-forward action; requires actual evidence
P11-05 | Completion and marine criteria | SCC p2 clauses2,3 | 12months from NOA. Monsoon16May–15October inclusive: conditional time relief for inability to work due to adverse weather, without extra mob/demob cost. Minimum60 special-personnel accommodation; minimum5tonne crane is for transfers, not proof of bridge lifting capability. | Workstream accountable owner | Use actual award, approved weather records and extension decisions. Engineer lift capacity at working radius using verified module/rigging weight, COG and marine conditions. | Carry-forward action; requires actual evidence
P11-06 | Marine compliance timing | SCC p3 clauses5.1–5.5 | Company predeployment and periodic audits apply. DGS phased lifeboat compliance in this source lists70% through15May2027 and100% beyond, with prior ONGC approval of phased compliance and additional provisions. | Workstream accountable owner | Check applicable current statutory requirements and company approvals at mobilisation; do not treat historical table as unconditional permission for a noncompliant vessel. | Carry-forward action; requires actual evidence
P11-07 | Painting and PPE acceptance | SCC p3 clause6; p9 clause8.5.3 | Paint applicator/manufacturer MOU and continuous manufacturer representative during platform maintenance painting are specified. PPE issue evidence is a work-start gate; non-use can cause stoppage and penalties as stated. | Workstream accountable owner | Include manufacturer attendance, joint-guarantee documentation, PPE issue/verification and replacement records in readiness and cost plans; reconcile P9 PPE list. | Carry-forward action; requires actual evidence
P11-08 | Delay records and e-measurement | SCC p13 clauses11,12 | Quarterly joint delay/progress analysis and monthly critical/near-critical activity logs are required. Daily measurements must enter digital e-MB; billing is linked to e-MB validation and approvals. | Workstream accountable owner | Add monthly signed logs, quarterly delay-review deliverables and e-MB/SES billing predecessors. Offline spreadsheets do not replace the required portal record; no portal entries were made. | Carry-forward action; requires actual evidence
P11-09 | LD and scrap disposal | SCC pp14-15 clauses13,14 | Progressive weekly LD slabs0.1/0.2/0.3/0.4%, capped as stated, include monsoon-rate provisions distinct from clause2 relief. Scrap handling, sea fastening, transport and handover at Nhava/Pipavav are contractor scope. | Workstream accountable owner | Model LD only against governing dates, scope bases and approved relief. Include scrap manifests, cargo capacity, port handling and handover evidence; reconcile A-10 named-port condition before claiming payment. | Carry-forward action; requires actual evidence
P11-10 | Technical qualification route | Technical BEC pp3-8 clauses5.1–5.4; original scanned11pages OCRed | Steel experience route explicitly states110MT in one project; marine route requires1000GT/GRT and6months/one construction season. Clauses5.3A/B specify consortium requirements unless the bidder also establishes the complementary experience. PM and qualifying main activities must be retained as specified. | Workstream accountable owner | Reconcile A-9 legacy350MT wording against these specific BEC clauses and amendments; record discrepancy formally. Qualification needs the full route and evidence, not110MT alone. No Shivansh eligibility determination made. | Carry-forward action; requires actual evidence
P11-11 | Deleted yard criterion versus execution capacity | Technical BEC p8 clause5.5; previous general Addendum | The original scanned BEC still contains yard-adequacy clause5.5; earlier general amendment deletes it. | Workstream accountable owner | Apply the deletion in bid evaluation. Continue execution-stage yard/resource capacity checks without presenting the deleted criterion as mandatory tender qualification. | Carry-forward action; requires actual evidence
P11-12 | TPI authentication | Technical BEC pp8,10-11 clause5.6 | Specified technical-BEC documents require empanelled TPI verification, original-authenticity wording and certificate; ONGC-issued experience documents and bidder self-undertakings have specified exclusions. Accreditation must be valid at verification date. | Workstream accountable owner | Check actual NABCB TypeA ISO/IEC17020 status and empanelment when appointing. Printed list includes expired dates; listing alone is not proof of current validity. Source is OCR; verify decisive wording against scans. | Carry-forward action; requires actual evidence
P11-13 | Financial qualification | General BEC DOCX paragraphs99,106 and surrounding financial section | Base financial section states turnover INR3,65,38,82,460 (365.388246crore) and working capital INR1,09,61,64,738 (109.6164738crore), with net-worth and evidence provisions. | Workstream accountable owner | Confirm amended applicability, financial-year rules, support/JV route and auditor certification using the complete financial section. These thresholds are eligibility criteria, not project budget or available funding. | Carry-forward action; requires actual evidence
P11-14 | Response forms and amendments | BRS workbook; BidderGTE workbook; ITB/GCC; P9 corrigenda | BRS and BidderGTE contents have no exact prior local hash match in this audit; this does not establish a new issued revision. Base forms must be read with corrigenda on45-day bid security, validity anchor, performance security and steel-origin evidence. | Workstream accountable owner | Complete clause-to-form matrix without fabricating confirmations. Cross-check BRS versus A-3 and actual priced/unpriced cover requirements; preserve base documents and amendment precedence. | Carry-forward action; requires actual evidence
P11-15 | Scope and source reuse | Specification Combined257pages; SOW/Bridge Report506pages; inventory | These are exact matches to prior local sources. Two SOW filenames are identical. Prior bridge geometry, source MTO discrepancies and design issues are not closed by re-upload. | Workstream accountable owner | Reuse prior analyses and retain references. Do not relabel tender GAs AFC or claim member/joint checks completed because the source set is repeated. | Carry-forward action; requires actual evidence
P13-01 | Master-plan status | Volumes4–6 document status and source-basis paragraphs | Volumes describe pre-award management planning, not construction release. Repeated copies are not proof of implementation or approval. | Workstream accountable owner | Use these as management frameworks; link every bridge-specific deliverable to a controlled drawing/calculation, owner, due date and acceptance record. | Carry-forward action; requires actual evidence
P13-02 | Marine plan | Volume4 clauses4.1–4.10 | Four proposed campaigns are management groupings, not four proven charters. Vessel selection, engineered module weights/COG, transport/lift/removal checks, permits and go/no-go gates remain evidence requirements. | Workstream accountable owner | Close module-by-module geometry/weight/COG and rigging; crane radius/configuration, deck strength/stability, positioning, weather workability, assurance and charter availability. Never treat282MT BHS package quantity as a single lift weight. | Carry-forward action; requires actual evidence
P13-03 | Internal logistics targets | Volume4 clause4.6 | 14-day cargo readiness and72-hour manifest are proposed management controls. They are not established here as ONGC contractual notice periods. | Workstream accountable owner | Mark proposed internal targets separately from mandatory contractual notices; coordinate actual shore-base and vessel booking requirements. | Carry-forward action; requires actual evidence
P13-04 | Schedule planning windows | Volume5 clauses5.1,5.3,5.5,5.10 | Provisional day-number windows and360-day target are expressly unvalidated. Volume5 states feasibility is not demonstrated. | Workstream accountable owner | Reconcile12months-from-NOA SCC against the360-day planning target; use actual commencement evidence, review-working-day calendars, monsoon conditions and resource capacity before approving baseline. | Carry-forward action; requires actual evidence
P13-05 | XML structural checks | ProjectLibre XML Tasks/PredecessorLink; XML_schedule_audit.json | 207 non-summary tasks,124 predecessor links. No duplicate task UIDs, missing referenced predecessor IDs or directed cycles found by structural screening. All links have Type1 (FS in Microsoft Project XML). | Workstream accountable owner | These checks establish parseable link structure only. Import compatibility and scheduling-engine calculations were not tested in ProjectLibre/P6. | Carry-forward action; requires actual evidence
P13-06 | Open network ends | XML link audit | 83 tasks have no predecessor;83 have no successor;17 are isolated. Multiple package starts/finishes can be intentional, but no integrated completion-path proof follows. | Workstream accountable owner | Review every open end and connect required engineering, procurement, inspection, fabrication, logistics, marine, installation and turnover gates. Add genuine project start/completion logic; do not add arbitrary links merely to reduce counts. | Carry-forward action; requires actual evidence
P13-07 | XML calendar and duration semantics | XML StartDate/Calendars/MinutesPerDay; task Notes | Start is assumed1November2026 at08:00; calendar is Standard5-day Placeholder with8hours/day and no calendar exceptions. Example first survey duration224hours corresponds28workingdays; provisional day windows in Notes are not calculated dates. | Workstream accountable owner | Establish calendar meaning for each task. Separate working-day engineering review, yard shifts, marine offshore calendars, weather/season restrictions and approved relief; re-evaluate durations from quantities/productivity. | Carry-forward action; requires actual evidence
P13-08 | Missing resource and CPM evidence | XML Resources/Assignments and task fields | No resources or assignments are present. Examined task fields do not establish calculated start/finish, total float or an accepted critical path. | Workstream accountable owner | Assign named capacity/units, work shifts, vessels, crews and workfront constraints. Run CPM then resource feasibility and sensitivity checks; retain scheduler settings and calculation logs. No revalidated finish date is claimed by this review. | Carry-forward action; requires actual evidence
P13-09 | Commercial and progress controls | Volume6 clauses6.1–6.4,6.9 | Cost/commitment/accrual/actual, earned value, certified progress and cash receipts are distinct controls. Generic framework text does not populate project budgets or demonstrate bank funding. | Workstream accountable owner | Link approved WBS quantities/rates and cost accounts to activity progress rules, amended A-10 milestones, invoicing/e-MB and full-life cash flow. Apply P9/P11 security, tax and amendment findings. | Carry-forward action; requires actual evidence
P13-10 | Quality, HSE and turnover | Volume6 clauses6.5–6.10 | QA/HSE/emergency/risk/turnover provisions specify required systems and evidence; tables and narrative do not establish that tests, drills, inspections or handovers occurred. | Workstream accountable owner | Issue scoped ITP/WPS/PQR/NDT/coating matrices; competent personnel and equipment records; HIRA/JSA/PTW/SIMOPS and emergency interfaces; bridge-wise completion, service reinstatement, scrap and acceptance dossiers. | Carry-forward action; requires actual evidence
P13-11 | Benchmark claims | Volumes4–6 external EPC benchmark statement | References to Saipem and McDermott are general benchmarks. This batch supplies no independent comparative performance evidence or verified internal company manuals. | Workstream accountable owner | Describe adopted practices and measurable controls without claiming superiority to either EPC contractor. | Carry-forward action; requires actual evidence
P13-12 | Reconciliation carry-forward | Volumes4–6 quantity basis; P8–P12 reviews | Repeated SOW/specification/tender material does not close MTO discrepancies, design questions, revised SCC/A-3 issue identity or engineering approvals. | Workstream accountable owner | Maintain open-item history, source precedence and amendment overlays; do not mark rows closed because a file was re-uploaded. | Carry-forward action; requires actual evidence
P13-13 | Unclassified file | ticket.pdf; unique-content extract | Classify separately based on actual content. A personal/travel document does not change project technical or commercial scope merely because uploaded with tender documents. | Workstream accountable owner | Exclude unrelated personal information from shared project deliverables; do not treat a ticket as project award, approval or mobilisation evidence without a relevant explicit reference. | Carry-forward action; requires actual evidence

## Bridge MTO
Bridge | Work type | New bridge MT | Bridge strengthen MT | New landing MT | Landing strengthen MT | Demolition MT | Handrail m | Grating m2 | GI sheet m2 | Construction MT | Status
ICW-ICG UD | Strengthening | 0 | 19 | 0 | 30 | 25 | 110 | 58 | 273 | 49 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
ICW-ICG LD | New/replacement | 57 | 0 | 65 | 0 | 1 | 118 | 88 | 0 | 122 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
ICG-ICP UD | Strengthening | 0 | 86 | 0 | 30 | 25 | 93 | 49 | 419 | 116 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
ICG-ICP LD | New/replacement | 115 | 0 | 45 | 0 | 1 | 176 | 132 | 0 | 160 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
BHS-SLQ | Replacement/services | 195 | 0 | 87 | 0 | 210 | 88 | 82 | 332 | 282 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
SLQ-WIS | Strengthening | 0 | 61 | 0 | 30 | 15 | 98 | 51 | 0 | 91 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
NQO-NQD | Strengthening | 0 | 63 | 0 | 30 | 25 | 93 | 58 | 250 | 93 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
WIN-NC | Strengthening | 0 | 6 | 0 | 40 | 10 | 45 | 29 | 0 | 46 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
SCA-SC1 | Strengthening | 0 | 35 | 0 | 28 | 15 | 88 | 55 | 0 | 63 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM
SCA-SCF | Strengthening | 0 | 91 | 0 | 28 | 30 | 257 | 116 | 0 | 119 | SOURCE TRANSCRIPTION; NOT PROCUREMENT BOM

## MTO Reconciliation
Item | Printed total | Sum source rows | Difference | Action
New bridge MT | 367 | 367 | 0 | Verify released design
Bridge strengthen MT | 361 | 361 | 0 | Verify released design
New landing MT | 197 | 197 | 0 | Verify released design
Landing strengthen MT | 217 | 216 | 1 | Resolve source discrepancy
Structural MT | 1142 | 1141 | 1 | Resolve before purchase baseline
Demolition MT | 357 | 357 | 0 | Verify removal allocations
Handrail m | 1168 | 1166 | 2 | Resolve source discrepancy
Grating m2 | 719 | 718 | 1 | Resolve source discrepancy
GI sheeting m2 | 1274 | 1274 | 0 | Verify design areas

## Design Basis
Parameter | Source criterion / query | Reference | Required resolution
Design life | New bridges25years | CriteriaPartII p119 | Confirm remaining/new component applicability
Elastic modulus | 210000MPa | Criteria p66 | Use approved material model
Density | 7850kg/m3 | Criteria p66 | Coatings/attachments/rigging separate
Global walkway live load | 250kg/m2 | Criteria pp42–43 | Do not replace local grating criteria
Local grating load | 500kg/m2 | Criteria p70 | Apply local design/approved combinations
Clear walkway | At least1.2m plus services allowance | Criteria pp42–43 | Verify actual service envelope
Piping load allowance | Operating/planned future plus20% as stated | Criteria pp42–43 | Resolve double-counting of future services
Bearing system | Pinned/hinged and sliding/PTFE-equivalent with guides | Criteria pp42–43 | Resolve BHS fixed/sliding source conflict
Movement/thrust | 150% specified platform translations/thrust basis | Criteria pp42–43 | Use verified platform movements and reactions
Deflection | Vertical L/400;lateral wind L/500 | Criteria p86 | Verify governing span and load case
Camber | Compensate DL; studies and generic L/200 conflict | Criteria/source bridge studies | Resolve profile rather than assume L/200
Weight/COG reanalysis | Weight>5%;COG>2% corresponding dimension | Criteria p20 | Track engineered thresholds and actual modules
Strengthening sequence | ICG/ICP/BHS wrap additions before new placement | Structural SOW addendum p1 | Engineer connection/stability; raw shell mass not capacity proof
Piping movement | Differential platform movement/extreme storm flexibility | Combined3 p260 clause5.3 | Iterate stress/support/bearing reactions
Geometry reference | Tender dimensions indicative; survey required | Combined1 GA notes; A9 | Do not adopt study span as surveyed geometry

## Engineering DCI
Proposed document ID | Bridge/platform | Deliverable | Mother/input dependency | Document category A/I/R | Review disposition A/B/C | Status | Source/evidence | Owner
SHV-B01-DB-R0 | ICW-ICG UD | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-SUR-R0 | ICW-ICG UD | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-ANA-R0 | ICW-ICG UD | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-PRE-R0 | ICW-ICG UD | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-SUP-R0 | ICW-ICG UD | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-JNT-R0 | ICW-ICG UD | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-GA-R0 | ICW-ICG UD | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-SHOP-R0 | ICW-ICG UD | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-BRG-R0 | ICW-ICG UD | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-TMP-R0 | ICW-ICG UD | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-LFT-R0 | ICW-ICG UD | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-MTO-R0 | ICW-ICG UD | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-IWP-R0 | ICW-ICG UD | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-ITP-R0 | ICW-ICG UD | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B01-TEST-R0 | ICW-ICG UD | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-ASB-R0 | ICW-ICG UD | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B01-TO-R0 | ICW-ICG UD | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B02-DB-R0 | ICW-ICG LD | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-SUR-R0 | ICW-ICG LD | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-ANA-R0 | ICW-ICG LD | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-PRE-R0 | ICW-ICG LD | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-SUP-R0 | ICW-ICG LD | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-JNT-R0 | ICW-ICG LD | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-GA-R0 | ICW-ICG LD | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-SHOP-R0 | ICW-ICG LD | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-BRG-R0 | ICW-ICG LD | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-TMP-R0 | ICW-ICG LD | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-LFT-R0 | ICW-ICG LD | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-MTO-R0 | ICW-ICG LD | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-IWP-R0 | ICW-ICG LD | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-ITP-R0 | ICW-ICG LD | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B02-TEST-R0 | ICW-ICG LD | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-ASB-R0 | ICW-ICG LD | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B02-TO-R0 | ICW-ICG LD | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B03-DB-R0 | ICG-ICP UD | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-SUR-R0 | ICG-ICP UD | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-ANA-R0 | ICG-ICP UD | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-PRE-R0 | ICG-ICP UD | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-SUP-R0 | ICG-ICP UD | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-JNT-R0 | ICG-ICP UD | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-GA-R0 | ICG-ICP UD | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-SHOP-R0 | ICG-ICP UD | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-BRG-R0 | ICG-ICP UD | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-TMP-R0 | ICG-ICP UD | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-LFT-R0 | ICG-ICP UD | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-MTO-R0 | ICG-ICP UD | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-IWP-R0 | ICG-ICP UD | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-ITP-R0 | ICG-ICP UD | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B03-TEST-R0 | ICG-ICP UD | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-ASB-R0 | ICG-ICP UD | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B03-TO-R0 | ICG-ICP UD | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B04-DB-R0 | ICG-ICP LD | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-SUR-R0 | ICG-ICP LD | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-ANA-R0 | ICG-ICP LD | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-PRE-R0 | ICG-ICP LD | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-SUP-R0 | ICG-ICP LD | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-JNT-R0 | ICG-ICP LD | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-GA-R0 | ICG-ICP LD | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-SHOP-R0 | ICG-ICP LD | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-BRG-R0 | ICG-ICP LD | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-TMP-R0 | ICG-ICP LD | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-LFT-R0 | ICG-ICP LD | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-MTO-R0 | ICG-ICP LD | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-IWP-R0 | ICG-ICP LD | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-ITP-R0 | ICG-ICP LD | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B04-TEST-R0 | ICG-ICP LD | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-ASB-R0 | ICG-ICP LD | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B04-TO-R0 | ICG-ICP LD | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B05-DB-R0 | BHS-SLQ | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-SUR-R0 | BHS-SLQ | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-ANA-R0 | BHS-SLQ | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-PRE-R0 | BHS-SLQ | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-SUP-R0 | BHS-SLQ | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-JNT-R0 | BHS-SLQ | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-GA-R0 | BHS-SLQ | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-SHOP-R0 | BHS-SLQ | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-BRG-R0 | BHS-SLQ | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-TMP-R0 | BHS-SLQ | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-LFT-R0 | BHS-SLQ | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-MTO-R0 | BHS-SLQ | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-IWP-R0 | BHS-SLQ | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-ITP-R0 | BHS-SLQ | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B05-TEST-R0 | BHS-SLQ | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-ASB-R0 | BHS-SLQ | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B05-TO-R0 | BHS-SLQ | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B06-DB-R0 | SLQ-WIS | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-SUR-R0 | SLQ-WIS | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-ANA-R0 | SLQ-WIS | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-PRE-R0 | SLQ-WIS | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-SUP-R0 | SLQ-WIS | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-JNT-R0 | SLQ-WIS | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-GA-R0 | SLQ-WIS | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-SHOP-R0 | SLQ-WIS | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-BRG-R0 | SLQ-WIS | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-TMP-R0 | SLQ-WIS | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-LFT-R0 | SLQ-WIS | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-MTO-R0 | SLQ-WIS | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-IWP-R0 | SLQ-WIS | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-ITP-R0 | SLQ-WIS | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B06-TEST-R0 | SLQ-WIS | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-ASB-R0 | SLQ-WIS | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B06-TO-R0 | SLQ-WIS | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B07-DB-R0 | NQO-NQD | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-SUR-R0 | NQO-NQD | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-ANA-R0 | NQO-NQD | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-PRE-R0 | NQO-NQD | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-SUP-R0 | NQO-NQD | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-JNT-R0 | NQO-NQD | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-GA-R0 | NQO-NQD | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-SHOP-R0 | NQO-NQD | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-BRG-R0 | NQO-NQD | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-TMP-R0 | NQO-NQD | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-LFT-R0 | NQO-NQD | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-MTO-R0 | NQO-NQD | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-IWP-R0 | NQO-NQD | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-ITP-R0 | NQO-NQD | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B07-TEST-R0 | NQO-NQD | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-ASB-R0 | NQO-NQD | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B07-TO-R0 | NQO-NQD | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B08-DB-R0 | WIN-NC | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-SUR-R0 | WIN-NC | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-ANA-R0 | WIN-NC | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-PRE-R0 | WIN-NC | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-SUP-R0 | WIN-NC | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-JNT-R0 | WIN-NC | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-GA-R0 | WIN-NC | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-SHOP-R0 | WIN-NC | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-BRG-R0 | WIN-NC | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-TMP-R0 | WIN-NC | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-LFT-R0 | WIN-NC | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-MTO-R0 | WIN-NC | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-IWP-R0 | WIN-NC | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-ITP-R0 | WIN-NC | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B08-TEST-R0 | WIN-NC | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-ASB-R0 | WIN-NC | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B08-TO-R0 | WIN-NC | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B09-DB-R0 | SCA-SC1 | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-SUR-R0 | SCA-SC1 | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-ANA-R0 | SCA-SC1 | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-PRE-R0 | SCA-SC1 | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-SUP-R0 | SCA-SC1 | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-JNT-R0 | SCA-SC1 | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-GA-R0 | SCA-SC1 | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-SHOP-R0 | SCA-SC1 | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-BRG-R0 | SCA-SC1 | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-TMP-R0 | SCA-SC1 | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-LFT-R0 | SCA-SC1 | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-MTO-R0 | SCA-SC1 | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-IWP-R0 | SCA-SC1 | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-ITP-R0 | SCA-SC1 | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B09-TEST-R0 | SCA-SC1 | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-ASB-R0 | SCA-SC1 | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B09-TO-R0 | SCA-SC1 | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B10-DB-R0 | SCA-SCF | Bridge-specific design basis | Survey and controlling criteria | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-SUR-R0 | SCA-SCF | Pre-engineering/condition survey dossier | Access, survey and NDT | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-ANA-R0 | SCA-SCF | Global bridge/serviceability/fatigue/VIV analysis | DB/SUR accepted | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-PRE-R0 | SCA-SCF | Preservice lift/transport/temporary-stage analysis | Module envelope and vessel inputs | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-SUP-R0 | SCA-SCF | Landing/deck/support and interface reaction report | Bridge/piping reactions | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-JNT-R0 | SCA-SCF | Connection/member/bearing check report | Global forces and verified materials | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-GA-R0 | SCA-SCF | General arrangement and geometry details | Accepted mother analysis | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-SHOP-R0 | SCA-SCF | Shop member, weld, joint and erection details | GA and checked connection calculations | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-BRG-R0 | SCA-SCF | Bearing, guides, setting and restraints | Movement/thrust and temperature envelope | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-TMP-R0 | SCA-SCF | Temporary supports/stability and strengthening details | Stage analyses and surveyed condition | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-LFT-R0 | SCA-SCF | Lift/rigging/padeye/loadout procedure and drawings | PRE/vessel/weight/COG | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-MTO-R0 | SCA-SCF | Detailed structural and services MTO | Released details and class specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-IWP-R0 | SCA-SCF | Installation/service-transfer/demolition work pack | Design, material, access and approved sequence | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-ITP-R0 | SCA-SCF | Inspection and test plan/records index | Applicable QA specifications | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-B10-TEST-R0 | SCA-SCF | Service reinstatement and acceptance procedures | Approved system boundaries | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-ASB-R0 | SCA-SCF | As-built/native model/vendor dossier | Verified final configuration | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | Engineering
SHV-B10-TO-R0 | SCA-SCF | Turnover and acceptance dossier | Completed records/punch closure | TBC in project DCI/MCI | TBC | NOT SUBMITTED | No signed approval evidence | QA/Completions
SHV-PLAT-ICP | ICP | Global deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-ICG | ICG | Global deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-ICW | ICW | Global deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-BHS | BHS | Global deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-SLQ | SLQ | Global deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-WIS | WIS | Local deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-NOQ/NQO | NOQ/NQO | Local — name query deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-NQD | NQD | Local deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-WIN | WIN | Local deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-NC | NC | Local deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-SC1 | SC1 | Local deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-SCA | SCA | Local deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural
SHV-PLAT-SCF | SCF | Local deck inplace assessment | Verified geometry + reactions | TBC | TBC | NOT SUBMITTED | Combined1 Annexure1 p2 | Structural

## Tender GA Mapping
Bridge | Source drawing | Source PDF page | Use | Open issue
ICW–ICG LD | B774-101-83-43-0001 | Combined1 p27 | Tender GA/source detailing | RegisterRev0 vs titleRevA; survey verification
ICP–ICG LD | B774-102-83-43-0001 sheets1–2 | Combined1 pp31–32 | Tender GA/source detailing | Mother calculation and survey required
BHS–SLQ | B774-103-83-43-0001 | Combined1 p36 | Tender replacement GA | Bearing orientation/camber/services resolution
BHS–SLQ old removal | B774-103-83-43-0006 | Combined1 p41 | Tender removal reference | Approved service transfer/temporary stability required
All bridges | MTO Drawings IRT and Combined1 register | MTOIRT34pages; Combined1 pp3–5 | Strengthening/landing/general detail sources | Map34entry updated register vs older38 before omission decisions

## Procurement 25
Package | Scope | Engineering input | Quantity/compliance basis | Owner | Price | Supplier date | Release gate | Status
STEEL-B01 | ICW-ICG UD structural material | B01-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B02 | ICW-ICG LD structural material | B02-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B03 | ICG-ICP UD structural material | B03-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B04 | ICG-ICP LD structural material | B04-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B05 | BHS-SLQ structural material | B05-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B06 | SLQ-WIS structural material | B06-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B07 | NQO-NQD structural material | B07-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B08 | WIN-NC structural material | B08-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B09 | SCA-SC1 structural material | B09-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
STEEL-B10 | SCA-SCF structural material | B10-MTO/AFC + PS | Verified member/plate BOM; grade; heat/MTC/origin | Procurement | UNPRICED | UNCONFIRMED | PS/material inspection release | OPEN
BEAR | Bearings, sliding interfaces and guides | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Engineering | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
GRAT | Grating, handrail and GI sheet supply | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Procurement | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
PIPE | Piping tie-ins, fittings and supports | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Piping | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
ELEC | Electrical materials and bonding | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Electrical | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
INST | Instrumentation/cable interface materials | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Instrumentation | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
COAT | Qualified coating system supply | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Coating | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
NDT | NDT, welding qualification and consumables | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | QA | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
MAR | Heavy-lift and accommodation spread readiness | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Marine | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
CARGO | Cargo vessel and shore-base readiness | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Logistics | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
SURV | Survey services mobilisation | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Survey | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
DES | Design agency capacity confirmation | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Engineering | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
TPI | TPI/CA services and audit arrangements | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | QA | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
SCAF | Scaffolding/access and temporary works supply | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Construction | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
PPE | Certified PPE and training readiness | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | HSE | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN
TRAY | Cable trays and support steel interfaces | Applicable approved requisition/PS/service scope | Quantity/specification/applicability to be confirmed | Electrical | UNPRICED | UNCONFIRMED | Applicable QA/company readiness release | OPEN

## Workpack Readiness
IWP | Bridge | Task | Unit | Verified quantity | Evidence index | AFC | Material | Access PTW | Crew tools | ITP QA | Marine SIMOPS | Method | Company release | Readiness screen | Acceptance evidence | Authorised release
B01-SUR | ICW-ICG UD | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B01-ENG | ICW-ICG UD | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B01-MAT | ICW-ICG UD | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B01-FAB | ICW-ICG UD | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B01-COAT | ICW-ICG UD | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B01-LOAD | ICW-ICG UD | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B01-SUP | ICW-ICG UD | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B01-INST | ICW-ICG UD | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B01-SERV | ICW-ICG UD | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B01-DEM | ICW-ICG UD | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B01-PUNCH | ICW-ICG UD | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B01-TURN | ICW-ICG UD | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B02-SUR | ICW-ICG LD | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B02-ENG | ICW-ICG LD | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B02-MAT | ICW-ICG LD | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B02-FAB | ICW-ICG LD | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B02-COAT | ICW-ICG LD | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B02-LOAD | ICW-ICG LD | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B02-SUP | ICW-ICG LD | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B02-INST | ICW-ICG LD | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B02-SERV | ICW-ICG LD | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B02-DEM | ICW-ICG LD | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B02-PUNCH | ICW-ICG LD | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B02-TURN | ICW-ICG LD | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B03-SUR | ICG-ICP UD | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B03-ENG | ICG-ICP UD | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B03-MAT | ICG-ICP UD | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B03-FAB | ICG-ICP UD | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B03-COAT | ICG-ICP UD | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B03-LOAD | ICG-ICP UD | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B03-SUP | ICG-ICP UD | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B03-INST | ICG-ICP UD | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B03-SERV | ICG-ICP UD | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B03-DEM | ICG-ICP UD | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B03-PUNCH | ICG-ICP UD | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B03-TURN | ICG-ICP UD | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B04-SUR | ICG-ICP LD | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B04-ENG | ICG-ICP LD | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B04-MAT | ICG-ICP LD | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B04-FAB | ICG-ICP LD | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B04-COAT | ICG-ICP LD | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B04-LOAD | ICG-ICP LD | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B04-SUP | ICG-ICP LD | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B04-INST | ICG-ICP LD | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B04-SERV | ICG-ICP LD | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B04-DEM | ICG-ICP LD | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B04-PUNCH | ICG-ICP LD | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B04-TURN | ICG-ICP LD | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B05-SUR | BHS-SLQ | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B05-ENG | BHS-SLQ | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B05-MAT | BHS-SLQ | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B05-FAB | BHS-SLQ | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B05-COAT | BHS-SLQ | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B05-LOAD | BHS-SLQ | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B05-SUP | BHS-SLQ | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B05-INST | BHS-SLQ | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B05-SERV | BHS-SLQ | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B05-DEM | BHS-SLQ | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B05-PUNCH | BHS-SLQ | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B05-TURN | BHS-SLQ | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B06-SUR | SLQ-WIS | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B06-ENG | SLQ-WIS | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B06-MAT | SLQ-WIS | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B06-FAB | SLQ-WIS | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B06-COAT | SLQ-WIS | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B06-LOAD | SLQ-WIS | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B06-SUP | SLQ-WIS | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B06-INST | SLQ-WIS | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B06-SERV | SLQ-WIS | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B06-DEM | SLQ-WIS | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B06-PUNCH | SLQ-WIS | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B06-TURN | SLQ-WIS | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B07-SUR | NQO-NQD | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B07-ENG | NQO-NQD | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B07-MAT | NQO-NQD | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B07-FAB | NQO-NQD | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B07-COAT | NQO-NQD | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B07-LOAD | NQO-NQD | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B07-SUP | NQO-NQD | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B07-INST | NQO-NQD | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B07-SERV | NQO-NQD | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B07-DEM | NQO-NQD | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B07-PUNCH | NQO-NQD | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B07-TURN | NQO-NQD | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B08-SUR | WIN-NC | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B08-ENG | WIN-NC | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B08-MAT | WIN-NC | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B08-FAB | WIN-NC | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B08-COAT | WIN-NC | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B08-LOAD | WIN-NC | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B08-SUP | WIN-NC | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B08-INST | WIN-NC | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B08-SERV | WIN-NC | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B08-DEM | WIN-NC | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B08-PUNCH | WIN-NC | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B08-TURN | WIN-NC | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B09-SUR | SCA-SC1 | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B09-ENG | SCA-SC1 | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B09-MAT | SCA-SC1 | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B09-FAB | SCA-SC1 | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B09-COAT | SCA-SC1 | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B09-LOAD | SCA-SC1 | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B09-SUP | SCA-SC1 | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B09-INST | SCA-SC1 | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B09-SERV | SCA-SC1 | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B09-DEM | SCA-SC1 | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B09-PUNCH | SCA-SC1 | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B09-TURN | SCA-SC1 | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED
B10-SUR | SCA-SCF | Survey and verified access | survey pack | [11 empty] | Accepted geometry/NDT | NOT RELEASED
B10-ENG | SCA-SCF | Design/detail/MTO release | document pack | [11 empty] | Checked analysis and AFC index | NOT RELEASED
B10-MAT | SCA-SCF | Material and traceability receipt | BOM item | [11 empty] | PS/MTC/origin and TPI release | NOT RELEASED
B10-FAB | SCA-SCF | Fabrication and connection work | member/weld/BOM | [11 empty] | WPS/welder/NDT/dimension records | NOT RELEASED
B10-COAT | SCA-SCF | Preparation/coating/curing | m2 by system | [11 empty] | Accepted surface/environment/DFT records | NOT RELEASED
B10-LOAD | SCA-SCF | Loadout/transport/receipt | module | [11 empty] | Weight/COG/rigging/sea-fastening approval | NOT RELEASED
B10-SUP | SCA-SCF | Support strengthening and temporary stability | member/joint | [11 empty] | Approved stage analysis and inspected installation | NOT RELEASED
B10-INST | SCA-SCF | Bridge installation/strengthening | member/module | [11 empty] | PTW and engineered method accepted | NOT RELEASED
B10-SERV | SCA-SCF | Service transfer/testing | line/circuit/system | [11 empty] | Isolation/test boundary/operations acceptance | NOT RELEASED
B10-DEM | SCA-SCF | Removal/scrap backload | item/MT | [11 empty] | Accepted support/service sequence and disposal receipt | NOT RELEASED
B10-PUNCH | SCA-SCF | Inspection/punch closure | punch item | [11 empty] | Accepted ITR and blocking-punch closure | NOT RELEASED
B10-TURN | SCA-SCF | As-built/turnover | dossier | [11 empty] | Accepted bridge/system completion | NOT RELEASED

## Resource Commitments
Resource | Scenario assumption | Actual capacity | Availability dates | Evidence | Owner | Status
Design teams | Parallel ten-bridge design assumed; loading not modelled |  |  |  | Engineering | UNVERIFIED
Fabrication | 2capacity-one bay chains at4MT/productive bay-day |  |  |  | Fabrication | UNVERIFIED
Coating | 1capacity-one cell;10yard-days/package |  |  |  | Coating | UNVERIFIED
NDT | No finite staffing capacity modelled |  |  |  | QA | UNVERIFIED
Strengthening | 3capacity-one crew chains;4MT/crew-day allowance |  |  |  | Construction | UNVERIFIED
Heavy lift | 1capacity-one new-bridge installation chain |  |  |  | Marine | UNVERIFIED
Cargo | 1capacity-one transport/demob chain |  |  |  | Logistics | UNVERIFIED
Services | 1capacity-one transfer/test team |  |  |  | Commissioning | UNVERIFIED
Removal | 1capacity-one removal team |  |  |  | Construction | UNVERIFIED
Survey | 1spread for common field survey |  |  |  | Survey | UNVERIFIED
Accommodation | Minimum60special-personnel requirement; totalPOB not proven |  |  |  | Marine | UNVERIFIED

## Schedule 285
ID | Bridge | Activity | Duration | Calendar | Predecessors | Resource | Owner | ES | EF exclusive | LS | LF exclusive | Float calendar days | Basis | Status
START | COMMON | Assumed commencement — scenario only | 0 | ALL |  |  | Contracts | 2026-11-01 | 2026-11-01 | 2026-11-02 | 2026-11-02 | 1 | 1Nov2026 assumed; actual NOA unconfirmed | PROPOSED / NOT APPROVED
G01 | COMMON | Contract/amendment matrix and scope reconciliation | 5 | OFFICE | START |  | Contracts | 2026-11-02 | 2026-11-07 | 2026-11-02 | 2026-11-09 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
G02 | COMMON | Survey permits, access and mobilisation preparation | 10 | OFFICE | G01 |  | Survey / Operations | 2026-11-09 | 2026-11-21 | 2026-11-09 | 2026-11-22 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
G03 | COMMON | Pre-engineering survey campaign | 15 | OFF | G02;D-SURV | Survey spread | Survey | 2026-11-21 | 2026-12-06 | 2026-11-22 | 2026-12-07 | 1 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
G04 | COMMON | Survey reports, geometry/condition reconciliation | 5 | OFFICE | G03 |  | Engineering | 2026-12-07 | 2026-12-12 | 2026-12-07 | 2026-12-14 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
G05 | COMMON | Survey/basis review and comment closure allowance | 10 | OFFICE | G04 |  | Engineering | 2026-12-14 | 2026-12-26 | 2026-12-14 | 2026-12-28 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
P-BEAR | COMMON | Bearings, sliding interfaces and guides — requisition/technical scope | 5 | OFFICE | G05 |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-11-05 | 2027-11-12 | 312 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-BEAR | COMMON | Bearings, sliding interfaces and guides — bid/PS review allowance | 10 | OFFICE | P-BEAR |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-11-12 | 2027-11-26 | 312 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-BEAR | COMMON | Bearings, sliding interfaces and guides — delivery/readiness | 35 | ALL | R-BEAR |  | Engineering | 2027-01-16 | 2027-02-20 | 2027-11-26 | 2027-12-31 | 314 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-GRAT | COMMON | Grating, handrail and GI sheet supply — requisition/technical scope | 5 | OFFICE | G05 |  | Procurement | 2026-12-28 | 2027-01-02 | 2027-11-05 | 2027-11-12 | 312 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-GRAT | COMMON | Grating, handrail and GI sheet supply — bid/PS review allowance | 10 | OFFICE | P-GRAT |  | Procurement | 2027-01-04 | 2027-01-16 | 2027-11-12 | 2027-11-26 | 312 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-GRAT | COMMON | Grating, handrail and GI sheet supply — delivery/readiness | 35 | ALL | R-GRAT |  | Procurement | 2027-01-16 | 2027-02-20 | 2027-11-26 | 2027-12-31 | 314 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-PIPE | COMMON | Piping tie-ins, fittings and supports — requisition/technical scope | 5 | OFFICE | G05 |  | Piping | 2026-12-28 | 2027-01-02 | 2027-11-09 | 2027-11-16 | 316 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-PIPE | COMMON | Piping tie-ins, fittings and supports — bid/PS review allowance | 10 | OFFICE | P-PIPE |  | Piping | 2027-01-04 | 2027-01-16 | 2027-11-16 | 2027-11-30 | 316 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-PIPE | COMMON | Piping tie-ins, fittings and supports — delivery/readiness | 45 | ALL | R-PIPE |  | Piping | 2027-01-16 | 2027-03-02 | 2027-11-30 | 2028-01-14 | 318 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-ELEC | COMMON | Electrical materials and bonding — requisition/technical scope | 5 | OFFICE | G05 |  | Electrical | 2026-12-28 | 2027-01-02 | 2027-11-15 | 2027-11-22 | 322 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-ELEC | COMMON | Electrical materials and bonding — bid/PS review allowance | 10 | OFFICE | P-ELEC |  | Electrical | 2027-01-04 | 2027-01-16 | 2027-11-22 | 2027-12-05 | 322 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-ELEC | COMMON | Electrical materials and bonding — delivery/readiness | 40 | ALL | R-ELEC |  | Electrical | 2027-01-16 | 2027-02-25 | 2027-12-05 | 2028-01-14 | 323 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-INST | COMMON | Instrumentation/cable interface materials — requisition/technical scope | 5 | OFFICE | G05 |  | Instrumentation | 2026-12-28 | 2027-01-02 | 2027-11-15 | 2027-11-22 | 322 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-INST | COMMON | Instrumentation/cable interface materials — bid/PS review allowance | 10 | OFFICE | P-INST |  | Instrumentation | 2027-01-04 | 2027-01-16 | 2027-11-22 | 2027-12-05 | 322 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-INST | COMMON | Instrumentation/cable interface materials — delivery/readiness | 40 | ALL | R-INST |  | Instrumentation | 2027-01-16 | 2027-02-25 | 2027-12-05 | 2028-01-14 | 323 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-COAT | COMMON | Qualified coating system supply — requisition/technical scope | 5 | OFFICE | G05 |  | Coating | 2026-12-28 | 2027-01-02 | 2027-08-09 | 2027-08-16 | 224 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-COAT | COMMON | Qualified coating system supply — bid/PS review allowance | 10 | OFFICE | P-COAT |  | Coating | 2027-01-04 | 2027-01-16 | 2027-08-16 | 2027-08-29 | 224 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-COAT | COMMON | Qualified coating system supply — delivery/readiness | 25 | ALL | R-COAT |  | Coating | 2027-01-16 | 2027-02-10 | 2027-08-29 | 2027-09-23 | 225 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-NDT | COMMON | NDT, welding qualification and consumables — requisition/technical scope | 5 | OFFICE | G05 |  | QA | 2026-12-28 | 2027-01-02 | 2027-04-07 | 2027-04-14 | 100 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-NDT | COMMON | NDT, welding qualification and consumables — bid/PS review allowance | 10 | OFFICE | P-NDT |  | QA | 2027-01-04 | 2027-01-16 | 2027-04-14 | 2027-04-28 | 100 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-NDT | COMMON | NDT, welding qualification and consumables — delivery/readiness | 20 | ALL | R-NDT |  | QA | 2027-01-16 | 2027-02-05 | 2027-04-28 | 2027-05-18 | 102 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-MAR | COMMON | Heavy-lift and accommodation spread readiness — requisition/technical scope | 5 | OFFICE | G05 |  | Marine | 2026-12-28 | 2027-01-02 | 2027-10-26 | 2027-11-02 | 302 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-MAR | COMMON | Heavy-lift and accommodation spread readiness — bid/PS review allowance | 10 | OFFICE | P-MAR |  | Marine | 2027-01-04 | 2027-01-16 | 2027-11-02 | 2027-11-16 | 302 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-MAR | COMMON | Heavy-lift and accommodation spread readiness — delivery/readiness | 45 | ALL | R-MAR |  | Marine | 2027-01-16 | 2027-03-02 | 2027-11-16 | 2027-12-31 | 304 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-CARGO | COMMON | Cargo vessel and shore-base readiness — requisition/technical scope | 5 | OFFICE | G05 |  | Logistics | 2026-12-28 | 2027-01-02 | 2027-10-11 | 2027-10-18 | 287 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-CARGO | COMMON | Cargo vessel and shore-base readiness — bid/PS review allowance | 10 | OFFICE | P-CARGO |  | Logistics | 2027-01-04 | 2027-01-16 | 2027-10-18 | 2027-10-31 | 287 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-CARGO | COMMON | Cargo vessel and shore-base readiness — delivery/readiness | 25 | ALL | R-CARGO |  | Logistics | 2027-01-16 | 2027-02-10 | 2027-10-31 | 2027-11-25 | 288 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-SURV | COMMON | Survey services mobilisation — requisition/technical scope | 2 | OFFICE | G01 |  | Survey | 2026-11-09 | 2026-11-11 | 2026-11-10 | 2026-11-12 | 1 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-SURV | COMMON | Survey services mobilisation — bid/PS review allowance | 3 | OFFICE | P-SURV |  | Survey | 2026-11-11 | 2026-11-14 | 2026-11-12 | 2026-11-17 | 1 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-SURV | COMMON | Survey services mobilisation — delivery/readiness | 5 | ALL | R-SURV |  | Survey | 2026-11-14 | 2026-11-19 | 2026-11-17 | 2026-11-22 | 3 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-DES | COMMON | Design agency capacity confirmation — requisition/technical scope | 5 | OFFICE | G01 |  | Engineering | 2026-11-09 | 2026-11-14 | 2026-11-27 | 2026-12-04 | 18 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-DES | COMMON | Design agency capacity confirmation — bid/PS review allowance | 10 | OFFICE | P-DES |  | Engineering | 2026-11-16 | 2026-11-28 | 2026-12-04 | 2026-12-18 | 18 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-DES | COMMON | Design agency capacity confirmation — delivery/readiness | 10 | ALL | R-DES |  | Engineering | 2026-11-28 | 2026-12-08 | 2026-12-18 | 2026-12-28 | 20 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-TPI | COMMON | TPI/CA services and audit arrangements — requisition/technical scope | 5 | OFFICE | G01 |  | QA | 2026-11-09 | 2026-11-14 | 2027-04-19 | 2027-04-26 | 161 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-TPI | COMMON | TPI/CA services and audit arrangements — bid/PS review allowance | 10 | OFFICE | P-TPI |  | QA | 2026-11-16 | 2026-11-28 | 2027-04-26 | 2027-05-08 | 161 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-TPI | COMMON | TPI/CA services and audit arrangements — delivery/readiness | 10 | ALL | R-TPI |  | QA | 2026-11-28 | 2026-12-08 | 2027-05-08 | 2027-05-18 | 161 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-SCAF | COMMON | Scaffolding/access and temporary works supply — requisition/technical scope | 5 | OFFICE | G05 |  | Construction | 2026-12-28 | 2027-01-02 | 2027-10-13 | 2027-10-20 | 289 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-SCAF | COMMON | Scaffolding/access and temporary works supply — bid/PS review allowance | 10 | OFFICE | P-SCAF |  | Construction | 2027-01-04 | 2027-01-16 | 2027-10-20 | 2027-11-03 | 289 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-SCAF | COMMON | Scaffolding/access and temporary works supply — delivery/readiness | 25 | ALL | R-SCAF |  | Construction | 2027-01-16 | 2027-02-10 | 2027-11-03 | 2027-11-28 | 291 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-PPE | COMMON | Certified PPE and training readiness — requisition/technical scope | 5 | OFFICE | G01 |  | HSE | 2026-11-09 | 2026-11-14 | 2027-10-25 | 2027-11-01 | 350 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-PPE | COMMON | Certified PPE and training readiness — bid/PS review allowance | 10 | OFFICE | P-PPE |  | HSE | 2026-11-16 | 2026-11-28 | 2027-11-01 | 2027-11-13 | 350 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-PPE | COMMON | Certified PPE and training readiness — delivery/readiness | 15 | ALL | R-PPE |  | HSE | 2026-11-28 | 2026-12-13 | 2027-11-13 | 2027-11-28 | 350 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
P-TRAY | COMMON | Cable trays and support steel interfaces — requisition/technical scope | 5 | OFFICE | G05 |  | Electrical | 2026-12-28 | 2027-01-02 | 2027-11-19 | 2027-11-26 | 326 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
R-TRAY | COMMON | Cable trays and support steel interfaces — bid/PS review allowance | 10 | OFFICE | P-TRAY |  | Electrical | 2027-01-04 | 2027-01-16 | 2027-11-26 | 2027-12-10 | 326 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
D-TRAY | COMMON | Cable trays and support steel interfaces — delivery/readiness | 35 | ALL | R-TRAY |  | Electrical | 2027-01-16 | 2027-02-20 | 2027-12-10 | 2028-01-14 | 328 | Unverified vendor/service lead-time allowance; no quote or commitment | PROPOSED / NOT APPROVED
B05-BAS | BHS-SLQ | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2026-12-28 | 2027-01-04 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-BRV | BHS-SLQ | Basis review and comment closure allowance | 10 | OFFICE | B05-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-01-04 | 2027-01-18 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-ANA | BHS-SLQ | Bridge/platform and preservice analysis preparation | 20 | OFFICE | B05-BRV |  | Structural | 2027-01-18 | 2027-02-13 | 2027-01-18 | 2027-02-15 | 0 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B05-ARV | BHS-SLQ | Analysis review and comment closure allowance | 10 | OFFICE | B05-ANA |  | Engineering | 2027-02-15 | 2027-02-27 | 2027-02-15 | 2027-03-01 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-DET | BHS-SLQ | Connection, bearing, landing and workpack detailing | 15 | OFFICE | B05-ARV |  | Structural | 2027-03-01 | 2027-03-20 | 2027-03-01 | 2027-03-22 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-DRV | BHS-SLQ | Drawing review and comment closure allowance | 10 | OFFICE | B05-DET |  | Engineering | 2027-03-22 | 2027-04-03 | 2027-03-22 | 2027-04-03 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-AFC | BHS-SLQ | AFC design/MTO independent check and release gate | 0 | ALL | B05-DRV |  | Engineering | 2027-04-03 | 2027-04-03 | 2027-04-03 | 2027-04-03 | 0 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B05-RFQ | BHS-SLQ | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B05-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-03-11 | 2027-03-22 | 52 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-PRV | BHS-SLQ | Bridge steel PS review allowance | 10 | OFFICE | B05-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-03-22 | 2027-04-03 | 54 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-PO | BHS-SLQ | Bridge steel compliant PO release gate | 0 | ALL | B05-AFC;B05-PRV |  | Procurement | 2027-04-03 | 2027-04-03 | 2027-04-03 | 2027-04-03 | 0 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B05-MAT | BHS-SLQ | Mill production, inspection and steel delivery | 45 | ALL | B05-PO |  | Procurement | 2027-04-03 | 2027-05-18 | 2027-04-03 | 2027-05-18 | 0 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B05-FAB | BHS-SLQ | Fit-up, welding and dimensional control | 71 | YARD | B05-MAT;D-NDT;D-TPI | Fabrication line 1 | Fabrication | 2027-05-18 | 2027-08-08 | 2027-05-18 | 2027-08-09 | 0 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B05-NDT | BHS-SLQ | NDT, repair allowance and dimensional release | 6 | YARD | B05-FAB |  | QA | 2027-08-09 | 2027-08-15 | 2027-09-16 | 2027-09-23 | 38 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-COA | BHS-SLQ | Surface preparation, coating and curing allowance | 10 | YARD | B05-NDT;D-COAT | Coating cell | Coating | 2027-08-16 | 2027-08-27 | 2027-09-23 | 2027-10-05 | 38 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-REL | BHS-SLQ | Trial fit, verified weight/COG and loadout release | 5 | YARD | B05-COA |  | QA / Marine | 2027-08-27 | 2027-09-02 | 2027-11-19 | 2027-11-25 | 84 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-TRN | BHS-SLQ | Loadout, transport and offshore receipt | 3 | OFF | B05-REL;D-CARGO | Cargo spread | Logistics | 2027-10-16 | 2027-10-19 | 2027-11-25 | 2027-11-28 | 40 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-PRE | BHS-SLQ | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B05-TRN;D-SCAF;D-PPE |  | Construction | 2027-10-19 | 2027-10-22 | 2027-11-28 | 2027-12-01 | 40 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-STR | BHS-SLQ | Landing/platform pre-install strengthening | 22 | OFF | B05-PRE | Strength crew 1 | Construction | 2027-10-22 | 2027-11-13 | 2027-12-01 | 2027-12-23 | 40 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B05-INS | BHS-SLQ | New bridge installation | 7 | OFF | B05-STR;D-MAR;D-BEAR;D-GRAT | Heavy-lift spread | Marine / Construction | 2027-11-13 | 2027-11-20 | 2028-01-03 | 2028-01-10 | 51 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B05-SRV | BHS-SLQ | Services transfer, test and accepted reinstatement | 5 | OFF | B05-INS;D-PIPE;D-ELEC;D-INST;D-TRAY | Service transfer team | Commissioning | 2027-11-20 | 2027-11-25 | 2028-01-14 | 2028-01-19 | 55 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-DEM | BHS-SLQ | Engineered demolition/removal and scrap backload | 14 | OFF | B05-SRV | Removal team | Construction | 2027-11-25 | 2027-12-09 | 2028-02-03 | 2028-02-17 | 70 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B05-PUN | BHS-SLQ | Inspection, touch-up and offshore punch closure | 3 | OFF | B05-DEM |  | QA / Commissioning | 2027-12-09 | 2027-12-12 | 2028-03-06 | 2028-03-09 | 88 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B05-DOS | BHS-SLQ | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B05-PUN |  | Document Control | 2027-12-13 | 2027-12-25 | 2028-03-09 | 2028-03-23 | 87 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-BAS | ICW-ICG LD | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-04-02 | 2027-04-09 | 95 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-BRV | ICW-ICG LD | Basis review and comment closure allowance | 10 | OFFICE | B02-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-04-09 | 2027-04-23 | 95 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-ANA | ICW-ICG LD | Bridge/platform and preservice analysis preparation | 20 | OFFICE | B02-BRV |  | Structural | 2027-01-18 | 2027-02-13 | 2027-04-23 | 2027-05-21 | 95 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B02-ARV | ICW-ICG LD | Analysis review and comment closure allowance | 10 | OFFICE | B02-ANA |  | Engineering | 2027-02-15 | 2027-02-27 | 2027-05-21 | 2027-06-04 | 95 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-DET | ICW-ICG LD | Connection, bearing, landing and workpack detailing | 15 | OFFICE | B02-ARV |  | Structural | 2027-03-01 | 2027-03-20 | 2027-06-04 | 2027-06-25 | 95 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-DRV | ICW-ICG LD | Drawing review and comment closure allowance | 10 | OFFICE | B02-DET |  | Engineering | 2027-03-22 | 2027-04-03 | 2027-06-25 | 2027-07-09 | 95 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-AFC | ICW-ICG LD | AFC design/MTO independent check and release gate | 0 | ALL | B02-DRV |  | Engineering | 2027-04-03 | 2027-04-03 | 2027-07-09 | 2027-07-09 | 97 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B02-RFQ | ICW-ICG LD | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B02-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-06-16 | 2027-06-25 | 149 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-PRV | ICW-ICG LD | Bridge steel PS review allowance | 10 | OFFICE | B02-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-06-25 | 2027-07-09 | 149 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-PO | ICW-ICG LD | Bridge steel compliant PO release gate | 0 | ALL | B02-AFC;B02-PRV |  | Procurement | 2027-04-03 | 2027-04-03 | 2027-07-09 | 2027-07-09 | 97 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B02-MAT | ICW-ICG LD | Mill production, inspection and steel delivery | 45 | ALL | B02-PO |  | Procurement | 2027-04-03 | 2027-05-18 | 2027-07-09 | 2027-08-23 | 97 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B02-FAB | ICW-ICG LD | Fit-up, welding and dimensional control | 31 | YARD | B02-MAT;D-NDT;D-TPI | Fabrication line 2 | Fabrication | 2027-05-18 | 2027-06-23 | 2027-08-23 | 2027-09-28 | 97 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B02-NDT | ICW-ICG LD | NDT, repair allowance and dimensional release | 6 | YARD | B02-FAB |  | QA | 2027-06-23 | 2027-06-30 | 2027-09-28 | 2027-10-05 | 97 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-COA | ICW-ICG LD | Surface preparation, coating and curing allowance | 10 | YARD | B02-NDT;D-COAT;B05-COA | Coating cell | Coating | 2027-08-27 | 2027-09-08 | 2027-10-05 | 2027-10-16 | 39 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-REL | ICW-ICG LD | Trial fit, verified weight/COG and loadout release | 5 | YARD | B02-COA |  | QA / Marine | 2027-09-08 | 2027-09-14 | 2027-12-06 | 2027-12-11 | 89 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-TRN | ICW-ICG LD | Loadout, transport and offshore receipt | 3 | OFF | B02-REL;D-CARGO;B05-TRN | Cargo spread | Logistics | 2027-10-19 | 2027-10-22 | 2027-12-11 | 2027-12-14 | 53 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-PRE | ICW-ICG LD | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B02-TRN;D-SCAF;D-PPE |  | Construction | 2027-10-22 | 2027-10-25 | 2027-12-15 | 2027-12-18 | 54 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-STR | ICW-ICG LD | Landing/platform pre-install strengthening | 17 | OFF | B02-PRE | Strength crew 2 | Construction | 2027-10-25 | 2027-11-11 | 2027-12-18 | 2028-01-04 | 54 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B02-INS | ICW-ICG LD | New bridge installation | 7 | OFF | B02-STR;D-MAR;D-BEAR;D-GRAT;B05-INS | Heavy-lift spread | Marine / Construction | 2027-11-20 | 2027-11-27 | 2028-01-10 | 2028-01-17 | 51 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B02-SRV | ICW-ICG LD | Services transfer, test and accepted reinstatement | 5 | OFF | B02-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B05-SRV | Service transfer team | Commissioning | 2027-11-27 | 2027-12-02 | 2028-01-19 | 2028-01-24 | 53 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-DEM | ICW-ICG LD | Engineered demolition/removal and scrap backload | 2 | OFF | B02-SRV;B05-DEM | Removal team | Construction | 2027-12-09 | 2027-12-11 | 2028-02-17 | 2028-02-19 | 70 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B02-PUN | ICW-ICG LD | Inspection, touch-up and offshore punch closure | 3 | OFF | B02-DEM |  | QA / Commissioning | 2027-12-11 | 2027-12-14 | 2028-03-06 | 2028-03-09 | 86 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B02-DOS | ICW-ICG LD | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B02-PUN |  | Document Control | 2027-12-14 | 2027-12-28 | 2028-03-09 | 2028-03-23 | 86 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-BAS | ICG-ICP LD | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-03-19 | 2027-03-26 | 81 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-BRV | ICG-ICP LD | Basis review and comment closure allowance | 10 | OFFICE | B04-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-03-26 | 2027-04-09 | 81 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-ANA | ICG-ICP LD | Bridge/platform and preservice analysis preparation | 20 | OFFICE | B04-BRV |  | Structural | 2027-01-18 | 2027-02-13 | 2027-04-09 | 2027-05-07 | 81 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B04-ARV | ICG-ICP LD | Analysis review and comment closure allowance | 10 | OFFICE | B04-ANA |  | Engineering | 2027-02-15 | 2027-02-27 | 2027-05-07 | 2027-05-21 | 81 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-DET | ICG-ICP LD | Connection, bearing, landing and workpack detailing | 15 | OFFICE | B04-ARV |  | Structural | 2027-03-01 | 2027-03-20 | 2027-05-21 | 2027-06-11 | 81 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-DRV | ICG-ICP LD | Drawing review and comment closure allowance | 10 | OFFICE | B04-DET |  | Engineering | 2027-03-22 | 2027-04-03 | 2027-06-11 | 2027-06-25 | 81 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-AFC | ICG-ICP LD | AFC design/MTO independent check and release gate | 0 | ALL | B04-DRV |  | Engineering | 2027-04-03 | 2027-04-03 | 2027-06-25 | 2027-06-25 | 83 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B04-RFQ | ICG-ICP LD | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B04-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-06-02 | 2027-06-11 | 135 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-PRV | ICG-ICP LD | Bridge steel PS review allowance | 10 | OFFICE | B04-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-06-11 | 2027-06-25 | 135 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-PO | ICG-ICP LD | Bridge steel compliant PO release gate | 0 | ALL | B04-AFC;B04-PRV |  | Procurement | 2027-04-03 | 2027-04-03 | 2027-06-25 | 2027-06-25 | 83 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B04-MAT | ICG-ICP LD | Mill production, inspection and steel delivery | 45 | ALL | B04-PO |  | Procurement | 2027-04-03 | 2027-05-18 | 2027-06-25 | 2027-08-09 | 83 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B04-FAB | ICG-ICP LD | Fit-up, welding and dimensional control | 40 | YARD | B04-MAT;D-NDT;D-TPI;B05-FAB | Fabrication line 1 | Fabrication | 2027-08-09 | 2027-09-24 | 2027-08-09 | 2027-09-24 | 0 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B04-NDT | ICG-ICP LD | NDT, repair allowance and dimensional release | 6 | YARD | B04-FAB |  | QA | 2027-09-24 | 2027-10-01 | 2027-10-09 | 2027-10-16 | 15 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-COA | ICG-ICP LD | Surface preparation, coating and curing allowance | 10 | YARD | B04-NDT;D-COAT;B02-COA | Coating cell | Coating | 2027-10-01 | 2027-10-13 | 2027-10-16 | 2027-10-28 | 15 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-REL | ICG-ICP LD | Trial fit, verified weight/COG and loadout release | 5 | YARD | B04-COA |  | QA / Marine | 2027-10-13 | 2027-10-19 | 2027-12-08 | 2027-12-14 | 56 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-TRN | ICG-ICP LD | Loadout, transport and offshore receipt | 3 | OFF | B04-REL;D-CARGO;B02-TRN | Cargo spread | Logistics | 2027-10-22 | 2027-10-25 | 2027-12-14 | 2027-12-17 | 53 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-PRE | ICG-ICP LD | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B04-TRN;D-SCAF;D-PPE |  | Construction | 2027-10-25 | 2027-10-28 | 2027-12-30 | 2028-01-02 | 66 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-STR | ICG-ICP LD | Landing/platform pre-install strengthening | 12 | OFF | B04-PRE | Strength crew 3 | Construction | 2027-10-28 | 2027-11-09 | 2028-01-02 | 2028-01-14 | 66 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B04-INS | ICG-ICP LD | New bridge installation | 7 | OFF | B04-STR;D-MAR;D-BEAR;D-GRAT;B02-INS | Heavy-lift spread | Marine / Construction | 2027-11-27 | 2027-12-04 | 2028-01-17 | 2028-01-24 | 51 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B04-SRV | ICG-ICP LD | Services transfer, test and accepted reinstatement | 5 | OFF | B04-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B02-SRV | Service transfer team | Commissioning | 2027-12-04 | 2027-12-09 | 2028-01-24 | 2028-01-29 | 51 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-DEM | ICG-ICP LD | Engineered demolition/removal and scrap backload | 2 | OFF | B04-SRV;B02-DEM | Removal team | Construction | 2027-12-11 | 2027-12-13 | 2028-02-19 | 2028-02-21 | 70 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B04-PUN | ICG-ICP LD | Inspection, touch-up and offshore punch closure | 3 | OFF | B04-DEM |  | QA / Commissioning | 2027-12-13 | 2027-12-16 | 2028-03-06 | 2028-03-09 | 84 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B04-DOS | ICG-ICP LD | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B04-PUN |  | Document Control | 2027-12-16 | 2027-12-30 | 2028-03-09 | 2028-03-23 | 84 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-BAS | ICW-ICG UD | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-05-27 | 2027-06-03 | 150 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-BRV | ICW-ICG UD | Basis review and comment closure allowance | 10 | OFFICE | B01-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-06-03 | 2027-06-17 | 150 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-ANA | ICW-ICG UD | Bridge/platform and preservice analysis preparation | 12 | OFFICE | B01-BRV |  | Structural | 2027-01-18 | 2027-02-03 | 2027-06-17 | 2027-07-05 | 150 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B01-ARV | ICW-ICG UD | Analysis review and comment closure allowance | 10 | OFFICE | B01-ANA |  | Engineering | 2027-02-03 | 2027-02-17 | 2027-07-05 | 2027-07-19 | 152 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-DET | ICW-ICG UD | Connection, bearing, landing and workpack detailing | 10 | OFFICE | B01-ARV |  | Structural | 2027-02-17 | 2027-03-03 | 2027-07-19 | 2027-08-02 | 152 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-DRV | ICW-ICG UD | Drawing review and comment closure allowance | 10 | OFFICE | B01-DET |  | Engineering | 2027-03-03 | 2027-03-17 | 2027-08-02 | 2027-08-16 | 152 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-AFC | ICW-ICG UD | AFC design/MTO independent check and release gate | 0 | ALL | B01-DRV |  | Engineering | 2027-03-17 | 2027-03-17 | 2027-08-16 | 2027-08-16 | 152 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B01-RFQ | ICW-ICG UD | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B01-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-07-22 | 2027-08-02 | 185 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-PRV | ICW-ICG UD | Bridge steel PS review allowance | 10 | OFFICE | B01-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-08-02 | 2027-08-16 | 187 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-PO | ICW-ICG UD | Bridge steel compliant PO release gate | 0 | ALL | B01-AFC;B01-PRV |  | Procurement | 2027-03-17 | 2027-03-17 | 2027-08-16 | 2027-08-16 | 152 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B01-MAT | ICW-ICG UD | Mill production, inspection and steel delivery | 45 | ALL | B01-PO |  | Procurement | 2027-03-17 | 2027-05-01 | 2027-08-16 | 2027-09-30 | 152 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B01-FAB | ICW-ICG UD | Fit-up, welding and dimensional control | 13 | YARD | B01-MAT;D-NDT;D-TPI;B02-FAB | Fabrication line 2 | Fabrication | 2027-06-23 | 2027-07-08 | 2027-09-30 | 2027-10-15 | 99 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B01-NDT | ICW-ICG UD | NDT, repair allowance and dimensional release | 6 | YARD | B01-FAB |  | QA | 2027-07-08 | 2027-07-15 | 2027-10-21 | 2027-10-28 | 105 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-COA | ICW-ICG UD | Surface preparation, coating and curing allowance | 10 | YARD | B01-NDT;D-COAT;B04-COA | Coating cell | Coating | 2027-10-13 | 2027-10-24 | 2027-10-28 | 2027-11-09 | 15 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-REL | ICW-ICG UD | Trial fit, verified weight/COG and loadout release | 5 | YARD | B01-COA |  | QA / Marine | 2027-10-25 | 2027-10-30 | 2027-12-11 | 2027-12-17 | 47 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-TRN | ICW-ICG UD | Loadout, transport and offshore receipt | 3 | OFF | B01-REL;D-CARGO;B04-TRN | Cargo spread | Logistics | 2027-10-30 | 2027-11-02 | 2027-12-17 | 2027-12-20 | 48 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-PRE | ICW-ICG UD | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B01-TRN;D-SCAF;D-PPE |  | Construction | 2027-11-02 | 2027-11-05 | 2027-12-20 | 2027-12-23 | 48 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-STR | ICW-ICG UD | Landing/platform pre-install strengthening | 8 | OFF | B01-PRE;B05-STR | Strength crew 1 | Construction | 2027-11-13 | 2027-11-21 | 2027-12-23 | 2027-12-31 | 40 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B01-INS | ICW-ICG UD | Bridge strengthening and replacement items | 5 | OFF | B01-STR;D-MAR;D-BEAR;D-GRAT | Strength crew 1 | Marine / Construction | 2027-11-21 | 2027-11-26 | 2027-12-31 | 2028-01-05 | 40 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B01-SRV | ICW-ICG UD | Services transfer, test and accepted reinstatement | 5 | OFF | B01-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B04-SRV | Service transfer team | Commissioning | 2027-12-09 | 2027-12-14 | 2028-01-29 | 2028-02-03 | 51 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-DEM | ICW-ICG UD | Engineered demolition/removal and scrap backload | 2 | OFF | B01-SRV;B04-DEM | Removal team | Construction | 2027-12-14 | 2027-12-16 | 2028-02-21 | 2028-02-23 | 69 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B01-PUN | ICW-ICG UD | Inspection, touch-up and offshore punch closure | 3 | OFF | B01-DEM |  | QA / Commissioning | 2027-12-16 | 2027-12-19 | 2028-03-06 | 2028-03-09 | 81 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B01-DOS | ICW-ICG UD | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B01-PUN |  | Document Control | 2027-12-20 | 2028-01-01 | 2028-03-09 | 2028-03-23 | 80 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-BAS | ICG-ICP UD | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-05-21 | 2027-05-28 | 144 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-BRV | ICG-ICP UD | Basis review and comment closure allowance | 10 | OFFICE | B03-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-05-28 | 2027-06-11 | 144 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-ANA | ICG-ICP UD | Bridge/platform and preservice analysis preparation | 12 | OFFICE | B03-BRV |  | Structural | 2027-01-18 | 2027-02-03 | 2027-06-11 | 2027-06-29 | 144 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B03-ARV | ICG-ICP UD | Analysis review and comment closure allowance | 10 | OFFICE | B03-ANA |  | Engineering | 2027-02-03 | 2027-02-17 | 2027-06-29 | 2027-07-13 | 146 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-DET | ICG-ICP UD | Connection, bearing, landing and workpack detailing | 10 | OFFICE | B03-ARV |  | Structural | 2027-02-17 | 2027-03-03 | 2027-07-13 | 2027-07-27 | 146 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-DRV | ICG-ICP UD | Drawing review and comment closure allowance | 10 | OFFICE | B03-DET |  | Engineering | 2027-03-03 | 2027-03-17 | 2027-07-27 | 2027-08-10 | 146 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-AFC | ICG-ICP UD | AFC design/MTO independent check and release gate | 0 | ALL | B03-DRV |  | Engineering | 2027-03-17 | 2027-03-17 | 2027-08-10 | 2027-08-10 | 146 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B03-RFQ | ICG-ICP UD | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B03-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-07-16 | 2027-07-27 | 179 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-PRV | ICG-ICP UD | Bridge steel PS review allowance | 10 | OFFICE | B03-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-07-27 | 2027-08-10 | 181 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-PO | ICG-ICP UD | Bridge steel compliant PO release gate | 0 | ALL | B03-AFC;B03-PRV |  | Procurement | 2027-03-17 | 2027-03-17 | 2027-08-10 | 2027-08-10 | 146 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B03-MAT | ICG-ICP UD | Mill production, inspection and steel delivery | 45 | ALL | B03-PO |  | Procurement | 2027-03-17 | 2027-05-01 | 2027-08-10 | 2027-09-24 | 146 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B03-FAB | ICG-ICP UD | Fit-up, welding and dimensional control | 29 | YARD | B03-MAT;D-NDT;D-TPI;B04-FAB | Fabrication line 1 | Fabrication | 2027-09-24 | 2027-10-28 | 2027-09-24 | 2027-10-28 | 0 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B03-NDT | ICG-ICP UD | NDT, repair allowance and dimensional release | 6 | YARD | B03-FAB |  | QA | 2027-10-28 | 2027-11-04 | 2027-11-02 | 2027-11-09 | 5 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-COA | ICG-ICP UD | Surface preparation, coating and curing allowance | 10 | YARD | B03-NDT;D-COAT;B01-COA | Coating cell | Coating | 2027-11-04 | 2027-11-16 | 2027-11-09 | 2027-11-20 | 5 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-REL | ICG-ICP UD | Trial fit, verified weight/COG and loadout release | 5 | YARD | B03-COA |  | QA / Marine | 2027-11-16 | 2027-11-21 | 2027-12-18 | 2027-12-24 | 32 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-TRN | ICG-ICP UD | Loadout, transport and offshore receipt | 3 | OFF | B03-REL;D-CARGO;B01-TRN | Cargo spread | Logistics | 2027-11-21 | 2027-11-24 | 2027-12-24 | 2027-12-27 | 33 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-PRE | ICG-ICP UD | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B03-TRN;D-SCAF;D-PPE |  | Construction | 2027-11-24 | 2027-11-27 | 2028-01-01 | 2028-01-04 | 38 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-STR | ICG-ICP UD | Landing/platform pre-install strengthening | 8 | OFF | B03-PRE;B02-STR | Strength crew 2 | Construction | 2027-11-27 | 2027-12-05 | 2028-01-04 | 2028-01-12 | 38 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B03-INS | ICG-ICP UD | Bridge strengthening and replacement items | 22 | OFF | B03-STR;D-MAR;D-BEAR;D-GRAT | Strength crew 2 | Marine / Construction | 2027-12-05 | 2027-12-27 | 2028-01-12 | 2028-02-03 | 38 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B03-SRV | ICG-ICP UD | Services transfer, test and accepted reinstatement | 5 | OFF | B03-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B01-SRV | Service transfer team | Commissioning | 2027-12-27 | 2028-01-01 | 2028-02-03 | 2028-02-08 | 38 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-DEM | ICG-ICP UD | Engineered demolition/removal and scrap backload | 2 | OFF | B03-SRV;B01-DEM | Removal team | Construction | 2028-01-01 | 2028-01-03 | 2028-02-23 | 2028-02-25 | 53 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B03-PUN | ICG-ICP UD | Inspection, touch-up and offshore punch closure | 3 | OFF | B03-DEM |  | QA / Commissioning | 2028-01-03 | 2028-01-06 | 2028-03-06 | 2028-03-09 | 63 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B03-DOS | ICG-ICP UD | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B03-PUN |  | Document Control | 2028-01-06 | 2028-01-20 | 2028-03-09 | 2028-03-23 | 63 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-BAS | SLQ-WIS | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-06-11 | 2027-06-18 | 165 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-BRV | SLQ-WIS | Basis review and comment closure allowance | 10 | OFFICE | B06-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-06-18 | 2027-07-02 | 165 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-ANA | SLQ-WIS | Bridge/platform and preservice analysis preparation | 12 | OFFICE | B06-BRV |  | Structural | 2027-01-18 | 2027-02-03 | 2027-07-02 | 2027-07-20 | 165 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B06-ARV | SLQ-WIS | Analysis review and comment closure allowance | 10 | OFFICE | B06-ANA |  | Engineering | 2027-02-03 | 2027-02-17 | 2027-07-20 | 2027-08-03 | 167 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-DET | SLQ-WIS | Connection, bearing, landing and workpack detailing | 10 | OFFICE | B06-ARV |  | Structural | 2027-02-17 | 2027-03-03 | 2027-08-03 | 2027-08-17 | 167 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-DRV | SLQ-WIS | Drawing review and comment closure allowance | 10 | OFFICE | B06-DET |  | Engineering | 2027-03-03 | 2027-03-17 | 2027-08-17 | 2027-08-31 | 167 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-AFC | SLQ-WIS | AFC design/MTO independent check and release gate | 0 | ALL | B06-DRV |  | Engineering | 2027-03-17 | 2027-03-17 | 2027-08-31 | 2027-08-31 | 167 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B06-RFQ | SLQ-WIS | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B06-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-08-06 | 2027-08-17 | 200 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-PRV | SLQ-WIS | Bridge steel PS review allowance | 10 | OFFICE | B06-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-08-17 | 2027-08-31 | 202 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-PO | SLQ-WIS | Bridge steel compliant PO release gate | 0 | ALL | B06-AFC;B06-PRV |  | Procurement | 2027-03-17 | 2027-03-17 | 2027-08-31 | 2027-08-31 | 167 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B06-MAT | SLQ-WIS | Mill production, inspection and steel delivery | 45 | ALL | B06-PO |  | Procurement | 2027-03-17 | 2027-05-01 | 2027-08-31 | 2027-10-15 | 167 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B06-FAB | SLQ-WIS | Fit-up, welding and dimensional control | 23 | YARD | B06-MAT;D-NDT;D-TPI;B01-FAB | Fabrication line 2 | Fabrication | 2027-07-08 | 2027-08-04 | 2027-10-15 | 2027-11-11 | 99 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B06-NDT | SLQ-WIS | NDT, repair allowance and dimensional release | 6 | YARD | B06-FAB |  | QA | 2027-08-04 | 2027-08-11 | 2027-11-13 | 2027-11-20 | 101 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-COA | SLQ-WIS | Surface preparation, coating and curing allowance | 10 | YARD | B06-NDT;D-COAT;B03-COA | Coating cell | Coating | 2027-11-16 | 2027-11-27 | 2027-11-20 | 2027-12-02 | 4 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-REL | SLQ-WIS | Trial fit, verified weight/COG and loadout release | 5 | YARD | B06-COA |  | QA / Marine | 2027-11-27 | 2027-12-03 | 2027-12-21 | 2027-12-27 | 24 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-TRN | SLQ-WIS | Loadout, transport and offshore receipt | 3 | OFF | B06-REL;D-CARGO;B03-TRN | Cargo spread | Logistics | 2027-12-03 | 2027-12-06 | 2027-12-27 | 2027-12-30 | 24 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-PRE | SLQ-WIS | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B06-TRN;D-SCAF;D-PPE |  | Construction | 2027-12-06 | 2027-12-09 | 2028-01-11 | 2028-01-14 | 36 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-STR | SLQ-WIS | Landing/platform pre-install strengthening | 8 | OFF | B06-PRE;B04-STR | Strength crew 3 | Construction | 2027-12-09 | 2027-12-17 | 2028-01-14 | 2028-01-22 | 36 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B06-INS | SLQ-WIS | Bridge strengthening and replacement items | 16 | OFF | B06-STR;D-MAR;D-BEAR;D-GRAT | Strength crew 3 | Marine / Construction | 2027-12-17 | 2028-01-02 | 2028-01-22 | 2028-02-07 | 36 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B06-SRV | SLQ-WIS | Services transfer, test and accepted reinstatement | 5 | OFF | B06-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B03-SRV | Service transfer team | Commissioning | 2028-01-02 | 2028-01-07 | 2028-02-08 | 2028-02-13 | 37 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-DEM | SLQ-WIS | Engineered demolition/removal and scrap backload | 2 | OFF | B06-SRV;B03-DEM | Removal team | Construction | 2028-01-07 | 2028-01-09 | 2028-02-25 | 2028-02-27 | 49 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B06-PUN | SLQ-WIS | Inspection, touch-up and offshore punch closure | 3 | OFF | B06-DEM |  | QA / Commissioning | 2028-01-09 | 2028-01-12 | 2028-03-06 | 2028-03-09 | 57 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B06-DOS | SLQ-WIS | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B06-PUN |  | Document Control | 2028-01-12 | 2028-01-26 | 2028-03-09 | 2028-03-23 | 57 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-BAS | NQO-NQD | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-06-24 | 2027-07-01 | 178 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-BRV | NQO-NQD | Basis review and comment closure allowance | 10 | OFFICE | B07-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-07-01 | 2027-07-15 | 178 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-ANA | NQO-NQD | Bridge/platform and preservice analysis preparation | 12 | OFFICE | B07-BRV |  | Structural | 2027-01-18 | 2027-02-03 | 2027-07-15 | 2027-08-02 | 178 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B07-ARV | NQO-NQD | Analysis review and comment closure allowance | 10 | OFFICE | B07-ANA |  | Engineering | 2027-02-03 | 2027-02-17 | 2027-08-02 | 2027-08-16 | 180 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-DET | NQO-NQD | Connection, bearing, landing and workpack detailing | 10 | OFFICE | B07-ARV |  | Structural | 2027-02-17 | 2027-03-03 | 2027-08-16 | 2027-08-30 | 180 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-DRV | NQO-NQD | Drawing review and comment closure allowance | 10 | OFFICE | B07-DET |  | Engineering | 2027-03-03 | 2027-03-17 | 2027-08-30 | 2027-09-13 | 180 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-AFC | NQO-NQD | AFC design/MTO independent check and release gate | 0 | ALL | B07-DRV |  | Engineering | 2027-03-17 | 2027-03-17 | 2027-09-13 | 2027-09-13 | 180 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B07-RFQ | NQO-NQD | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B07-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-08-19 | 2027-08-30 | 213 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-PRV | NQO-NQD | Bridge steel PS review allowance | 10 | OFFICE | B07-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-08-30 | 2027-09-13 | 215 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-PO | NQO-NQD | Bridge steel compliant PO release gate | 0 | ALL | B07-AFC;B07-PRV |  | Procurement | 2027-03-17 | 2027-03-17 | 2027-09-13 | 2027-09-13 | 180 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B07-MAT | NQO-NQD | Mill production, inspection and steel delivery | 45 | ALL | B07-PO |  | Procurement | 2027-03-17 | 2027-05-01 | 2027-09-13 | 2027-10-28 | 180 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B07-FAB | NQO-NQD | Fit-up, welding and dimensional control | 24 | YARD | B07-MAT;D-NDT;D-TPI;B03-FAB | Fabrication line 1 | Fabrication | 2027-10-28 | 2027-11-25 | 2027-10-28 | 2027-11-25 | 0 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B07-NDT | NQO-NQD | NDT, repair allowance and dimensional release | 6 | YARD | B07-FAB |  | QA | 2027-11-25 | 2027-12-02 | 2027-11-25 | 2027-12-02 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-COA | NQO-NQD | Surface preparation, coating and curing allowance | 10 | YARD | B07-NDT;D-COAT;B06-COA | Coating cell | Coating | 2027-12-02 | 2027-12-14 | 2027-12-02 | 2027-12-14 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-REL | NQO-NQD | Trial fit, verified weight/COG and loadout release | 5 | YARD | B07-COA |  | QA / Marine | 2027-12-14 | 2027-12-19 | 2027-12-24 | 2027-12-30 | 10 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-TRN | NQO-NQD | Loadout, transport and offshore receipt | 3 | OFF | B07-REL;D-CARGO;B06-TRN | Cargo spread | Logistics | 2027-12-19 | 2027-12-22 | 2027-12-30 | 2028-01-02 | 11 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-PRE | NQO-NQD | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B07-TRN;D-SCAF;D-PPE |  | Construction | 2027-12-22 | 2027-12-25 | 2028-01-02 | 2028-01-05 | 11 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-STR | NQO-NQD | Landing/platform pre-install strengthening | 8 | OFF | B07-PRE;B01-INS | Strength crew 1 | Construction | 2027-12-25 | 2028-01-02 | 2028-01-05 | 2028-01-13 | 11 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B07-INS | NQO-NQD | Bridge strengthening and replacement items | 16 | OFF | B07-STR;D-MAR;D-BEAR;D-GRAT | Strength crew 1 | Marine / Construction | 2028-01-02 | 2028-01-18 | 2028-01-13 | 2028-01-29 | 11 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B07-SRV | NQO-NQD | Services transfer, test and accepted reinstatement | 5 | OFF | B07-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B06-SRV | Service transfer team | Commissioning | 2028-01-18 | 2028-01-23 | 2028-02-13 | 2028-02-18 | 26 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-DEM | NQO-NQD | Engineered demolition/removal and scrap backload | 2 | OFF | B07-SRV;B06-DEM | Removal team | Construction | 2028-01-23 | 2028-01-25 | 2028-02-27 | 2028-02-29 | 35 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B07-PUN | NQO-NQD | Inspection, touch-up and offshore punch closure | 3 | OFF | B07-DEM |  | QA / Commissioning | 2028-01-25 | 2028-01-28 | 2028-03-06 | 2028-03-09 | 41 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B07-DOS | NQO-NQD | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B07-PUN |  | Document Control | 2028-01-28 | 2028-02-11 | 2028-03-09 | 2028-03-23 | 41 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-BAS | WIN-NC | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-07-08 | 2027-07-15 | 192 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-BRV | WIN-NC | Basis review and comment closure allowance | 10 | OFFICE | B08-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-07-15 | 2027-07-29 | 192 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-ANA | WIN-NC | Bridge/platform and preservice analysis preparation | 12 | OFFICE | B08-BRV |  | Structural | 2027-01-18 | 2027-02-03 | 2027-07-29 | 2027-08-16 | 192 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B08-ARV | WIN-NC | Analysis review and comment closure allowance | 10 | OFFICE | B08-ANA |  | Engineering | 2027-02-03 | 2027-02-17 | 2027-08-16 | 2027-08-30 | 194 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-DET | WIN-NC | Connection, bearing, landing and workpack detailing | 10 | OFFICE | B08-ARV |  | Structural | 2027-02-17 | 2027-03-03 | 2027-08-30 | 2027-09-13 | 194 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-DRV | WIN-NC | Drawing review and comment closure allowance | 10 | OFFICE | B08-DET |  | Engineering | 2027-03-03 | 2027-03-17 | 2027-09-13 | 2027-09-27 | 194 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-AFC | WIN-NC | AFC design/MTO independent check and release gate | 0 | ALL | B08-DRV |  | Engineering | 2027-03-17 | 2027-03-17 | 2027-09-27 | 2027-09-27 | 194 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B08-RFQ | WIN-NC | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B08-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-09-02 | 2027-09-13 | 227 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-PRV | WIN-NC | Bridge steel PS review allowance | 10 | OFFICE | B08-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-09-13 | 2027-09-27 | 229 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-PO | WIN-NC | Bridge steel compliant PO release gate | 0 | ALL | B08-AFC;B08-PRV |  | Procurement | 2027-03-17 | 2027-03-17 | 2027-09-27 | 2027-09-27 | 194 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B08-MAT | WIN-NC | Mill production, inspection and steel delivery | 45 | ALL | B08-PO |  | Procurement | 2027-03-17 | 2027-05-01 | 2027-09-27 | 2027-11-11 | 194 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B08-FAB | WIN-NC | Fit-up, welding and dimensional control | 12 | YARD | B08-MAT;D-NDT;D-TPI;B06-FAB | Fabrication line 2 | Fabrication | 2027-08-04 | 2027-08-18 | 2027-11-11 | 2027-11-25 | 99 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B08-NDT | WIN-NC | NDT, repair allowance and dimensional release | 6 | YARD | B08-FAB |  | QA | 2027-08-18 | 2027-08-25 | 2027-12-07 | 2027-12-14 | 111 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-COA | WIN-NC | Surface preparation, coating and curing allowance | 10 | YARD | B08-NDT;D-COAT;B07-COA | Coating cell | Coating | 2027-12-14 | 2027-12-25 | 2027-12-14 | 2027-12-25 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-REL | WIN-NC | Trial fit, verified weight/COG and loadout release | 5 | YARD | B08-COA |  | QA / Marine | 2027-12-25 | 2027-12-31 | 2028-01-11 | 2028-01-17 | 17 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-TRN | WIN-NC | Loadout, transport and offshore receipt | 3 | OFF | B08-REL;D-CARGO;B07-TRN | Cargo spread | Logistics | 2027-12-31 | 2028-01-03 | 2028-01-17 | 2028-01-20 | 17 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-PRE | WIN-NC | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B08-TRN;D-SCAF;D-PPE |  | Construction | 2028-01-03 | 2028-01-06 | 2028-01-31 | 2028-02-03 | 28 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-STR | WIN-NC | Landing/platform pre-install strengthening | 10 | OFF | B08-PRE;B03-INS | Strength crew 2 | Construction | 2028-01-06 | 2028-01-16 | 2028-02-03 | 2028-02-13 | 28 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B08-INS | WIN-NC | Bridge strengthening and replacement items | 5 | OFF | B08-STR;D-MAR;D-BEAR;D-GRAT | Strength crew 2 | Marine / Construction | 2028-01-16 | 2028-01-21 | 2028-02-13 | 2028-02-18 | 28 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B08-SRV | WIN-NC | Services transfer, test and accepted reinstatement | 5 | OFF | B08-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B07-SRV | Service transfer team | Commissioning | 2028-01-23 | 2028-01-28 | 2028-02-18 | 2028-02-23 | 26 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-DEM | WIN-NC | Engineered demolition/removal and scrap backload | 2 | OFF | B08-SRV;B07-DEM | Removal team | Construction | 2028-01-28 | 2028-01-30 | 2028-02-29 | 2028-03-02 | 32 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B08-PUN | WIN-NC | Inspection, touch-up and offshore punch closure | 3 | OFF | B08-DEM |  | QA / Commissioning | 2028-01-30 | 2028-02-02 | 2028-03-06 | 2028-03-09 | 36 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B08-DOS | WIN-NC | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B08-PUN |  | Document Control | 2028-02-02 | 2028-02-16 | 2028-03-09 | 2028-03-23 | 36 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-BAS | SCA-SC1 | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-07-29 | 2027-08-05 | 213 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-BRV | SCA-SC1 | Basis review and comment closure allowance | 10 | OFFICE | B09-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-08-05 | 2027-08-19 | 213 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-ANA | SCA-SC1 | Bridge/platform and preservice analysis preparation | 12 | OFFICE | B09-BRV |  | Structural | 2027-01-18 | 2027-02-03 | 2027-08-19 | 2027-09-06 | 213 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B09-ARV | SCA-SC1 | Analysis review and comment closure allowance | 10 | OFFICE | B09-ANA |  | Engineering | 2027-02-03 | 2027-02-17 | 2027-09-06 | 2027-09-20 | 215 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-DET | SCA-SC1 | Connection, bearing, landing and workpack detailing | 10 | OFFICE | B09-ARV |  | Structural | 2027-02-17 | 2027-03-03 | 2027-09-20 | 2027-10-04 | 215 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-DRV | SCA-SC1 | Drawing review and comment closure allowance | 10 | OFFICE | B09-DET |  | Engineering | 2027-03-03 | 2027-03-17 | 2027-10-04 | 2027-10-16 | 215 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-AFC | SCA-SC1 | AFC design/MTO independent check and release gate | 0 | ALL | B09-DRV |  | Engineering | 2027-03-17 | 2027-03-17 | 2027-10-16 | 2027-10-16 | 213 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B09-RFQ | SCA-SC1 | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B09-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-09-23 | 2027-10-04 | 248 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-PRV | SCA-SC1 | Bridge steel PS review allowance | 10 | OFFICE | B09-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-10-04 | 2027-10-16 | 250 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-PO | SCA-SC1 | Bridge steel compliant PO release gate | 0 | ALL | B09-AFC;B09-PRV |  | Procurement | 2027-03-17 | 2027-03-17 | 2027-10-16 | 2027-10-16 | 213 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B09-MAT | SCA-SC1 | Mill production, inspection and steel delivery | 45 | ALL | B09-PO |  | Procurement | 2027-03-17 | 2027-05-01 | 2027-10-16 | 2027-11-30 | 213 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B09-FAB | SCA-SC1 | Fit-up, welding and dimensional control | 16 | YARD | B09-MAT;D-NDT;D-TPI;B07-FAB | Fabrication line 1 | Fabrication | 2027-11-25 | 2027-12-14 | 2027-11-30 | 2027-12-18 | 5 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B09-NDT | SCA-SC1 | NDT, repair allowance and dimensional release | 6 | YARD | B09-FAB |  | QA | 2027-12-14 | 2027-12-21 | 2027-12-18 | 2027-12-25 | 4 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-COA | SCA-SC1 | Surface preparation, coating and curing allowance | 10 | YARD | B09-NDT;D-COAT;B08-COA | Coating cell | Coating | 2027-12-25 | 2028-01-06 | 2027-12-25 | 2028-01-06 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-REL | SCA-SC1 | Trial fit, verified weight/COG and loadout release | 5 | YARD | B09-COA |  | QA / Marine | 2028-01-06 | 2028-01-12 | 2028-01-14 | 2028-01-20 | 8 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-TRN | SCA-SC1 | Loadout, transport and offshore receipt | 3 | OFF | B09-REL;D-CARGO;B08-TRN | Cargo spread | Logistics | 2028-01-12 | 2028-01-15 | 2028-01-20 | 2028-01-23 | 8 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-PRE | SCA-SC1 | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B09-TRN;D-SCAF;D-PPE |  | Construction | 2028-01-15 | 2028-01-18 | 2028-02-04 | 2028-02-07 | 20 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-STR | SCA-SC1 | Landing/platform pre-install strengthening | 7 | OFF | B09-PRE;B06-INS | Strength crew 3 | Construction | 2028-01-18 | 2028-01-25 | 2028-02-07 | 2028-02-14 | 20 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B09-INS | SCA-SC1 | Bridge strengthening and replacement items | 9 | OFF | B09-STR;D-MAR;D-BEAR;D-GRAT | Strength crew 3 | Marine / Construction | 2028-01-25 | 2028-02-03 | 2028-02-14 | 2028-02-23 | 20 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B09-SRV | SCA-SC1 | Services transfer, test and accepted reinstatement | 5 | OFF | B09-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B08-SRV | Service transfer team | Commissioning | 2028-02-03 | 2028-02-08 | 2028-02-23 | 2028-02-28 | 20 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-DEM | SCA-SC1 | Engineered demolition/removal and scrap backload | 2 | OFF | B09-SRV;B08-DEM | Removal team | Construction | 2028-02-08 | 2028-02-10 | 2028-03-02 | 2028-03-04 | 23 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B09-PUN | SCA-SC1 | Inspection, touch-up and offshore punch closure | 3 | OFF | B09-DEM |  | QA / Commissioning | 2028-02-10 | 2028-02-13 | 2028-03-06 | 2028-03-09 | 25 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B09-DOS | SCA-SC1 | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B09-PUN |  | Document Control | 2028-02-14 | 2028-02-26 | 2028-03-09 | 2028-03-23 | 24 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-BAS | SCA-SCF | Design basis, loads and interfaces | 5 | OFFICE | G05;D-DES |  | Engineering | 2026-12-28 | 2027-01-02 | 2027-07-22 | 2027-07-29 | 206 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-BRV | SCA-SCF | Basis review and comment closure allowance | 10 | OFFICE | B10-BAS |  | Engineering | 2027-01-04 | 2027-01-16 | 2027-07-29 | 2027-08-12 | 206 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-ANA | SCA-SCF | Bridge/platform and preservice analysis preparation | 12 | OFFICE | B10-BRV |  | Structural | 2027-01-18 | 2027-02-03 | 2027-08-12 | 2027-08-30 | 206 | Proposed engineering effort window; native analysis/check evidence not supplied | PROPOSED / NOT APPROVED
B10-ARV | SCA-SCF | Analysis review and comment closure allowance | 10 | OFFICE | B10-ANA |  | Engineering | 2027-02-03 | 2027-02-17 | 2027-08-30 | 2027-09-13 | 208 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-DET | SCA-SCF | Connection, bearing, landing and workpack detailing | 10 | OFFICE | B10-ARV |  | Structural | 2027-02-17 | 2027-03-03 | 2027-09-13 | 2027-09-27 | 208 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-DRV | SCA-SCF | Drawing review and comment closure allowance | 10 | OFFICE | B10-DET |  | Engineering | 2027-03-03 | 2027-03-17 | 2027-09-27 | 2027-10-11 | 208 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-AFC | SCA-SCF | AFC design/MTO independent check and release gate | 0 | ALL | B10-DRV |  | Engineering | 2027-03-17 | 2027-03-17 | 2027-10-11 | 2027-10-11 | 208 | Gate; actual signed release not established | PROPOSED / NOT APPROVED
B10-RFQ | SCA-SCF | Bridge steel RFQ, evaluation and PS preparation | 7 | OFFICE | B10-BRV |  | Procurement | 2027-01-18 | 2027-01-27 | 2027-09-16 | 2027-09-27 | 241 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-PRV | SCA-SCF | Bridge steel PS review allowance | 10 | OFFICE | B10-RFQ |  | Procurement | 2027-01-27 | 2027-02-10 | 2027-09-27 | 2027-10-11 | 243 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-PO | SCA-SCF | Bridge steel compliant PO release gate | 0 | ALL | B10-AFC;B10-PRV |  | Procurement | 2027-03-17 | 2027-03-17 | 2027-10-11 | 2027-10-11 | 208 | No at-risk purchase assumed; amended domestic-origin evidence required | PROPOSED / NOT APPROVED
B10-MAT | SCA-SCF | Mill production, inspection and steel delivery | 45 | ALL | B10-PO |  | Procurement | 2027-03-17 | 2027-05-01 | 2027-10-11 | 2027-11-25 | 208 | Unquoted45calendar-day placeholder; origin, mill capacity and transport unresolved | PROPOSED / NOT APPROVED
B10-FAB | SCA-SCF | Fit-up, welding and dimensional control | 30 | YARD | B10-MAT;D-NDT;D-TPI;B08-FAB | Fabrication line 2 | Fabrication | 2027-08-18 | 2027-09-22 | 2027-11-25 | 2027-12-30 | 99 | Assumed4MT per productive bay-day; includes aggregate steel, not validated shop productivity | PROPOSED / NOT APPROVED
B10-NDT | SCA-SCF | NDT, repair allowance and dimensional release | 6 | YARD | B10-FAB |  | QA | 2027-09-22 | 2027-09-29 | 2027-12-30 | 2028-01-06 | 99 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-COA | SCA-SCF | Surface preparation, coating and curing allowance | 10 | YARD | B10-NDT;D-COAT;B09-COA | Coating cell | Coating | 2028-01-06 | 2028-01-18 | 2028-01-06 | 2028-01-18 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-REL | SCA-SCF | Trial fit, verified weight/COG and loadout release | 5 | YARD | B10-COA |  | QA / Marine | 2028-01-18 | 2028-01-23 | 2028-01-18 | 2028-01-23 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-TRN | SCA-SCF | Loadout, transport and offshore receipt | 3 | OFF | B10-REL;D-CARGO;B09-TRN | Cargo spread | Logistics | 2028-01-23 | 2028-01-26 | 2028-01-23 | 2028-01-26 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-PRE | SCA-SCF | PTW, access, SIMOPS and work-front readiness | 3 | OFF | B10-TRN;D-SCAF;D-PPE |  | Construction | 2028-01-26 | 2028-01-29 | 2028-01-26 | 2028-01-29 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-STR | SCA-SCF | Landing/platform pre-install strengthening | 7 | OFF | B10-PRE;B07-INS | Strength crew 1 | Construction | 2028-01-29 | 2028-02-05 | 2028-01-29 | 2028-02-05 | 0 | Proposed4MT/crew-day; actual weld/access quantities not validated | PROPOSED / NOT APPROVED
B10-INS | SCA-SCF | Bridge strengthening and replacement items | 23 | OFF | B10-STR;D-MAR;D-BEAR;D-GRAT | Strength crew 1 | Marine / Construction | 2028-02-05 | 2028-02-28 | 2028-02-05 | 2028-02-28 | 0 | Aggregate planning allowance; engineered lifts and temporary stability required | PROPOSED / NOT APPROVED
B10-SRV | SCA-SCF | Services transfer, test and accepted reinstatement | 5 | OFF | B10-INS;D-PIPE;D-ELEC;D-INST;D-TRAY;B09-SRV | Service transfer team | Commissioning | 2028-02-28 | 2028-03-04 | 2028-02-28 | 2028-03-04 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-DEM | SCA-SCF | Engineered demolition/removal and scrap backload | 2 | OFF | B10-SRV;B09-DEM | Removal team | Construction | 2028-03-04 | 2028-03-06 | 2028-03-04 | 2028-03-06 | 0 | Proposed15MT/day allowance; BHS sequence after safe new service transfer, subject to approved method | PROPOSED / NOT APPROVED
B10-PUN | SCA-SCF | Inspection, touch-up and offshore punch closure | 3 | OFF | B10-DEM |  | QA / Commissioning | 2028-03-06 | 2028-03-09 | 2028-03-06 | 2028-03-09 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
B10-DOS | SCA-SCF | As-built, QA and turnover dossier acceptance | 10 | OFFICE | B10-PUN |  | Document Control | 2028-03-09 | 2028-03-23 | 2028-03-09 | 2028-03-23 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
OFFDONE | COMMON | All bridge offshore work completed | 0 | ALL | B05-PUN;B02-PUN;B04-PUN;B01-PUN;B03-PUN;B06-PUN;B07-PUN;B08-PUN;B09-PUN;B10-PUN |  | Project Manager | 2028-03-09 | 2028-03-09 | 2028-03-18 | 2028-03-18 | 9 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
DEMOB | COMMON | Spread demobilisation allowance | 5 | OFF | OFFDONE;B10-TRN | Cargo spread | Marine | 2028-03-09 | 2028-03-14 | 2028-03-18 | 2028-03-23 | 9 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
CLOSE | COMMON | Integrated acceptance, final measurements and account preparation | 10 | OFFICE | B05-DOS;B02-DOS;B04-DOS;B01-DOS;B03-DOS;B06-DOS;B07-DOS;B08-DOS;B09-DOS;B10-DOS;DEMOB |  | Project Manager | 2028-03-23 | 2028-04-06 | 2028-03-23 | 2028-04-06 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED
FINISH | COMMON | Proposed contract-completion milestone | 0 | ALL | CLOSE |  | Project Director | 2028-04-06 | 2028-04-06 | 2028-04-06 | 2028-04-06 | 0 | Proposed allowance; replace with verified inputs | PROPOSED / NOT APPROVED

## Driving Chain
Sequence | ID | Activity | Start | Finish exclusive | Float
1 | START | Assumed commencement — scenario only | 2026-11-01 | 2026-11-01 | 1
2 | G01 | Contract/amendment matrix and scope reconciliation | 2026-11-02 | 2026-11-07 | 0
3 | G02 | Survey permits, access and mobilisation preparation | 2026-11-09 | 2026-11-21 | 0
4 | G03 | Pre-engineering survey campaign | 2026-11-21 | 2026-12-06 | 1
5 | G04 | Survey reports, geometry/condition reconciliation | 2026-12-07 | 2026-12-12 | 0
6 | G05 | Survey/basis review and comment closure allowance | 2026-12-14 | 2026-12-26 | 0
7 | B05-BAS | Design basis, loads and interfaces | 2026-12-28 | 2027-01-02 | 0
8 | B05-BRV | Basis review and comment closure allowance | 2027-01-04 | 2027-01-16 | 0
9 | B05-ANA | Bridge/platform and preservice analysis preparation | 2027-01-18 | 2027-02-13 | 0
10 | B05-ARV | Analysis review and comment closure allowance | 2027-02-15 | 2027-02-27 | 0
11 | B05-DET | Connection, bearing, landing and workpack detailing | 2027-03-01 | 2027-03-20 | 0
12 | B05-DRV | Drawing review and comment closure allowance | 2027-03-22 | 2027-04-03 | 0
13 | B05-AFC | AFC design/MTO independent check and release gate | 2027-04-03 | 2027-04-03 | 0
14 | B05-PO | Bridge steel compliant PO release gate | 2027-04-03 | 2027-04-03 | 0
15 | B05-MAT | Mill production, inspection and steel delivery | 2027-04-03 | 2027-05-18 | 0
16 | B05-FAB | Fit-up, welding and dimensional control | 2027-05-18 | 2027-08-08 | 0
17 | B04-FAB | Fit-up, welding and dimensional control | 2027-08-09 | 2027-09-24 | 0
18 | B03-FAB | Fit-up, welding and dimensional control | 2027-09-24 | 2027-10-28 | 0
19 | B07-FAB | Fit-up, welding and dimensional control | 2027-10-28 | 2027-11-25 | 0
20 | B07-NDT | NDT, repair allowance and dimensional release | 2027-11-25 | 2027-12-02 | 0
21 | B07-COA | Surface preparation, coating and curing allowance | 2027-12-02 | 2027-12-14 | 0
22 | B08-COA | Surface preparation, coating and curing allowance | 2027-12-14 | 2027-12-25 | 0
23 | B09-COA | Surface preparation, coating and curing allowance | 2027-12-25 | 2028-01-06 | 0
24 | B10-COA | Surface preparation, coating and curing allowance | 2028-01-06 | 2028-01-18 | 0
25 | B10-REL | Trial fit, verified weight/COG and loadout release | 2028-01-18 | 2028-01-23 | 0
26 | B10-TRN | Loadout, transport and offshore receipt | 2028-01-23 | 2028-01-26 | 0
27 | B10-PRE | PTW, access, SIMOPS and work-front readiness | 2028-01-26 | 2028-01-29 | 0
28 | B10-STR | Landing/platform pre-install strengthening | 2028-01-29 | 2028-02-05 | 0
29 | B10-INS | Bridge strengthening and replacement items | 2028-02-05 | 2028-02-28 | 0
30 | B10-SRV | Services transfer, test and accepted reinstatement | 2028-02-28 | 2028-03-04 | 0
31 | B10-DEM | Engineered demolition/removal and scrap backload | 2028-03-04 | 2028-03-06 | 0
32 | B10-PUN | Inspection, touch-up and offshore punch closure | 2028-03-06 | 2028-03-09 | 0
33 | B10-DOS | As-built, QA and turnover dossier acceptance | 2028-03-09 | 2028-03-23 | 0
34 | CLOSE | Integrated acceptance, final measurements and account preparation | 2028-03-23 | 2028-04-06 | 0
35 | FINISH | Proposed contract-completion milestone | 2028-04-06 | 2028-04-06 | 0

## Schedule Scenarios
Scenario | Bays | MT per bay-day | Steel lead calendar days | Finish exclusive | Calendar days beyond assumed anniversary | Evidence status
BASE | 2 | 4 | 45 | 2028-04-06 | 157 | All capacity/lead-time assumptions unverified; not contractual delay entitlement
MORE_YARD | 4 | 8 | 45 | 2028-02-26 | 117 | All capacity/lead-time assumptions unverified; not contractual delay entitlement
FAST_SUPPLY_MORE_YARD | 4 | 8 | 15 | 2028-02-26 | 117 | All capacity/lead-time assumptions unverified; not contractual delay entitlement

## Calendars and Method
Control | Rule
OFFICE | Mon–Fri8h; holidays absent
YARD | Mon–Sat; unverified shift/capacity
OFF | 7days;16May–15Oct blocked as planning scenario, indivisible work phase must fit open season
ALL | 7calendar days
Date convention | Half-open intervals: finish is next-day boundary; zero duration milestones at boundary
Links | FS0 including explicit proposed resource-sequencing links
Offshore season | Planning exclusion16May–15Oct; offshore phase indivisible; qualifying contractual relief needs actual evidence
Capacity limitation | Named chains only; engineering/NDT/POB/access/charter actual capacity unverified; not a full resource-feasibility result
Float | Calendar-day latest-start slack to scenario completion, not float against approved contractual dates
Target comparison | 1Nov2027 is assumed12month anniversary; convention and relief require contracts confirmation
Algorithm checks | All IDs/predecessors valid, DAG/cycle check, forward/backward dates, nonnegative computed float, FS constraints
Sensitivity limitation | Three deterministic scenarios; no probabilisticP80 or quantified contingency claim

## Risk Register
ID | Event | Early warning | Owner | Required mitigation | Hold/escalation | Likelihood | Impact | Residual exposure
R01 | Wrong source revision or unrelated S&SRP scope | Revised SCC/A3 not positively mapped; common platform names | Contracts | Freeze affected release and resolve applicability/precedence | PO/AFC release blocked for disputed requirement |  |  | NOT QUANTIFIED
R02 | Survey geometry or corrosion differs from tender | Span/elevation/thickness/support condition outside accepted model | Engineering | Survey, NDT, independent check and controlled redesign | Affected design and load-path release held |  |  | NOT QUANTIFIED
R03 | Steel grade/origin unavailable in lead time | Mill quote fails grade, dimensions or Melt&Pour/DVA evidence | Procurement | Qualify alternative compliant mill/section through design approval | No unauthorised substitution |  |  | NOT QUANTIFIED
R04 | First offshore season missed | Ready-for-installation forecast beyond15May under scenario | Planning | Stage independent releases and verify earlier supply/capacity; cost second season | Seek schedule/contract decision with evidence |  |  | NOT QUANTIFIED
R05 | Vessel capacity or availability fails | Crane chart, deck/stability or booking does not cover module | Marine | Engineer module envelope and qualify alternate spread | No charter/lift commitment without assurance |  |  | NOT QUANTIFIED
R06 | Shared crews/yard bottleneck | Weekly demand exceeds named capacity or coating/NDT queue grows | Construction | Resource loading, workfront sequencing and priced additional capacity | Escalate before lookahead freeze |  |  | NOT QUANTIFIED
R07 | Piping/platform movement mismatch | Stress/support reactions not accepted by structural team | Piping/Structural | Iterate movement/stiffness and supporting deck checks | Bearing/service design release held |  |  | NOT QUANTIFIED
R08 | Live-service loss or unsafe demolition | Isolation/bypass/temporary support not accepted | Operations | Integrated SIMOPS/transfer and staged stability review | Stop affected work; complete controlled readiness |  |  | NOT QUANTIFIED
R09 | NDT/coating rework or curing delays | Rejects, environment or DFT outside approved procedure | QA | Qualify process, monitor environment, inspect and repair | No loadout before release |  |  | NOT QUANTIFIED
R10 | Funding shortfall | Unpriced charters, unverified receipts or late certification | Finance | Priced estimate, full-life cash, committed facility and scenario stress | Spending within authorised funded ceiling |  |  | NOT QUANTIFIED
R11 | Measurement/payment rejection | No accepted e-MB/SES or amended milestone evidence | Controls | Contemporaneous measurements and invoice reconciliation | Correct records before billing claim |  |  | NOT QUANTIFIED
R12 | Emergency/weather disruption | Forecast reaches abort thresholds or vessel critical system fails | Marine/HSE | Refuge/evacuation plan, drills, stop/abort authority and reserve strategy | Record decision and personnel accountability |  |  | NOT QUANTIFIED

## QA and Release Gates
Gate | Prerequisite evidence | Accountable | Release authority | Status
Survey/basis | Accepted survey, source hierarchy and design queries | Engineering | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Design release | Checked analysis, connection/bearing/stage checks and matching drawings | Engineering | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Purchase release | ApprovedPS, origin/compliance and authorised cost commitment | Procurement | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Weld start | ApprovedWPS/PQR, welder qualifications, material identity | QA | Project authority/company/CA as contract applies | HOLD — evidence not supplied
NDT release | Accepted procedure/personnel/calibration/reports and repair closure | QA | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Coating start | Approved system, surface condition, environment and hold-point release | QA | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Loadout | Dimensions, weight/COG, trial fit, lifting and transport assurance | Marine | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Sailout | Vessel certificates/audit, cargo/seafastening and readiness | Marine | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Installation | PTW/SIMOPS/support readiness, weather and approved lift plan | Construction | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Removal | Accepted alternate support/service configuration and engineered sequence | Construction | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Reinstatement | Approved test boundaries/results and operations authorisation | Commissioning | Project authority/company/CA as contract applies | HOLD — evidence not supplied
Turnover | As-builts, inspection records, punch closure and formal acceptance | Completions | Project authority/company/CA as contract applies | HOLD — evidence not supplied

## Marine Assurance
Operation | Required engineered checks | Required records | Status
Module definition | Dimensions, centre of gravity, attachments, loose items and tolerances | Weight report/drawing revision | OPEN
Lift | Crane at radius/configuration; dynamics, rigging/load share, padeyes and local structure | Independent checked lift pack; certified gear | OPEN
Loadout/voyage | Deck capacity/stability, supports, accelerations, seafastening, route/forecast | Loadout/voyage approval and survey | OPEN
Positioning | Mooring/DP, clearance, seabed/caisson risks, operational limits | Approved positioning/anchor plan | OPEN
Landing | Movement/thrust, support strength, alignment, bearing setting and restraint removal | Survey, support release and ITR | OPEN
Demolition | Stage-by-stage load path, temporary support, cut/lift points and services | Accepted removal pack and permit | OPEN
Personnel | POB/certificates/medical/training, transfer and evacuation | C9/C10 audit and emergency records | OPEN

## HSE and SIMOPS
Hazard/control | Minimum evidence | Owner | Status
Isolation/LOTO | Approved boundary, register, gas tests and operations verification | HSE/Operations | OPEN
Hot work | Permit, gas monitoring, fire watch and extinguisher provision | HSE/Operations | OPEN
Working at height | Certified access, harness/anchors and rescue plan | HSE/Operations | OPEN
Lifting/dropped objects | Engineered lifts, exclusion zone, communications and tool control | HSE/Operations | OPEN
Scaffolding | Design/load class, tags, inspection and rescue access | HSE/Operations | OPEN
Marine transfers | Vessel/platform interface, personnel transfer limits and certification | HSE/Operations | OPEN
Coating/chemicals | SDS, ventilation, respiratory/skin protection and exposure controls | HSE/Operations | OPEN
Noise/manual handling | Assessment, protection and handling methods | HSE/Operations | OPEN
PPE | Certified issuance/replacement matrix before work | HSE/Operations | OPEN
Emergency | Platform/vessel command, muster/POB, medevac and joint drills | HSE/Operations | OPEN
Electrical | Approved isolation, competent persons and certified equipment | HSE/Operations | OPEN
Environmental | Spill prevention, waste segregation, scrap and disposal records | HSE/Operations | OPEN

## Daily Production
Date | IWP | Planned quantity | Accepted quantity | Unit | Actual crew-hours | Nonproductive hours | Rework quantity | Acceptance record | Constraint | Responsible

## Progress Rules
Workstream | Proposed or contractual basis | Evidence | Guardrail
Engineering | C8 review dispositionC=0/B=60/A=100 on applicable engineering item basis | Accepted projectDCI and review status | Not overall-project or cash percentage
Procurement | C8 two-stagePS5%+5% of applicable procurement-item weight | MCI applicability and stage approvals | Not10% of contract value
Fabrication | Accepted BOM/weld/tonnage stages under approved rules | Material/weld/NDT/dimension records | No double count with offshore installation
Installation | Accepted installed work quantities and test stages | ITRs/e-MB/service acceptance | Exclude rejected/rework quantities
Turnover | Accepted dossiers and contractual milestone | Company acceptance | Submission alone does not equal acceptance
EVM | EV=approvedBAC×approved accepted progress;SPI=EV/PV;CPI=EV/AC | PricedBAC,timephasedPV,actualAC | Do not calculate without these inputs

## Cost Commitments
Package | Approved budget INR | PO commitment INR | Accrued unpaid INR | Actual paid INR | Forecast remaining INR | Forecast total INR | Quote/evidence | Owner
STEEL-B01 | [7 empty] | Procurement
STEEL-B02 | [7 empty] | Procurement
STEEL-B03 | [7 empty] | Procurement
STEEL-B04 | [7 empty] | Procurement
STEEL-B05 | [7 empty] | Procurement
STEEL-B06 | [7 empty] | Procurement
STEEL-B07 | [7 empty] | Procurement
STEEL-B08 | [7 empty] | Procurement
STEEL-B09 | [7 empty] | Procurement
STEEL-B10 | [7 empty] | Procurement
BEAR | [7 empty] | Engineering
GRAT | [7 empty] | Procurement
PIPE | [7 empty] | Piping
ELEC | [7 empty] | Electrical
INST | [7 empty] | Instrumentation
COAT | [7 empty] | Coating
NDT | [7 empty] | QA
MAR | [7 empty] | Marine
CARGO | [7 empty] | Logistics
SURV | [7 empty] | Survey
DES | [7 empty] | Engineering
TPI | [7 empty] | QA
SCAF | [7 empty] | Construction
PPE | [7 empty] | HSE
TRAY | [7 empty] | Electrical

## Financial Basis
Input / control | Value | Instruction
Opening available project cash INR |  | Enter funded amount and evidence; blank is unknown
Contract value INR |  | Verified bid/award amount; do not infer from qualification threshold
Status | UNPRICED | No financial-feasibility conclusion
EAC convention | Actual paid plus all forecast remaining | Remaining must include accrued unpaid, open commitments and uncommittedETC without duplication
Horizon | 156weeks, extend if required | Include actual warranty/retention/security/final-account dates;156weeks is not proof every obligation ends
Receipts | Actual contract milestones and payment lags | Deleted separate mob/demob payments excluded unless governing amendment states otherwise
Tax | Transaction-specific GST/customs/TDS/credits | Gross invoice, net receipt and recoverable tax separate
Security | Guarantee face value differs from margin cash/fees | Track expiry, bank commission and margin release independently

## 156 Week Cash
Week | Scenario week start | Contract receipts INR | Retention/security cash release | Other cash-in | Vendor/subcontract payments | Wages/overheads | Marine/logistics | Tax/financing/BG margin | Other cash-out | Net cash | Cumulative net cash | Cash incl opening | Verification status: VERIFIED only after all8inputs evidenced
1 | 2026-11-01
2 | 2026-11-08
3 | 2026-11-15
4 | 2026-11-22
5 | 2026-11-29
6 | 2026-12-06
7 | 2026-12-13
8 | 2026-12-20
9 | 2026-12-27
10 | 2027-01-03
11 | 2027-01-10
12 | 2027-01-17
13 | 2027-01-24
14 | 2027-01-31
15 | 2027-02-07
16 | 2027-02-14
17 | 2027-02-21
18 | 2027-02-28
19 | 2027-03-07
20 | 2027-03-14
21 | 2027-03-21
22 | 2027-03-28
23 | 2027-04-04
24 | 2027-04-11
25 | 2027-04-18
26 | 2027-04-25
27 | 2027-05-02
28 | 2027-05-09
29 | 2027-05-16
30 | 2027-05-23
31 | 2027-05-30
32 | 2027-06-06
33 | 2027-06-13
34 | 2027-06-20
35 | 2027-06-27
36 | 2027-07-04
37 | 2027-07-11
38 | 2027-07-18
39 | 2027-07-25
40 | 2027-08-01
41 | 2027-08-08
42 | 2027-08-15
43 | 2027-08-22
44 | 2027-08-29
45 | 2027-09-05
46 | 2027-09-12
47 | 2027-09-19
48 | 2027-09-26
49 | 2027-10-03
50 | 2027-10-10
51 | 2027-10-17
52 | 2027-10-24
53 | 2027-10-31
54 | 2027-11-07
55 | 2027-11-14
56 | 2027-11-21
57 | 2027-11-28
58 | 2027-12-05
59 | 2027-12-12
60 | 2027-12-19
61 | 2027-12-26
62 | 2028-01-02
63 | 2028-01-09
64 | 2028-01-16
65 | 2028-01-23
66 | 2028-01-30
67 | 2028-02-06
68 | 2028-02-13
69 | 2028-02-20
70 | 2028-02-27
71 | 2028-03-05
72 | 2028-03-12
73 | 2028-03-19
74 | 2028-03-26
75 | 2028-04-02
76 | 2028-04-09
77 | 2028-04-16
78 | 2028-04-23
79 | 2028-04-30
80 | 2028-05-07
81 | 2028-05-14
82 | 2028-05-21
83 | 2028-05-28
84 | 2028-06-04
85 | 2028-06-11
86 | 2028-06-18
87 | 2028-06-25
88 | 2028-07-02
89 | 2028-07-09
90 | 2028-07-16
91 | 2028-07-23
92 | 2028-07-30
93 | 2028-08-06
94 | 2028-08-13
95 | 2028-08-20
96 | 2028-08-27
97 | 2028-09-03
98 | 2028-09-10
99 | 2028-09-17
100 | 2028-09-24
101 | 2028-10-01
102 | 2028-10-08
103 | 2028-10-15
104 | 2028-10-22
105 | 2028-10-29
106 | 2028-11-05
107 | 2028-11-12
108 | 2028-11-19
109 | 2028-11-26
110 | 2028-12-03
111 | 2028-12-10
112 | 2028-12-17
113 | 2028-12-24
114 | 2028-12-31
115 | 2029-01-07
116 | 2029-01-14
117 | 2029-01-21
118 | 2029-01-28
119 | 2029-02-04
120 | 2029-02-11
121 | 2029-02-18
122 | 2029-02-25
123 | 2029-03-04
124 | 2029-03-11
125 | 2029-03-18
126 | 2029-03-25
127 | 2029-04-01
128 | 2029-04-08
129 | 2029-04-15
130 | 2029-04-22
131 | 2029-04-29
132 | 2029-05-06
133 | 2029-05-13
134 | 2029-05-20
135 | 2029-05-27
136 | 2029-06-03
137 | 2029-06-10
138 | 2029-06-17
139 | 2029-06-24
140 | 2029-07-01
141 | 2029-07-08
142 | 2029-07-15
143 | 2029-07-22
144 | 2029-07-29
145 | 2029-08-05
146 | 2029-08-12
147 | 2029-08-19
148 | 2029-08-26
149 | 2029-09-02
150 | 2029-09-09
151 | 2029-09-16
152 | 2029-09-23
153 | 2029-09-30
154 | 2029-10-07
155 | 2029-10-14
156 | 2029-10-21

## Change and Delay
Event ID | Date | Source instruction | Scope/bridge | Notice deadline | Owner | Baseline activity | Cause/attribution | Cost evidence | Schedule evidence | Decision | Status
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN
OPEN

## Turnover
Bridge | Boundary | Required dossier | Owner | Blocking punch status | Company acceptance | Evidence
ICW-ICG UD | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICW-ICG UD | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICW-ICG UD | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICW-ICG UD | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICW-ICG LD | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICW-ICG LD | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICW-ICG LD | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICW-ICG LD | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP UD | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP UD | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP UD | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP UD | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP LD | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP LD | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP LD | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
ICG-ICP LD | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
BHS-SLQ | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
BHS-SLQ | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
BHS-SLQ | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
BHS-SLQ | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
SLQ-WIS | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
SLQ-WIS | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
SLQ-WIS | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
SLQ-WIS | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
NQO-NQD | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
NQO-NQD | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
NQO-NQD | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
NQO-NQD | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
WIN-NC | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
WIN-NC | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
WIN-NC | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
WIN-NC | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SC1 | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SC1 | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SC1 | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SC1 | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SCF | Structure/bearings | As-built geometry, weld/NDT/coating, MTC, bearing setting and inspection | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SCF | Services | Isolation/transfer and accepted pressure/electrical/instrument functional tests as applicable | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SCF | Scrap | Removal/backload/transport and ONGC yard receipt | Completions | NOT ESTABLISHED | NOT ACCEPTED
SCA-SCF | Documentation | Native/as-built drawings/calculations/vendor data and accepted dossier index | Completions | NOT ESTABLISHED | NOT ACCEPTED

## 90 Day Mobilisation
Relative day target | Outcome | Accountable | Required evidence | Status | Dependency note
1 | Confirm authorised mobilisation basis | Contracts | ActualNOA, funding ceiling and scope register | OPEN | No spending authority inferred
7 | Appoint named team and data ownership | Project Director | RACI and availability | OPEN | Competence and retention of qualifying activities
15 | Secure engineering/yard/marine offers | Project Director | Audited capacities and dated quotations | OPEN | Conditional reservations need authorised commercial decision
30 | Accept survey/basis and validated schedule plan | Engineering/Planning | Survey/evidence and calendar/network review | OPEN | Target, not guarantee; field survey duration may control
45 | First independently releasable engineering packages where achievable | Engineering | Signed accepted analysis/drawing/MTO release | OPEN | Not assumed in P14 base which releases later
60 | Funded compliant procurement and released workfronts | Procurement | ApprovedPS/PO/release records | OPEN | No unapproved fabrication
75 | Demonstrate accepted production and marine envelope | Fabrication/Marine | Actual productivity, quality and module/vessel studies | OPEN | Reforecast on evidence
90 | Integrated feasibility and recovery decision | Project Director | CPM/resource/cash/release review | OPEN | Approve revised commitments only after verification

## KPI and Escalation
Metric | Definition | Proposed trigger | Action | Current value
Release readiness | All applicable evidence accepted for IWP | Any mandatory hold open | Do not release | NO VERIFIED DATA
Critical/near-critical delay | Updated validated network vs approved milestone | Negative target float or missed gate | Recovery review; no invented actualfloat | NO VERIFIED DATA
Plan reliability | Completed accepted weekly commitments / due commitments | Below agreed target for2periods | Constraint/root-cause review | NO VERIFIED DATA
Productivity | Acceptedquantity / productivecrew-day | Below validated estimate | Check access, resources, rework and forecast | NO VERIFIED DATA
Quality rework | Rejected/reworked quantity / inspected quantity | Any structural rejection or recurring trend | NCR and method review | NO VERIFIED DATA
Cash cover | Funded available cash vs next13week obligations | Forecast negative balance | Finance/spending decision | NO VERIFIED DATA
Document review | Age since valid submission vs applicable C8 period | Overdue and driving release | Escalate through agreed review route | NO VERIFIED DATA
Handover | Accepted systems/dossiers vs due boundaries | Blocking punch or dossier gap | Dedicated closure owner | NO VERIFIED DATA

## Technical Queries
Query | Issue | Source | Required resolution | Owner | Release affected | Status
TQ01 | BHS/SLQ fixed-versus-sliding bearing orientation differs between sources | SOW/study versus criteria | Confirm fixed point, sliding direction/travel, guide restraints and final bearing setting | Structural/Company | Bearing and supporting-deck design | OPEN
TQ02 | Tender GA dimensions versus surveyed support/elevation geometry | Combined1 p27,pp31–32,p36; original studies | Verify centreline/gap/end-zone/extents and field tolerances; retain dimension conventions | Survey/Structural | Global model and shop details | OPEN
TQ03 | ICW live-load resultant differs between report and model summary | ICW preliminary report156.25kN versus SACS144.69kN | Reconcile loaded area, load units and actual model loading; no error conclusion without model check | Structural | Load-case and calculation release | OPEN
TQ04 | Camber based on DL versus genericL/200 source wording | Criteria and three preliminary bridge studies | Approve camber profile, fabrication tolerances, dead-load stage and field setting | Structural/Fabrication | Shop geometry | OPEN
TQ05 | Procurement material grade and thickness not established by studyFy alone | StudyFy50ksi and tender member references | Specify grade, toughness/weldability, corrosion allowance and mill records for actual sections | Structural/Procurement | Material purchase | OPEN
TQ06 | Actual corrosion loss/member joint condition | Pre-engineering/NDT scope | Use surveyed thickness/defects in capacity checks and repair details | Survey/Structural | Strengthening design | OPEN
TQ07 | Wrap strengthening connection and staged capacity | StructuralSOW addendumICG/ICP/BHS | Check interface/weld/shear transfer, existing member condition, temporary stage and inspection access | Structural | Pre-install support release | OPEN
TQ08 | Platform displacement and piping reactions | Criteria movement/thrust; Combined3 p260 | Agree platform translation/rotation/thermal movements and iterate piping/support/bearing reactions | Structural/Piping | Bearings/services/supports | OPEN
TQ09 | Future piping allowance double counting | Criteria operating/planned-future plus20% wording | Separate known future loads from allowance and approve load schedule | Piping/Structural | Design-basis freeze | OPEN
TQ10 | New drawing register34entries versus older38entries | Combined1 pp3–5 | Map omitted/renumbered sheets and revisions; do not infer scope deletion | DocumentControl/Structural | Drawing applicability baseline | OPEN
TQ11 | ICW source GA registerRev0 versus titleRevA | Combined1 p27 | Obtain controlled issue identity and revision disposition | DocumentControl | Tender-to-detail mapping | OPEN
TQ12 | NQO/NOQ platform naming | Combined1 Annexure1 and bridge scope | Confirm platform ID, coordinates and interfaces | Interface/Company | Platform assessment scope | OPEN
TQ13 | Quantity discrepancies | SOW/MTO1142vs1141MT;1168vs1166m;719vs718m² | Resolve against controlled detail MTO and company disposition; preserve printed/source-row totals | QuantityEngineer | Purchase/budget/progress baseline | OPEN
TQ14 | Preservice/installation/removal vessel input envelope | Newbridge GAs; module/vessel registers | Confirm modules, lift weights/COG, actual-radius charts, transport motion and temporary load paths | Marine/Structural | Marine operation assurance | OPEN
TQ15 | Discipline specification applicability and tie-in/test boundaries | Combined1/2/3; bridge-specific scope | Define actual piping/electrical/instrument/firewater/cable transfers and required tests; reject unrelated generic additions | DisciplineLeads/Operations | Service transfer and commissioning | OPEN

## Stage Integration
Uploaded model | P14 control | Required correction or integration
Stage27 | Cost Commitments / Requirements / Daily Production | Separate quantity/EV, certified billing and cash; maintain unknown inputs
Stage28 | Schedule285 / Calendars and Method | Replace illustrative120activity chain with traceable integrated dependencies; actualL4detail still needs constructability
Stage29 | Schedule Scenarios / Resource Commitments | Scenario capacity is uncommitted; verify bottlenecks and cost recovery
Stage30 | Workpack Readiness / Daily Production | Verified quantities and accepted productivity required
Stage31 | Workpack Readiness / QA and Release Gates | Screen alone cannot authorise work; require evidence and signed release
Stage32 | Productivity Forecast / Schedule285 | Productive crew-day estimate is not calendarCPM; route remaining workdays to validated network
Stage33 | Risk Register / KPI and Escalation | Track early-warning evidence and actual mitigation owner
Stage34 | CEO Decisions / Resource Commitments | Use one source of date/cost/progress truth; no inconsistent parallel baselines
Stage35 | 90Day Mobilisation | D45firstAFCis an objective; not demonstrated by baseline assumptions
Volumes1–6 | A–Z Execution Plan and linked registers | Framework text remains planning; fill bridge-specific evidence and authority

## Productivity Forecast
Bridge | Source indicative MT | Approved baseline MT | Accepted actual MT | Productive crew-days | Observed MT/productive crew-day | Remaining approved MT | Verified assigned crews | Future productive utilisation0–1 | Remaining productive workdays | Updated CPMfinish input | Status/evidence
ICW-ICG UD | 49 | [9 empty] | No approved quantity/productivity yet
ICW-ICG LD | 122 | [9 empty] | No approved quantity/productivity yet
ICG-ICP UD | 116 | [9 empty] | No approved quantity/productivity yet
ICG-ICP LD | 160 | [9 empty] | No approved quantity/productivity yet
BHS-SLQ | 282 | [9 empty] | No approved quantity/productivity yet
SLQ-WIS | 91 | [9 empty] | No approved quantity/productivity yet
NQO-NQD | 93 | [9 empty] | No approved quantity/productivity yet
WIN-NC | 46 | [9 empty] | No approved quantity/productivity yet
SCA-SC1 | 63 | [9 empty] | No approved quantity/productivity yet
SCA-SCF | 119 | [9 empty] | No approved quantity/productivity yet