# Integrated Bridge Project Management and Engineering Package

Revision P5 | 25 October 2026 | Ten bridge packages | Construction release deferred

Prepared from the uploaded tender, criteria, drawings, specifications and planning files. This package integrates scope, design-development controls, MTO, procurement, fabrication, marine installation, execution planning, commissioning, handover, scheduling and critical-path analysis. It does not represent completed field work, approved purchases, AFC approval or independently completed structural design.

# 1. Executive delivery basis and management decisions

The recovery scenario contains 205 planned activities/milestones (161 nonzero tasks). It assumes commencement 1 November 2026, two fabrication lines, one strengthening cell, three strengthening crews, separate installation/support capacity and sequential heavy-lift/cargo reservations. The earliest internal handover milestone is 15 June 2027. These are conditional planning results, not commitments.

The controlling physical interfaces are survey-to-design, checked material release-to-fabrication, jacket/landing readiness-to-installation, BHS service acceptance-to-demolition, and completed inspections/records-to-handover. Appoint a single Project Director and package owners; retain separate technical, client-operational and vessel authority.

| Requirement | Preparedcontent | Status | Remaining |
| --- | --- | --- | --- |
| Scopeofwork | Tenbridges;100 work packages | Preparedforreview | Quantities/interfacesmustbefrozen |
| Designbasis | 24 criteriarecordsplus 14 source records | Consolidatedfromuploads | Resolveapplication/conflicts |
| Structuraldesign | P 4 source-basedreviewandcalculations | PARTIAL / DEVELOPMENT | Independentglobal/member/joint/fatiguemodelnotcompleted |
| Detailedengineering | 101 document/drawingdeliverableregister;P 4 developmentdrawings | PARTIAL / DEVELOPMENT | Finaldimensions,sections,connections,bearings/temporary worksremainopen |
| AFCdrawings | AFCreadiness/reviewregisterandcontrolprocedure | NOT AFC | Noapproval/signatureinvented |
| MTO | Tenbridgequantityregisterplusdiscrepancies | Tenderquantitybasis | NotfinalpurchasingMTO |
| Procurement | 25 packagesandreleaseworkflow | Planned;noenquiry/orderissued | Quotes/lead time/vendorapproval/fundingrequired |
| Fabrication | Workpacks,sequence,QA/ITPrequirements | Planned;notperformed | Releaseddrawings/materials/yardresourcesrequired |
| Installation | Bridge-specificsequencesandmarinegates | Planned;notperformed | Operation-specificengineering/permitsrequired |
| Executionmethodology | SourceRevCconvertedintomanagement/work packprocedures | Forreview;notanapprovedoperationmethod | Temporaryworks/lifting/transportcalculationsrequired |
| Commissioning | Tenreadiness/test/acceptancecategories | Planned;notperformed | Approveddiscipline-specificprocedures/testvaluesrequired |
| Scheduling | 205 activityrecoverycaseand 207 activitytwo-crew Case | Computedscenarios | Duration/resource/NOAassumptionsunverified |
| Criticalpath | Forward/backwardpass;53 zero-floatnonzero tasks | Computedagainstinternal finish | Notafinalapprovedresource-levelledP 6 baseline |
| Overallprojectschedule | 1 Nov 2026 scenario;15 Jun 2027 handover milestone | Conditionaltarget | ActualNOAandseasonalmarginrequirevalidation |
| Costandcash | 16 unpricedcategoriesandbillingcontrols | Inputstructureprepared | Noapprovedbudget, margin and funding forecast |
| Handoverandwarranty | Dossier/punch/acceptance/warrantyworkflow | Planned | Actualacceptanceandguarantee releasespending |

# 2. Source hierarchy and document control

Read the executed contract and controlling addenda together. Apply the uploaded BRRP-specific Part II with general structural Part I Rev 14. The general structural criteria repeated in Section 3 match, but S&SRP/WSSRP-2 project-specific provisions are not silently added to BRRP. Maintain numbered revisions, controlled transmittals, comment resolution, superseded-drawing withdrawal and signed release evidence.

| ID | Source | File / location | Application |
| --- | --- | --- | --- |
| S01 | GCC | Vol-I-II GCC.docx; 2.1.1;6.3.1.1; related contract clauses | EPC responsibilities and 12 months from NOA; executed contract governs |
| S02 | Technical SCC | Technical_SCC.pdf; 2;3;13;digitalmeasurement provisions | Completion/conditionalmonsoon relief; marine requirements; LD; e-MB |
| S03 | Structural scope | SOW & Bridge Report Combined.pdf; 15-53; structuralSOW RevC | Ten bridges; landings; services/demolition interfaces; drawings are tender references |
| S04 | Source replacement studies | SOW & Bridge Report Combined.pdf; 97-100;122-123;133-135;152-153;196-199;207-209 | Study geometry/results only; not independently reproduced |
| S05 | Design criteria | Design Criteria & Execution Methodology.pdf; Part I 1-116;BRRPPart II 117-120 | Rev 14 generalcriteria;25 yearlife; project-specificapplicability |
| S06 | Execution methodology | Design Criteria & Execution Methodology.pdf; 133-154 | B774-000-83-43-EM-0001 RevC; tender-level method |
| S07 | Structural addendum | Addendum_Structure_SOW.pdf; 1 | ICG ICP BHS jacket strengthening |
| S08 | MTO drawings inspection | MTO Drawings IRT.pdf; 1;2-7;8-14;15-34 | MTO;partiallandings;standards;IRT |
| S09 | Specifications | Specification Combined.pdf; 1-2;3-38;55-81;91-168;169-243 | Structural register;weld/NDT;fabrication;coating;materialinstallation |
| S10 | Commercial amendments | Addendum (1).pdf;AddendumtoA 3.pdf; Applicableamendments | Vendor/agencyprovisions;catering;paymentchanges;currency/localcontent |
| S11 | Commercial price/payment schedules | Appendix A-3;Appendix A-10; BRS; Applywithamendments | Quote/billingstructures; not cost evidence |
| S12 | Planning files | Sixmastervolumes;Stages 10/25-35;Level 3/360 day; Pre-awardplanning | Assumptions only; schedule/resource/cost/quantity discrepancies are retained |
| S13 | Other-projectpackage | Section 2.pdf;Section 3.pdf; Cover andproject-specificPart II | S&SRP/WSSRP-2 content not automatically imported into BRRP |
| S14 | Shivanshwebsite | shivanshoffshore.in; Accessblockedearlier | No current fleet ownership/suitability/availability claims verified |

# 3. Scope of work and bridge boundaries

Common scope: records review, pre-engineering and construction surveys, engineering, procurement, fabrication, inspection/coating, temporary works, loadout, transport, marine support, offshore work, testing/commissioning, demolition where specified, accepted measurements and as-built handover. Confirm interfaces and any company supply explicitly; do not assume platform cranes, accommodation or storage are available.

| Bridge | Worktype | Structural row MT | Demolition MT | Handrailm | Gratingm 2 | GI sheeting m² |
| --- | --- | --- | --- | --- | --- | --- |
| ICW-ICG UD | Strengthening | 49 | 25 | 110 | 58 | 273 |
| ICW-ICG LD | New/replacement | 122 | 1 | 118 | 88 | 0 |
| ICG-ICP UD | Strengthening | 116 | 25 | 93 | 49 | 419 |
| ICG-ICP LD | New/replacement | 160 | 1 | 176 | 132 | 0 |
| BHS-SLQ | Replacement/services | 282 | 210 | 88 | 82 | 332 |
| SLQ-WIS | Strengthening | 91 | 15 | 98 | 51 | 0 |
| NQO-NQD | Strengthening | 93 | 25 | 93 | 58 | 250 |
| WIN-NC | Strengthening | 46 | 10 | 45 | 29 | 0 |
| SCA-SC1 | Strengthening | 63 | 15 | 88 | 55 | 0 |
| SCA-SCF | Strengthening | 119 | 30 | 257 | 116 | 0 |

Replacement ICW–ICG and ICP–ICG: new lower-deck bridges, fixed-intent/hinged and sliding support interfaces, landing/deck extensions and modifications, applicable jacket strengthening, access fittings and electrical interfaces.

BHS–SLQ: new bridge and supports, landings, piping/cable/lighting/support interfaces, roofing/cladding, lifeboat/muster and safety-study interfaces as specified; install/commission the new facility before removal of the old bridge.

Seven strengthening bridges: verify corrosion and scope, establish approved access/temporary conditions, strengthen specified members/joints/landings, restore grating/handrails/sheeting as applicable, inspect and accept. Do not derive full work quantities only from tonnage.

All modified facilities and temporary arrangements require planned restoration/closure. Scope questions and source-reference conflicts remain in a controlled technical-query register.

# 4. Design basis and structural engineering programme

Design life: 25 years. Source BRRP Part II p 119. Status CONFIRMED.

Elastic modulus E: 210000 MPa. Source Part I Annexure 2 p 66. Status CONFIRMED.

Shear modulus G: 80770 MPa. Source Part I Annexure 2 p 66. Status CONFIRMED.

Poisson ratio: 0.3 ratio. Source Part I Annexure 2 p 66. Status CONFIRMED.

Steel density: 7850 kg/m3. Source Part I Annexure 2 p 66. Status CONFIRMED.

Gravity: 9.81 m/s2. Source Part I Annexure 2 p 66. Status CONFIRMED.

Thermal expansion: 1.2 e-05 per C. Source Part I Annexure 2 p 66. Status CONFIRMED.

Global walkway loading: 250 kg/m2. Source Bridge clause p 42; Annexure 4. Status CONFIRMED.

Local grating loading: 500 kg/m2. Source Annexure 4 p 70. Status CONFIRMED.

Minimum clear walkway: 1.2 m. Source Bridge clause p 43. Status CONFIRMED.

Bridge vertical limit: L/400 mm consistent with L. Source p 43;Annexure 12 pp 85-86. Status CONFIRMED.

Bridge lateral wind limit: L/500 mm consistent with L. Source Annexure 12 p 86. Status CONFIRMED.

Differential translation multiplier: 1.5 ratio. Source Bridge clause p 43. Status CONFIRMED; input movements pending.

Hinged axial thrust multiplier: 1.5 ratio. Source Bridge clause p 43. Status CONFIRMED; thrust envelope pending.

Future piping operating-load allowance: 20 percent. Source Bridge clause p 42. Status CONFIRMED; included/excluded basis to reconcile.

Camber: Compensate dead-load deflection profile. Source Bridge clause p 43. Status RULE CONFIRMED; magnitude/profile pending.

Wind gust for 56 m/84 m: 15 seconds. Source Annexure 5 p 73. Status CONFIRMED.

Wind gust for 42 m: 3 seconds. Source Annexure 5 p 73. Status CONFIRMED.

Environment: MH North and South field. Source Part II p 119;Annexure 13 A. Status CONFIRMED; height adjustment/calculation pending.

Material procurement: Spec 6001 F Rev 14 requirements. Source Specification Combined pp 169-243. Status Grade/toughness selection pending.

Welding/NDT: FS2009F Rev 8 requirements. Source Specification Combined pp 3-38. Status Apply by joint and inspection plan.

Coating: FS2005 Rev 9 requirements. Source Specification Combined pp 91-168. Status Exposure-specific system selection pending.

Roof: Process-platform connecting bridges; slope minimum 1:50 applicability. Source Bridge clause p 43. Status Confirm bridge-specific implementation.

Location tolerance: +1.0 m as written in source requirement. Source Bridge clause p 43. Status Clarify interpretation for existing supports; NOT bearing travel.

Design sequence: validate survey, coordinates and datums; establish actual loads and combinations; reconstruct member connectivity/groups and restraints; reproduce source gravity checks; run strength/stability/serviceability; check joints, fatigue/VIV and movements; transfer concurrent signed reactions to existing platform models; engineer temporary/marine conditions. Independent model reproduction and member/connection/bearing resistance design remain open.

The source braced space-truss models use 56/84/42 m lengths, compared with approximate reported gaps 54.5/80.5/40 m. These are not final shop dimensions. Source fixed-support language must not be interpreted as fully moment-rigid restraint. Clarify the BHS SLQ support-wording conflict.

| Bridge | Sourcevertical/limitmm | Sourcelateral/limitmm | Listedmember/jointUC |
| --- | --- | --- | --- |
| ICW-ICG LD | 105/140 | 87/112 | 0.557/0.509 |
| ICP-ICG LD | 177/210 | 123/168 | 0.61/0.625 |
| BHS-SLQ LD | 32/105 | 76/84 | 0.916/0.859 |

These are transcribed source analysis results with independently recalculated criterion limits; no new global analysis is claimed. P4 arithmetic, thermal/section calculations and source-based sheets are carried forward as development evidence, not final design.

# 5. Detailed engineering and AFC preparation

Maintain a calculation-to-drawing matrix. Each GA, member schedule, connection, bearing and landing detail must cite a checked calculation and survey revision.

For new bridges prepare framing, secondary steel, access, service supports, bearings, end connections, platform strengthening, temporary works, lifting/transport interfaces and detailed MTO. BHS also needs service transfer and demolition engineering.

For strengthening bridges prepare existing-condition markups, member/joint repairs, temporary load paths, landing interfaces, access/fittings and inspection work packs.

Engineering checking includes geometry, actual material grade/toughness, effective lengths, local effects, welds/bolts, corrosion basis, fatigue details, movement envelopes, tolerances and inspectability. Do not infer these from screenshots.

AFC workflow: prepare → discipline check → independent/technical review as required → multidisciplinary/interface clearance → ONGC review as applicable → close comments → authorised release/transmittal.

No drawing is stamped AFC, signed or assigned a fictitious approval date in this package. For-review title blocks, registers and review sheets support later release; they are not approved drawings.

The deliverable register contains 101 proposed documents/drawings. P4 source-based development sheets are included in the package as reference material; all applicable open engineering items remain visible.

# 6. MTO, measurement and material control

The source MTO is indicative and must be developed into member/plate/component quantities from detailed engineering. Separate structural additions, demolition, grating, handrails, sheeting, services and temporary works. Tender steel quantities are not lift weights. Procurement requires material specifications, cut sizes, lengths, grades, certificates and wastage rules.

| Category | Calculatedrows | Printedsourcetotal | Difference | Action |
| --- | --- | --- | --- | --- |
| NewbridgeMT | 367 | 367 | 0 | ARITHMETICMATCH |
| ExistingbridgestrengthMT | 361 | 361 | 0 | ARITHMETICMATCH |
| Newlanding/deckMT | 197 | 197 | 0 | ARITHMETICMATCH |
| ExistinglandingstrengthMT | 216 | 217 | 1 | RECONCILE |
| Demolition MT | 357 | 357 | 0 | ARITHMETICMATCH |
| Handrailm | 1166 | 1168 | 2 | RECONCILE |
| Gratingm 2 | 718 | 719 | 1 | RECONCILE |
| GIsheetingm 2 | 1274 | 1274 | 0 | ARITHMETICMATCH |
| StructuraltotalMT | 1141 | 1142 | 1 | RECONCILE |

The 1 MT steel discrepancy comes from existing landing/deck strengthening 216 MT by rows versus 217 MT printed. Additional checks establish 1166 m handrail by rows versus 1168 m printed and 718 m2 grating versus 719 m2 printed. Retain both versions; no silent correction or purchase release.

Addendum jacket wraps are an overlay requiring inclusion reconciliation: ideal shell estimates from P4 are 2.479 MT ICG,3.092 MT ICP and 0.346 MT BHS. They exclude gaps, quarter fabrication, welding, allowances, corrosion/fit and wastage; do not add them to tender totals or order them without confirming existing inclusion and detailing.

Issue controlled MTO revision and material requisition per bridge/work pack.

Receive with certificates, heat/mark identification and inspection records; segregate nonconforming material.

Track receipt, storage, preservation, issue, installed quantities, surplus and returns.

Record accepted measurement and digital e-MB evidence as required for certification/billing; progress quantities and commercial quantities may use different rules.

# 7. Procurement and subcontract management

The 25 package procurement plan is a preparation register. No enquiry, order or charter has been issued. Vendor lists/agency provisions must be read with amendments; technical suitability, commitments and applicable client review still apply.

Create approved requisitions and bid packages with drawings, specifications, quantities, inspection, documentation, packing and delivery requirements.

Obtain comparable quotations; perform technical and commercial evaluations; verify subcontractor facilities and capacity.

Use authorised purchase commitments only after funding and delegated approval. Flow down applicable contract, HSE, QA, insurance, documentation and change requirements.

Expedite engineering/manufacturing/inspection/dispatch milestones, not only promised delivery dates.

Treat bearings, lifesaving equipment, cables/piping and specialist services as potential lead-time constraints. The schedule 25 daybulk-material assumption does not validate every package.

Inspect and release by approved ITP/IRT; control substitutions through engineering and applicable client approval.

| ID | Package | Quantitybasis | Release / issue |
| --- | --- | --- | --- |
| P01 | Structural tubulars / sections | TBC | FinalmemberMTO/grade/toughness; Bulkprocurement; no finalsectionselection |
| P02 | Plates / gussets / stiffeners | TBC | Connection/local designMTO; Do not infer from totalsteeltonnage |
| P03 | Jacket wrap steel | TBC | Addendumgeometry;P 4 estimateonly; Inclusionwithin tenderMTO unresolved; avoiddoublecount |
| P04 | Grating | 718 m2 | Source row sum; printed 719; Reconcile beforepurchase; local 500 kg/m 2 check |
| P05 | Handrails | 1166 m | Source row sum; printed 1168; Reconcile beforepurchase; fittings/detail allowances |
| P06 | GI sheeting / roofing | 1274 m2 | SourceMTO; actualsheetlayoutpending; Coating/material/fixing compatibility |
| P07 | Bearings / PTFE / guides | TBC | Verifiedreactions/movements/detail; Vendorengineering; lead timeunconfirmed |
| P08 | Structural bolts / fasteners | TBC | Approvedjointdetail; Grade/size/tensioningprocedurepending |
| P09 | Welding consumables | TBC | ApprovedWPS/materialcombination; Storage/handling/batchtraceability |
| P10 | Coating system / abrasives | TBC | Exposure/system/area/DFT; No inventedcoating area or genericpaintquantity |
| P11 | Cables / cable trays / lighting | TBC | ElectricalMTOandapprovedrouting; Testing/certification/earthing |
| P12 | BHS piping / fittings / valves | TBC | Linelists/isometrics/specs; Hydrotest/transfer/operatingloads |
| P13 | Instrument / control interfaces | TBC | Instrumentlist/loopboundary; Isolation/loop/functionaltestrequirements |
| P14 | Service supports / monorail | TBC | Verifiedservice/monorailloads; Localdesignandliftingequipmentrequirements |
| P15 | Lifeboat / survival craft interfaces | TBC | Confirmedscopeandapprovedsafetystudy; Potentiallonglead; notverifiedby 25 daybulkassumption |
| P16 | Scaffolding / access / temporary steel | TBC | Engineeredtemporary works; Design/inspection/permitcontrols |
| P17 | Lifting gear / spreader / rigging | TBC | Approvedlift study; Certifiedgearandsuitability; no lift release |
| P18 | Sea-fastening / grillage | TBC | Approvedtransport/vesselanalysis; Actualbarge/deckandvoyageroute |
| P19 | Survey services | TBC | Approvedsurvey/inspectionplan; Accessandcompetence |
| P20 | Engineering specialist services | TBC | Document/calculation register; Namedtechnical authority/capacity |
| P21 | NDT / dimensional / coating inspection | TBC | ITP/IRTandproductiondemand; Independentqualified coverage |
| P22 | Fabrication yard slots | TBC | Capacityauditandloadoutaccess; Two linesandcellareassumptions |
| P23 | Heavy-lift / cargo / support spreads | TBC | Engineeredselectionandavailability; Price standby/mob/demob/offhire/cross-project conflicts |
| P24 | Towage / anchorhandling / supply | TBC | Spread/fieldrequirements; No fleet availabilityassumed |
| P25 | Waste handling / backload / disposal | TBC | Approvedwasteclassificationandrecords; Traceabledisposalroute |

# 8. Fabrication execution and production control

Audit fabrication bays, cranes, material flow, welding manpower, inspection capacity, coating throughput, storage and loadout access before committing capacity.

Release shop work packs with current authorised drawings, material/cut lists, member/weld marks, WPS, NDT, tolerances, coating and inspection points.

Verify material identity before cutting; retain traceability through splits, assemblies and repairs.

Sequence preparation, fit-up, welding, NDT, repairs, dimensional acceptance and coating. Use qualified personnel and approved procedures; no welding parameters or inspection percentages are invented.

Conduct constructability and suitable trial-fit checks; record measured interface dimensions and changes.

Protect coating and identification through handling/storage. Issue yard release only after required inspection/NCR closure.

Track accepted stage output and actual labour-hours; separate replacement modules from strengthening kits and offshore labour.

First 20 daykitrelease is a gate within one 35 dayproductionstream. It is not additional duplicate cell capacity.

Resolve inspection/coating bottlenecks in the six-week look-ahead. Two lines and one cell are capacity assumptions, not demonstrated throughput.

# 9. Marine engineering, logistics and offshore readiness

Establish module dimensions, verified weights/COG and lift boundaries before vessel selection. Do not size a crane from aggregate bridge tonnage.

Check crane curves at actual radii, configuration, stability, deck loading, positioning, operating limits, certification and availability.

Prepare loadout, grillage, sea-fastening and transport analyses against actual vessel/route/motion data and source criteria.

Prepare the required 3 D lift analysis with rigging/skew/dynamic/weight-COG cases, landing arrangements, guides and temporary conditions.

Obtain required marine assurance/MWS reviews under applicable criteria/specification; no lift is released by a management programme alone.

Plan accommodation, supply, cargo, towage, transfers, field moves, waste/backload and emergency readiness. SCC minimum 60 special-personnel accommodation is a floor, not proof of capacity for simultaneous crews.

Source methodology does not provide platform accommodation/space or company deck-crane use for construction; arrange contractor-supported resources.

Define weather decision authority, operating limits, forecast windows, suspension/cyclone actions and safe departure. Contractor fleet capability and commitments remain unverified.

# 10. Installation and execution methodology

The following are management sequences for developing approved work packs. They do not specify cutting, welding, rigging or demolition instructions. Every operation requires project-specific engineering, permits and readiness release.

## 10.1 ICW–ICG and ICP–ICG new lower-deck bridges

Accept survey and engineering; verify geometry/clearances and existing platform capacity.

Complete applicable ICG/ICP jacket strengthening and landing/deck modifications under checked temporary conditions.

Accept fabricated bridge, dimensions, coating and traceability; verify mass/COG and transport configuration.

Complete loadout/transport releases, site access, permits, SIMOPS and operational interfaces.

Execute the approved lift/landing and support-setting procedure; retain engineered temporary stability until permanent connections are accepted.

Complete permanent connections, bearings/guides, walkway/access fittings and electrical interfaces; inspect and restore coatings.

Verify bearing settings and clearances, accepted quantities, functional checks and package handover.

## 10.2 BHS–SLQ integrated replacement and services

Verify all existing services, new routing, operating significance, tie-ins, isolation requirements and safety/lifesaving/muster interfaces.

Complete required jacket/landing readiness and release the new bridge for approved installation.

Install/connect the new bridge and service supports; complete applicable piping, electrical and instrumentation work and approved tests.

Agree and execute authorised service transfers and reinstatement with ONGC; confirm required new-facility operational acceptance.

Only then release existing bridge demolition after confirming redundant services, isolations, temporary stability and engineered removal/backload plan.

Inspect remaining structures, restore affected facilities, document waste/disposal and close punch/dossiers.

## 10.3 Seven strengthening bridges

Verify existing thickness/condition and authorised repair scope; locate live services and restricted areas.

Issue a complete bridge-specific kit/work pack and prepare approved access, protection and temporary conditions.

Execute authorised strengthening/modification without unapproved load-path changes.

Perform required connection/NDT/dimensional acceptance and coating restoration.

Restore access, grating, handrails/sheeting as applicable; remove temporary arrangements only under authorised sequence.

Record accepted quantities and inspection evidence; close package punch and handover.

# 11. Quality, HSE and operational control

Use source specifications/IRT to produce approved inspection/test plans, responsibilities, notices and release points. Maintain competent inspection, material traceability, calibrated equipment, nonconformance/concession control and progressive dossiers.

| ID | Stage | Verification | Basis | Responsibility | Release |
| --- | --- | --- | --- | --- | --- |
| Q01 | Materials | MTC/identity/grade/dimensions and specified tests | Applicable IRT/specification | QA / CA/TPI as applicable | HOLDpendingapproved ITP |
| Q02 | Weldingreadiness | WPS/PQR/welderqualifications/consumables | FS2009F Rev 8 | QA / Weldingengineer | Beforeproduction |
| Q03 | Fit-up | Geometry/gaps/alignment/preparation | Approveddrawings/WPS | FabricationQA | Beforewelding |
| Q04 | Weld/NDT | Method/extent/acceptance and repairclosure | FS2009F/approved ITP | QualifiedNDT/QA | Nopercentageinvented |
| Q05 | Dimensions | Coordinates/tolerances/interfacefit | Approveddrawings/procedure | Survey/QA | Beforecoating/loadout |
| Q06 | Coating | Surfaceprep/environment/DFT/repairs | FS2005/approvedsystem/IRT | Coatinginspector | Beforepreservation/release |
| Q07 | Loadout | Release/weight/COG/transportconfiguration | Approvedmarineengineering | Marine/QA/MWSasrequired | Sail-awaygate |
| Q08 | Offshoreconnections | Fit-up/weld/bolt/inspection/restoration | Approvedwork pack/ITP | OffshoreQA | Beforeacceptance |
| Q09 | Commissioning | Specifiedtests/operationalrecords | Approvedtestprocedures | Completions/ONGC | Beforehandover |
| Q10 | Turnover | Dossier/punch/quantities/as-builts | Contractacceptanceindex | QA/ONGC | Clientacceptance |

Implement permit-to-work, SIMOPS, isolation, hotwork, lifting, work-at-height, dropped-object and marine-transfer controls.

Verify competence, medical/training/certification as applicable; plan fatigue, rotations, rescue and medical evacuation with relevant authorities.

Conduct hazard/constructability reviews, toolbox briefings, inspections, drills and corrective-action follow-up.

Project Director coordinates delivery; technical authority, ONGC operations and vessel authorities retain their respective powers.

Maintain a safe suspension/second-season plan if weather/calendar scenarios require it; the comparator assumes such a plan and does not prove it.

# 12. Testing, commissioning and operational acceptance

Prepare discipline-specific test packs with system boundaries, prerequisites, approved test values, calibrated equipment, witnessing, acceptance criteria, reinstatement and records. No generic hydrotest pressure, insulation threshold or torque is selected here.

| ID | Discipline | Scope | Verification | Procedurebasis | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| C01 | Structural readiness | All | Acceptedconnections;dimensions;grating;handrails;access;coating | Approvedstructuralchecks/ITP | QA / Construction | Open |
| C02 | Bearings and movements | Newbridges | Position/guideclearance/setting and protection perapproved details | Approvedbearinginstallationrequirements | Engineering/QA | Open |
| C03 | Electrical | Applicablebridgecircuits | Continuity/insulation/earthing/lighting and other specifiedchecks | Approvedelectricalprocedures;valuesfromspecification | Electrical/ONGC | Open |
| C04 | Instrumentation | ApplicableBHSinterfaces | Loop/function/control verification and restoration | Approvedinstrumentprocedures | Instrumentation/ONGC | Open |
| C05 | Piping | ApplicableBHSsystems | Inspection;pressure/leaktest as specified;cleaning/reinstatement | Approvedline-specificprocedures;notassumedtestpressures | Piping/ONGC | Open |
| C06 | Service transfer | BHS-SLQ | Approvedisolations;tie-ins;functionalacceptance;contingency | ONGCoperational release | Commissioning/ONGC | Open |
| C07 | Demolition release | BHS-SLQ | Newbridgeandservicesaccepted;temporary-stabilityandisolationverified | Signeddemolitionreadinessgate | Technical Authority/ONGC | Hold |
| C08 | Safety/lifesaving interfaces | Applicablelandings | Muster/access/lifesavingrequirementsandsafetystudyactions | Approvedvendorandoperationalrequirements | HSE/Marine/ONGC | Open |
| C09 | Punch clearance | All | Closeacceptance-criticalitems;recordauthorisedresidualitems | Agreedpunch classification | Completions/ONGC | Open |
| C10 | Handover / e-MB | All | Acceptedquantities;as-builts;quality/test records;certificates | Contractualacceptanceandbillingrequirements | QA/Contracts/ONGC | Open |

Structural acceptance is not a substitute for service commissioning. BHS transfer requires agreed isolations/tie-ins, functional readiness, restoration and operational authorisation. Demolition is a separate gate after the new bridge/services meet their release requirements.

# 13. Integrated schedule and critical-path analysis

Commencement: 1 Nov 2026 is an unconfirmed scenario. Rebase full calendars after actual NOA; do not merely shiftdates acrossmonsoon.

Contract: ReviewedGCC/SCC 12 months fromNOA. Conservative lastworkday 31 Oct 2027 in this scenario; confirm convention and extensions.

Duration: Elapsedcalendardays; seven-dayonshoreplanning. All durations are illustrative allocations within prior scenario, not measured productivity/vendor commitments.

Offshorecalendar: No productive offshore work 16 May-15 Oct inclusive. Each split activity fits wholly in an open season; safe stoppoints/renewedpermits require engineering.

Relationship: FSzero-lag; duration d occupies [ES,ES+d); milestone marks boundary. Lastworkingdate is EFminus 1, while milestone date is EF.

Resources: 2 fabricationlines+1 strengtheningcell;3 strengtheningcrews plus installation/supportresources;1 heavy-liftspread;1 cargospread. Namedexclusivewindows checked; NOT full labour/POB/coating/QAlevelling.

F041: Firstkitrelease milestone at 20 days within one 35-day strengtheningproductionstream; not duplicateproduction.

Weatherreserve: 10 days modeled as a seasonal capacity hold after plannedoffshorecompletion, then 3 demobdays. This is a conservative allowance, not validatedmetoceanworkability.

CPM: Calendar-aware forward/backwardpass. Float is elapsedcalendar difference between latest and earlieststart, not an availableworkdaycount. Critical means zero float to internalearliest finish; tied paths may exist.

Contractfloat: Separate backwardpass to unextended deadline. Completionmilestone float is NOT offshore float; seasonal barrier can leave only a fewdays of offshore margin.

Comparator: Twostrengtheningcrews withNQaftercrewApackages; explicit 7 daysecond-season remobilisation; safe suspension,capacity,costandweather are assumptions.

Scenario sensitivity: Extra days on P010.02 test calendar thresholds; not a probabilistic prediction. Noautomaticcontractualextension assumed.

The 205 activityrecoverycase includes 161 nonzero tasks and 44 milestones. Forward/backwardpasses check all dependencies and calendars. Namedexclusive fabrication, strengthening, heavy-lift and cargo reservations are sequenced. It is not fully quantity-loaded crew/POB/QA/coatinglevelling or an approvedP 6 baseline.

A phase-completion milestone is the boundary after its last workday. The target offshore work finishes 1 May 2027, with milestone 2 May; reserved allowance 2–11 May and demobilisation 12–14 May, with phase-completeboundary 15 May. Dossiersrun 2–31 May; finalreview 1–14 June; handover milestone 15 June.

| ID | Milestoneboundary | Threecrewscenario | Twocrewscenario |
| --- | --- | --- | --- |
| M000 | Assumed NOA / commencement | 2026-11-01 | 2026-11-01 |
| E030 | Detailed design, AFC drawings and ITP approval - phase complete | 2026-12-24 | 2026-12-24 |
| P010 | Vendor approval, steel purchase and phased yard delivery - phase complete | 2027-01-03 | 2027-01-03 |
| F010 | Fabricate, NDT, dimensional inspection and coating - phase complete | 2027-02-07 | 2027-02-07 |
| F020 | Fabricate, NDT, dimensional inspection and coating - phase complete | 2027-02-27 | 2027-02-27 |
| F030 | Fabricate, NDT, dimensional inspection and coating - phase complete | 2027-03-19 | 2027-03-19 |
| I010 | Install, connect, inspect and accept replacement bridge - phase complete | 2027-03-02 | 2027-03-02 |
| I020 | Install new bridge, transfer services and commission - phase complete | 2027-03-24 | 2027-03-24 |
| D020 | Isolate, dismantle old bridge and remove to shore - phase complete | 2027-03-31 | 2027-03-31 |
| I030 | Install, connect, inspect and accept replacement bridge - phase complete | 2027-04-18 | 2027-04-18 |
| M100 | Planned offshore works complete | 2027-05-02 | 2027-05-13 |
| O100 | Offshore demobilisation - phase complete | 2027-05-15 | 2027-11-05 |
| M200 | Internal target: all works complete and handover accepted | 2027-06-15 | 2027-11-19 |

Selected driving parent chain: M000 → G010 → S010 → S020 → E020 → P010 → F020 → L020 → I020 → D020 → I030 → D030 → O090 → M100 → C010 → C020 → M200. The workbook lists every zero-float nonzero activity, including tied branches.53 nonzero tasks have zero float to internal finish.

In practical terms the driving route is mobilisation/survey → early material definition → procurement → BHS fabrication → BHS transport and installation/service acceptance → old BHS demolition → ICP–ICG installation → residual removal/offshore punch → dossiers and final acceptance. This is scenario logic, not proof of actual productivity or approved method feasibility.

Contract headroom at the handover milestone must not be confused with offshore recovery margin. Several driving offshore tasks have only 3 calendar days of backward-pass float to the unextended deadline because of the seasonal closure. Float at a zero-durationphase boundary can differ from its physical child tasks; use detailedtaskfloat for work-front decisions.

| Extra critical material days | Offshore milestone | Demobboundary | Overallmilestone | Calendaroverrun |
| --- | --- | --- | --- | --- |
| 0 | 2027-05-02 | 2027-05-15 | 2027-06-15 | 0 |
| 1 | 2027-05-03 | 2027-05-16 | 2027-06-16 | 0 |
| 3 | 2027-05-05 | 2027-10-18 | 2027-11-01 | 1 |
| 4 | 2027-05-06 | 2027-10-19 | 2027-11-02 | 2 |
| 7 | 2027-05-09 | 2027-10-29 | 2027-11-12 | 12 |
| 14 | 2027-05-16 | 2027-10-29 | 2027-11-12 | 12 |

Sensitivity is a conservative calendar stress test: the 10 dayreserve is modeled as a seasonal capacity hold, and marine tasks cannot use the closed season. A few days can move remaining work toOctober. It is not a probabilistic forecast. A robust baseline needs validated workability, safe stopping/revalidation and an agreed demob strategy, plus greater earlyseasonmargin or evidenced recovery.

The two-crew comparator forecasts 19 November 2027, including assumed 7 daysecond-season remobilisation. This exceeds the 31 October 2027 unextendedscenario date; actual entitlement/extensions and remobilisationcosts are not assumed. This detailedP 5 comparator supersedes earliercoarsercase dates; activitygranularity and remobilisationlogic are explicit.

# 14. Resources, mobilisation and capability commitments

Name deliveryleadership and competentdiscipline/checkingresources; confirmavailablehours and competingprojects.

Obtain fabricationcapacityevidence and commitments; allocate two lines plusstrengtheningcell only after audit.

Secure threecomplete strengtheningcrews and installation/support capacity, with tools, inspection and independentwork fronts.

Verify vesselcertificates/configuration/technicalfit, crew, POB, transfers, charter windows and assurance.

Obtain subcontractorcommitmentletters as required; website/serviceclaims alone do not establish projectavailability.

Use weeklylook-ahead to reconcile engineering/material/readiness gates with people, vessels and authorisedwork.

# 15. Commercial, cost, cash and changes

The cost register contains 16 unpricedcategories. Blank fields remain unknown, not zero-cost or approvedbudget. Obtain vendor/yard/charter quotations; define sharedcost allocation and prevent doublecounting. Forecastcost=actual+remaining only when bothinputs are available.

Review guarantees, insurance, LD, taxes, currency/localcontent, subcontracting, variation/notice and warranty provisions under controllingdocuments.

ReconcileA-3/A-10/BRSwithaddenda; do not assume deleted separate mobilisation/demobilisationpayment entries produce receipts.

Model deliverypayments, charter standby, seasonalremob, certification/paymentlags, bankcashmargins, retention/release ifapplicable, financing and tax.

Maintain acceptedmeasurements/e-MB, certificates, invoicepack, collectiondates and outstandingamounts.

Record changedconditions/instructions promptly; issue requirednotices and substantiate cost/timeeffect without assuming entitlement.

Use risk-based contingency and funding triggers; do not report margin or fundingadequacy until priced and reviewed.

# 16. Handover, warranty and project closure

Define package/systemboundaries and dossierindex early.

Maintain as-built/red-lines, material/weld/NDT/coating/test records, accepted quantities and punch status.

Agree acceptance-critical versus authorisedresidualitems under thecontract; no unilateralclassification.

Obtain clientacceptance/certification and record actualwarranty commencement.

Track twelve-monthwarranty under governingterms, defectresponses, guaranteevalidity, final account and releases.

Close subcontractcommitments, return/surplus/waste records and lessonslearned; preserve technical/commercialrecords.

# 17. Risk, decisions and management rhythm

| ID | Risk | Priority | Owner | Action | Timing |
| --- | --- | --- | --- | --- | --- |
| R01 | ActualNOAunconfirmed | Critical | Contracts | Rebaseallcalendars/dates;do notshiftlinearlyacrossmonsoon | Beforebaseline |
| R02 | Threequantitydiscrepancies | High | Engineering/QS | Resolve 1 MTsteel,2 mhandrail,1 m 2 grating;preserveprintedandrows | Beforeprocurement |
| R03 | BHScriticalpath | Critical | Project Director | Protectmaterial/fabrication/service transfer/lift/demolitionchain | Weekly |
| R04 | Only 3 dayscalendarfloatforseveraloffshorecriticalactivitiesagainstunextended deadline | Critical | Planning/Marine | Do notinterpret 139 dayshandover headroomasoffshorefloat;weatherbarrierlimitsrecovery | Weekly |
| R05 | Thirdstrengtheningcrewuncommitted | High | Construction | Securecompletecrew/supportcapacityoradopttwo-seasonforecast | Beforemobilisation |
| R06 | Yard/QA/coatingcapacityunverified | High | Fabrication/QA | Auditbays/people/inspection/coating/loadout;validateallrates | Beforecommitment |
| R07 | Marinewindowandweightsunknown | Critical | Marine | Verifylift weights/COG/cranes/radii/vessels/availability | Beforecharter |
| R08 | EngineeringanddrawingsnotAFC | Critical | Engineering | Reconstructmodel;completechecking;resolveinputs;maintainrelease gates | Beforefabrication |
| R09 | Actualservice-loadsandmovementspending | Critical | Engineering | Reconcilepipingfutureallowance,LLareas,camber and supportrestraints | Beforedesignfreeze |
| R10 | Operationalaccess/SIMOPS | Critical | Offshore/ONGC | Agreeaccess,isolations,shutdowns,transferwindowsandemergencyarrangements | Six-weeklook-ahead |
| R11 | Cost/financeunpriced | High | Finance | Populatequotes,charters,bankmargins,billinglags,taxandfunding | Beforecommitment |
| R12 | Specialequipmentlead time | High | Procurement | Validatebearings/lifeboat/services;25 daybulklead timeisnotproof | Beforebaseline |
| R13 | Monsoonrelief/costexposure | High | Contracts | Compliantnotices;extensionreview;standby/remob/demobcosts | Beforeimpact |
| R14 | Other-projectscopecontamination | High | DocumentControl | UseBRRP-specificPart II;checkallimportedscope | Eachrelease |
| R15 | Second-seasoncomparator | High | Marine/Planning | 7 dayremobassumed;all capacity/cost/revalidationmustbeconfirmed | Beforeadoptingscenario |

Daily: safety/permit/readiness, production and marinecoordination; record actual hours, accepted quantities and delaycauses.

Weekly: six-week look-ahead, critical/near-criticalmovement, engineering/material/QAconstraints, resource commitments, cost and collections.

Monthly: integrated forecastcompletion/cost at completion/cashrequirement, majorrisks, changes and managementdecisions.

At every gate: signed evidence or HOLDwithowner/closuredate. Do not credit plannedwork as actual progress.

# 18. Release-gate matrix

| Gate | Release | Evidence | Authority |
| --- | --- | --- | --- |
| G0 | Mobilisationauthority | Award/start/funding/leadership | Project Director/Contracts |
| G1 | Scope/surveybasis | Acceptedcoverage;quantityandinterfaceregister | Engineering |
| G2 | Engineeringrelease | Checkedcalculations;drawingreviews;resolvedcriticalqueries | Technical Authority/ONGCasrequired |
| G3 | Procurementrelease | Approvedrequisition/vendor/funding/inspection | Procurement/Engineering |
| G4 | Fabricationreadiness | AFCstatuswhere required;materials;procedures;ITP | Engineering/QA/Fabrication |
| G5 | Yardrelease | NDT/dimensions/coating/NCRclosure/traceability | QA |
| G6 | Marinereadiness | Suitablevessels;verifiedweights;lift/transportengineering;assurance | Marine/competentauthorities |
| G7 | Offshorework | Workpack;permits;SIMOPS;isolations;people/tools/access | Construction/ONGC |
| G8 | Demolition | Newbridge/servicesaccepted;stability/isolation/removalapproved | Technical Authority/ONGC |
| G9 | Handover | Acceptedwork/punch/dossiers/e-MB/certificates | ONGCacceptanceauthority |

# 19. Immediate baseline actions

| No | Action | Owner | Needby |
| --- | --- | --- | --- |
| 1 | ConfirmNOA and contractual calendar | Contracts | Beforebaseline |
| 2 | Resolve 1 MTsteel,2 mhandrail,1 m 2 gratingdifferences | Engineering/QS | Beforematerial release |
| 3 | Obtain/modelcompletegeometry,sections,loadsandreactions | Engineering | Beforefinal design |
| 4 | Completecheckedconnections/bearings/platformandtemporary works | Technical Authority | Beforeapplicabledrawingrelease |
| 5 | Confirmyards,thirdcrew,QA/coatingandPOBcapacity | Project Director | Beforecommitment |
| 6 | Confirmactual vendor lead timeandmarinewindows | Procurement/Marine | Beforebaseline |
| 7 | Increaseverifiedseasonalmargin; reviewweatherhold/demobassumptions | Planning/Marine | Beforebaselineapproval |
| 8 | Pricecost, cash and charter standbyandsecond seasonexposure | Finance/Commercial | Beforefinancialsanction |

# Appendix A — Bridge work-package execution matrix

## ICW-ICG UD — Strengthening

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-01-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-01-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Check temporaryloadpath and existing corrosion at member/joint work front. |

## ICW-ICG LD — New/replacement

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-02-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Include associated jacket/platform strengthening where applicable. |
| WP-02-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Include associated jacket/platform strengthening where applicable. |
| WP-02-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Include associated jacket/platform strengthening where applicable. |
| WP-02-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Include associated jacket/platform strengthening where applicable. |
| WP-02-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Include associated jacket/platform strengthening where applicable. |
| WP-02-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Include associated jacket/platform strengthening where applicable. |
| WP-02-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Include associated jacket/platform strengthening where applicable. |
| WP-02-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Include associated jacket/platform strengthening where applicable. |
| WP-02-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Include associated jacket/platform strengthening where applicable. |
| WP-02-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Include associated jacket/platform strengthening where applicable. |

## ICG-ICP UD — Strengthening

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-03-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-03-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Check temporaryloadpath and existing corrosion at member/joint work front. |

## ICG-ICP LD — New/replacement

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-04-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Include associated jacket/platform strengthening where applicable. |
| WP-04-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Include associated jacket/platform strengthening where applicable. |
| WP-04-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Include associated jacket/platform strengthening where applicable. |
| WP-04-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Include associated jacket/platform strengthening where applicable. |
| WP-04-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Include associated jacket/platform strengthening where applicable. |
| WP-04-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Include associated jacket/platform strengthening where applicable. |
| WP-04-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Include associated jacket/platform strengthening where applicable. |
| WP-04-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Include associated jacket/platform strengthening where applicable. |
| WP-04-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Include associated jacket/platform strengthening where applicable. |
| WP-04-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Include associated jacket/platform strengthening where applicable. |

## BHS-SLQ — Replacement/services

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-05-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |
| WP-05-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify. |

## SLQ-WIS — Strengthening

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-06-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-06-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Check temporaryloadpath and existing corrosion at member/joint work front. |

## NQO-NQD — Strengthening

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-07-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-07-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Check temporaryloadpath and existing corrosion at member/joint work front. |

## WIN-NC — Strengthening

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-08-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-08-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Check temporaryloadpath and existing corrosion at member/joint work front. |

## SCA-SC1 — Strengthening

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-09-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-09-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Check temporaryloadpath and existing corrosion at member/joint work front. |

## SCA-SCF — Strengthening

| Workpack | Stage / owner | Prerequisites | Deliverable / acceptance | Bridge-specificcontrol |
| --- | --- | --- | --- | --- |
| WP-10-GOV | Project governance / Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register; Signed internal authority and contract basis | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-SUR | Survey and existing condition / Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register; Accepted survey coverage and unresolved-area record | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-ENG | Engineering and analysis / Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability; Checked calculations and resolved technical comments | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-DET | Detailed engineering / AFC preparation / Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO; Documented checker and applicable ONGC release; otherwise HOLD | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-BUY | Procurement and materials / Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates; Accepted material and traceability; no unapproved substitutions | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-FAB | Fabrication / coating / Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating; QA release; NCR closure; preservation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-MAR | Marine / logistics / Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves; Required engineering/assurance and sail-away release | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-OFF | Offshore execution / Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections; Accepted permanentwork and operational interfaces | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-COM | Testing and commissioning / Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure; Accepted tests; operational authorisation | Check temporaryloadpath and existing corrosion at member/joint work front. |
| WP-10-HAN | Handover / warranty / Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister; Client acceptance and recorded residual obligations | Check temporaryloadpath and existing corrosion at member/joint work front. |

# Appendix B — Engineering and AFC-review deliverable register

| ProposedID | Bridge | Deliverable | Currentstatus / release | Evidence |
| --- | --- | --- | --- | --- |
| SHV-BRRP-01-GA-P5 | ICW-ICG UD | Surveyed arrangement and scope markups | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-01-AN-P5 | ICW-ICG UD | Existing condition and strengthening calculations | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-01-FR-P5 | ICW-ICG UD | Strengthening member and joint details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-01-LA-P5 | ICW-ICG UD | Landing/deck interface details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-01-TW-P5 | ICW-ICG UD | Temporary stability/access details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-01-AC-P5 | ICW-ICG UD | Grating handrail sheeting and restoration details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-01-MT-P5 | ICW-ICG UD | Bridge-specific MTO and traceability | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-01-QA-P5 | ICW-ICG UD | Workpack ITP and completion records | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-GA-P5 | ICW-ICG LD | General arrangement and coordinates | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-FR-P5 | ICW-ICG LD | Primary/secondary framing and member schedule | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-AN-P5 | ICW-ICG LD | Global strength stability and serviceability analysis | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-JN-P5 | ICW-ICG LD | Connections and tubular joint calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-BE-P5 | ICW-ICG LD | Bearings guides and movement details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-LA-P5 | ICW-ICG LD | Landing/deck/jacket interface calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-TW-P5 | ICW-ICG LD | Temporary conditions and installation interfaces | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-SV-P5 | ICW-ICG LD | Piping/cable/lighting/support coordination | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-AC-P5 | ICW-ICG LD | Access grating handrails and escape interfaces | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-MT-P5 | ICW-ICG LD | Detailed MTO and traceability schedule | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-ML-P5 | ICW-ICG LD | Loadout transport lifting calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-02-QA-P5 | ICW-ICG LD | Inspection and fabrication dossier requirements | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-GA-P5 | ICG-ICP UD | Surveyed arrangement and scope markups | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-AN-P5 | ICG-ICP UD | Existing condition and strengthening calculations | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-FR-P5 | ICG-ICP UD | Strengthening member and joint details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-LA-P5 | ICG-ICP UD | Landing/deck interface details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-TW-P5 | ICG-ICP UD | Temporary stability/access details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-AC-P5 | ICG-ICP UD | Grating handrail sheeting and restoration details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-MT-P5 | ICG-ICP UD | Bridge-specific MTO and traceability | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-03-QA-P5 | ICG-ICP UD | Workpack ITP and completion records | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-GA-P5 | ICG-ICP LD | General arrangement and coordinates | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-FR-P5 | ICG-ICP LD | Primary/secondary framing and member schedule | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-AN-P5 | ICG-ICP LD | Global strength stability and serviceability analysis | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-JN-P5 | ICG-ICP LD | Connections and tubular joint calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-BE-P5 | ICG-ICP LD | Bearings guides and movement details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-LA-P5 | ICG-ICP LD | Landing/deck/jacket interface calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-TW-P5 | ICG-ICP LD | Temporary conditions and installation interfaces | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-SV-P5 | ICG-ICP LD | Piping/cable/lighting/support coordination | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-AC-P5 | ICG-ICP LD | Access grating handrails and escape interfaces | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-MT-P5 | ICG-ICP LD | Detailed MTO and traceability schedule | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-ML-P5 | ICG-ICP LD | Loadout transport lifting calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-04-QA-P5 | ICG-ICP LD | Inspection and fabrication dossier requirements | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-GA-P5 | BHS-SLQ | General arrangement and coordinates | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-FR-P5 | BHS-SLQ | Primary/secondary framing and member schedule | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-AN-P5 | BHS-SLQ | Global strength stability and serviceability analysis | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-JN-P5 | BHS-SLQ | Connections and tubular joint calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-BE-P5 | BHS-SLQ | Bearings guides and movement details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-LA-P5 | BHS-SLQ | Landing/deck/jacket interface calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-TW-P5 | BHS-SLQ | Temporary conditions and installation interfaces | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-SV-P5 | BHS-SLQ | Piping/cable/lighting/support coordination | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-AC-P5 | BHS-SLQ | Access grating handrails and escape interfaces | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-MT-P5 | BHS-SLQ | Detailed MTO and traceability schedule | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-ML-P5 | BHS-SLQ | Loadout transport lifting calculations/details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-QA-P5 | BHS-SLQ | Inspection and fabrication dossier requirements | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-05-DM-P5 | BHS-SLQ | Existing bridge demolition and services isolation | ENGINEERING OPEN; NOT AFC | New bridge/services accepted first |
| SHV-BRRP-06-GA-P5 | SLQ-WIS | Surveyed arrangement and scope markups | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-06-AN-P5 | SLQ-WIS | Existing condition and strengthening calculations | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-06-FR-P5 | SLQ-WIS | Strengthening member and joint details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-06-LA-P5 | SLQ-WIS | Landing/deck interface details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-06-TW-P5 | SLQ-WIS | Temporary stability/access details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-06-AC-P5 | SLQ-WIS | Grating handrail sheeting and restoration details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-06-MT-P5 | SLQ-WIS | Bridge-specific MTO and traceability | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-06-QA-P5 | SLQ-WIS | Workpack ITP and completion records | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-GA-P5 | NQO-NQD | Surveyed arrangement and scope markups | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-AN-P5 | NQO-NQD | Existing condition and strengthening calculations | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-FR-P5 | NQO-NQD | Strengthening member and joint details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-LA-P5 | NQO-NQD | Landing/deck interface details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-TW-P5 | NQO-NQD | Temporary stability/access details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-AC-P5 | NQO-NQD | Grating handrail sheeting and restoration details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-MT-P5 | NQO-NQD | Bridge-specific MTO and traceability | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-07-QA-P5 | NQO-NQD | Workpack ITP and completion records | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-GA-P5 | WIN-NC | Surveyed arrangement and scope markups | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-AN-P5 | WIN-NC | Existing condition and strengthening calculations | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-FR-P5 | WIN-NC | Strengthening member and joint details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-LA-P5 | WIN-NC | Landing/deck interface details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-TW-P5 | WIN-NC | Temporary stability/access details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-AC-P5 | WIN-NC | Grating handrail sheeting and restoration details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-MT-P5 | WIN-NC | Bridge-specific MTO and traceability | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-08-QA-P5 | WIN-NC | Workpack ITP and completion records | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-GA-P5 | SCA-SC1 | Surveyed arrangement and scope markups | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-AN-P5 | SCA-SC1 | Existing condition and strengthening calculations | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-FR-P5 | SCA-SC1 | Strengthening member and joint details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-LA-P5 | SCA-SC1 | Landing/deck interface details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-TW-P5 | SCA-SC1 | Temporary stability/access details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-AC-P5 | SCA-SC1 | Grating handrail sheeting and restoration details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-MT-P5 | SCA-SC1 | Bridge-specific MTO and traceability | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-09-QA-P5 | SCA-SC1 | Workpack ITP and completion records | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-GA-P5 | SCA-SCF | Surveyed arrangement and scope markups | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-AN-P5 | SCA-SCF | Existing condition and strengthening calculations | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-FR-P5 | SCA-SCF | Strengthening member and joint details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-LA-P5 | SCA-SCF | Landing/deck interface details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-TW-P5 | SCA-SCF | Temporary stability/access details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-AC-P5 | SCA-SCF | Grating handrail sheeting and restoration details | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-MT-P5 | SCA-SCF | Bridge-specific MTO and traceability | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-10-QA-P5 | SCA-SCF | Workpack ITP and completion records | DRAFT REGISTER / ENGINEERING OPEN; NOT AFC | Source/model/survey/calculation references required |
| SHV-BRRP-COM-DB-P5 | COMMON | Design basis and code/applicability register | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |
| SHV-BRRP-COM-QP-P5 | COMMON | Project quality and inspection plan | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |
| SHV-BRRP-COM-HP-P5 | COMMON | HSE/SIMOPS/emergency plan | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |
| SHV-BRRP-COM-MP-P5 | COMMON | Marine execution and assurance plan | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |
| SHV-BRRP-COM-SC-P5 | COMMON | Integrated schedule and progressrules | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |
| SHV-BRRP-COM-CP-P5 | COMMON | Cost/cash/billingplan | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |
| SHV-BRRP-COM-CO-P5 | COMMON | Commissioning and completion plan | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |
| SHV-BRRP-COM-CH-P5 | COMMON | Change and commercial notices plan | DRAFT / FOR REVIEW; NOT AFC | Applycontrollingcontract/addenda |

# Appendix C — Detailed driving chain

| ID | Activity | Bridge | Start | Lastworkday / milestone | Duration |
| --- | --- | --- | --- | --- | --- |
| M000 | Assumed NOA / commencement | COMMON | 2026-11-01 | 2026-11-01 | 0 |
| G010.01 | Contract kick-off and obligations | COMMON | 2026-11-01 | 2026-11-02 | 2 |
| G010.02 | Leadership and authority assignments | COMMON | 2026-11-03 | 2026-11-04 | 2 |
| G010.03 | Guarantee insurance and funding arrangements | COMMON | 2026-11-05 | 2026-11-07 | 3 |
| G010 | Kick-off, obligations, guarantees and funding arrangements - phase complete | COMMON | 2026-11-08 | 2026-11-08 | 0 |
| S010.01 | Survey scope and inspection plan | COMMON | 2026-11-08 | 2026-11-09 | 2 |
| S010.02 | Access permits and operational coordination | COMMON | 2026-11-10 | 2026-11-12 | 3 |
| S010.03 | Survey spread readiness | COMMON | 2026-11-13 | 2026-11-14 | 2 |
| S010 | Survey permits, mobilisation and access planning - phase complete | COMMON | 2026-11-15 | 2026-11-15 | 0 |
| S020.01 | IC complex survey | ALL | 2026-11-15 | 2026-11-17 | 3 |
| S020.02 | BHS complex survey | ALL | 2026-11-18 | 2026-11-20 | 3 |
| S020.03 | Other bridge survey campaign | ALL | 2026-11-21 | 2026-11-24 | 4 |
| S020.04 | Survey data validation and accepted report | ALL | 2026-11-25 | 2026-11-28 | 4 |
| S020 | Bridge and platform verification survey campaign - phase complete | ALL | 2026-11-29 | 2026-11-29 | 0 |
| E020.01 | Preliminary checked quantities | ALL | 2026-11-29 | 2026-12-01 | 3 |
| E020.02 | Material requisitions and specifications | ALL | 2026-12-02 | 2026-12-04 | 3 |
| E020.03 | Technical procurement release | ALL | 2026-12-05 | 2026-12-08 | 4 |
| E020 | Checked material requisitions / early material release - phase complete | ALL | 2026-12-09 | 2026-12-09 | 0 |
| P010.01 | Vendor approval and purchase authorisation | ALL | 2026-12-09 | 2026-12-11 | 3 |
| P010.02 | Material manufacturing and expediting | ALL | 2026-12-12 | 2026-12-26 | 15 |
| P010.03 | Inspection and release documentation | ALL | 2026-12-27 | 2026-12-30 | 4 |
| P010.04 | Phased receipt and traceability | ALL | 2026-12-31 | 2027-01-02 | 3 |
| P010 | Vendor approval, steel purchase and phased yard delivery - phase complete | ALL | 2027-01-03 | 2027-01-03 | 0 |
| F020.01 | Traceable material preparation | BHS-SLQ | 2027-01-03 | 2027-01-07 | 5 |
| F020.02 | Assembly and fit-up | BHS-SLQ | 2027-01-08 | 2027-01-15 | 8 |
| F020.03 | Welding and production | BHS-SLQ | 2027-01-16 | 2027-02-09 | 25 |
| F020.04 | NDT and repair closure | BHS-SLQ | 2027-02-10 | 2027-02-16 | 7 |
| F020.05 | Dimensional acceptance | BHS-SLQ | 2027-02-17 | 2027-02-21 | 5 |
| F020.06 | Coating preservation and yard release | BHS-SLQ | 2027-02-22 | 2027-02-26 | 5 |
| F020 | Fabricate, NDT, dimensional inspection and coating - phase complete | BHS-SLQ | 2027-02-27 | 2027-02-27 | 0 |
| L020.01 | Loadout and sea-fastening release | BHS-SLQ | 2027-02-27 | 2027-02-28 | 2 |
| L020.02 | Marine transport | BHS-SLQ | 2027-03-01 | 2027-03-02 | 2 |
| L020.03 | Site receipt and installation readiness | BHS-SLQ | 2027-03-03 | 2027-03-03 | 1 |
| L020 | Loadout, sea-fastening and transport - phase complete | BHS-SLQ | 2027-03-04 | 2027-03-04 | 0 |
| I020.01 | BHS landing and operational readiness | BHS-SLQ | 2027-03-04 | 2027-03-05 | 2 |
| I020.02 | Approved lift and new-bridge landing | BHS-SLQ | 2027-03-06 | 2027-03-09 | 4 |
| I020.03 | Structural connections and inspection | BHS-SLQ | 2027-03-10 | 2027-03-13 | 4 |
| I020.04 | Service transfer and commissioning | BHS-SLQ | 2027-03-14 | 2027-03-19 | 6 |
| I020.05 | Operational acceptance before demolition | BHS-SLQ | 2027-03-20 | 2027-03-21 | 2 |
| I020.06 | Package release | BHS-SLQ | 2027-03-22 | 2027-03-23 | 2 |
| I020 | Install new bridge, transfer services and commission - phase complete | BHS-SLQ | 2027-03-24 | 2027-03-24 | 0 |
| D020.01 | Demolition release and isolation confirmation | BHS-SLQ | 2027-03-24 | 2027-03-24 | 1 |
| D020.02 | Approved dismantling and controlled removal | BHS-SLQ | 2027-03-25 | 2027-03-28 | 4 |
| D020.03 | Backload and clearance | BHS-SLQ | 2027-03-29 | 2027-03-30 | 2 |
| D020 | Isolate, dismantle old bridge and remove to shore - phase complete | BHS-SLQ | 2027-03-31 | 2027-03-31 | 0 |
| I030.01 | Landing and interface readiness | ICG-ICP LD | 2027-03-31 | 2027-04-01 | 2 |
| I030.02 | Approved lift and bridge landing | ICG-ICP LD | 2027-04-02 | 2027-04-06 | 5 |
| I030.03 | Structural connections and access fittings | ICG-ICP LD | 2027-04-07 | 2027-04-12 | 6 |
| I030.04 | Inspection and service checks | ICG-ICP LD | 2027-04-13 | 2027-04-15 | 3 |
| I030.05 | Package acceptance | ICG-ICP LD | 2027-04-16 | 2027-04-17 | 2 |
| I030 | Install, connect, inspect and accept replacement bridge - phase complete | ICG-ICP LD | 2027-04-18 | 2027-04-18 | 0 |
| D030.01 | Other-bridge demolition quantity and release check | OTHER BRIDGES | 2027-04-18 | 2027-04-19 | 2 |
| D030.02 | Approved residual removal | OTHER BRIDGES | 2027-04-20 | 2027-04-22 | 3 |
| D030.03 | Waste/backload and records | OTHER BRIDGES | 2027-04-23 | 2027-04-24 | 2 |
| D030 | Other removal, waste backload and allocated demolition closure - phase complete | OTHER BRIDGES | 2027-04-25 | 2027-04-25 | 0 |
| O090.01 | Final offshore walkdowns | ALL | 2027-04-25 | 2027-04-27 | 3 |
| O090.02 | Acceptance-critical punch closure | ALL | 2027-04-28 | 2027-04-30 | 3 |
| O090.03 | Operational acceptance records | ALL | 2027-05-01 | 2027-05-01 | 1 |
| O090 | Final offshore inspections, punch closure and operational acceptance - phase complete | ALL | 2027-05-02 | 2027-05-02 | 0 |
| M100 | Planned offshore works complete | ALL | 2027-05-02 | 2027-05-02 | 0 |
| C010.01 | As-built and red-line consolidation | ALL | 2027-05-02 | 2027-05-11 | 10 |
| C010.02 | Quality and commissioning dossiers | ALL | 2027-05-12 | 2027-05-21 | 10 |
| C010.03 | Accepted measurement and e-MB records | ALL | 2027-05-22 | 2027-05-26 | 5 |
| C010.04 | Handover submission | ALL | 2027-05-27 | 2027-05-31 | 5 |
| C010 | As-built dossiers, e-MB records, QA records and handover compilation - phase complete | ALL | 2027-06-01 | 2027-06-01 | 0 |
| C020.01 | Client review and comments | ALL | 2027-06-01 | 2027-06-07 | 7 |
| C020.02 | Document and residual acceptance closure | ALL | 2027-06-08 | 2027-06-12 | 5 |
| C020.03 | Completion certificate processing | ALL | 2027-06-13 | 2027-06-14 | 2 |
| C020 | Final document review and completion certificate processing - phase complete | ALL | 2027-06-15 | 2027-06-15 | 0 |
| M200 | Internal target: all works complete and handover accepted | ALL | 2027-06-15 | 2027-06-15 | 0 |

# Appendix D — Full activity list

| ID | Package / activity | Duration | FSpredecessors | Start | Lastworkday/milestone | Float |
| --- | --- | --- | --- | --- | --- | --- |
| M000 | COMMON / Assumed NOA / commencement | 0 |  | 2026-11-01 | 2026-11-01 | 0 |
| G010.01 | COMMON / Contract kick-off and obligations | 2 | M000 | 2026-11-01 | 2026-11-02 | 0 |
| G010.02 | COMMON / Leadership and authority assignments | 2 | G010.01 | 2026-11-03 | 2026-11-04 | 0 |
| G010.03 | COMMON / Guarantee insurance and funding arrangements | 3 | G010.02 | 2026-11-05 | 2026-11-07 | 0 |
| G010 | COMMON / Kick-off, obligations, guarantees and funding arrangements - phase complete | 0 | G010.03 | 2026-11-08 | 2026-11-08 | 0 |
| E010.01 | COMMON / Criteria hierarchy and code register | 4 | G010 | 2026-11-08 | 2026-11-11 | 7 |
| E010.02 | COMMON / Loads and environmental basis | 5 | E010.01 | 2026-11-12 | 2026-11-16 | 7 |
| E010.03 | COMMON / Design-basis/interface review | 5 | E010.02 | 2026-11-17 | 2026-11-21 | 7 |
| E010 | COMMON / Design basis and interface approval - phase complete | 0 | E010.03 | 2026-11-22 | 2026-11-22 | 7 |
| G020.01 | COMMON / Source/addendum register and scope boundaries | 4 | G010 | 2026-11-08 | 2026-11-11 | 7 |
| G020.02 | COMMON / Bridge quantity and demolition reconciliation | 5 | G020.01 | 2026-11-12 | 2026-11-16 | 7 |
| G020.03 | COMMON / Interface register and baseline assumptions | 5 | G020.02 | 2026-11-17 | 2026-11-21 | 7 |
| G020 | COMMON / Controlled document / addendum and quantity reconciliation - phase complete | 0 | G020.03 | 2026-11-22 | 2026-11-22 | 7 |
| MR10.01 | COMMON / Marine campaign requirements | 7 | G010 | 2026-11-08 | 2026-11-14 | 23 |
| MR10.02 | COMMON / Vessel enquiries and technical audits | 14 | MR10.01 | 2026-11-15 | 2026-11-28 | 23 |
| MR10.03 | COMMON / Availability and charter evaluation | 7 | MR10.02 | 2026-11-29 | 2026-12-05 | 23 |
| MR10.04 | COMMON / Conditional reservations and assurance plan | 7 | MR10.03 | 2026-12-06 | 2026-12-12 | 23 |
| MR10 | COMMON / Vessel market enquiry, technical audit and conditional reservation - phase complete | 0 | MR10.04 | 2026-12-13 | 2026-12-13 | 23 |
| S010.01 | COMMON / Survey scope and inspection plan | 2 | G010 | 2026-11-08 | 2026-11-09 | 0 |
| S010.02 | COMMON / Access permits and operational coordination | 3 | S010.01 | 2026-11-10 | 2026-11-12 | 0 |
| S010.03 | COMMON / Survey spread readiness | 2 | S010.02 | 2026-11-13 | 2026-11-14 | 0 |
| S010 | COMMON / Survey permits, mobilisation and access planning - phase complete | 0 | S010.03 | 2026-11-15 | 2026-11-15 | 0 |
| S020.01 | ALL / IC complex survey | 3 | S010 | 2026-11-15 | 2026-11-17 | 0 |
| S020.02 | ALL / BHS complex survey | 3 | S020.01 | 2026-11-18 | 2026-11-20 | 0 |
| S020.03 | ALL / Other bridge survey campaign | 4 | S020.02 | 2026-11-21 | 2026-11-24 | 0 |
| S020.04 | ALL / Survey data validation and accepted report | 4 | S020.03 | 2026-11-25 | 2026-11-28 | 0 |
| S020 | ALL / Bridge and platform verification survey campaign - phase complete | 0 | S020.04 | 2026-11-29 | 2026-11-29 | 0 |
| E020.01 | ALL / Preliminary checked quantities | 3 | S020;E010;G020 | 2026-11-29 | 2026-12-01 | 0 |
| E020.02 | ALL / Material requisitions and specifications | 3 | E020.01 | 2026-12-02 | 2026-12-04 | 0 |
| E020.03 | ALL / Technical procurement release | 4 | E020.02 | 2026-12-05 | 2026-12-08 | 0 |
| E020 | ALL / Checked material requisitions / early material release - phase complete | 0 | E020.03 | 2026-12-09 | 2026-12-09 | 0 |
| E030.01 | REPLACEMENTS / Replacement geometry and model preparation | 5 | S020;E010 | 2026-11-29 | 2026-12-03 | 10 |
| E030.02 | REPLACEMENTS / Global strength and serviceability analysis | 7 | E030.01 | 2026-12-04 | 2026-12-10 | 10 |
| E030.03 | REPLACEMENTS / Connections bearings and landing checks | 5 | E030.02 | 2026-12-11 | 2026-12-15 | 10 |
| E030.04 | REPLACEMENTS / Marine constructability and services review | 4 | E030.03 | 2026-12-16 | 2026-12-19 | 10 |
| E030.05 | REPLACEMENTS / Engineering review comments and release | 4 | E030.04 | 2026-12-20 | 2026-12-23 | 10 |
| E030 | REPLACEMENTS / Detailed design, AFC drawings and ITP approval - phase complete | 0 | E030.05 | 2026-12-24 | 2026-12-24 | 10 |
| E040.01 | REFURBISHMENTS / Existing condition and strengthening models | 5 | S020;E010 | 2026-11-29 | 2026-12-03 | 12 |
| E040.02 | REFURBISHMENTS / Member joint and platform interface checks | 7 | E040.01 | 2026-12-04 | 2026-12-10 | 12 |
| E040.03 | REFURBISHMENTS / Jacket addendum and temporary conditions | 5 | E040.02 | 2026-12-11 | 2026-12-15 | 12 |
| E040.04 | REFURBISHMENTS / Workpack drawings and MTO | 4 | E040.03 | 2026-12-16 | 2026-12-19 | 12 |
| E040.05 | REFURBISHMENTS / Engineering review and release | 4 | E040.04 | 2026-12-20 | 2026-12-23 | 12 |
| E040 | REFURBISHMENTS / Bridge and jacket strengthening design / AFC work packs - phase complete | 0 | E040.05 | 2026-12-24 | 2026-12-24 | 12 |
| E050.01 | BHS-SLQ / BHS service register and operational interfaces | 7 | S020;E010 | 2026-11-29 | 2026-12-05 | 60 |
| E050.02 | BHS-SLQ / New service-support and transfer engineering | 10 | E050.01 | 2026-12-06 | 2026-12-15 | 60 |
| E050.03 | BHS-SLQ / Temporary stability and demolition design | 10 | E050.02 | 2026-12-16 | 2026-12-25 | 60 |
| E050.04 | BHS-SLQ / Multidiscipline review and ONGC comments | 8 | E050.03 | 2026-12-26 | 2027-01-02 | 60 |
| E050 | BHS-SLQ / Utility transfer, temporary stability and demolition design - phase complete | 0 | E050.04 | 2027-01-03 | 2027-01-03 | 60 |
| MR20.01 | REPLACEMENTS / Module boundaries weight and COG basis | 7 | E030;MR10 | 2026-12-24 | 2026-12-30 | 12 |
| MR20.02 | REPLACEMENTS / Lift and landing structural engineering | 10 | MR20.01 | 2026-12-31 | 2027-01-09 | 12 |
| MR20.03 | REPLACEMENTS / Loadout transport and sea-fastening engineering | 10 | MR20.02 | 2027-01-10 | 2027-01-19 | 12 |
| MR20.04 | REPLACEMENTS / Marine assurance and review | 8 | MR20.03 | 2027-01-20 | 2027-01-27 | 12 |
| MR20 | REPLACEMENTS / Lift, loadout, transport and sea-fastening engineering - phase complete | 0 | MR20.04 | 2027-01-28 | 2027-01-28 | 12 |
| P010.01 | ALL / Vendor approval and purchase authorisation | 3 | E020 | 2026-12-09 | 2026-12-11 | 0 |
| P010.02 | ALL / Material manufacturing and expediting | 15 | P010.01 | 2026-12-12 | 2026-12-26 | 0 |
| P010.03 | ALL / Inspection and release documentation | 4 | P010.02 | 2026-12-27 | 2026-12-30 | 0 |
| P010.04 | ALL / Phased receipt and traceability | 3 | P010.03 | 2026-12-31 | 2027-01-02 | 0 |
| P010 | ALL / Vendor approval, steel purchase and phased yard delivery - phase complete | 0 | P010.04 | 2027-01-03 | 2027-01-03 | 0 |
| F010.01 | ICW-ICG LD / Traceable material preparation | 3 | P010;E030 | 2027-01-03 | 2027-01-05 | 4 |
| F010.02 | ICW-ICG LD / Assembly and fit-up | 5 | F010.01 | 2027-01-06 | 2027-01-10 | 4 |
| F010.03 | ICW-ICG LD / Welding and production | 15 | F010.02 | 2027-01-11 | 2027-01-25 | 4 |
| F010.04 | ICW-ICG LD / NDT and repair closure | 4 | F010.03 | 2027-01-26 | 2027-01-29 | 4 |
| F010.05 | ICW-ICG LD / Dimensional acceptance | 3 | F010.04 | 2027-01-30 | 2027-02-01 | 4 |
| F010.06 | ICW-ICG LD / Coating preservation and yard release | 5 | F010.05 | 2027-02-02 | 2027-02-06 | 4 |
| F010 | ICW-ICG LD / Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F010.06 | 2027-02-07 | 2027-02-07 | 4 |
| F020.01 | BHS-SLQ / Traceable material preparation | 5 | P010;E030 | 2027-01-03 | 2027-01-07 | 0 |
| F020.02 | BHS-SLQ / Assembly and fit-up | 8 | F020.01 | 2027-01-08 | 2027-01-15 | 0 |
| F020.03 | BHS-SLQ / Welding and production | 25 | F020.02 | 2027-01-16 | 2027-02-09 | 0 |
| F020.04 | BHS-SLQ / NDT and repair closure | 7 | F020.03 | 2027-02-10 | 2027-02-16 | 0 |
| F020.05 | BHS-SLQ / Dimensional acceptance | 5 | F020.04 | 2027-02-17 | 2027-02-21 | 0 |
| F020.06 | BHS-SLQ / Coating preservation and yard release | 5 | F020.05 | 2027-02-22 | 2027-02-26 | 0 |
| F020 | BHS-SLQ / Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F020.06 | 2027-02-27 | 2027-02-27 | 0 |
| F030.01 | ICG-ICP LD / Traceable material preparation | 3 | F010 | 2027-02-07 | 2027-02-09 | 7 |
| F030.02 | ICG-ICP LD / Assembly and fit-up | 7 | F030.01 | 2027-02-10 | 2027-02-16 | 7 |
| F030.03 | ICG-ICP LD / Welding and production | 18 | F030.02 | 2027-02-17 | 2027-03-06 | 7 |
| F030.04 | ICG-ICP LD / NDT and repair closure | 5 | F030.03 | 2027-03-07 | 2027-03-11 | 7 |
| F030.05 | ICG-ICP LD / Dimensional acceptance | 3 | F030.04 | 2027-03-12 | 2027-03-14 | 7 |
| F030.06 | ICG-ICP LD / Coating preservation and yard release | 4 | F030.05 | 2027-03-15 | 2027-03-18 | 7 |
| F030 | ICG-ICP LD / Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F030.06 | 2027-03-19 | 2027-03-19 | 7 |
| F040.01 | ALL STRENGTHENING / Strengthening kit material preparation | 3 | P010;E040 | 2027-01-03 | 2027-01-05 | 2 |
| F040.02 | ALL STRENGTHENING / First-batch assembly and fit-up | 5 | F040.01 | 2027-01-06 | 2027-01-10 | 2 |
| F040.03 | ALL STRENGTHENING / First-batch production | 8 | F040.02 | 2027-01-11 | 2027-01-18 | 2 |
| F040.04 | ALL STRENGTHENING / First-batch inspection coating and release | 4 | F040.03 | 2027-01-19 | 2027-01-22 | 2 |
| F040.05 | ALL STRENGTHENING / Remaining kit production | 10 | F040.04 | 2027-01-23 | 2027-02-01 | 14 |
| F040.06 | ALL STRENGTHENING / Remaining kit inspection coating and release | 5 | F040.05 | 2027-02-02 | 2027-02-06 | 14 |
| F040 | ALL STRENGTHENING / All strengthening kits available | 0 | F040.06 | 2027-02-07 | 2027-02-07 | 14 |
| F041 | ALL STRENGTHENING / First approved strengthening kits available | 0 | F040.04 | 2027-01-23 | 2027-01-23 | 2 |
| L010.01 | ICW-ICG LD / Loadout and sea-fastening release | 2 | F010;MR20 | 2027-02-07 | 2027-02-08 | 4 |
| L010.02 | ICW-ICG LD / Marine transport | 2 | L010.01 | 2027-02-09 | 2027-02-10 | 4 |
| L010.03 | ICW-ICG LD / Site receipt and installation readiness | 1 | L010.02 | 2027-02-11 | 2027-02-11 | 4 |
| L010 | ICW-ICG LD / Loadout, sea-fastening and transport - phase complete | 0 | L010.03 | 2027-02-12 | 2027-02-12 | 4 |
| L020.01 | BHS-SLQ / Loadout and sea-fastening release | 2 | F020;MR20;L010 | 2027-02-27 | 2027-02-28 | 0 |
| L020.02 | BHS-SLQ / Marine transport | 2 | L020.01 | 2027-03-01 | 2027-03-02 | 0 |
| L020.03 | BHS-SLQ / Site receipt and installation readiness | 1 | L020.02 | 2027-03-03 | 2027-03-03 | 0 |
| L020 | BHS-SLQ / Loadout, sea-fastening and transport - phase complete | 0 | L020.03 | 2027-03-04 | 2027-03-04 | 0 |
| L030.01 | ICG-ICP LD / Loadout and sea-fastening release | 2 | F030;MR20;L020 | 2027-03-19 | 2027-03-20 | 7 |
| L030.02 | ICG-ICP LD / Marine transport | 2 | L030.01 | 2027-03-21 | 2027-03-22 | 7 |
| L030.03 | ICG-ICP LD / Site receipt and installation readiness | 1 | L030.02 | 2027-03-23 | 2027-03-23 | 7 |
| L030 | ICG-ICP LD / Loadout, sea-fastening and transport - phase complete | 0 | L030.03 | 2027-03-24 | 2027-03-24 | 7 |
| O010.01 | ALL / Accommodation/support spread mobilisation | 3 | F041;MR10 | 2027-01-23 | 2027-01-25 | 2 |
| O010.02 | ALL / Offshore crew competence and emergency readiness | 3 | O010.01 | 2027-01-26 | 2027-01-28 | 2 |
| O010.03 | ALL / Permits SIMOPS and work front release | 4 | O010.02 | 2027-01-29 | 2027-02-01 | 2 |
| O010 | ALL / Accommodation/support mobilisation, permits, SIMOPS and readiness - phase complete | 0 | O010.03 | 2027-02-02 | 2027-02-02 | 2 |
| H010.01 | COMMON / Heavy-lift spread mobilisation | 3 | MR20;O010 | 2027-02-02 | 2027-02-04 | 7 |
| H010.02 | COMMON / Equipment/certification verification | 2 | H010.01 | 2027-02-05 | 2027-02-06 | 7 |
| H010.03 | COMMON / Operational readiness and lift release | 2 | H010.02 | 2027-02-07 | 2027-02-08 | 7 |
| H010 | COMMON / Heavy-lift spread mobilisation and operational readiness - phase complete | 0 | H010.03 | 2027-02-09 | 2027-02-09 | 7 |
| J010.01 | ICG / BHS / ICG/BHS access and approved temporary conditions | 2 | O010 | 2027-02-02 | 2027-02-03 | 2 |
| J010.02 | ICG / BHS / Addendum jacket strengthening | 7 | J010.01 | 2027-02-04 | 2027-02-10 | 2 |
| J010.03 | ICG / BHS / NDT acceptance and installation-interface release | 3 | J010.02 | 2027-02-11 | 2027-02-13 | 2 |
| J010 | ICG / BHS / Addendum jacket strengthening and acceptance - phase complete | 0 | J010.03 | 2027-02-14 | 2027-02-14 | 2 |
| I010.01 | ICW-ICG LD / Landing and interface readiness | 2 | L010;H010;J010 | 2027-02-14 | 2027-02-15 | 2 |
| I010.02 | ICW-ICG LD / Approved lift and bridge landing | 4 | I010.01 | 2027-02-16 | 2027-02-19 | 2 |
| I010.03 | ICW-ICG LD / Structural connections and access fittings | 5 | I010.02 | 2027-02-20 | 2027-02-24 | 2 |
| I010.04 | ICW-ICG LD / Inspection coating restoration and services checks | 3 | I010.03 | 2027-02-25 | 2027-02-27 | 2 |
| I010.05 | ICW-ICG LD / Package acceptance | 2 | I010.04 | 2027-02-28 | 2027-03-01 | 2 |
| I010 | ICW-ICG LD / Install, connect, inspect and accept replacement bridge - phase complete | 0 | I010.05 | 2027-03-02 | 2027-03-02 | 2 |
| I020.01 | BHS-SLQ / BHS landing and operational readiness | 2 | L020;I010;J010;E050 | 2027-03-04 | 2027-03-05 | 0 |
| I020.02 | BHS-SLQ / Approved lift and new-bridge landing | 4 | I020.01 | 2027-03-06 | 2027-03-09 | 0 |
| I020.03 | BHS-SLQ / Structural connections and inspection | 4 | I020.02 | 2027-03-10 | 2027-03-13 | 0 |
| I020.04 | BHS-SLQ / Service transfer and commissioning | 6 | I020.03 | 2027-03-14 | 2027-03-19 | 0 |
| I020.05 | BHS-SLQ / Operational acceptance before demolition | 2 | I020.04 | 2027-03-20 | 2027-03-21 | 0 |
| I020.06 | BHS-SLQ / Package release | 2 | I020.05 | 2027-03-22 | 2027-03-23 | 0 |
| I020 | BHS-SLQ / Install new bridge, transfer services and commission - phase complete | 0 | I020.06 | 2027-03-24 | 2027-03-24 | 0 |
| D020.01 | BHS-SLQ / Demolition release and isolation confirmation | 1 | I020 | 2027-03-24 | 2027-03-24 | 0 |
| D020.02 | BHS-SLQ / Approved dismantling and controlled removal | 4 | D020.01 | 2027-03-25 | 2027-03-28 | 0 |
| D020.03 | BHS-SLQ / Backload and clearance | 2 | D020.02 | 2027-03-29 | 2027-03-30 | 0 |
| D020 | BHS-SLQ / Isolate, dismantle old bridge and remove to shore - phase complete | 0 | D020.03 | 2027-03-31 | 2027-03-31 | 0 |
| J020.01 | ICP / ICP access and approved temporary conditions | 2 | O010 | 2027-02-02 | 2027-02-03 | 13 |
| J020.02 | ICP / Addendum jacket strengthening | 6 | J020.01 | 2027-02-04 | 2027-02-09 | 13 |
| J020.03 | ICP / NDT acceptance and installation-interface release | 2 | J020.02 | 2027-02-10 | 2027-02-11 | 13 |
| J020 | ICP / Addendum jacket strengthening and acceptance - phase complete | 0 | J020.03 | 2027-02-12 | 2027-02-12 | 13 |
| I030.01 | ICG-ICP LD / Landing and interface readiness | 2 | L030;D020;J020 | 2027-03-31 | 2027-04-01 | 0 |
| I030.02 | ICG-ICP LD / Approved lift and bridge landing | 5 | I030.01 | 2027-04-02 | 2027-04-06 | 0 |
| I030.03 | ICG-ICP LD / Structural connections and access fittings | 6 | I030.02 | 2027-04-07 | 2027-04-12 | 0 |
| I030.04 | ICG-ICP LD / Inspection and service checks | 3 | I030.03 | 2027-04-13 | 2027-04-15 | 0 |
| I030.05 | ICG-ICP LD / Package acceptance | 2 | I030.04 | 2027-04-16 | 2027-04-17 | 0 |
| I030 | ICG-ICP LD / Install, connect, inspect and accept replacement bridge - phase complete | 0 | I030.05 | 2027-04-18 | 2027-04-18 | 0 |
| RA01.01 | ICW-ICG UD / Permit access and material readiness | 2 | J010;F040 | 2027-02-14 | 2027-02-15 | 7 |
| RA01.02 | ICW-ICG UD / Approved temporary works and preparation | 2 | RA01.01 | 2027-02-16 | 2027-02-17 | 7 |
| RA01.03 | ICW-ICG UD / Strengthening installation and connections | 8 | RA01.02 | 2027-02-18 | 2027-02-25 | 7 |
| RA01.04 | ICW-ICG UD / NDT dimensional and coating acceptance | 2 | RA01.03 | 2027-02-26 | 2027-02-27 | 7 |
| RA01.05 | ICW-ICG UD / Punch closure and package acceptance | 2 | RA01.04 | 2027-02-28 | 2027-03-01 | 7 |
| RA01 | ICW-ICG UD / Strengthening, inspection and bridge acceptance - phase complete | 0 | RA01.05 | 2027-03-02 | 2027-03-02 | 7 |
| RA02.01 | ICG-ICP UD / Permit access and material readiness | 2 | RA01;F040 | 2027-03-02 | 2027-03-03 | 7 |
| RA02.02 | ICG-ICP UD / Approved temporary works and preparation | 2 | RA02.01 | 2027-03-04 | 2027-03-05 | 7 |
| RA02.03 | ICG-ICP UD / Strengthening installation and connections | 14 | RA02.02 | 2027-03-06 | 2027-03-19 | 7 |
| RA02.04 | ICG-ICP UD / NDT dimensional and coating acceptance | 2 | RA02.03 | 2027-03-20 | 2027-03-21 | 7 |
| RA02.05 | ICG-ICP UD / Punch closure and package acceptance | 2 | RA02.04 | 2027-03-22 | 2027-03-23 | 7 |
| RA02 | ICG-ICP UD / Strengthening, inspection and bridge acceptance - phase complete | 0 | RA02.05 | 2027-03-24 | 2027-03-24 | 7 |
| RA03.01 | SLQ-WIS / Permit access and material readiness | 2 | RA02;F040 | 2027-03-24 | 2027-03-25 | 7 |
| RA03.02 | SLQ-WIS / Approved temporary works and preparation | 2 | RA03.01 | 2027-03-26 | 2027-03-27 | 7 |
| RA03.03 | SLQ-WIS / Strengthening installation and connections | 10 | RA03.02 | 2027-03-28 | 2027-04-06 | 7 |
| RA03.04 | SLQ-WIS / NDT dimensional and coating acceptance | 2 | RA03.03 | 2027-04-07 | 2027-04-08 | 7 |
| RA03.05 | SLQ-WIS / Punch closure and package acceptance | 2 | RA03.04 | 2027-04-09 | 2027-04-10 | 7 |
| RA03 | SLQ-WIS / Strengthening, inspection and bridge acceptance - phase complete | 0 | RA03.05 | 2027-04-11 | 2027-04-11 | 7 |
| RA04.01 | NQO-NQD / Permit access and material readiness | 2 | O010;F040 | 2027-02-07 | 2027-02-08 | 52 |
| RA04.02 | NQO-NQD / Approved temporary works and preparation | 2 | RA04.01 | 2027-02-09 | 2027-02-10 | 52 |
| RA04.03 | NQO-NQD / Strengthening installation and connections | 10 | RA04.02 | 2027-02-11 | 2027-02-20 | 52 |
| RA04.04 | NQO-NQD / NDT dimensional and coating acceptance | 2 | RA04.03 | 2027-02-21 | 2027-02-22 | 52 |
| RA04.05 | NQO-NQD / Punch closure and package acceptance | 2 | RA04.04 | 2027-02-23 | 2027-02-24 | 52 |
| RA04 | NQO-NQD / Strengthening, inspection and bridge acceptance - phase complete | 0 | RA04.05 | 2027-02-25 | 2027-02-25 | 52 |
| RB01.01 | WIN-NC / Permit access and material readiness | 2 | J020;F040 | 2027-02-12 | 2027-02-13 | 13 |
| RB01.02 | WIN-NC / Approved temporary works and preparation | 2 | RB01.01 | 2027-02-14 | 2027-02-15 | 13 |
| RB01.03 | WIN-NC / Strengthening installation and connections | 4 | RB01.02 | 2027-02-16 | 2027-02-19 | 13 |
| RB01.04 | WIN-NC / NDT dimensional and coating acceptance | 2 | RB01.03 | 2027-02-20 | 2027-02-21 | 13 |
| RB01.05 | WIN-NC / Punch closure and package acceptance | 2 | RB01.04 | 2027-02-22 | 2027-02-23 | 13 |
| RB01 | WIN-NC / Strengthening, inspection and bridge acceptance - phase complete | 0 | RB01.05 | 2027-02-24 | 2027-02-24 | 13 |
| RB02.01 | SCA-SC1 / Permit access and material readiness | 2 | RB01;F040 | 2027-02-24 | 2027-02-25 | 13 |
| RB02.02 | SCA-SC1 / Approved temporary works and preparation | 2 | RB02.01 | 2027-02-26 | 2027-02-27 | 13 |
| RB02.03 | SCA-SC1 / Strengthening installation and connections | 8 | RB02.02 | 2027-02-28 | 2027-03-07 | 13 |
| RB02.04 | SCA-SC1 / NDT dimensional and coating acceptance | 2 | RB02.03 | 2027-03-08 | 2027-03-09 | 13 |
| RB02.05 | SCA-SC1 / Punch closure and package acceptance | 2 | RB02.04 | 2027-03-10 | 2027-03-11 | 13 |
| RB02 | SCA-SC1 / Strengthening, inspection and bridge acceptance - phase complete | 0 | RB02.05 | 2027-03-12 | 2027-03-12 | 13 |
| RB03.01 | SCA-SCF / Permit access and material readiness | 2 | RB02;F040 | 2027-03-12 | 2027-03-13 | 13 |
| RB03.02 | SCA-SCF / Approved temporary works and preparation | 2 | RB03.01 | 2027-03-14 | 2027-03-15 | 13 |
| RB03.03 | SCA-SCF / Strengthening installation and connections | 16 | RB03.02 | 2027-03-16 | 2027-03-31 | 13 |
| RB03.04 | SCA-SCF / NDT dimensional and coating acceptance | 2 | RB03.03 | 2027-04-01 | 2027-04-02 | 13 |
| RB03.05 | SCA-SCF / Punch closure and package acceptance | 2 | RB03.04 | 2027-04-03 | 2027-04-04 | 13 |
| RB03 | SCA-SCF / Strengthening, inspection and bridge acceptance - phase complete | 0 | RB03.05 | 2027-04-05 | 2027-04-05 | 13 |
| D030.01 | OTHER BRIDGES / Other-bridge demolition quantity and release check | 2 | I030;RA04;RB03;RA03 | 2027-04-18 | 2027-04-19 | 0 |
| D030.02 | OTHER BRIDGES / Approved residual removal | 3 | D030.01 | 2027-04-20 | 2027-04-22 | 0 |
| D030.03 | OTHER BRIDGES / Waste/backload and records | 2 | D030.02 | 2027-04-23 | 2027-04-24 | 0 |
| D030 | OTHER BRIDGES / Other removal, waste backload and allocated demolition closure - phase complete | 0 | D030.03 | 2027-04-25 | 2027-04-25 | 0 |
| O090.01 | ALL / Final offshore walkdowns | 3 | D030 | 2027-04-25 | 2027-04-27 | 0 |
| O090.02 | ALL / Acceptance-critical punch closure | 3 | O090.01 | 2027-04-28 | 2027-04-30 | 0 |
| O090.03 | ALL / Operational acceptance records | 1 | O090.02 | 2027-05-01 | 2027-05-01 | 0 |
| O090 | ALL / Final offshore inspections, punch closure and operational acceptance - phase complete | 0 | O090.03 | 2027-05-02 | 2027-05-02 | 0 |
| M100 | ALL / Planned offshore works complete | 0 | O090 | 2027-05-02 | 2027-05-02 | 0 |
| C010.01 | ALL / As-built and red-line consolidation | 10 | M100 | 2027-05-02 | 2027-05-11 | 0 |
| C010.02 | ALL / Quality and commissioning dossiers | 10 | C010.01 | 2027-05-12 | 2027-05-21 | 0 |
| C010.03 | ALL / Accepted measurement and e-MB records | 5 | C010.02 | 2027-05-22 | 2027-05-26 | 0 |
| C010.04 | ALL / Handover submission | 5 | C010.03 | 2027-05-27 | 2027-05-31 | 0 |
| C010 | ALL / As-built dossiers, e-MB records, QA records and handover compilation - phase complete | 0 | C010.04 | 2027-06-01 | 2027-06-01 | 0 |
| W010.01 | ALL / Offshore weather / access allowance (not productive work) | 10 | M100 | 2027-05-02 | 2027-05-11 | 1 |
| W010 | ALL / Offshore weather / access allowance (not productive work) - phase complete | 0 | W010.01 | 2027-05-12 | 2027-05-12 | 1 |
| O100.01 | ALL / Demobilisation clearance | 1 | W010 | 2027-05-12 | 2027-05-12 | 1 |
| O100.02 | ALL / Personnel and equipment backload | 1 | O100.01 | 2027-05-13 | 2027-05-13 | 1 |
| O100.03 | ALL / Spread departure and closeout records | 1 | O100.02 | 2027-05-14 | 2027-05-14 | 1 |
| O100 | ALL / Offshore demobilisation - phase complete | 0 | O100.03 | 2027-05-15 | 2027-05-15 | 17 |
| C020.01 | ALL / Client review and comments | 7 | C010;O100 | 2027-06-01 | 2027-06-07 | 0 |
| C020.02 | ALL / Document and residual acceptance closure | 5 | C020.01 | 2027-06-08 | 2027-06-12 | 0 |
| C020.03 | ALL / Completion certificate processing | 2 | C020.02 | 2027-06-13 | 2027-06-14 | 0 |
| C020 | ALL / Final document review and completion certificate processing - phase complete | 0 | C020.03 | 2027-06-15 | 2027-06-15 | 0 |
| M200 | ALL / Internal target: all works complete and handover accepted | 0 | C020 | 2027-06-15 | 2027-06-15 | 0 |