## READ ME
Topic | Basis
Status | P5 integrated preliminary project-management and engineering-development package; construction release deferred by user.
Scope | All 10 bridges; execution/procurement/fabrication/commissioning are planned activities, not completed field work.
Commencement | 1 Nov 2026 is an unconfirmed scenario. Rebase full calendars after actual NOA; do not merely shiftdates acrossmonsoon.
Contract | ReviewedGCC/SCC 12 months fromNOA. Conservative lastworkday 31 Oct 2027 in this scenario; confirm convention and extensions.
Duration | Elapsedcalendardays; seven-dayonshoreplanning. All durations are illustrative allocations within prior scenario, not measured productivity/vendor commitments.
Offshorecalendar | No productive offshore work 16 May-15 Oct inclusive. Each split activity fits wholly in an open season; safe stoppoints/renewedpermits require engineering.
Relationship | FSzero-lag; duration d occupies [ES,ES+d); milestone marks boundary. Lastworkingdate is EFminus 1, while milestone date is EF.
Resources | 2 fabricationlines+1 strengtheningcell;3 strengtheningcrews plus installation/supportresources;1 heavy-liftspread;1 cargospread. Namedexclusivewindows checked; NOT full labour/POB/coating/QAlevelling.
F041 | Firstkitrelease milestone at 20 days within one 35-day strengtheningproductionstream; not duplicateproduction.
Weatherreserve | 10 days modeled as a seasonal capacity hold after plannedoffshorecompletion, then 3 demobdays. This is a conservative allowance, not validatedmetoceanworkability.
CPM | Calendar-aware forward/backwardpass. Float is elapsedcalendar difference between latest and earlieststart, not an availableworkdaycount. Critical means zero float to internalearliest finish; tied paths may exist.
Contractfloat | Separate backwardpass to unextended deadline. Completionmilestone float is NOT offshore float; seasonal barrier can leave only a fewdays of offshore margin.
Comparator | Twostrengtheningcrews withNQaftercrewApackages; explicit 7 daysecond-season remobilisation; safe suspension,capacity,costandweather are assumptions.
Scenario sensitivity | Extra days on P010.02 test calendar thresholds; not a probabilistic prediction. Noautomaticcontractualextension assumed.
Quantities | Row sums and printed totals both preserved. Steel 1141 vs 1142 MT;handrail 1166 vs 1168 m;grating 718 vs 719 m2.
Design | P4 arithmetic/source-based drawings included; new global 3D, member/connection/bearing/fatigue/lifting designs remainopen.
AFC | FOR REVIEW / AFC PREPARATION only. No document is labelled actuallyapprovedforconstruction without evidence.
Actualprogress | No assumedpercentcomplete or procurement/fieldcompletion is credited.
Otherprojectdocuments | S&SRP/WSSRP-2 project-specific clauses not automaticallyadopted; BRRPPart II controlsapplicability.
Shivanshassets | Website/fleet capabilities not independentlyverified; candidateassets are not projectcommitments.

## Coverage and Status
Requirement | Prepared content | Actual status | Remaining
Scopeofwork | Tenbridges;100 work packages | Preparedforreview | Quantities/interfacesmustbefrozen
Designbasis | 24 criteriarecordsplus 14 source records | Consolidatedfromuploads | Resolveapplication/conflicts
Structuraldesign | P 4 source-basedreviewandcalculations | PARTIAL / DEVELOPMENT | Independentglobal/member/joint/fatiguemodelnotcompleted
Detailedengineering | 101 document/drawingdeliverableregister;P 4 developmentdrawings | PARTIAL / DEVELOPMENT | Finaldimensions,sections,connections,bearings/temporary worksremainopen
AFCdrawings | AFCreadiness/reviewregisterandcontrolprocedure | NOT AFC | Noapproval/signatureinvented
MTO | Tenbridgequantityregisterplusdiscrepancies | Tenderquantitybasis | NotfinalpurchasingMTO
Procurement | 25 packagesandreleaseworkflow | Planned;noenquiry/orderissued | Quotes/lead time/vendorapproval/fundingrequired
Fabrication | Workpacks,sequence,QA/ITPrequirements | Planned;notperformed | Releaseddrawings/materials/yardresourcesrequired
Installation | Bridge-specificsequencesandmarinegates | Planned;notperformed | Operation-specificengineering/permitsrequired
Executionmethodology | SourceRevCconvertedintomanagement/work packprocedures | Forreview;notanapprovedoperationmethod | Temporaryworks/lifting/transportcalculationsrequired
Commissioning | Tenreadiness/test/acceptancecategories | Planned;notperformed | Approveddiscipline-specificprocedures/testvaluesrequired
Scheduling | 205 activityrecoverycaseand 207 activitytwo-crew Case | Computedscenarios | Duration/resource/NOAassumptionsunverified
Criticalpath | Forward/backwardpass;53 zero-floatnonzero tasks | Computedagainstinternal finish | Notafinalapprovedresource-levelledP 6 baseline
Overallprojectschedule | 1 Nov 2026 scenario;15 Jun 2027 handover milestone | Conditionaltarget | ActualNOAandseasonalmarginrequirevalidation
Costandcash | 16 unpricedcategoriesandbillingcontrols | Inputstructureprepared | Noapprovedbudget, margin and funding forecast
Handoverandwarranty | Dossier/punch/acceptance/warrantyworkflow | Planned | Actualacceptanceandguarantee releasespending

## Source Register
ID | Source type | File | Pages / clauses | Applicability
S01 | GCC | Vol-I-II GCC.docx | 2.1.1;6.3.1.1; related contract clauses | EPC responsibilities and 12 months from NOA; executed contract governs
S02 | Technical SCC | Technical_SCC.pdf | 2;3;13;digitalmeasurement provisions | Completion/conditionalmonsoon relief; marine requirements; LD; e-MB
S03 | Structural scope | SOW & Bridge Report Combined.pdf | 15-53; structuralSOW RevC | Ten bridges; landings; services/demolition interfaces; drawings are tender references
S04 | Source replacement studies | SOW & Bridge Report Combined.pdf | 97-100;122-123;133-135;152-153;196-199;207-209 | Study geometry/results only; not independently reproduced
S05 | Design criteria | Design Criteria & Execution Methodology.pdf | Part I 1-116;BRRPPart II 117-120 | Rev 14 generalcriteria;25 yearlife; project-specificapplicability
S06 | Execution methodology | Design Criteria & Execution Methodology.pdf | 133-154 | B774-000-83-43-EM-0001 RevC; tender-level method
S07 | Structural addendum | Addendum_Structure_SOW.pdf | 1 | ICG ICP BHS jacket strengthening
S08 | MTO drawings inspection | MTO Drawings IRT.pdf | 1;2-7;8-14;15-34 | MTO;partiallandings;standards;IRT
S09 | Specifications | Specification Combined.pdf | 1-2;3-38;55-81;91-168;169-243 | Structural register;weld/NDT;fabrication;coating;materialinstallation
S10 | Commercial amendments | Addendum (1).pdf;AddendumtoA 3.pdf | Applicableamendments | Vendor/agencyprovisions;catering;paymentchanges;currency/localcontent
S11 | Commercial price/payment schedules | Appendix A-3;Appendix A-10; BRS | Applywithamendments | Quote/billingstructures; not cost evidence
S12 | Planning files | Sixmastervolumes;Stages 10/25-35;Level 3/360 day | Pre-awardplanning | Assumptions only; schedule/resource/cost/quantity discrepancies are retained
S13 | Other-projectpackage | Section 2.pdf;Section 3.pdf | Cover andproject-specificPart II | S&SRP/WSSRP-2 content not automatically imported into BRRP
S14 | Shivanshwebsite | shivanshoffshore.in | Accessblockedearlier | No current fleet ownership/suitability/availability claims verified

## Design Basis
Parameter | Value | Units | Source | Status
Design life | 25 | years | BRRP Part II p 119 | CONFIRMED
Elastic modulus E | 210000 | MPa | Part I Annexure 2 p 66 | CONFIRMED
Shear modulus G | 80770 | MPa | Part I Annexure 2 p 66 | CONFIRMED
Poisson ratio | 0.3 | ratio | Part I Annexure 2 p 66 | CONFIRMED
Steel density | 7850 | kg/m3 | Part I Annexure 2 p 66 | CONFIRMED
Gravity | 9.81 | m/s2 | Part I Annexure 2 p 66 | CONFIRMED
Thermal expansion | 1.2e-05 | per C | Part I Annexure 2 p 66 | CONFIRMED
Global walkway loading | 250 | kg/m2 | Bridge clause p 42; Annexure 4 | CONFIRMED
Local grating loading | 500 | kg/m2 | Annexure 4 p 70 | CONFIRMED
Minimum clear walkway | 1.2 | m | Bridge clause p 43 | CONFIRMED
Bridge vertical limit | L/400 | mm consistent with L | p 43;Annexure 12 pp 85-86 | CONFIRMED
Bridge lateral wind limit | L/500 | mm consistent with L | Annexure 12 p 86 | CONFIRMED
Differential translation multiplier | 1.5 | ratio | Bridge clause p 43 | CONFIRMED; input movements pending
Hinged axial thrust multiplier | 1.5 | ratio | Bridge clause p 43 | CONFIRMED; thrust envelope pending
Future piping operating-load allowance | 20 | percent | Bridge clause p 42 | CONFIRMED; included/excluded basis to reconcile
Camber | Compensate dead-load deflection | profile | Bridge clause p 43 | RULE CONFIRMED; magnitude/profile pending
Wind gust for 56 m/84 m | 15 | seconds | Annexure 5 p 73 | CONFIRMED
Wind gust for 42 m | 3 | seconds | Annexure 5 p 73 | CONFIRMED
Environment | MH North and South | field | Part II p 119;Annexure 13 A | CONFIRMED; height adjustment/calculation pending
Material procurement | Spec 6001 F Rev 14 | requirements | Specification Combined pp 169-243 | Grade/toughness selection pending
Welding/NDT | FS2009F Rev 8 | requirements | Specification Combined pp 3-38 | Apply by joint and inspection plan
Coating | FS2005 Rev 9 | requirements | Specification Combined pp 91-168 | Exposure-specific system selection pending
Roof | Process-platform connecting bridges; slope minimum 1:50 | applicability | Bridge clause p 43 | Confirm bridge-specific implementation
Location tolerance | +1.0 m as written in source | requirement | Bridge clause p 43 | Clarify interpretation for existing supports; NOT bearing travel

## Bridge MTO
Bridge | Worktype | NewbridgeMT | ExistingbridgestrengthMT | Newlanding/deckMT | ExistinglandingstrengthMT | StructuralrowtotalMT | Demolition MT | Handrailm | Gratingm 2 | GIsheetingm 2 | Basis
ICW-ICG UD | Strengthening | 0 | 19 | 0 | 30 | 49 | 25 | 110 | 58 | 273 | TenderMTOp 1;notfinalorderquantity
ICW-ICG LD | New/replacement | 57 | 0 | 65 | 0 | 122 | 1 | 118 | 88 | 0 | TenderMTOp 1;notfinalorderquantity
ICG-ICP UD | Strengthening | 0 | 86 | 0 | 30 | 116 | 25 | 93 | 49 | 419 | TenderMTOp 1;notfinalorderquantity
ICG-ICP LD | New/replacement | 115 | 0 | 45 | 0 | 160 | 1 | 176 | 132 | 0 | TenderMTOp 1;notfinalorderquantity
BHS-SLQ | Replacement/services | 195 | 0 | 87 | 0 | 282 | 210 | 88 | 82 | 332 | TenderMTOp 1;notfinalorderquantity
SLQ-WIS | Strengthening | 0 | 61 | 0 | 30 | 91 | 15 | 98 | 51 | 0 | TenderMTOp 1;notfinalorderquantity
NQO-NQD | Strengthening | 0 | 63 | 0 | 30 | 93 | 25 | 93 | 58 | 250 | TenderMTOp 1;notfinalorderquantity
WIN-NC | Strengthening | 0 | 6 | 0 | 40 | 46 | 10 | 45 | 29 | 0 | TenderMTOp 1;notfinalorderquantity
SCA-SC1 | Strengthening | 0 | 35 | 0 | 28 | 63 | 15 | 88 | 55 | 0 | TenderMTOp 1;notfinalorderquantity
SCA-SCF | Strengthening | 0 | 91 | 0 | 28 | 119 | 30 | 257 | 116 | 0 | TenderMTOp 1;notfinalorderquantity

## MTO Reconciliation
Category | Calculatedrows | Printedsourcetotal | Printedminusrows | Status
NewbridgeMT | 367 | 367 | 0 | ARITHMETICMATCH
ExistingbridgestrengthMT | 361 | 361 | 0 | ARITHMETICMATCH
Newlanding/deckMT | 197 | 197 | 0 | ARITHMETICMATCH
ExistinglandingstrengthMT | 216 | 217 | 1 | RECONCILE
Demolition MT | 357 | 357 | 0 | ARITHMETICMATCH
Handrailm | 1166 | 1168 | 2 | RECONCILE
Gratingm 2 | 718 | 719 | 1 | RECONCILE
GIsheetingm 2 | 1274 | 1274 | 0 | ARITHMETICMATCH
StructuraltotalMT | 1141 | 1142 | 1 | RECONCILE

## Work Packages
ID | Bridge | Stage | Owner | Prerequisites | Deliverables | Acceptance | Status | Bridge-specificnote
WP-01-GOV | ICW-ICG UD | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-SUR | ICW-ICG UD | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-ENG | ICW-ICG UD | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-DET | ICW-ICG UD | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-BUY | ICW-ICG UD | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-FAB | ICW-ICG UD | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-MAR | ICW-ICG UD | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-OFF | ICW-ICG UD | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-COM | ICW-ICG UD | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-01-HAN | ICW-ICG UD | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-02-GOV | ICW-ICG LD | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-SUR | ICW-ICG LD | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-ENG | ICW-ICG LD | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-DET | ICW-ICG LD | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-BUY | ICW-ICG LD | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-FAB | ICW-ICG LD | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-MAR | ICW-ICG LD | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-OFF | ICW-ICG LD | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-COM | ICW-ICG LD | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-02-HAN | ICW-ICG LD | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-03-GOV | ICG-ICP UD | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-SUR | ICG-ICP UD | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-ENG | ICG-ICP UD | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-DET | ICG-ICP UD | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-BUY | ICG-ICP UD | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-FAB | ICG-ICP UD | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-MAR | ICG-ICP UD | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-OFF | ICG-ICP UD | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-COM | ICG-ICP UD | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-03-HAN | ICG-ICP UD | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-04-GOV | ICG-ICP LD | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-SUR | ICG-ICP LD | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-ENG | ICG-ICP LD | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-DET | ICG-ICP LD | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-BUY | ICG-ICP LD | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-FAB | ICG-ICP LD | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-MAR | ICG-ICP LD | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-OFF | ICG-ICP LD | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-COM | ICG-ICP LD | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-04-HAN | ICG-ICP LD | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Include associated jacket/platform strengthening where applicable.
WP-05-GOV | BHS-SLQ | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-SUR | BHS-SLQ | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-ENG | BHS-SLQ | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-DET | BHS-SLQ | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-BUY | BHS-SLQ | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-FAB | BHS-SLQ | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-MAR | BHS-SLQ | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-OFF | BHS-SLQ | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-COM | BHS-SLQ | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-05-HAN | BHS-SLQ | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | BHS: new bridge/services acceptance before old bridge demolition; lifeboat/muster and piping/cableinterfaces to verify.
WP-06-GOV | SLQ-WIS | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-SUR | SLQ-WIS | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-ENG | SLQ-WIS | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-DET | SLQ-WIS | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-BUY | SLQ-WIS | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-FAB | SLQ-WIS | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-MAR | SLQ-WIS | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-OFF | SLQ-WIS | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-COM | SLQ-WIS | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-06-HAN | SLQ-WIS | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-GOV | NQO-NQD | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-SUR | NQO-NQD | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-ENG | NQO-NQD | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-DET | NQO-NQD | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-BUY | NQO-NQD | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-FAB | NQO-NQD | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-MAR | NQO-NQD | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-OFF | NQO-NQD | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-COM | NQO-NQD | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-07-HAN | NQO-NQD | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-GOV | WIN-NC | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-SUR | WIN-NC | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-ENG | WIN-NC | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-DET | WIN-NC | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-BUY | WIN-NC | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-FAB | WIN-NC | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-MAR | WIN-NC | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-OFF | WIN-NC | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-COM | WIN-NC | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-08-HAN | WIN-NC | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-GOV | SCA-SC1 | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-SUR | SCA-SC1 | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-ENG | SCA-SC1 | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-DET | SCA-SC1 | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-BUY | SCA-SC1 | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-FAB | SCA-SC1 | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-MAR | SCA-SC1 | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-OFF | SCA-SC1 | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-COM | SCA-SC1 | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-09-HAN | SCA-SC1 | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-GOV | SCA-SCF | Project governance | Project Director | Award/start evidence; named leadership; funding authority | Charter; RACI; obligations; decision register | Signed internal authority and contract basis | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-SUR | SCA-SCF | Survey and existing condition | Survey / Engineering | Approved scope; access; inspection plan | Coordinates; levels; UT/condition; service register | Accepted survey coverage and unresolved-area record | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-ENG | SCA-SCF | Engineering and analysis | Engineering Manager | Accepted survey; criteria; controlled inputs | Model; loads; members/joints; supports; serviceability | Checked calculations and resolved technical comments | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-DET | SCA-SCF | Detailed engineering / AFC preparation | Technical Authority | Checked analysis; interfaces; specifications | GA; framing; connections; bearings; work packs; MTO | Documented checker and applicable ONGC release; otherwise HOLD | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-BUY | SCA-SCF | Procurement and materials | Procurement Manager | Checked requisition; authorised funding; approved vendorbasis | Enquiry; evaluation; purchase; expediting; certificates | Accepted material and traceability; no unapproved substitutions | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-FAB | SCA-SCF | Fabrication / coating | Fabrication Manager | Released drawings; accepted material; procedures; ITP | Preparation; assembly; welding; NDT; dimensions; coating | QA release; NCR closure; preservation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-MAR | SCA-SCF | Marine / logistics | Marine Manager | Module data; suitability; procedures; permits | Loadout; sea-fastening; cargo; transport; fieldmoves | Required engineering/assurance and sail-away release | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-OFF | SCA-SCF | Offshore execution | Offshore Manager | Workpack; people; materials; access; temporary conditions | Strengthening or installation; connections; inspections | Accepted permanentwork and operational interfaces | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-COM | SCA-SCF | Testing and commissioning | Completions Manager | Structural readiness; services; approved testboundaries | Inspection; testing; commissioning; punch closure | Accepted tests; operational authorisation | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.
WP-10-HAN | SCA-SCF | Handover / warranty | Project Director / QA | Acceptedwork; quantities; records | As-builts; dossiers; certificates; warrantyregister | Client acceptance and recorded residual obligations | PLANNED / NOT RELEASED | Check temporaryloadpath and existing corrosion at member/joint work front.

## AFC Review Register
ProposedID | Bridge | Deliverable | Owner | Currentstatus | Requiredreview | AFCstatus | Evidence
SHV-BRRP-01-GA-P5 | ICW-ICG UD | Surveyed arrangement and scope markups | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-01-AN-P5 | ICW-ICG UD | Existing condition and strengthening calculations | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-01-FR-P5 | ICW-ICG UD | Strengthening member and joint details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-01-LA-P5 | ICW-ICG UD | Landing/deck interface details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-01-TW-P5 | ICW-ICG UD | Temporary stability/access details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-01-AC-P5 | ICW-ICG UD | Grating handrail sheeting and restoration details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-01-MT-P5 | ICW-ICG UD | Bridge-specific MTO and traceability | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-01-QA-P5 | ICW-ICG UD | Workpack ITP and completion records | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-GA-P5 | ICW-ICG LD | General arrangement and coordinates | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-FR-P5 | ICW-ICG LD | Primary/secondary framing and member schedule | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-AN-P5 | ICW-ICG LD | Global strength stability and serviceability analysis | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-JN-P5 | ICW-ICG LD | Connections and tubular joint calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-BE-P5 | ICW-ICG LD | Bearings guides and movement details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-LA-P5 | ICW-ICG LD | Landing/deck/jacket interface calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-TW-P5 | ICW-ICG LD | Temporary conditions and installation interfaces | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-SV-P5 | ICW-ICG LD | Piping/cable/lighting/support coordination | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-AC-P5 | ICW-ICG LD | Access grating handrails and escape interfaces | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-MT-P5 | ICW-ICG LD | Detailed MTO and traceability schedule | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-ML-P5 | ICW-ICG LD | Loadout transport lifting calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-02-QA-P5 | ICW-ICG LD | Inspection and fabrication dossier requirements | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-GA-P5 | ICG-ICP UD | Surveyed arrangement and scope markups | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-AN-P5 | ICG-ICP UD | Existing condition and strengthening calculations | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-FR-P5 | ICG-ICP UD | Strengthening member and joint details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-LA-P5 | ICG-ICP UD | Landing/deck interface details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-TW-P5 | ICG-ICP UD | Temporary stability/access details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-AC-P5 | ICG-ICP UD | Grating handrail sheeting and restoration details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-MT-P5 | ICG-ICP UD | Bridge-specific MTO and traceability | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-03-QA-P5 | ICG-ICP UD | Workpack ITP and completion records | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-GA-P5 | ICG-ICP LD | General arrangement and coordinates | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-FR-P5 | ICG-ICP LD | Primary/secondary framing and member schedule | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-AN-P5 | ICG-ICP LD | Global strength stability and serviceability analysis | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-JN-P5 | ICG-ICP LD | Connections and tubular joint calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-BE-P5 | ICG-ICP LD | Bearings guides and movement details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-LA-P5 | ICG-ICP LD | Landing/deck/jacket interface calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-TW-P5 | ICG-ICP LD | Temporary conditions and installation interfaces | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-SV-P5 | ICG-ICP LD | Piping/cable/lighting/support coordination | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-AC-P5 | ICG-ICP LD | Access grating handrails and escape interfaces | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-MT-P5 | ICG-ICP LD | Detailed MTO and traceability schedule | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-ML-P5 | ICG-ICP LD | Loadout transport lifting calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-04-QA-P5 | ICG-ICP LD | Inspection and fabrication dossier requirements | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-GA-P5 | BHS-SLQ | General arrangement and coordinates | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-FR-P5 | BHS-SLQ | Primary/secondary framing and member schedule | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-AN-P5 | BHS-SLQ | Global strength stability and serviceability analysis | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-JN-P5 | BHS-SLQ | Connections and tubular joint calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-BE-P5 | BHS-SLQ | Bearings guides and movement details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-LA-P5 | BHS-SLQ | Landing/deck/jacket interface calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-TW-P5 | BHS-SLQ | Temporary conditions and installation interfaces | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-SV-P5 | BHS-SLQ | Piping/cable/lighting/support coordination | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-AC-P5 | BHS-SLQ | Access grating handrails and escape interfaces | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-MT-P5 | BHS-SLQ | Detailed MTO and traceability schedule | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-ML-P5 | BHS-SLQ | Loadout transport lifting calculations/details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-QA-P5 | BHS-SLQ | Inspection and fabrication dossier requirements | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-05-DM-P5 | BHS-SLQ | Existing bridge demolition and services isolation | Technical Authority / ONGC | ENGINEERING OPEN | Competent checker; ONGC operations | NOT AFC | New bridge/services accepted first
SHV-BRRP-06-GA-P5 | SLQ-WIS | Surveyed arrangement and scope markups | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-06-AN-P5 | SLQ-WIS | Existing condition and strengthening calculations | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-06-FR-P5 | SLQ-WIS | Strengthening member and joint details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-06-LA-P5 | SLQ-WIS | Landing/deck interface details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-06-TW-P5 | SLQ-WIS | Temporary stability/access details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-06-AC-P5 | SLQ-WIS | Grating handrail sheeting and restoration details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-06-MT-P5 | SLQ-WIS | Bridge-specific MTO and traceability | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-06-QA-P5 | SLQ-WIS | Workpack ITP and completion records | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-GA-P5 | NQO-NQD | Surveyed arrangement and scope markups | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-AN-P5 | NQO-NQD | Existing condition and strengthening calculations | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-FR-P5 | NQO-NQD | Strengthening member and joint details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-LA-P5 | NQO-NQD | Landing/deck interface details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-TW-P5 | NQO-NQD | Temporary stability/access details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-AC-P5 | NQO-NQD | Grating handrail sheeting and restoration details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-MT-P5 | NQO-NQD | Bridge-specific MTO and traceability | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-07-QA-P5 | NQO-NQD | Workpack ITP and completion records | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-GA-P5 | WIN-NC | Surveyed arrangement and scope markups | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-AN-P5 | WIN-NC | Existing condition and strengthening calculations | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-FR-P5 | WIN-NC | Strengthening member and joint details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-LA-P5 | WIN-NC | Landing/deck interface details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-TW-P5 | WIN-NC | Temporary stability/access details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-AC-P5 | WIN-NC | Grating handrail sheeting and restoration details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-MT-P5 | WIN-NC | Bridge-specific MTO and traceability | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-08-QA-P5 | WIN-NC | Workpack ITP and completion records | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-GA-P5 | SCA-SC1 | Surveyed arrangement and scope markups | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-AN-P5 | SCA-SC1 | Existing condition and strengthening calculations | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-FR-P5 | SCA-SC1 | Strengthening member and joint details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-LA-P5 | SCA-SC1 | Landing/deck interface details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-TW-P5 | SCA-SC1 | Temporary stability/access details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-AC-P5 | SCA-SC1 | Grating handrail sheeting and restoration details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-MT-P5 | SCA-SC1 | Bridge-specific MTO and traceability | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-09-QA-P5 | SCA-SC1 | Workpack ITP and completion records | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-GA-P5 | SCA-SCF | Surveyed arrangement and scope markups | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-AN-P5 | SCA-SCF | Existing condition and strengthening calculations | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-FR-P5 | SCA-SCF | Strengthening member and joint details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-LA-P5 | SCA-SCF | Landing/deck interface details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-TW-P5 | SCA-SCF | Temporary stability/access details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-AC-P5 | SCA-SCF | Grating handrail sheeting and restoration details | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-MT-P5 | SCA-SCF | Bridge-specific MTO and traceability | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-10-QA-P5 | SCA-SCF | Workpack ITP and completion records | Engineering / appropriate discipline | DRAFT REGISTER / ENGINEERING OPEN | Competent checker; ONGC as required | NOT AFC | Source/model/survey/calculation references required
SHV-BRRP-COM-DB-P5 | COMMON | Design basis and code/applicability register | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda
SHV-BRRP-COM-QP-P5 | COMMON | Project quality and inspection plan | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda
SHV-BRRP-COM-HP-P5 | COMMON | HSE/SIMOPS/emergency plan | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda
SHV-BRRP-COM-MP-P5 | COMMON | Marine execution and assurance plan | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda
SHV-BRRP-COM-SC-P5 | COMMON | Integrated schedule and progressrules | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda
SHV-BRRP-COM-CP-P5 | COMMON | Cost/cash/billingplan | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda
SHV-BRRP-COM-CO-P5 | COMMON | Commissioning and completion plan | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda
SHV-BRRP-COM-CH-P5 | COMMON | Change and commercial notices plan | Projectlead | DRAFT / FOR REVIEW | Relevantauthority | NOT AFC | Applycontrollingcontract/addenda

## Procurement
ID | Package | Bridge/scope | Quantitybasis | Unit | Source/measurementbasis | Owner | Commitmentstatus | Leadtime/price | Releasecondition | Specialissue
P01 | Structural tubulars / sections | All |  | MT | FinalmemberMTO/grade/toughness | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Bulkprocurement; no finalsectionselection
P02 | Plates / gussets / stiffeners | All |  | MT | Connection/local designMTO | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Do not infer from totalsteeltonnage
P03 | Jacket wrap steel | ICG ICP BHS |  | MT | Addendumgeometry;P 4 estimateonly | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Inclusionwithin tenderMTO unresolved; avoiddoublecount
P04 | Grating | All | 718 | m2 | Source row sum; printed 719 | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Reconcile beforepurchase; local 500 kg/m 2 check
P05 | Handrails | All | 1166 | m | Source row sum; printed 1168 | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Reconcile beforepurchase; fittings/detail allowances
P06 | GI sheeting / roofing | Relevantbridges | 1274 | m2 | SourceMTO; actualsheetlayoutpending | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Coating/material/fixing compatibility
P07 | Bearings / PTFE / guides | Newbridges |  | set | Verifiedreactions/movements/detail | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Vendorengineering; lead timeunconfirmed
P08 | Structural bolts / fasteners | Asdesigned |  | set | Approvedjointdetail | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Grade/size/tensioningprocedurepending
P09 | Welding consumables | All |  | lot | ApprovedWPS/materialcombination | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Storage/handling/batchtraceability
P10 | Coating system / abrasives | All |  | lot | Exposure/system/area/DFT | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | No inventedcoating area or genericpaintquantity
P11 | Cables / cable trays / lighting | Newbridges / BHSinterfaces |  | lot | ElectricalMTOandapprovedrouting | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Testing/certification/earthing
P12 | BHS piping / fittings / valves | BHS-SLQ |  | lot | Linelists/isometrics/specs | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Hydrotest/transfer/operatingloads
P13 | Instrument / control interfaces | BHS-SLQasapplicable |  | lot | Instrumentlist/loopboundary | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Isolation/loop/functionaltestrequirements
P14 | Service supports / monorail | BHS-SLQasapplicable |  | lot | Verifiedservice/monorailloads | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Localdesignandliftingequipmentrequirements
P15 | Lifeboat / survival craft interfaces | BHS/SLQscope |  | lot | Confirmedscopeandapprovedsafetystudy | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Potentiallonglead; notverifiedby 25 daybulkassumption
P16 | Scaffolding / access / temporary steel | All |  | lot | Engineeredtemporary works | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Design/inspection/permitcontrols
P17 | Lifting gear / spreader / rigging | Newbridgeoperations |  | set | Approvedlift study | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Certifiedgearandsuitability; no lift release
P18 | Sea-fastening / grillage | Transportoperations |  | lot | Approvedtransport/vesselanalysis | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Actualbarge/deckandvoyageroute
P19 | Survey services | All |  | service | Approvedsurvey/inspectionplan | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Accessandcompetence
P20 | Engineering specialist services | All |  | service | Document/calculation register | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Namedtechnical authority/capacity
P21 | NDT / dimensional / coating inspection | All |  | service | ITP/IRTandproductiondemand | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Independentqualified coverage
P22 | Fabrication yard slots | All |  | service | Capacityauditandloadoutaccess | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Two linesandcellareassumptions
P23 | Heavy-lift / cargo / support spreads | Offshorecampaign |  | charter | Engineeredselectionandavailability | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Price standby/mob/demob/offhire/cross-project conflicts
P24 | Towage / anchorhandling / supply | Asmarineplan |  | charter | Spread/fieldrequirements | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | No fleet availabilityassumed
P25 | Waste handling / backload / disposal | Demolition |  | service | Approvedwasteclassificationandrecords | Procurement Manager | ENQUIRY NOT SENT / NO ORDER | Lead time and price TBC | Approved requisition, technical evaluation, funding and inspection requirements | Traceabledisposalroute

## Detailed Schedule
ID | Parent | Phase | Bridge/package | Activity | Durationdays | FSpredecessors | Resource | Owner | Start | Lastworkday/milestone | ESday 0 | EFboundaryday 0 | Lateststartday 0 | Totalfloatcalendardays | Contractfloatcalendardays | Seasonalwaitdays | Criticaltointernal finish | Status
M000 | M000 | Milestone | COMMON | Assumed NOA / commencement | 0 |  | Milestone | Contracts | 2026-11-01 | 2026-11-01 | 0 | 0 | 0 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
G010.01 | G010 | Management | COMMON | Contract kick-off and obligations | 2 | M000 | Project team | Project Director | 2026-11-01 | 2026-11-02 | 0 | 2 | 0 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
G010.02 | G010 | Management | COMMON | Leadership and authority assignments | 2 | G010.01 | Project team | Project Director | 2026-11-03 | 2026-11-04 | 2 | 4 | 2 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
G010.03 | G010 | Management | COMMON | Guarantee insurance and funding arrangements | 3 | G010.02 | Project team | Project Director | 2026-11-05 | 2026-11-07 | 4 | 7 | 4 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
G010 | G010 | Management | COMMON | Kick-off, obligations, guarantees and funding arrangements - phase complete | 0 | G010.03 | Milestone | Project Director | 2026-11-08 | 2026-11-08 | 7 | 7 | 7 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E010.01 | E010 | Engineering | COMMON | Criteria hierarchy and code register | 4 | G010 | Engineering | Engineering Manager | 2026-11-08 | 2026-11-11 | 7 | 11 | 14 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
E010.02 | E010 | Engineering | COMMON | Loads and environmental basis | 5 | E010.01 | Engineering | Engineering Manager | 2026-11-12 | 2026-11-16 | 11 | 16 | 18 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
E010.03 | E010 | Engineering | COMMON | Design-basis/interface review | 5 | E010.02 | Engineering | Engineering Manager | 2026-11-17 | 2026-11-21 | 16 | 21 | 23 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
E010 | E010 | Engineering | COMMON | Design basis and interface approval - phase complete | 0 | E010.03 | Milestone | Engineering Manager | 2026-11-22 | 2026-11-22 | 21 | 21 | 28 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
G020.01 | G020 | Management | COMMON | Source/addendum register and scope boundaries | 4 | G010 | Project team | Engineering | 2026-11-08 | 2026-11-11 | 7 | 11 | 14 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
G020.02 | G020 | Management | COMMON | Bridge quantity and demolition reconciliation | 5 | G020.01 | Project team | Engineering | 2026-11-12 | 2026-11-16 | 11 | 16 | 18 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
G020.03 | G020 | Management | COMMON | Interface register and baseline assumptions | 5 | G020.02 | Project team | Engineering | 2026-11-17 | 2026-11-21 | 16 | 21 | 23 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
G020 | G020 | Management | COMMON | Controlled document / addendum and quantity reconciliation - phase complete | 0 | G020.03 | Milestone | Engineering | 2026-11-22 | 2026-11-22 | 21 | 21 | 28 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
MR10.01 | MR10 | Marine | COMMON | Marine campaign requirements | 7 | G010 | Marine engineering | Marine Manager | 2026-11-08 | 2026-11-14 | 7 | 14 | 30 | 23 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10.02 | MR10 | Marine | COMMON | Vessel enquiries and technical audits | 14 | MR10.01 | Marine engineering | Marine Manager | 2026-11-15 | 2026-11-28 | 14 | 28 | 37 | 23 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10.03 | MR10 | Marine | COMMON | Availability and charter evaluation | 7 | MR10.02 | Marine engineering | Marine Manager | 2026-11-29 | 2026-12-05 | 28 | 35 | 51 | 23 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10.04 | MR10 | Marine | COMMON | Conditional reservations and assurance plan | 7 | MR10.03 | Marine engineering | Marine Manager | 2026-12-06 | 2026-12-12 | 35 | 42 | 58 | 23 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10 | MR10 | Marine | COMMON | Vessel market enquiry, technical audit and conditional reservation - phase complete | 0 | MR10.04 | Milestone | Marine Manager | 2026-12-13 | 2026-12-13 | 42 | 42 | 65 | 23 | 26 | 0 | NO | PROPOSED / UNVERIFIED
S010.01 | S010 | Survey | COMMON | Survey scope and inspection plan | 2 | G010 | Survey team | Survey Manager | 2026-11-08 | 2026-11-09 | 7 | 9 | 7 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S010.02 | S010 | Survey | COMMON | Access permits and operational coordination | 3 | S010.01 | Survey team | Survey Manager | 2026-11-10 | 2026-11-12 | 9 | 12 | 9 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S010.03 | S010 | Survey | COMMON | Survey spread readiness | 2 | S010.02 | Survey team | Survey Manager | 2026-11-13 | 2026-11-14 | 12 | 14 | 12 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S010 | S010 | Survey | COMMON | Survey permits, mobilisation and access planning - phase complete | 0 | S010.03 | Milestone | Survey Manager | 2026-11-15 | 2026-11-15 | 14 | 14 | 14 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.01 | S020 | Survey | ALL | IC complex survey | 3 | S010 | Survey spread | Survey Manager | 2026-11-15 | 2026-11-17 | 14 | 17 | 14 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.02 | S020 | Survey | ALL | BHS complex survey | 3 | S020.01 | Survey spread | Survey Manager | 2026-11-18 | 2026-11-20 | 17 | 20 | 17 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.03 | S020 | Survey | ALL | Other bridge survey campaign | 4 | S020.02 | Survey spread | Survey Manager | 2026-11-21 | 2026-11-24 | 20 | 24 | 20 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.04 | S020 | Survey | ALL | Survey data validation and accepted report | 4 | S020.03 | Survey spread | Survey Manager | 2026-11-25 | 2026-11-28 | 24 | 28 | 24 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020 | S020 | Survey | ALL | Bridge and platform verification survey campaign - phase complete | 0 | S020.04 | Milestone | Survey Manager | 2026-11-29 | 2026-11-29 | 28 | 28 | 28 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E020.01 | E020 | Engineering | ALL | Preliminary checked quantities | 3 | S020;E010;G020 | Engineering | Engineering Manager | 2026-11-29 | 2026-12-01 | 28 | 31 | 28 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E020.02 | E020 | Engineering | ALL | Material requisitions and specifications | 3 | E020.01 | Engineering | Engineering Manager | 2026-12-02 | 2026-12-04 | 31 | 34 | 31 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E020.03 | E020 | Engineering | ALL | Technical procurement release | 4 | E020.02 | Engineering | Engineering Manager | 2026-12-05 | 2026-12-08 | 34 | 38 | 34 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E020 | E020 | Engineering | ALL | Checked material requisitions / early material release - phase complete | 0 | E020.03 | Milestone | Engineering Manager | 2026-12-09 | 2026-12-09 | 38 | 38 | 38 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E030.01 | E030 | Engineering | REPLACEMENTS | Replacement geometry and model preparation | 5 | S020;E010 | Design team A | Engineering Manager | 2026-11-29 | 2026-12-03 | 28 | 33 | 38 | 10 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.02 | E030 | Engineering | REPLACEMENTS | Global strength and serviceability analysis | 7 | E030.01 | Design team A | Engineering Manager | 2026-12-04 | 2026-12-10 | 33 | 40 | 43 | 10 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.03 | E030 | Engineering | REPLACEMENTS | Connections bearings and landing checks | 5 | E030.02 | Design team A | Engineering Manager | 2026-12-11 | 2026-12-15 | 40 | 45 | 50 | 10 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.04 | E030 | Engineering | REPLACEMENTS | Marine constructability and services review | 4 | E030.03 | Design team A | Engineering Manager | 2026-12-16 | 2026-12-19 | 45 | 49 | 55 | 10 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.05 | E030 | Engineering | REPLACEMENTS | Engineering review comments and release | 4 | E030.04 | Design team A | Engineering Manager | 2026-12-20 | 2026-12-23 | 49 | 53 | 59 | 10 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030 | E030 | Engineering | REPLACEMENTS | Detailed design, AFC drawings and ITP approval - phase complete | 0 | E030.05 | Milestone | Engineering Manager | 2026-12-24 | 2026-12-24 | 53 | 53 | 63 | 10 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E040.01 | E040 | Engineering | REFURBISHMENTS | Existing condition and strengthening models | 5 | S020;E010 | Design team B | Engineering Manager | 2026-11-29 | 2026-12-03 | 28 | 33 | 40 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
E040.02 | E040 | Engineering | REFURBISHMENTS | Member joint and platform interface checks | 7 | E040.01 | Design team B | Engineering Manager | 2026-12-04 | 2026-12-10 | 33 | 40 | 45 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
E040.03 | E040 | Engineering | REFURBISHMENTS | Jacket addendum and temporary conditions | 5 | E040.02 | Design team B | Engineering Manager | 2026-12-11 | 2026-12-15 | 40 | 45 | 52 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
E040.04 | E040 | Engineering | REFURBISHMENTS | Workpack drawings and MTO | 4 | E040.03 | Design team B | Engineering Manager | 2026-12-16 | 2026-12-19 | 45 | 49 | 57 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
E040.05 | E040 | Engineering | REFURBISHMENTS | Engineering review and release | 4 | E040.04 | Design team B | Engineering Manager | 2026-12-20 | 2026-12-23 | 49 | 53 | 61 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
E040 | E040 | Engineering | REFURBISHMENTS | Bridge and jacket strengthening design / AFC work packs - phase complete | 0 | E040.05 | Milestone | Engineering Manager | 2026-12-24 | 2026-12-24 | 53 | 53 | 65 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
E050.01 | E050 | Engineering | BHS-SLQ | BHS service register and operational interfaces | 7 | S020;E010 | Design team A | Technical Authority | 2026-11-29 | 2026-12-05 | 28 | 35 | 88 | 60 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050.02 | E050 | Engineering | BHS-SLQ | New service-support and transfer engineering | 10 | E050.01 | Design team A | Technical Authority | 2026-12-06 | 2026-12-15 | 35 | 45 | 95 | 60 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050.03 | E050 | Engineering | BHS-SLQ | Temporary stability and demolition design | 10 | E050.02 | Design team A | Technical Authority | 2026-12-16 | 2026-12-25 | 45 | 55 | 105 | 60 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050.04 | E050 | Engineering | BHS-SLQ | Multidiscipline review and ONGC comments | 8 | E050.03 | Design team A | Technical Authority | 2026-12-26 | 2027-01-02 | 55 | 63 | 115 | 60 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050 | E050 | Engineering | BHS-SLQ | Utility transfer, temporary stability and demolition design - phase complete | 0 | E050.04 | Milestone | Technical Authority | 2027-01-03 | 2027-01-03 | 63 | 63 | 123 | 60 | 63 | 0 | NO | PROPOSED / UNVERIFIED
MR20.01 | MR20 | Marine | REPLACEMENTS | Module boundaries weight and COG basis | 7 | E030;MR10 | Marine engineering | Marine Manager | 2026-12-24 | 2026-12-30 | 53 | 60 | 65 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20.02 | MR20 | Marine | REPLACEMENTS | Lift and landing structural engineering | 10 | MR20.01 | Marine engineering | Marine Manager | 2026-12-31 | 2027-01-09 | 60 | 70 | 72 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20.03 | MR20 | Marine | REPLACEMENTS | Loadout transport and sea-fastening engineering | 10 | MR20.02 | Marine engineering | Marine Manager | 2027-01-10 | 2027-01-19 | 70 | 80 | 82 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20.04 | MR20 | Marine | REPLACEMENTS | Marine assurance and review | 8 | MR20.03 | Marine engineering | Marine Manager | 2027-01-20 | 2027-01-27 | 80 | 88 | 92 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20 | MR20 | Marine | REPLACEMENTS | Lift, loadout, transport and sea-fastening engineering - phase complete | 0 | MR20.04 | Milestone | Marine Manager | 2027-01-28 | 2027-01-28 | 88 | 88 | 100 | 12 | 15 | 0 | NO | PROPOSED / UNVERIFIED
P010.01 | P010 | Procurement | ALL | Vendor approval and purchase authorisation | 3 | E020 | Procurement | Procurement Manager | 2026-12-09 | 2026-12-11 | 38 | 41 | 38 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010.02 | P010 | Procurement | ALL | Material manufacturing and expediting | 15 | P010.01 | Procurement | Procurement Manager | 2026-12-12 | 2026-12-26 | 41 | 56 | 41 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010.03 | P010 | Procurement | ALL | Inspection and release documentation | 4 | P010.02 | Procurement | Procurement Manager | 2026-12-27 | 2026-12-30 | 56 | 60 | 56 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010.04 | P010 | Procurement | ALL | Phased receipt and traceability | 3 | P010.03 | Procurement | Procurement Manager | 2026-12-31 | 2027-01-02 | 60 | 63 | 60 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010 | P010 | Procurement | ALL | Vendor approval, steel purchase and phased yard delivery - phase complete | 0 | P010.04 | Milestone | Procurement Manager | 2027-01-03 | 2027-01-03 | 63 | 63 | 63 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F010.01 | F010 | Fabrication | ICW-ICG LD | Traceable material preparation | 3 | P010;E030 | Fabrication line 1 | Fabrication Manager | 2027-01-03 | 2027-01-05 | 63 | 66 | 67 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.02 | F010 | Fabrication | ICW-ICG LD | Assembly and fit-up | 5 | F010.01 | Fabrication line 1 | Fabrication Manager | 2027-01-06 | 2027-01-10 | 66 | 71 | 70 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.03 | F010 | Fabrication | ICW-ICG LD | Welding and production | 15 | F010.02 | Fabrication line 1 | Fabrication Manager | 2027-01-11 | 2027-01-25 | 71 | 86 | 75 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.04 | F010 | Fabrication | ICW-ICG LD | NDT and repair closure | 4 | F010.03 | Fabrication line 1 | Fabrication Manager | 2027-01-26 | 2027-01-29 | 86 | 90 | 90 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.05 | F010 | Fabrication | ICW-ICG LD | Dimensional acceptance | 3 | F010.04 | Fabrication line 1 | Fabrication Manager | 2027-01-30 | 2027-02-01 | 90 | 93 | 94 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.06 | F010 | Fabrication | ICW-ICG LD | Coating preservation and yard release | 5 | F010.05 | Fabrication line 1 | Fabrication Manager | 2027-02-02 | 2027-02-06 | 93 | 98 | 97 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010 | F010 | Fabrication | ICW-ICG LD | Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F010.06 | Milestone | Fabrication Manager | 2027-02-07 | 2027-02-07 | 98 | 98 | 102 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F020.01 | F020 | Fabrication | BHS-SLQ | Traceable material preparation | 5 | P010;E030 | Fabrication line 2 | Fabrication Manager | 2027-01-03 | 2027-01-07 | 63 | 68 | 63 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.02 | F020 | Fabrication | BHS-SLQ | Assembly and fit-up | 8 | F020.01 | Fabrication line 2 | Fabrication Manager | 2027-01-08 | 2027-01-15 | 68 | 76 | 68 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.03 | F020 | Fabrication | BHS-SLQ | Welding and production | 25 | F020.02 | Fabrication line 2 | Fabrication Manager | 2027-01-16 | 2027-02-09 | 76 | 101 | 76 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.04 | F020 | Fabrication | BHS-SLQ | NDT and repair closure | 7 | F020.03 | Fabrication line 2 | Fabrication Manager | 2027-02-10 | 2027-02-16 | 101 | 108 | 101 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.05 | F020 | Fabrication | BHS-SLQ | Dimensional acceptance | 5 | F020.04 | Fabrication line 2 | Fabrication Manager | 2027-02-17 | 2027-02-21 | 108 | 113 | 108 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.06 | F020 | Fabrication | BHS-SLQ | Coating preservation and yard release | 5 | F020.05 | Fabrication line 2 | Fabrication Manager | 2027-02-22 | 2027-02-26 | 113 | 118 | 113 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020 | F020 | Fabrication | BHS-SLQ | Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F020.06 | Milestone | Fabrication Manager | 2027-02-27 | 2027-02-27 | 118 | 118 | 118 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F030.01 | F030 | Fabrication | ICG-ICP LD | Traceable material preparation | 3 | F010 | Fabrication line 1 | Fabrication Manager | 2027-02-07 | 2027-02-09 | 98 | 101 | 105 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.02 | F030 | Fabrication | ICG-ICP LD | Assembly and fit-up | 7 | F030.01 | Fabrication line 1 | Fabrication Manager | 2027-02-10 | 2027-02-16 | 101 | 108 | 108 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.03 | F030 | Fabrication | ICG-ICP LD | Welding and production | 18 | F030.02 | Fabrication line 1 | Fabrication Manager | 2027-02-17 | 2027-03-06 | 108 | 126 | 115 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.04 | F030 | Fabrication | ICG-ICP LD | NDT and repair closure | 5 | F030.03 | Fabrication line 1 | Fabrication Manager | 2027-03-07 | 2027-03-11 | 126 | 131 | 133 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.05 | F030 | Fabrication | ICG-ICP LD | Dimensional acceptance | 3 | F030.04 | Fabrication line 1 | Fabrication Manager | 2027-03-12 | 2027-03-14 | 131 | 134 | 138 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.06 | F030 | Fabrication | ICG-ICP LD | Coating preservation and yard release | 4 | F030.05 | Fabrication line 1 | Fabrication Manager | 2027-03-15 | 2027-03-18 | 134 | 138 | 141 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030 | F030 | Fabrication | ICG-ICP LD | Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F030.06 | Milestone | Fabrication Manager | 2027-03-19 | 2027-03-19 | 138 | 138 | 145 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F040.01 | F040 | Fabrication | ALL STRENGTHENING | Strengthening kit material preparation | 3 | P010;E040 | Dedicated strengthening cell | Fabrication Manager | 2027-01-03 | 2027-01-05 | 63 | 66 | 65 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
F040.02 | F040 | Fabrication | ALL STRENGTHENING | First-batch assembly and fit-up | 5 | F040.01 | Dedicated strengthening cell | Fabrication Manager | 2027-01-06 | 2027-01-10 | 66 | 71 | 68 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
F040.03 | F040 | Fabrication | ALL STRENGTHENING | First-batch production | 8 | F040.02 | Dedicated strengthening cell | Fabrication Manager | 2027-01-11 | 2027-01-18 | 71 | 79 | 73 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
F040.04 | F040 | Fabrication | ALL STRENGTHENING | First-batch inspection coating and release | 4 | F040.03 | Dedicated strengthening cell | Fabrication Manager | 2027-01-19 | 2027-01-22 | 79 | 83 | 81 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
F040.05 | F040 | Fabrication | ALL STRENGTHENING | Remaining kit production | 10 | F040.04 | Dedicated strengthening cell | Fabrication Manager | 2027-01-23 | 2027-02-01 | 83 | 93 | 97 | 14 | 17 | 0 | NO | PROPOSED / UNVERIFIED
F040.06 | F040 | Fabrication | ALL STRENGTHENING | Remaining kit inspection coating and release | 5 | F040.05 | Dedicated strengthening cell | Fabrication Manager | 2027-02-02 | 2027-02-06 | 93 | 98 | 107 | 14 | 17 | 0 | NO | PROPOSED / UNVERIFIED
F040 | F040 | Fabrication | ALL STRENGTHENING | All strengthening kits available | 0 | F040.06 | Milestone | Fabrication Manager | 2027-02-07 | 2027-02-07 | 98 | 98 | 112 | 14 | 17 | 0 | NO | PROPOSED / UNVERIFIED
F041 | F041 | Fabrication | ALL STRENGTHENING | First approved strengthening kits available | 0 | F040.04 | Milestone within strengthening-cell production | Fabrication Manager | 2027-01-23 | 2027-01-23 | 83 | 83 | 85 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
L010.01 | L010 | Marine | ICW-ICG LD | Loadout and sea-fastening release | 2 | F010;MR20 | Cargo spread | Marine Manager | 2027-02-07 | 2027-02-08 | 98 | 100 | 102 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L010.02 | L010 | Marine | ICW-ICG LD | Marine transport | 2 | L010.01 | Cargo spread | Marine Manager | 2027-02-09 | 2027-02-10 | 100 | 102 | 104 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L010.03 | L010 | Marine | ICW-ICG LD | Site receipt and installation readiness | 1 | L010.02 | Cargo spread | Marine Manager | 2027-02-11 | 2027-02-11 | 102 | 103 | 106 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L010 | L010 | Marine | ICW-ICG LD | Loadout, sea-fastening and transport - phase complete | 0 | L010.03 | Milestone | Marine Manager | 2027-02-12 | 2027-02-12 | 103 | 103 | 107 | 4 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L020.01 | L020 | Marine | BHS-SLQ | Loadout and sea-fastening release | 2 | F020;MR20;L010 | Cargo spread | Marine Manager | 2027-02-27 | 2027-02-28 | 118 | 120 | 118 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
L020.02 | L020 | Marine | BHS-SLQ | Marine transport | 2 | L020.01 | Cargo spread | Marine Manager | 2027-03-01 | 2027-03-02 | 120 | 122 | 120 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
L020.03 | L020 | Marine | BHS-SLQ | Site receipt and installation readiness | 1 | L020.02 | Cargo spread | Marine Manager | 2027-03-03 | 2027-03-03 | 122 | 123 | 122 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
L020 | L020 | Marine | BHS-SLQ | Loadout, sea-fastening and transport - phase complete | 0 | L020.03 | Milestone | Marine Manager | 2027-03-04 | 2027-03-04 | 123 | 123 | 123 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
L030.01 | L030 | Marine | ICG-ICP LD | Loadout and sea-fastening release | 2 | F030;MR20;L020 | Cargo spread | Marine Manager | 2027-03-19 | 2027-03-20 | 138 | 140 | 145 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
L030.02 | L030 | Marine | ICG-ICP LD | Marine transport | 2 | L030.01 | Cargo spread | Marine Manager | 2027-03-21 | 2027-03-22 | 140 | 142 | 147 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
L030.03 | L030 | Marine | ICG-ICP LD | Site receipt and installation readiness | 1 | L030.02 | Cargo spread | Marine Manager | 2027-03-23 | 2027-03-23 | 142 | 143 | 149 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
L030 | L030 | Marine | ICG-ICP LD | Loadout, sea-fastening and transport - phase complete | 0 | L030.03 | Milestone | Marine Manager | 2027-03-24 | 2027-03-24 | 143 | 143 | 150 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
O010.01 | O010 | Offshore readiness | ALL | Accommodation/support spread mobilisation | 3 | F041;MR10 | Support spread | Offshore Manager | 2027-01-23 | 2027-01-25 | 83 | 86 | 85 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
O010.02 | O010 | Offshore readiness | ALL | Offshore crew competence and emergency readiness | 3 | O010.01 | Support spread | Offshore Manager | 2027-01-26 | 2027-01-28 | 86 | 89 | 88 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
O010.03 | O010 | Offshore readiness | ALL | Permits SIMOPS and work front release | 4 | O010.02 | Support spread | Offshore Manager | 2027-01-29 | 2027-02-01 | 89 | 93 | 91 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
O010 | O010 | Offshore readiness | ALL | Accommodation/support mobilisation, permits, SIMOPS and readiness - phase complete | 0 | O010.03 | Milestone | Offshore Manager | 2027-02-02 | 2027-02-02 | 93 | 93 | 95 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
H010.01 | H010 | Marine | COMMON | Heavy-lift spread mobilisation | 3 | MR20;O010 | Heavy-lift spread | Marine Manager | 2027-02-02 | 2027-02-04 | 93 | 96 | 100 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
H010.02 | H010 | Marine | COMMON | Equipment/certification verification | 2 | H010.01 | Heavy-lift spread | Marine Manager | 2027-02-05 | 2027-02-06 | 96 | 98 | 103 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
H010.03 | H010 | Marine | COMMON | Operational readiness and lift release | 2 | H010.02 | Heavy-lift spread | Marine Manager | 2027-02-07 | 2027-02-08 | 98 | 100 | 105 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
H010 | H010 | Marine | COMMON | Heavy-lift spread mobilisation and operational readiness - phase complete | 0 | H010.03 | Milestone | Marine Manager | 2027-02-09 | 2027-02-09 | 100 | 100 | 107 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
J010.01 | J010 | Offshore | ICG / BHS | ICG/BHS access and approved temporary conditions | 2 | O010 | Strengthening crew A | Offshore Manager | 2027-02-02 | 2027-02-03 | 93 | 95 | 95 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
J010.02 | J010 | Offshore | ICG / BHS | Addendum jacket strengthening | 7 | J010.01 | Strengthening crew A | Offshore Manager | 2027-02-04 | 2027-02-10 | 95 | 102 | 97 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
J010.03 | J010 | Offshore | ICG / BHS | NDT acceptance and installation-interface release | 3 | J010.02 | Strengthening crew A | Offshore Manager | 2027-02-11 | 2027-02-13 | 102 | 105 | 104 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
J010 | J010 | Offshore | ICG / BHS | Addendum jacket strengthening and acceptance - phase complete | 0 | J010.03 | Milestone | Offshore Manager | 2027-02-14 | 2027-02-14 | 105 | 105 | 107 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.01 | I010 | Offshore | ICW-ICG LD | Landing and interface readiness | 2 | L010;H010;J010 | Heavy-lift spread | Offshore Manager | 2027-02-14 | 2027-02-15 | 105 | 107 | 107 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.02 | I010 | Offshore | ICW-ICG LD | Approved lift and bridge landing | 4 | I010.01 | Heavy-lift spread | Offshore Manager | 2027-02-16 | 2027-02-19 | 107 | 111 | 109 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.03 | I010 | Offshore | ICW-ICG LD | Structural connections and access fittings | 5 | I010.02 | Heavy-lift spread | Offshore Manager | 2027-02-20 | 2027-02-24 | 111 | 116 | 113 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.04 | I010 | Offshore | ICW-ICG LD | Inspection coating restoration and services checks | 3 | I010.03 | Heavy-lift spread | Offshore Manager | 2027-02-25 | 2027-02-27 | 116 | 119 | 118 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.05 | I010 | Offshore | ICW-ICG LD | Package acceptance | 2 | I010.04 | Heavy-lift spread | Offshore Manager | 2027-02-28 | 2027-03-01 | 119 | 121 | 121 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010 | I010 | Offshore | ICW-ICG LD | Install, connect, inspect and accept replacement bridge - phase complete | 0 | I010.05 | Milestone | Offshore Manager | 2027-03-02 | 2027-03-02 | 121 | 121 | 123 | 2 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I020.01 | I020 | Offshore | BHS-SLQ | BHS landing and operational readiness | 2 | L020;I010;J010;E050 | Heavy-lift spread | Offshore Manager | 2027-03-04 | 2027-03-05 | 123 | 125 | 123 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.02 | I020 | Offshore | BHS-SLQ | Approved lift and new-bridge landing | 4 | I020.01 | Heavy-lift spread | Offshore Manager | 2027-03-06 | 2027-03-09 | 125 | 129 | 125 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.03 | I020 | Offshore | BHS-SLQ | Structural connections and inspection | 4 | I020.02 | Heavy-lift spread | Offshore Manager | 2027-03-10 | 2027-03-13 | 129 | 133 | 129 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.04 | I020 | Offshore | BHS-SLQ | Service transfer and commissioning | 6 | I020.03 | Heavy-lift spread | Offshore Manager | 2027-03-14 | 2027-03-19 | 133 | 139 | 133 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.05 | I020 | Offshore | BHS-SLQ | Operational acceptance before demolition | 2 | I020.04 | Heavy-lift spread | Offshore Manager | 2027-03-20 | 2027-03-21 | 139 | 141 | 139 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.06 | I020 | Offshore | BHS-SLQ | Package release | 2 | I020.05 | Heavy-lift spread | Offshore Manager | 2027-03-22 | 2027-03-23 | 141 | 143 | 141 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020 | I020 | Offshore | BHS-SLQ | Install new bridge, transfer services and commission - phase complete | 0 | I020.06 | Milestone | Offshore Manager | 2027-03-24 | 2027-03-24 | 143 | 143 | 143 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D020.01 | D020 | Demolition | BHS-SLQ | Demolition release and isolation confirmation | 1 | I020 | Heavy-lift spread | Offshore Manager | 2027-03-24 | 2027-03-24 | 143 | 144 | 143 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D020.02 | D020 | Demolition | BHS-SLQ | Approved dismantling and controlled removal | 4 | D020.01 | Heavy-lift spread | Offshore Manager | 2027-03-25 | 2027-03-28 | 144 | 148 | 144 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D020.03 | D020 | Demolition | BHS-SLQ | Backload and clearance | 2 | D020.02 | Heavy-lift spread | Offshore Manager | 2027-03-29 | 2027-03-30 | 148 | 150 | 148 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D020 | D020 | Demolition | BHS-SLQ | Isolate, dismantle old bridge and remove to shore - phase complete | 0 | D020.03 | Milestone | Offshore Manager | 2027-03-31 | 2027-03-31 | 150 | 150 | 150 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
J020.01 | J020 | Offshore | ICP | ICP access and approved temporary conditions | 2 | O010 | Strengthening crew B | Offshore Manager | 2027-02-02 | 2027-02-03 | 93 | 95 | 106 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
J020.02 | J020 | Offshore | ICP | Addendum jacket strengthening | 6 | J020.01 | Strengthening crew B | Offshore Manager | 2027-02-04 | 2027-02-09 | 95 | 101 | 108 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
J020.03 | J020 | Offshore | ICP | NDT acceptance and installation-interface release | 2 | J020.02 | Strengthening crew B | Offshore Manager | 2027-02-10 | 2027-02-11 | 101 | 103 | 114 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
J020 | J020 | Offshore | ICP | Addendum jacket strengthening and acceptance - phase complete | 0 | J020.03 | Milestone | Offshore Manager | 2027-02-12 | 2027-02-12 | 103 | 103 | 116 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
I030.01 | I030 | Offshore | ICG-ICP LD | Landing and interface readiness | 2 | L030;D020;J020 | Heavy-lift spread | Offshore Manager | 2027-03-31 | 2027-04-01 | 150 | 152 | 150 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.02 | I030 | Offshore | ICG-ICP LD | Approved lift and bridge landing | 5 | I030.01 | Heavy-lift spread | Offshore Manager | 2027-04-02 | 2027-04-06 | 152 | 157 | 152 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.03 | I030 | Offshore | ICG-ICP LD | Structural connections and access fittings | 6 | I030.02 | Heavy-lift spread | Offshore Manager | 2027-04-07 | 2027-04-12 | 157 | 163 | 157 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.04 | I030 | Offshore | ICG-ICP LD | Inspection and service checks | 3 | I030.03 | Heavy-lift spread | Offshore Manager | 2027-04-13 | 2027-04-15 | 163 | 166 | 163 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.05 | I030 | Offshore | ICG-ICP LD | Package acceptance | 2 | I030.04 | Heavy-lift spread | Offshore Manager | 2027-04-16 | 2027-04-17 | 166 | 168 | 166 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030 | I030 | Offshore | ICG-ICP LD | Install, connect, inspect and accept replacement bridge - phase complete | 0 | I030.05 | Milestone | Offshore Manager | 2027-04-18 | 2027-04-18 | 168 | 168 | 168 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
RA01.01 | RA01 | Offshore | ICW-ICG UD | Permit access and material readiness | 2 | J010;F040 | Strengthening crew A | Offshore Manager | 2027-02-14 | 2027-02-15 | 105 | 107 | 112 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA01.02 | RA01 | Offshore | ICW-ICG UD | Approved temporary works and preparation | 2 | RA01.01 | Strengthening crew A | Offshore Manager | 2027-02-16 | 2027-02-17 | 107 | 109 | 114 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA01.03 | RA01 | Offshore | ICW-ICG UD | Strengthening installation and connections | 8 | RA01.02 | Strengthening crew A | Offshore Manager | 2027-02-18 | 2027-02-25 | 109 | 117 | 116 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA01.04 | RA01 | Offshore | ICW-ICG UD | NDT dimensional and coating acceptance | 2 | RA01.03 | Strengthening crew A | Offshore Manager | 2027-02-26 | 2027-02-27 | 117 | 119 | 124 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA01.05 | RA01 | Offshore | ICW-ICG UD | Punch closure and package acceptance | 2 | RA01.04 | Strengthening crew A | Offshore Manager | 2027-02-28 | 2027-03-01 | 119 | 121 | 126 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA01 | RA01 | Offshore | ICW-ICG UD | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA01.05 | Milestone | Offshore Manager | 2027-03-02 | 2027-03-02 | 121 | 121 | 128 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA02.01 | RA02 | Offshore | ICG-ICP UD | Permit access and material readiness | 2 | RA01;F040 | Strengthening crew A | Offshore Manager | 2027-03-02 | 2027-03-03 | 121 | 123 | 128 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA02.02 | RA02 | Offshore | ICG-ICP UD | Approved temporary works and preparation | 2 | RA02.01 | Strengthening crew A | Offshore Manager | 2027-03-04 | 2027-03-05 | 123 | 125 | 130 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA02.03 | RA02 | Offshore | ICG-ICP UD | Strengthening installation and connections | 14 | RA02.02 | Strengthening crew A | Offshore Manager | 2027-03-06 | 2027-03-19 | 125 | 139 | 132 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA02.04 | RA02 | Offshore | ICG-ICP UD | NDT dimensional and coating acceptance | 2 | RA02.03 | Strengthening crew A | Offshore Manager | 2027-03-20 | 2027-03-21 | 139 | 141 | 146 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA02.05 | RA02 | Offshore | ICG-ICP UD | Punch closure and package acceptance | 2 | RA02.04 | Strengthening crew A | Offshore Manager | 2027-03-22 | 2027-03-23 | 141 | 143 | 148 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA02 | RA02 | Offshore | ICG-ICP UD | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA02.05 | Milestone | Offshore Manager | 2027-03-24 | 2027-03-24 | 143 | 143 | 150 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA03.01 | RA03 | Offshore | SLQ-WIS | Permit access and material readiness | 2 | RA02;F040 | Strengthening crew A | Offshore Manager | 2027-03-24 | 2027-03-25 | 143 | 145 | 150 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA03.02 | RA03 | Offshore | SLQ-WIS | Approved temporary works and preparation | 2 | RA03.01 | Strengthening crew A | Offshore Manager | 2027-03-26 | 2027-03-27 | 145 | 147 | 152 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA03.03 | RA03 | Offshore | SLQ-WIS | Strengthening installation and connections | 10 | RA03.02 | Strengthening crew A | Offshore Manager | 2027-03-28 | 2027-04-06 | 147 | 157 | 154 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA03.04 | RA03 | Offshore | SLQ-WIS | NDT dimensional and coating acceptance | 2 | RA03.03 | Strengthening crew A | Offshore Manager | 2027-04-07 | 2027-04-08 | 157 | 159 | 164 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA03.05 | RA03 | Offshore | SLQ-WIS | Punch closure and package acceptance | 2 | RA03.04 | Strengthening crew A | Offshore Manager | 2027-04-09 | 2027-04-10 | 159 | 161 | 166 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA03 | RA03 | Offshore | SLQ-WIS | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA03.05 | Milestone | Offshore Manager | 2027-04-11 | 2027-04-11 | 161 | 161 | 168 | 7 | 10 | 0 | NO | PROPOSED / UNVERIFIED
RA04.01 | RA04 | Offshore | NQO-NQD | Permit access and material readiness | 2 | O010;F040 | Strengthening crew C (additional) | Offshore Manager | 2027-02-07 | 2027-02-08 | 98 | 100 | 150 | 52 | 55 | 0 | NO | PROPOSED / UNVERIFIED
RA04.02 | RA04 | Offshore | NQO-NQD | Approved temporary works and preparation | 2 | RA04.01 | Strengthening crew C (additional) | Offshore Manager | 2027-02-09 | 2027-02-10 | 100 | 102 | 152 | 52 | 55 | 0 | NO | PROPOSED / UNVERIFIED
RA04.03 | RA04 | Offshore | NQO-NQD | Strengthening installation and connections | 10 | RA04.02 | Strengthening crew C (additional) | Offshore Manager | 2027-02-11 | 2027-02-20 | 102 | 112 | 154 | 52 | 55 | 0 | NO | PROPOSED / UNVERIFIED
RA04.04 | RA04 | Offshore | NQO-NQD | NDT dimensional and coating acceptance | 2 | RA04.03 | Strengthening crew C (additional) | Offshore Manager | 2027-02-21 | 2027-02-22 | 112 | 114 | 164 | 52 | 55 | 0 | NO | PROPOSED / UNVERIFIED
RA04.05 | RA04 | Offshore | NQO-NQD | Punch closure and package acceptance | 2 | RA04.04 | Strengthening crew C (additional) | Offshore Manager | 2027-02-23 | 2027-02-24 | 114 | 116 | 166 | 52 | 55 | 0 | NO | PROPOSED / UNVERIFIED
RA04 | RA04 | Offshore | NQO-NQD | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA04.05 | Milestone | Offshore Manager | 2027-02-25 | 2027-02-25 | 116 | 116 | 168 | 52 | 55 | 0 | NO | PROPOSED / UNVERIFIED
RB01.01 | RB01 | Offshore | WIN-NC | Permit access and material readiness | 2 | J020;F040 | Strengthening crew B | Offshore Manager | 2027-02-12 | 2027-02-13 | 103 | 105 | 116 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.02 | RB01 | Offshore | WIN-NC | Approved temporary works and preparation | 2 | RB01.01 | Strengthening crew B | Offshore Manager | 2027-02-14 | 2027-02-15 | 105 | 107 | 118 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.03 | RB01 | Offshore | WIN-NC | Strengthening installation and connections | 4 | RB01.02 | Strengthening crew B | Offshore Manager | 2027-02-16 | 2027-02-19 | 107 | 111 | 120 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.04 | RB01 | Offshore | WIN-NC | NDT dimensional and coating acceptance | 2 | RB01.03 | Strengthening crew B | Offshore Manager | 2027-02-20 | 2027-02-21 | 111 | 113 | 124 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.05 | RB01 | Offshore | WIN-NC | Punch closure and package acceptance | 2 | RB01.04 | Strengthening crew B | Offshore Manager | 2027-02-22 | 2027-02-23 | 113 | 115 | 126 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01 | RB01 | Offshore | WIN-NC | Strengthening, inspection and bridge acceptance - phase complete | 0 | RB01.05 | Milestone | Offshore Manager | 2027-02-24 | 2027-02-24 | 115 | 115 | 128 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.01 | RB02 | Offshore | SCA-SC1 | Permit access and material readiness | 2 | RB01;F040 | Strengthening crew B | Offshore Manager | 2027-02-24 | 2027-02-25 | 115 | 117 | 128 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.02 | RB02 | Offshore | SCA-SC1 | Approved temporary works and preparation | 2 | RB02.01 | Strengthening crew B | Offshore Manager | 2027-02-26 | 2027-02-27 | 117 | 119 | 130 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.03 | RB02 | Offshore | SCA-SC1 | Strengthening installation and connections | 8 | RB02.02 | Strengthening crew B | Offshore Manager | 2027-02-28 | 2027-03-07 | 119 | 127 | 132 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.04 | RB02 | Offshore | SCA-SC1 | NDT dimensional and coating acceptance | 2 | RB02.03 | Strengthening crew B | Offshore Manager | 2027-03-08 | 2027-03-09 | 127 | 129 | 140 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.05 | RB02 | Offshore | SCA-SC1 | Punch closure and package acceptance | 2 | RB02.04 | Strengthening crew B | Offshore Manager | 2027-03-10 | 2027-03-11 | 129 | 131 | 142 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02 | RB02 | Offshore | SCA-SC1 | Strengthening, inspection and bridge acceptance - phase complete | 0 | RB02.05 | Milestone | Offshore Manager | 2027-03-12 | 2027-03-12 | 131 | 131 | 144 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.01 | RB03 | Offshore | SCA-SCF | Permit access and material readiness | 2 | RB02;F040 | Strengthening crew B | Offshore Manager | 2027-03-12 | 2027-03-13 | 131 | 133 | 144 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.02 | RB03 | Offshore | SCA-SCF | Approved temporary works and preparation | 2 | RB03.01 | Strengthening crew B | Offshore Manager | 2027-03-14 | 2027-03-15 | 133 | 135 | 146 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.03 | RB03 | Offshore | SCA-SCF | Strengthening installation and connections | 16 | RB03.02 | Strengthening crew B | Offshore Manager | 2027-03-16 | 2027-03-31 | 135 | 151 | 148 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.04 | RB03 | Offshore | SCA-SCF | NDT dimensional and coating acceptance | 2 | RB03.03 | Strengthening crew B | Offshore Manager | 2027-04-01 | 2027-04-02 | 151 | 153 | 164 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.05 | RB03 | Offshore | SCA-SCF | Punch closure and package acceptance | 2 | RB03.04 | Strengthening crew B | Offshore Manager | 2027-04-03 | 2027-04-04 | 153 | 155 | 166 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03 | RB03 | Offshore | SCA-SCF | Strengthening, inspection and bridge acceptance - phase complete | 0 | RB03.05 | Milestone | Offshore Manager | 2027-04-05 | 2027-04-05 | 155 | 155 | 168 | 13 | 16 | 0 | NO | PROPOSED / UNVERIFIED
D030.01 | D030 | Demolition | OTHER BRIDGES | Other-bridge demolition quantity and release check | 2 | I030;RA04;RB03;RA03 | Heavy-lift spread | Offshore Manager | 2027-04-18 | 2027-04-19 | 168 | 170 | 168 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D030.02 | D030 | Demolition | OTHER BRIDGES | Approved residual removal | 3 | D030.01 | Heavy-lift spread | Offshore Manager | 2027-04-20 | 2027-04-22 | 170 | 173 | 170 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D030.03 | D030 | Demolition | OTHER BRIDGES | Waste/backload and records | 2 | D030.02 | Heavy-lift spread | Offshore Manager | 2027-04-23 | 2027-04-24 | 173 | 175 | 173 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D030 | D030 | Demolition | OTHER BRIDGES | Other removal, waste backload and allocated demolition closure - phase complete | 0 | D030.03 | Milestone | Offshore Manager | 2027-04-25 | 2027-04-25 | 175 | 175 | 175 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
O090.01 | O090 | Offshore | ALL | Final offshore walkdowns | 3 | D030 | Support spread | Completions Manager | 2027-04-25 | 2027-04-27 | 175 | 178 | 175 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
O090.02 | O090 | Offshore | ALL | Acceptance-critical punch closure | 3 | O090.01 | Support spread | Completions Manager | 2027-04-28 | 2027-04-30 | 178 | 181 | 178 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
O090.03 | O090 | Offshore | ALL | Operational acceptance records | 1 | O090.02 | Support spread | Completions Manager | 2027-05-01 | 2027-05-01 | 181 | 182 | 181 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
O090 | O090 | Offshore | ALL | Final offshore inspections, punch closure and operational acceptance - phase complete | 0 | O090.03 | Milestone | Completions Manager | 2027-05-02 | 2027-05-02 | 182 | 182 | 182 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
M100 | M100 | Milestone | ALL | Planned offshore works complete | 0 | O090 | Milestone | Project Director | 2027-05-02 | 2027-05-02 | 182 | 182 | 182 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
C010.01 | C010 | Closeout | ALL | As-built and red-line consolidation | 10 | M100 | Completions team | QA / Completions | 2027-05-02 | 2027-05-11 | 182 | 192 | 182 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C010.02 | C010 | Closeout | ALL | Quality and commissioning dossiers | 10 | C010.01 | Completions team | QA / Completions | 2027-05-12 | 2027-05-21 | 192 | 202 | 192 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C010.03 | C010 | Closeout | ALL | Accepted measurement and e-MB records | 5 | C010.02 | Completions team | QA / Completions | 2027-05-22 | 2027-05-26 | 202 | 207 | 202 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C010.04 | C010 | Closeout | ALL | Handover submission | 5 | C010.03 | Completions team | QA / Completions | 2027-05-27 | 2027-05-31 | 207 | 212 | 207 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C010 | C010 | Closeout | ALL | As-built dossiers, e-MB records, QA records and handover compilation - phase complete | 0 | C010.04 | Milestone | QA / Completions | 2027-06-01 | 2027-06-01 | 212 | 212 | 212 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
W010.01 | W010 | Allowance | ALL | Offshore weather / access allowance (not productive work) | 10 | M100 | Reserved marine capacity | Marine Manager | 2027-05-02 | 2027-05-11 | 182 | 192 | 183 | 1 | 3 | 0 | NO | PROPOSED / UNVERIFIED
W010 | W010 | Allowance | ALL | Offshore weather / access allowance (not productive work) - phase complete | 0 | W010.01 | Milestone | Marine Manager | 2027-05-12 | 2027-05-12 | 192 | 192 | 193 | 1 | 3 | 0 | NO | PROPOSED / UNVERIFIED
O100.01 | O100 | Marine | ALL | Demobilisation clearance | 1 | W010 | Support spread | Marine Manager | 2027-05-12 | 2027-05-12 | 192 | 193 | 193 | 1 | 3 | 0 | NO | PROPOSED / UNVERIFIED
O100.02 | O100 | Marine | ALL | Personnel and equipment backload | 1 | O100.01 | Support spread | Marine Manager | 2027-05-13 | 2027-05-13 | 193 | 194 | 194 | 1 | 156 | 0 | NO | PROPOSED / UNVERIFIED
O100.03 | O100 | Marine | ALL | Spread departure and closeout records | 1 | O100.02 | Support spread | Marine Manager | 2027-05-14 | 2027-05-14 | 194 | 195 | 195 | 1 | 156 | 0 | NO | PROPOSED / UNVERIFIED
O100 | O100 | Marine | ALL | Offshore demobilisation - phase complete | 0 | O100.03 | Milestone | Marine Manager | 2027-05-15 | 2027-05-15 | 195 | 195 | 212 | 17 | 156 | 0 | NO | PROPOSED / UNVERIFIED
C020.01 | C020 | Closeout | ALL | Client review and comments | 7 | C010;O100 | Project team | Project Director | 2027-06-01 | 2027-06-07 | 212 | 219 | 212 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C020.02 | C020 | Closeout | ALL | Document and residual acceptance closure | 5 | C020.01 | Project team | Project Director | 2027-06-08 | 2027-06-12 | 219 | 224 | 219 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C020.03 | C020 | Closeout | ALL | Completion certificate processing | 2 | C020.02 | Project team | Project Director | 2027-06-13 | 2027-06-14 | 224 | 226 | 224 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C020 | C020 | Closeout | ALL | Final document review and completion certificate processing - phase complete | 0 | C020.03 | Milestone | Project Director | 2027-06-15 | 2027-06-15 | 226 | 226 | 226 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
M200 | M200 | Milestone | ALL | Internal target: all works complete and handover accepted | 0 | C020 | Milestone | Project Director | 2027-06-15 | 2027-06-15 | 226 | 226 | 226 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED

## Two Crew Scenario
ID | Parent | Phase | Bridge/package | Activity | Durationdays | FSpredecessors | Resource | Owner | Start | Lastworkday/milestone | ESday 0 | EFboundaryday 0 | Lateststartday 0 | Totalfloatcalendardays | Contractfloatcalendardays | Seasonalwaitdays | Criticaltointernal finish | Status
M000 | M000 | Milestone | COMMON | Assumed NOA / commencement | 0 |  | Milestone | Contracts | 2026-11-01 | 2026-11-01 | 0 | 0 | 3 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
G010.01 | G010 | Management | COMMON | Contract kick-off and obligations | 2 | M000 | Project team | Project Director | 2026-11-01 | 2026-11-02 | 0 | 2 | 3 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
G010.02 | G010 | Management | COMMON | Leadership and authority assignments | 2 | G010.01 | Project team | Project Director | 2026-11-03 | 2026-11-04 | 2 | 4 | 5 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
G010.03 | G010 | Management | COMMON | Guarantee insurance and funding arrangements | 3 | G010.02 | Project team | Project Director | 2026-11-05 | 2026-11-07 | 4 | 7 | 7 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
G010 | G010 | Management | COMMON | Kick-off, obligations, guarantees and funding arrangements - phase complete | 0 | G010.03 | Milestone | Project Director | 2026-11-08 | 2026-11-08 | 7 | 7 | 10 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
E010.01 | E010 | Engineering | COMMON | Criteria hierarchy and code register | 4 | G010 | Engineering | Engineering Manager | 2026-11-08 | 2026-11-11 | 7 | 11 | 17 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
E010.02 | E010 | Engineering | COMMON | Loads and environmental basis | 5 | E010.01 | Engineering | Engineering Manager | 2026-11-12 | 2026-11-16 | 11 | 16 | 21 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
E010.03 | E010 | Engineering | COMMON | Design-basis/interface review | 5 | E010.02 | Engineering | Engineering Manager | 2026-11-17 | 2026-11-21 | 16 | 21 | 26 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
E010 | E010 | Engineering | COMMON | Design basis and interface approval - phase complete | 0 | E010.03 | Milestone | Engineering Manager | 2026-11-22 | 2026-11-22 | 21 | 21 | 31 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
G020.01 | G020 | Management | COMMON | Source/addendum register and scope boundaries | 4 | G010 | Project team | Engineering | 2026-11-08 | 2026-11-11 | 7 | 11 | 17 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
G020.02 | G020 | Management | COMMON | Bridge quantity and demolition reconciliation | 5 | G020.01 | Project team | Engineering | 2026-11-12 | 2026-11-16 | 11 | 16 | 21 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
G020.03 | G020 | Management | COMMON | Interface register and baseline assumptions | 5 | G020.02 | Project team | Engineering | 2026-11-17 | 2026-11-21 | 16 | 21 | 26 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
G020 | G020 | Management | COMMON | Controlled document / addendum and quantity reconciliation - phase complete | 0 | G020.03 | Milestone | Engineering | 2026-11-22 | 2026-11-22 | 21 | 21 | 31 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
M2OPEN | SECOND_SEASON | Marine | ALL | Second offshore season opens - planning constraint | 0 | M000 | Milestone | Marine Manager | 2027-10-16 | 2027-10-16 | 349 | 349 | 349 | 0 | -171 | 0 | YES | PROPOSED / UNVERIFIED
M2MOB | SECOND_SEASON | Marine | ALL | Second-season marine/crew remobilisation and renewed readiness | 7 | M2OPEN | Second-season marine spread | Marine Manager | 2027-10-16 | 2027-10-22 | 349 | 356 | 349 | 0 | -171 | 0 | YES | PROPOSED / UNVERIFIED
MR10.01 | MR10 | Marine | COMMON | Marine campaign requirements | 7 | G010 | Marine engineering | Marine Manager | 2026-11-08 | 2026-11-14 | 7 | 14 | 44 | 37 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10.02 | MR10 | Marine | COMMON | Vessel enquiries and technical audits | 14 | MR10.01 | Marine engineering | Marine Manager | 2026-11-15 | 2026-11-28 | 14 | 28 | 51 | 37 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10.03 | MR10 | Marine | COMMON | Availability and charter evaluation | 7 | MR10.02 | Marine engineering | Marine Manager | 2026-11-29 | 2026-12-05 | 28 | 35 | 65 | 37 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10.04 | MR10 | Marine | COMMON | Conditional reservations and assurance plan | 7 | MR10.03 | Marine engineering | Marine Manager | 2026-12-06 | 2026-12-12 | 35 | 42 | 72 | 37 | 26 | 0 | NO | PROPOSED / UNVERIFIED
MR10 | MR10 | Marine | COMMON | Vessel market enquiry, technical audit and conditional reservation - phase complete | 0 | MR10.04 | Milestone | Marine Manager | 2026-12-13 | 2026-12-13 | 42 | 42 | 79 | 37 | 26 | 0 | NO | PROPOSED / UNVERIFIED
S010.01 | S010 | Survey | COMMON | Survey scope and inspection plan | 2 | G010 | Survey team | Survey Manager | 2026-11-08 | 2026-11-09 | 7 | 9 | 10 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S010.02 | S010 | Survey | COMMON | Access permits and operational coordination | 3 | S010.01 | Survey team | Survey Manager | 2026-11-10 | 2026-11-12 | 9 | 12 | 12 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S010.03 | S010 | Survey | COMMON | Survey spread readiness | 2 | S010.02 | Survey team | Survey Manager | 2026-11-13 | 2026-11-14 | 12 | 14 | 15 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S010 | S010 | Survey | COMMON | Survey permits, mobilisation and access planning - phase complete | 0 | S010.03 | Milestone | Survey Manager | 2026-11-15 | 2026-11-15 | 14 | 14 | 17 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S020.01 | S020 | Survey | ALL | IC complex survey | 3 | S010 | Survey spread | Survey Manager | 2026-11-15 | 2026-11-17 | 14 | 17 | 17 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S020.02 | S020 | Survey | ALL | BHS complex survey | 3 | S020.01 | Survey spread | Survey Manager | 2026-11-18 | 2026-11-20 | 17 | 20 | 20 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S020.03 | S020 | Survey | ALL | Other bridge survey campaign | 4 | S020.02 | Survey spread | Survey Manager | 2026-11-21 | 2026-11-24 | 20 | 24 | 23 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S020.04 | S020 | Survey | ALL | Survey data validation and accepted report | 4 | S020.03 | Survey spread | Survey Manager | 2026-11-25 | 2026-11-28 | 24 | 28 | 27 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
S020 | S020 | Survey | ALL | Bridge and platform verification survey campaign - phase complete | 0 | S020.04 | Milestone | Survey Manager | 2026-11-29 | 2026-11-29 | 28 | 28 | 31 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
E020.01 | E020 | Engineering | ALL | Preliminary checked quantities | 3 | S020;E010;G020 | Engineering | Engineering Manager | 2026-11-29 | 2026-12-01 | 28 | 31 | 31 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
E020.02 | E020 | Engineering | ALL | Material requisitions and specifications | 3 | E020.01 | Engineering | Engineering Manager | 2026-12-02 | 2026-12-04 | 31 | 34 | 34 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
E020.03 | E020 | Engineering | ALL | Technical procurement release | 4 | E020.02 | Engineering | Engineering Manager | 2026-12-05 | 2026-12-08 | 34 | 38 | 37 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
E020 | E020 | Engineering | ALL | Checked material requisitions / early material release - phase complete | 0 | E020.03 | Milestone | Engineering Manager | 2026-12-09 | 2026-12-09 | 38 | 38 | 41 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
E030.01 | E030 | Engineering | REPLACEMENTS | Replacement geometry and model preparation | 5 | S020;E010 | Design team A | Engineering Manager | 2026-11-29 | 2026-12-03 | 28 | 33 | 52 | 24 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.02 | E030 | Engineering | REPLACEMENTS | Global strength and serviceability analysis | 7 | E030.01 | Design team A | Engineering Manager | 2026-12-04 | 2026-12-10 | 33 | 40 | 57 | 24 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.03 | E030 | Engineering | REPLACEMENTS | Connections bearings and landing checks | 5 | E030.02 | Design team A | Engineering Manager | 2026-12-11 | 2026-12-15 | 40 | 45 | 64 | 24 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.04 | E030 | Engineering | REPLACEMENTS | Marine constructability and services review | 4 | E030.03 | Design team A | Engineering Manager | 2026-12-16 | 2026-12-19 | 45 | 49 | 69 | 24 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030.05 | E030 | Engineering | REPLACEMENTS | Engineering review comments and release | 4 | E030.04 | Design team A | Engineering Manager | 2026-12-20 | 2026-12-23 | 49 | 53 | 73 | 24 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E030 | E030 | Engineering | REPLACEMENTS | Detailed design, AFC drawings and ITP approval - phase complete | 0 | E030.05 | Milestone | Engineering Manager | 2026-12-24 | 2026-12-24 | 53 | 53 | 77 | 24 | 13 | 0 | NO | PROPOSED / UNVERIFIED
E040.01 | E040 | Engineering | REFURBISHMENTS | Existing condition and strengthening models | 5 | S020;E010 | Design team B | Engineering Manager | 2026-11-29 | 2026-12-03 | 28 | 33 | 41 | 13 | 2 | 0 | NO | PROPOSED / UNVERIFIED
E040.02 | E040 | Engineering | REFURBISHMENTS | Member joint and platform interface checks | 7 | E040.01 | Design team B | Engineering Manager | 2026-12-04 | 2026-12-10 | 33 | 40 | 46 | 13 | 2 | 0 | NO | PROPOSED / UNVERIFIED
E040.03 | E040 | Engineering | REFURBISHMENTS | Jacket addendum and temporary conditions | 5 | E040.02 | Design team B | Engineering Manager | 2026-12-11 | 2026-12-15 | 40 | 45 | 53 | 13 | 2 | 0 | NO | PROPOSED / UNVERIFIED
E040.04 | E040 | Engineering | REFURBISHMENTS | Workpack drawings and MTO | 4 | E040.03 | Design team B | Engineering Manager | 2026-12-16 | 2026-12-19 | 45 | 49 | 58 | 13 | 2 | 0 | NO | PROPOSED / UNVERIFIED
E040.05 | E040 | Engineering | REFURBISHMENTS | Engineering review and release | 4 | E040.04 | Design team B | Engineering Manager | 2026-12-20 | 2026-12-23 | 49 | 53 | 62 | 13 | 2 | 0 | NO | PROPOSED / UNVERIFIED
E040 | E040 | Engineering | REFURBISHMENTS | Bridge and jacket strengthening design / AFC work packs - phase complete | 0 | E040.05 | Milestone | Engineering Manager | 2026-12-24 | 2026-12-24 | 53 | 53 | 66 | 13 | 2 | 0 | NO | PROPOSED / UNVERIFIED
E050.01 | E050 | Engineering | BHS-SLQ | BHS service register and operational interfaces | 7 | S020;E010 | Design team A | Technical Authority | 2026-11-29 | 2026-12-05 | 28 | 35 | 102 | 74 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050.02 | E050 | Engineering | BHS-SLQ | New service-support and transfer engineering | 10 | E050.01 | Design team A | Technical Authority | 2026-12-06 | 2026-12-15 | 35 | 45 | 109 | 74 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050.03 | E050 | Engineering | BHS-SLQ | Temporary stability and demolition design | 10 | E050.02 | Design team A | Technical Authority | 2026-12-16 | 2026-12-25 | 45 | 55 | 119 | 74 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050.04 | E050 | Engineering | BHS-SLQ | Multidiscipline review and ONGC comments | 8 | E050.03 | Design team A | Technical Authority | 2026-12-26 | 2027-01-02 | 55 | 63 | 129 | 74 | 63 | 0 | NO | PROPOSED / UNVERIFIED
E050 | E050 | Engineering | BHS-SLQ | Utility transfer, temporary stability and demolition design - phase complete | 0 | E050.04 | Milestone | Technical Authority | 2027-01-03 | 2027-01-03 | 63 | 63 | 137 | 74 | 63 | 0 | NO | PROPOSED / UNVERIFIED
MR20.01 | MR20 | Marine | REPLACEMENTS | Module boundaries weight and COG basis | 7 | E030;MR10 | Marine engineering | Marine Manager | 2026-12-24 | 2026-12-30 | 53 | 60 | 79 | 26 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20.02 | MR20 | Marine | REPLACEMENTS | Lift and landing structural engineering | 10 | MR20.01 | Marine engineering | Marine Manager | 2026-12-31 | 2027-01-09 | 60 | 70 | 86 | 26 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20.03 | MR20 | Marine | REPLACEMENTS | Loadout transport and sea-fastening engineering | 10 | MR20.02 | Marine engineering | Marine Manager | 2027-01-10 | 2027-01-19 | 70 | 80 | 96 | 26 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20.04 | MR20 | Marine | REPLACEMENTS | Marine assurance and review | 8 | MR20.03 | Marine engineering | Marine Manager | 2027-01-20 | 2027-01-27 | 80 | 88 | 106 | 26 | 15 | 0 | NO | PROPOSED / UNVERIFIED
MR20 | MR20 | Marine | REPLACEMENTS | Lift, loadout, transport and sea-fastening engineering - phase complete | 0 | MR20.04 | Milestone | Marine Manager | 2027-01-28 | 2027-01-28 | 88 | 88 | 114 | 26 | 15 | 0 | NO | PROPOSED / UNVERIFIED
P010.01 | P010 | Procurement | ALL | Vendor approval and purchase authorisation | 3 | E020 | Procurement | Procurement Manager | 2026-12-09 | 2026-12-11 | 38 | 41 | 41 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
P010.02 | P010 | Procurement | ALL | Material manufacturing and expediting | 15 | P010.01 | Procurement | Procurement Manager | 2026-12-12 | 2026-12-26 | 41 | 56 | 44 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
P010.03 | P010 | Procurement | ALL | Inspection and release documentation | 4 | P010.02 | Procurement | Procurement Manager | 2026-12-27 | 2026-12-30 | 56 | 60 | 59 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
P010.04 | P010 | Procurement | ALL | Phased receipt and traceability | 3 | P010.03 | Procurement | Procurement Manager | 2026-12-31 | 2027-01-02 | 60 | 63 | 63 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
P010 | P010 | Procurement | ALL | Vendor approval, steel purchase and phased yard delivery - phase complete | 0 | P010.04 | Milestone | Procurement Manager | 2027-01-03 | 2027-01-03 | 63 | 63 | 66 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
F010.01 | F010 | Fabrication | ICW-ICG LD | Traceable material preparation | 3 | P010;E030 | Fabrication line 1 | Fabrication Manager | 2027-01-03 | 2027-01-05 | 63 | 66 | 81 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.02 | F010 | Fabrication | ICW-ICG LD | Assembly and fit-up | 5 | F010.01 | Fabrication line 1 | Fabrication Manager | 2027-01-06 | 2027-01-10 | 66 | 71 | 84 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.03 | F010 | Fabrication | ICW-ICG LD | Welding and production | 15 | F010.02 | Fabrication line 1 | Fabrication Manager | 2027-01-11 | 2027-01-25 | 71 | 86 | 89 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.04 | F010 | Fabrication | ICW-ICG LD | NDT and repair closure | 4 | F010.03 | Fabrication line 1 | Fabrication Manager | 2027-01-26 | 2027-01-29 | 86 | 90 | 104 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.05 | F010 | Fabrication | ICW-ICG LD | Dimensional acceptance | 3 | F010.04 | Fabrication line 1 | Fabrication Manager | 2027-01-30 | 2027-02-01 | 90 | 93 | 108 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010.06 | F010 | Fabrication | ICW-ICG LD | Coating preservation and yard release | 5 | F010.05 | Fabrication line 1 | Fabrication Manager | 2027-02-02 | 2027-02-06 | 93 | 98 | 111 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F010 | F010 | Fabrication | ICW-ICG LD | Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F010.06 | Milestone | Fabrication Manager | 2027-02-07 | 2027-02-07 | 98 | 98 | 116 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
F020.01 | F020 | Fabrication | BHS-SLQ | Traceable material preparation | 5 | P010;E030 | Fabrication line 2 | Fabrication Manager | 2027-01-03 | 2027-01-07 | 63 | 68 | 77 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
F020.02 | F020 | Fabrication | BHS-SLQ | Assembly and fit-up | 8 | F020.01 | Fabrication line 2 | Fabrication Manager | 2027-01-08 | 2027-01-15 | 68 | 76 | 82 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
F020.03 | F020 | Fabrication | BHS-SLQ | Welding and production | 25 | F020.02 | Fabrication line 2 | Fabrication Manager | 2027-01-16 | 2027-02-09 | 76 | 101 | 90 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
F020.04 | F020 | Fabrication | BHS-SLQ | NDT and repair closure | 7 | F020.03 | Fabrication line 2 | Fabrication Manager | 2027-02-10 | 2027-02-16 | 101 | 108 | 115 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
F020.05 | F020 | Fabrication | BHS-SLQ | Dimensional acceptance | 5 | F020.04 | Fabrication line 2 | Fabrication Manager | 2027-02-17 | 2027-02-21 | 108 | 113 | 122 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
F020.06 | F020 | Fabrication | BHS-SLQ | Coating preservation and yard release | 5 | F020.05 | Fabrication line 2 | Fabrication Manager | 2027-02-22 | 2027-02-26 | 113 | 118 | 127 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
F020 | F020 | Fabrication | BHS-SLQ | Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F020.06 | Milestone | Fabrication Manager | 2027-02-27 | 2027-02-27 | 118 | 118 | 132 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
F030.01 | F030 | Fabrication | ICG-ICP LD | Traceable material preparation | 3 | F010 | Fabrication line 1 | Fabrication Manager | 2027-02-07 | 2027-02-09 | 98 | 101 | 119 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.02 | F030 | Fabrication | ICG-ICP LD | Assembly and fit-up | 7 | F030.01 | Fabrication line 1 | Fabrication Manager | 2027-02-10 | 2027-02-16 | 101 | 108 | 122 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.03 | F030 | Fabrication | ICG-ICP LD | Welding and production | 18 | F030.02 | Fabrication line 1 | Fabrication Manager | 2027-02-17 | 2027-03-06 | 108 | 126 | 129 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.04 | F030 | Fabrication | ICG-ICP LD | NDT and repair closure | 5 | F030.03 | Fabrication line 1 | Fabrication Manager | 2027-03-07 | 2027-03-11 | 126 | 131 | 147 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.05 | F030 | Fabrication | ICG-ICP LD | Dimensional acceptance | 3 | F030.04 | Fabrication line 1 | Fabrication Manager | 2027-03-12 | 2027-03-14 | 131 | 134 | 152 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030.06 | F030 | Fabrication | ICG-ICP LD | Coating preservation and yard release | 4 | F030.05 | Fabrication line 1 | Fabrication Manager | 2027-03-15 | 2027-03-18 | 134 | 138 | 155 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F030 | F030 | Fabrication | ICG-ICP LD | Fabricate, NDT, dimensional inspection and coating - phase complete | 0 | F030.06 | Milestone | Fabrication Manager | 2027-03-19 | 2027-03-19 | 138 | 138 | 159 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
F040.01 | F040 | Fabrication | ALL STRENGTHENING | Strengthening kit material preparation | 3 | P010;E040 | Dedicated strengthening cell | Fabrication Manager | 2027-01-03 | 2027-01-05 | 63 | 66 | 66 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
F040.02 | F040 | Fabrication | ALL STRENGTHENING | First-batch assembly and fit-up | 5 | F040.01 | Dedicated strengthening cell | Fabrication Manager | 2027-01-06 | 2027-01-10 | 66 | 71 | 69 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
F040.03 | F040 | Fabrication | ALL STRENGTHENING | First-batch production | 8 | F040.02 | Dedicated strengthening cell | Fabrication Manager | 2027-01-11 | 2027-01-18 | 71 | 79 | 74 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
F040.04 | F040 | Fabrication | ALL STRENGTHENING | First-batch inspection coating and release | 4 | F040.03 | Dedicated strengthening cell | Fabrication Manager | 2027-01-19 | 2027-01-22 | 79 | 83 | 82 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
F040.05 | F040 | Fabrication | ALL STRENGTHENING | Remaining kit production | 10 | F040.04 | Dedicated strengthening cell | Fabrication Manager | 2027-01-23 | 2027-02-01 | 83 | 93 | 93 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
F040.06 | F040 | Fabrication | ALL STRENGTHENING | Remaining kit inspection coating and release | 5 | F040.05 | Dedicated strengthening cell | Fabrication Manager | 2027-02-02 | 2027-02-06 | 93 | 98 | 103 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
F040 | F040 | Fabrication | ALL STRENGTHENING | All strengthening kits available | 0 | F040.06 | Milestone | Fabrication Manager | 2027-02-07 | 2027-02-07 | 98 | 98 | 108 | 10 | -1 | 0 | NO | PROPOSED / UNVERIFIED
F041 | F041 | Fabrication | ALL STRENGTHENING | First approved strengthening kits available | 0 | F040.04 | Milestone within strengthening-cell production | Fabrication Manager | 2027-01-23 | 2027-01-23 | 83 | 83 | 86 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
L010.01 | L010 | Marine | ICW-ICG LD | Loadout and sea-fastening release | 2 | F010;MR20 | Cargo spread | Marine Manager | 2027-02-07 | 2027-02-08 | 98 | 100 | 116 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L010.02 | L010 | Marine | ICW-ICG LD | Marine transport | 2 | L010.01 | Cargo spread | Marine Manager | 2027-02-09 | 2027-02-10 | 100 | 102 | 118 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L010.03 | L010 | Marine | ICW-ICG LD | Site receipt and installation readiness | 1 | L010.02 | Cargo spread | Marine Manager | 2027-02-11 | 2027-02-11 | 102 | 103 | 120 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L010 | L010 | Marine | ICW-ICG LD | Loadout, sea-fastening and transport - phase complete | 0 | L010.03 | Milestone | Marine Manager | 2027-02-12 | 2027-02-12 | 103 | 103 | 121 | 18 | 7 | 0 | NO | PROPOSED / UNVERIFIED
L020.01 | L020 | Marine | BHS-SLQ | Loadout and sea-fastening release | 2 | F020;MR20;L010 | Cargo spread | Marine Manager | 2027-02-27 | 2027-02-28 | 118 | 120 | 132 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
L020.02 | L020 | Marine | BHS-SLQ | Marine transport | 2 | L020.01 | Cargo spread | Marine Manager | 2027-03-01 | 2027-03-02 | 120 | 122 | 134 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
L020.03 | L020 | Marine | BHS-SLQ | Site receipt and installation readiness | 1 | L020.02 | Cargo spread | Marine Manager | 2027-03-03 | 2027-03-03 | 122 | 123 | 136 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
L020 | L020 | Marine | BHS-SLQ | Loadout, sea-fastening and transport - phase complete | 0 | L020.03 | Milestone | Marine Manager | 2027-03-04 | 2027-03-04 | 123 | 123 | 137 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
L030.01 | L030 | Marine | ICG-ICP LD | Loadout and sea-fastening release | 2 | F030;MR20;L020 | Cargo spread | Marine Manager | 2027-03-19 | 2027-03-20 | 138 | 140 | 159 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
L030.02 | L030 | Marine | ICG-ICP LD | Marine transport | 2 | L030.01 | Cargo spread | Marine Manager | 2027-03-21 | 2027-03-22 | 140 | 142 | 161 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
L030.03 | L030 | Marine | ICG-ICP LD | Site receipt and installation readiness | 1 | L030.02 | Cargo spread | Marine Manager | 2027-03-23 | 2027-03-23 | 142 | 143 | 163 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
L030 | L030 | Marine | ICG-ICP LD | Loadout, sea-fastening and transport - phase complete | 0 | L030.03 | Milestone | Marine Manager | 2027-03-24 | 2027-03-24 | 143 | 143 | 164 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
O010.01 | O010 | Offshore readiness | ALL | Accommodation/support spread mobilisation | 3 | F041;MR10 | Support spread | Offshore Manager | 2027-01-23 | 2027-01-25 | 83 | 86 | 86 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
O010.02 | O010 | Offshore readiness | ALL | Offshore crew competence and emergency readiness | 3 | O010.01 | Support spread | Offshore Manager | 2027-01-26 | 2027-01-28 | 86 | 89 | 89 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
O010.03 | O010 | Offshore readiness | ALL | Permits SIMOPS and work front release | 4 | O010.02 | Support spread | Offshore Manager | 2027-01-29 | 2027-02-01 | 89 | 93 | 92 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
O010 | O010 | Offshore readiness | ALL | Accommodation/support mobilisation, permits, SIMOPS and readiness - phase complete | 0 | O010.03 | Milestone | Offshore Manager | 2027-02-02 | 2027-02-02 | 93 | 93 | 96 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
H010.01 | H010 | Marine | COMMON | Heavy-lift spread mobilisation | 3 | MR20;O010 | Heavy-lift spread | Marine Manager | 2027-02-02 | 2027-02-04 | 93 | 96 | 114 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
H010.02 | H010 | Marine | COMMON | Equipment/certification verification | 2 | H010.01 | Heavy-lift spread | Marine Manager | 2027-02-05 | 2027-02-06 | 96 | 98 | 117 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
H010.03 | H010 | Marine | COMMON | Operational readiness and lift release | 2 | H010.02 | Heavy-lift spread | Marine Manager | 2027-02-07 | 2027-02-08 | 98 | 100 | 119 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
H010 | H010 | Marine | COMMON | Heavy-lift spread mobilisation and operational readiness - phase complete | 0 | H010.03 | Milestone | Marine Manager | 2027-02-09 | 2027-02-09 | 100 | 100 | 121 | 21 | 10 | 0 | NO | PROPOSED / UNVERIFIED
J010.01 | J010 | Offshore | ICG / BHS | ICG/BHS access and approved temporary conditions | 2 | O010 | Strengthening crew A | Offshore Manager | 2027-02-02 | 2027-02-03 | 93 | 95 | 96 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
J010.02 | J010 | Offshore | ICG / BHS | Addendum jacket strengthening | 7 | J010.01 | Strengthening crew A | Offshore Manager | 2027-02-04 | 2027-02-10 | 95 | 102 | 98 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
J010.03 | J010 | Offshore | ICG / BHS | NDT acceptance and installation-interface release | 3 | J010.02 | Strengthening crew A | Offshore Manager | 2027-02-11 | 2027-02-13 | 102 | 105 | 105 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
J010 | J010 | Offshore | ICG / BHS | Addendum jacket strengthening and acceptance - phase complete | 0 | J010.03 | Milestone | Offshore Manager | 2027-02-14 | 2027-02-14 | 105 | 105 | 108 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
I010.01 | I010 | Offshore | ICW-ICG LD | Landing and interface readiness | 2 | L010;H010;J010 | Heavy-lift spread | Offshore Manager | 2027-02-14 | 2027-02-15 | 105 | 107 | 121 | 16 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.02 | I010 | Offshore | ICW-ICG LD | Approved lift and bridge landing | 4 | I010.01 | Heavy-lift spread | Offshore Manager | 2027-02-16 | 2027-02-19 | 107 | 111 | 123 | 16 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.03 | I010 | Offshore | ICW-ICG LD | Structural connections and access fittings | 5 | I010.02 | Heavy-lift spread | Offshore Manager | 2027-02-20 | 2027-02-24 | 111 | 116 | 127 | 16 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.04 | I010 | Offshore | ICW-ICG LD | Inspection coating restoration and services checks | 3 | I010.03 | Heavy-lift spread | Offshore Manager | 2027-02-25 | 2027-02-27 | 116 | 119 | 132 | 16 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010.05 | I010 | Offshore | ICW-ICG LD | Package acceptance | 2 | I010.04 | Heavy-lift spread | Offshore Manager | 2027-02-28 | 2027-03-01 | 119 | 121 | 135 | 16 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I010 | I010 | Offshore | ICW-ICG LD | Install, connect, inspect and accept replacement bridge - phase complete | 0 | I010.05 | Milestone | Offshore Manager | 2027-03-02 | 2027-03-02 | 121 | 121 | 137 | 16 | 5 | 0 | NO | PROPOSED / UNVERIFIED
I020.01 | I020 | Offshore | BHS-SLQ | BHS landing and operational readiness | 2 | L020;I010;J010;E050 | Heavy-lift spread | Offshore Manager | 2027-03-04 | 2027-03-05 | 123 | 125 | 137 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I020.02 | I020 | Offshore | BHS-SLQ | Approved lift and new-bridge landing | 4 | I020.01 | Heavy-lift spread | Offshore Manager | 2027-03-06 | 2027-03-09 | 125 | 129 | 139 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I020.03 | I020 | Offshore | BHS-SLQ | Structural connections and inspection | 4 | I020.02 | Heavy-lift spread | Offshore Manager | 2027-03-10 | 2027-03-13 | 129 | 133 | 143 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I020.04 | I020 | Offshore | BHS-SLQ | Service transfer and commissioning | 6 | I020.03 | Heavy-lift spread | Offshore Manager | 2027-03-14 | 2027-03-19 | 133 | 139 | 147 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I020.05 | I020 | Offshore | BHS-SLQ | Operational acceptance before demolition | 2 | I020.04 | Heavy-lift spread | Offshore Manager | 2027-03-20 | 2027-03-21 | 139 | 141 | 153 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I020.06 | I020 | Offshore | BHS-SLQ | Package release | 2 | I020.05 | Heavy-lift spread | Offshore Manager | 2027-03-22 | 2027-03-23 | 141 | 143 | 155 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I020 | I020 | Offshore | BHS-SLQ | Install new bridge, transfer services and commission - phase complete | 0 | I020.06 | Milestone | Offshore Manager | 2027-03-24 | 2027-03-24 | 143 | 143 | 157 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
D020.01 | D020 | Demolition | BHS-SLQ | Demolition release and isolation confirmation | 1 | I020 | Heavy-lift spread | Offshore Manager | 2027-03-24 | 2027-03-24 | 143 | 144 | 157 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
D020.02 | D020 | Demolition | BHS-SLQ | Approved dismantling and controlled removal | 4 | D020.01 | Heavy-lift spread | Offshore Manager | 2027-03-25 | 2027-03-28 | 144 | 148 | 158 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
D020.03 | D020 | Demolition | BHS-SLQ | Backload and clearance | 2 | D020.02 | Heavy-lift spread | Offshore Manager | 2027-03-29 | 2027-03-30 | 148 | 150 | 162 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
D020 | D020 | Demolition | BHS-SLQ | Isolate, dismantle old bridge and remove to shore - phase complete | 0 | D020.03 | Milestone | Offshore Manager | 2027-03-31 | 2027-03-31 | 150 | 150 | 164 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
J020.01 | J020 | Offshore | ICP | ICP access and approved temporary conditions | 2 | O010 | Strengthening crew B | Offshore Manager | 2027-02-02 | 2027-02-03 | 93 | 95 | 120 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
J020.02 | J020 | Offshore | ICP | Addendum jacket strengthening | 6 | J020.01 | Strengthening crew B | Offshore Manager | 2027-02-04 | 2027-02-09 | 95 | 101 | 122 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
J020.03 | J020 | Offshore | ICP | NDT acceptance and installation-interface release | 2 | J020.02 | Strengthening crew B | Offshore Manager | 2027-02-10 | 2027-02-11 | 101 | 103 | 128 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
J020 | J020 | Offshore | ICP | Addendum jacket strengthening and acceptance - phase complete | 0 | J020.03 | Milestone | Offshore Manager | 2027-02-12 | 2027-02-12 | 103 | 103 | 130 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
I030.01 | I030 | Offshore | ICG-ICP LD | Landing and interface readiness | 2 | L030;D020;J020 | Heavy-lift spread | Offshore Manager | 2027-03-31 | 2027-04-01 | 150 | 152 | 164 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I030.02 | I030 | Offshore | ICG-ICP LD | Approved lift and bridge landing | 5 | I030.01 | Heavy-lift spread | Offshore Manager | 2027-04-02 | 2027-04-06 | 152 | 157 | 166 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I030.03 | I030 | Offshore | ICG-ICP LD | Structural connections and access fittings | 6 | I030.02 | Heavy-lift spread | Offshore Manager | 2027-04-07 | 2027-04-12 | 157 | 163 | 171 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I030.04 | I030 | Offshore | ICG-ICP LD | Inspection and service checks | 3 | I030.03 | Heavy-lift spread | Offshore Manager | 2027-04-13 | 2027-04-15 | 163 | 166 | 177 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I030.05 | I030 | Offshore | ICG-ICP LD | Package acceptance | 2 | I030.04 | Heavy-lift spread | Offshore Manager | 2027-04-16 | 2027-04-17 | 166 | 168 | 180 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
I030 | I030 | Offshore | ICG-ICP LD | Install, connect, inspect and accept replacement bridge - phase complete | 0 | I030.05 | Milestone | Offshore Manager | 2027-04-18 | 2027-04-18 | 168 | 168 | 182 | 14 | 3 | 0 | NO | PROPOSED / UNVERIFIED
RA01.01 | RA01 | Offshore | ICW-ICG UD | Permit access and material readiness | 2 | J010;F040 | Strengthening crew A | Offshore Manager | 2027-02-14 | 2027-02-15 | 105 | 107 | 108 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA01.02 | RA01 | Offshore | ICW-ICG UD | Approved temporary works and preparation | 2 | RA01.01 | Strengthening crew A | Offshore Manager | 2027-02-16 | 2027-02-17 | 107 | 109 | 110 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA01.03 | RA01 | Offshore | ICW-ICG UD | Strengthening installation and connections | 8 | RA01.02 | Strengthening crew A | Offshore Manager | 2027-02-18 | 2027-02-25 | 109 | 117 | 112 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA01.04 | RA01 | Offshore | ICW-ICG UD | NDT dimensional and coating acceptance | 2 | RA01.03 | Strengthening crew A | Offshore Manager | 2027-02-26 | 2027-02-27 | 117 | 119 | 120 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA01.05 | RA01 | Offshore | ICW-ICG UD | Punch closure and package acceptance | 2 | RA01.04 | Strengthening crew A | Offshore Manager | 2027-02-28 | 2027-03-01 | 119 | 121 | 122 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA01 | RA01 | Offshore | ICW-ICG UD | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA01.05 | Milestone | Offshore Manager | 2027-03-02 | 2027-03-02 | 121 | 121 | 124 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA02.01 | RA02 | Offshore | ICG-ICP UD | Permit access and material readiness | 2 | RA01;F040 | Strengthening crew A | Offshore Manager | 2027-03-02 | 2027-03-03 | 121 | 123 | 124 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA02.02 | RA02 | Offshore | ICG-ICP UD | Approved temporary works and preparation | 2 | RA02.01 | Strengthening crew A | Offshore Manager | 2027-03-04 | 2027-03-05 | 123 | 125 | 126 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA02.03 | RA02 | Offshore | ICG-ICP UD | Strengthening installation and connections | 14 | RA02.02 | Strengthening crew A | Offshore Manager | 2027-03-06 | 2027-03-19 | 125 | 139 | 128 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA02.04 | RA02 | Offshore | ICG-ICP UD | NDT dimensional and coating acceptance | 2 | RA02.03 | Strengthening crew A | Offshore Manager | 2027-03-20 | 2027-03-21 | 139 | 141 | 142 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA02.05 | RA02 | Offshore | ICG-ICP UD | Punch closure and package acceptance | 2 | RA02.04 | Strengthening crew A | Offshore Manager | 2027-03-22 | 2027-03-23 | 141 | 143 | 144 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA02 | RA02 | Offshore | ICG-ICP UD | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA02.05 | Milestone | Offshore Manager | 2027-03-24 | 2027-03-24 | 143 | 143 | 146 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA03.01 | RA03 | Offshore | SLQ-WIS | Permit access and material readiness | 2 | RA02;F040 | Strengthening crew A | Offshore Manager | 2027-03-24 | 2027-03-25 | 143 | 145 | 146 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA03.02 | RA03 | Offshore | SLQ-WIS | Approved temporary works and preparation | 2 | RA03.01 | Strengthening crew A | Offshore Manager | 2027-03-26 | 2027-03-27 | 145 | 147 | 148 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA03.03 | RA03 | Offshore | SLQ-WIS | Strengthening installation and connections | 10 | RA03.02 | Strengthening crew A | Offshore Manager | 2027-03-28 | 2027-04-06 | 147 | 157 | 150 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA03.04 | RA03 | Offshore | SLQ-WIS | NDT dimensional and coating acceptance | 2 | RA03.03 | Strengthening crew A | Offshore Manager | 2027-04-07 | 2027-04-08 | 157 | 159 | 160 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA03.05 | RA03 | Offshore | SLQ-WIS | Punch closure and package acceptance | 2 | RA03.04 | Strengthening crew A | Offshore Manager | 2027-04-09 | 2027-04-10 | 159 | 161 | 162 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA03 | RA03 | Offshore | SLQ-WIS | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA03.05 | Milestone | Offshore Manager | 2027-04-11 | 2027-04-11 | 161 | 161 | 164 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA04.01 | RA04 | Offshore | NQO-NQD | Permit access and material readiness | 2 | O010;F040;RA03 | Strengthening crew A | Offshore Manager | 2027-04-11 | 2027-04-12 | 161 | 163 | 164 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA04.02 | RA04 | Offshore | NQO-NQD | Approved temporary works and preparation | 2 | RA04.01 | Strengthening crew A | Offshore Manager | 2027-04-13 | 2027-04-14 | 163 | 165 | 166 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA04.03 | RA04 | Offshore | NQO-NQD | Strengthening installation and connections | 10 | RA04.02 | Strengthening crew A | Offshore Manager | 2027-04-15 | 2027-04-24 | 165 | 175 | 168 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA04.04 | RA04 | Offshore | NQO-NQD | NDT dimensional and coating acceptance | 2 | RA04.03 | Strengthening crew A | Offshore Manager | 2027-04-25 | 2027-04-26 | 175 | 177 | 178 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA04.05 | RA04 | Offshore | NQO-NQD | Punch closure and package acceptance | 2 | RA04.04 | Strengthening crew A | Offshore Manager | 2027-04-27 | 2027-04-28 | 177 | 179 | 180 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RA04 | RA04 | Offshore | NQO-NQD | Strengthening, inspection and bridge acceptance - phase complete | 0 | RA04.05 | Milestone | Offshore Manager | 2027-04-29 | 2027-04-29 | 179 | 179 | 182 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
RB01.01 | RB01 | Offshore | WIN-NC | Permit access and material readiness | 2 | J020;F040 | Strengthening crew B | Offshore Manager | 2027-02-12 | 2027-02-13 | 103 | 105 | 130 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.02 | RB01 | Offshore | WIN-NC | Approved temporary works and preparation | 2 | RB01.01 | Strengthening crew B | Offshore Manager | 2027-02-14 | 2027-02-15 | 105 | 107 | 132 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.03 | RB01 | Offshore | WIN-NC | Strengthening installation and connections | 4 | RB01.02 | Strengthening crew B | Offshore Manager | 2027-02-16 | 2027-02-19 | 107 | 111 | 134 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.04 | RB01 | Offshore | WIN-NC | NDT dimensional and coating acceptance | 2 | RB01.03 | Strengthening crew B | Offshore Manager | 2027-02-20 | 2027-02-21 | 111 | 113 | 138 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01.05 | RB01 | Offshore | WIN-NC | Punch closure and package acceptance | 2 | RB01.04 | Strengthening crew B | Offshore Manager | 2027-02-22 | 2027-02-23 | 113 | 115 | 140 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB01 | RB01 | Offshore | WIN-NC | Strengthening, inspection and bridge acceptance - phase complete | 0 | RB01.05 | Milestone | Offshore Manager | 2027-02-24 | 2027-02-24 | 115 | 115 | 142 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.01 | RB02 | Offshore | SCA-SC1 | Permit access and material readiness | 2 | RB01;F040 | Strengthening crew B | Offshore Manager | 2027-02-24 | 2027-02-25 | 115 | 117 | 142 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.02 | RB02 | Offshore | SCA-SC1 | Approved temporary works and preparation | 2 | RB02.01 | Strengthening crew B | Offshore Manager | 2027-02-26 | 2027-02-27 | 117 | 119 | 144 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.03 | RB02 | Offshore | SCA-SC1 | Strengthening installation and connections | 8 | RB02.02 | Strengthening crew B | Offshore Manager | 2027-02-28 | 2027-03-07 | 119 | 127 | 146 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.04 | RB02 | Offshore | SCA-SC1 | NDT dimensional and coating acceptance | 2 | RB02.03 | Strengthening crew B | Offshore Manager | 2027-03-08 | 2027-03-09 | 127 | 129 | 154 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02.05 | RB02 | Offshore | SCA-SC1 | Punch closure and package acceptance | 2 | RB02.04 | Strengthening crew B | Offshore Manager | 2027-03-10 | 2027-03-11 | 129 | 131 | 156 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB02 | RB02 | Offshore | SCA-SC1 | Strengthening, inspection and bridge acceptance - phase complete | 0 | RB02.05 | Milestone | Offshore Manager | 2027-03-12 | 2027-03-12 | 131 | 131 | 158 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.01 | RB03 | Offshore | SCA-SCF | Permit access and material readiness | 2 | RB02;F040 | Strengthening crew B | Offshore Manager | 2027-03-12 | 2027-03-13 | 131 | 133 | 158 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.02 | RB03 | Offshore | SCA-SCF | Approved temporary works and preparation | 2 | RB03.01 | Strengthening crew B | Offshore Manager | 2027-03-14 | 2027-03-15 | 133 | 135 | 160 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.03 | RB03 | Offshore | SCA-SCF | Strengthening installation and connections | 16 | RB03.02 | Strengthening crew B | Offshore Manager | 2027-03-16 | 2027-03-31 | 135 | 151 | 162 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.04 | RB03 | Offshore | SCA-SCF | NDT dimensional and coating acceptance | 2 | RB03.03 | Strengthening crew B | Offshore Manager | 2027-04-01 | 2027-04-02 | 151 | 153 | 178 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03.05 | RB03 | Offshore | SCA-SCF | Punch closure and package acceptance | 2 | RB03.04 | Strengthening crew B | Offshore Manager | 2027-04-03 | 2027-04-04 | 153 | 155 | 180 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
RB03 | RB03 | Offshore | SCA-SCF | Strengthening, inspection and bridge acceptance - phase complete | 0 | RB03.05 | Milestone | Offshore Manager | 2027-04-05 | 2027-04-05 | 155 | 155 | 182 | 27 | 16 | 0 | NO | PROPOSED / UNVERIFIED
D030.01 | D030 | Demolition | OTHER BRIDGES | Other-bridge demolition quantity and release check | 2 | I030;RA04;RB03;RA03 | Heavy-lift spread | Offshore Manager | 2027-04-29 | 2027-04-30 | 179 | 181 | 182 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
D030.02 | D030 | Demolition | OTHER BRIDGES | Approved residual removal | 3 | D030.01 | Heavy-lift spread | Offshore Manager | 2027-05-01 | 2027-05-03 | 181 | 184 | 184 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
D030.03 | D030 | Demolition | OTHER BRIDGES | Waste/backload and records | 2 | D030.02 | Heavy-lift spread | Offshore Manager | 2027-05-04 | 2027-05-05 | 184 | 186 | 187 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
D030 | D030 | Demolition | OTHER BRIDGES | Other removal, waste backload and allocated demolition closure - phase complete | 0 | D030.03 | Milestone | Offshore Manager | 2027-05-06 | 2027-05-06 | 186 | 186 | 189 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
O090.01 | O090 | Offshore | ALL | Final offshore walkdowns | 3 | D030 | Support spread | Completions Manager | 2027-05-06 | 2027-05-08 | 186 | 189 | 189 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
O090.02 | O090 | Offshore | ALL | Acceptance-critical punch closure | 3 | O090.01 | Support spread | Completions Manager | 2027-05-09 | 2027-05-11 | 189 | 192 | 192 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
O090.03 | O090 | Offshore | ALL | Operational acceptance records | 1 | O090.02 | Support spread | Completions Manager | 2027-05-12 | 2027-05-12 | 192 | 193 | 195 | 3 | -8 | 0 | NO | PROPOSED / UNVERIFIED
O090 | O090 | Offshore | ALL | Final offshore inspections, punch closure and operational acceptance - phase complete | 0 | O090.03 | Milestone | Completions Manager | 2027-05-13 | 2027-05-13 | 193 | 193 | 339 | 146 | -8 | 0 | NO | PROPOSED / UNVERIFIED
M100 | M100 | Milestone | ALL | Planned offshore works complete | 0 | O090 | Milestone | Project Director | 2027-05-13 | 2027-05-13 | 193 | 193 | 339 | 146 | -8 | 0 | NO | PROPOSED / UNVERIFIED
C010.01 | C010 | Closeout | ALL | As-built and red-line consolidation | 10 | M100 | Completions team | QA / Completions | 2027-05-13 | 2027-05-22 | 193 | 203 | 339 | 146 | 128 | 0 | NO | PROPOSED / UNVERIFIED
C010.02 | C010 | Closeout | ALL | Quality and commissioning dossiers | 10 | C010.01 | Completions team | QA / Completions | 2027-05-23 | 2027-06-01 | 203 | 213 | 349 | 146 | 128 | 0 | NO | PROPOSED / UNVERIFIED
C010.03 | C010 | Closeout | ALL | Accepted measurement and e-MB records | 5 | C010.02 | Completions team | QA / Completions | 2027-06-02 | 2027-06-06 | 213 | 218 | 359 | 146 | 128 | 0 | NO | PROPOSED / UNVERIFIED
C010.04 | C010 | Closeout | ALL | Handover submission | 5 | C010.03 | Completions team | QA / Completions | 2027-06-07 | 2027-06-11 | 218 | 223 | 364 | 146 | 128 | 0 | NO | PROPOSED / UNVERIFIED
C010 | C010 | Closeout | ALL | As-built dossiers, e-MB records, QA records and handover compilation - phase complete | 0 | C010.04 | Milestone | QA / Completions | 2027-06-12 | 2027-06-12 | 223 | 223 | 369 | 146 | 128 | 0 | NO | PROPOSED / UNVERIFIED
W010.01 | W010 | Allowance | ALL | Offshore weather / access allowance (not productive work) | 10 | M100;M2MOB | Reserved marine capacity | Marine Manager | 2027-10-23 | 2027-11-01 | 356 | 366 | 356 | 0 | -171 | 0 | YES | PROPOSED / UNVERIFIED
W010 | W010 | Allowance | ALL | Offshore weather / access allowance (not productive work) - phase complete | 0 | W010.01 | Milestone | Marine Manager | 2027-11-02 | 2027-11-02 | 366 | 366 | 366 | 0 | -171 | 0 | YES | PROPOSED / UNVERIFIED
O100.01 | O100 | Marine | ALL | Demobilisation clearance | 1 | W010;M2MOB | Support spread | Marine Manager | 2027-11-02 | 2027-11-02 | 366 | 367 | 366 | 0 | -171 | 0 | YES | PROPOSED / UNVERIFIED
O100.02 | O100 | Marine | ALL | Personnel and equipment backload | 1 | O100.01;M2MOB | Support spread | Marine Manager | 2027-11-03 | 2027-11-03 | 367 | 368 | 367 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED
O100.03 | O100 | Marine | ALL | Spread departure and closeout records | 1 | O100.02;M2MOB | Support spread | Marine Manager | 2027-11-04 | 2027-11-04 | 368 | 369 | 368 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED
O100 | O100 | Marine | ALL | Offshore demobilisation - phase complete | 0 | O100.03 | Milestone | Marine Manager | 2027-11-05 | 2027-11-05 | 369 | 369 | 369 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED
C020.01 | C020 | Closeout | ALL | Client review and comments | 7 | C010;O100 | Project team | Project Director | 2027-11-05 | 2027-11-11 | 369 | 376 | 369 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED
C020.02 | C020 | Closeout | ALL | Document and residual acceptance closure | 5 | C020.01 | Project team | Project Director | 2027-11-12 | 2027-11-16 | 376 | 381 | 376 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED
C020.03 | C020 | Closeout | ALL | Completion certificate processing | 2 | C020.02 | Project team | Project Director | 2027-11-17 | 2027-11-18 | 381 | 383 | 381 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED
C020 | C020 | Closeout | ALL | Final document review and completion certificate processing - phase complete | 0 | C020.03 | Milestone | Project Director | 2027-11-19 | 2027-11-19 | 383 | 383 | 383 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED
M200 | M200 | Milestone | ALL | Internal target: all works complete and handover accepted | 0 | C020 | Milestone | Project Director | 2027-11-19 | 2027-11-19 | 383 | 383 | 383 | 0 | -18 | 0 | YES | PROPOSED / UNVERIFIED

## Critical Activities
ID | Parent | Phase | Bridge/package | Activity | Durationdays | FSpredecessors | Resource | Owner | Start | Lastworkday/milestone | ESday 0 | EFboundaryday 0 | Lateststartday 0 | Totalfloatcalendardays | Contractfloatcalendardays | Seasonalwaitdays | Criticaltointernal finish | Status
G010.01 | G010 | Management | COMMON | Contract kick-off and obligations | 2 | M000 | Project team | Project Director | 2026-11-01 | 2026-11-02 | 0 | 2 | 0 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
G010.02 | G010 | Management | COMMON | Leadership and authority assignments | 2 | G010.01 | Project team | Project Director | 2026-11-03 | 2026-11-04 | 2 | 4 | 2 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
G010.03 | G010 | Management | COMMON | Guarantee insurance and funding arrangements | 3 | G010.02 | Project team | Project Director | 2026-11-05 | 2026-11-07 | 4 | 7 | 4 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S010.01 | S010 | Survey | COMMON | Survey scope and inspection plan | 2 | G010 | Survey team | Survey Manager | 2026-11-08 | 2026-11-09 | 7 | 9 | 7 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S010.02 | S010 | Survey | COMMON | Access permits and operational coordination | 3 | S010.01 | Survey team | Survey Manager | 2026-11-10 | 2026-11-12 | 9 | 12 | 9 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S010.03 | S010 | Survey | COMMON | Survey spread readiness | 2 | S010.02 | Survey team | Survey Manager | 2026-11-13 | 2026-11-14 | 12 | 14 | 12 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.01 | S020 | Survey | ALL | IC complex survey | 3 | S010 | Survey spread | Survey Manager | 2026-11-15 | 2026-11-17 | 14 | 17 | 14 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.02 | S020 | Survey | ALL | BHS complex survey | 3 | S020.01 | Survey spread | Survey Manager | 2026-11-18 | 2026-11-20 | 17 | 20 | 17 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.03 | S020 | Survey | ALL | Other bridge survey campaign | 4 | S020.02 | Survey spread | Survey Manager | 2026-11-21 | 2026-11-24 | 20 | 24 | 20 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
S020.04 | S020 | Survey | ALL | Survey data validation and accepted report | 4 | S020.03 | Survey spread | Survey Manager | 2026-11-25 | 2026-11-28 | 24 | 28 | 24 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E020.01 | E020 | Engineering | ALL | Preliminary checked quantities | 3 | S020;E010;G020 | Engineering | Engineering Manager | 2026-11-29 | 2026-12-01 | 28 | 31 | 28 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E020.02 | E020 | Engineering | ALL | Material requisitions and specifications | 3 | E020.01 | Engineering | Engineering Manager | 2026-12-02 | 2026-12-04 | 31 | 34 | 31 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
E020.03 | E020 | Engineering | ALL | Technical procurement release | 4 | E020.02 | Engineering | Engineering Manager | 2026-12-05 | 2026-12-08 | 34 | 38 | 34 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010.01 | P010 | Procurement | ALL | Vendor approval and purchase authorisation | 3 | E020 | Procurement | Procurement Manager | 2026-12-09 | 2026-12-11 | 38 | 41 | 38 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010.02 | P010 | Procurement | ALL | Material manufacturing and expediting | 15 | P010.01 | Procurement | Procurement Manager | 2026-12-12 | 2026-12-26 | 41 | 56 | 41 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010.03 | P010 | Procurement | ALL | Inspection and release documentation | 4 | P010.02 | Procurement | Procurement Manager | 2026-12-27 | 2026-12-30 | 56 | 60 | 56 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
P010.04 | P010 | Procurement | ALL | Phased receipt and traceability | 3 | P010.03 | Procurement | Procurement Manager | 2026-12-31 | 2027-01-02 | 60 | 63 | 60 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.01 | F020 | Fabrication | BHS-SLQ | Traceable material preparation | 5 | P010;E030 | Fabrication line 2 | Fabrication Manager | 2027-01-03 | 2027-01-07 | 63 | 68 | 63 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.02 | F020 | Fabrication | BHS-SLQ | Assembly and fit-up | 8 | F020.01 | Fabrication line 2 | Fabrication Manager | 2027-01-08 | 2027-01-15 | 68 | 76 | 68 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.03 | F020 | Fabrication | BHS-SLQ | Welding and production | 25 | F020.02 | Fabrication line 2 | Fabrication Manager | 2027-01-16 | 2027-02-09 | 76 | 101 | 76 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.04 | F020 | Fabrication | BHS-SLQ | NDT and repair closure | 7 | F020.03 | Fabrication line 2 | Fabrication Manager | 2027-02-10 | 2027-02-16 | 101 | 108 | 101 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.05 | F020 | Fabrication | BHS-SLQ | Dimensional acceptance | 5 | F020.04 | Fabrication line 2 | Fabrication Manager | 2027-02-17 | 2027-02-21 | 108 | 113 | 108 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
F020.06 | F020 | Fabrication | BHS-SLQ | Coating preservation and yard release | 5 | F020.05 | Fabrication line 2 | Fabrication Manager | 2027-02-22 | 2027-02-26 | 113 | 118 | 113 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
L020.01 | L020 | Marine | BHS-SLQ | Loadout and sea-fastening release | 2 | F020;MR20;L010 | Cargo spread | Marine Manager | 2027-02-27 | 2027-02-28 | 118 | 120 | 118 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
L020.02 | L020 | Marine | BHS-SLQ | Marine transport | 2 | L020.01 | Cargo spread | Marine Manager | 2027-03-01 | 2027-03-02 | 120 | 122 | 120 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
L020.03 | L020 | Marine | BHS-SLQ | Site receipt and installation readiness | 1 | L020.02 | Cargo spread | Marine Manager | 2027-03-03 | 2027-03-03 | 122 | 123 | 122 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.01 | I020 | Offshore | BHS-SLQ | BHS landing and operational readiness | 2 | L020;I010;J010;E050 | Heavy-lift spread | Offshore Manager | 2027-03-04 | 2027-03-05 | 123 | 125 | 123 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.02 | I020 | Offshore | BHS-SLQ | Approved lift and new-bridge landing | 4 | I020.01 | Heavy-lift spread | Offshore Manager | 2027-03-06 | 2027-03-09 | 125 | 129 | 125 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.03 | I020 | Offshore | BHS-SLQ | Structural connections and inspection | 4 | I020.02 | Heavy-lift spread | Offshore Manager | 2027-03-10 | 2027-03-13 | 129 | 133 | 129 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.04 | I020 | Offshore | BHS-SLQ | Service transfer and commissioning | 6 | I020.03 | Heavy-lift spread | Offshore Manager | 2027-03-14 | 2027-03-19 | 133 | 139 | 133 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.05 | I020 | Offshore | BHS-SLQ | Operational acceptance before demolition | 2 | I020.04 | Heavy-lift spread | Offshore Manager | 2027-03-20 | 2027-03-21 | 139 | 141 | 139 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I020.06 | I020 | Offshore | BHS-SLQ | Package release | 2 | I020.05 | Heavy-lift spread | Offshore Manager | 2027-03-22 | 2027-03-23 | 141 | 143 | 141 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D020.01 | D020 | Demolition | BHS-SLQ | Demolition release and isolation confirmation | 1 | I020 | Heavy-lift spread | Offshore Manager | 2027-03-24 | 2027-03-24 | 143 | 144 | 143 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D020.02 | D020 | Demolition | BHS-SLQ | Approved dismantling and controlled removal | 4 | D020.01 | Heavy-lift spread | Offshore Manager | 2027-03-25 | 2027-03-28 | 144 | 148 | 144 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D020.03 | D020 | Demolition | BHS-SLQ | Backload and clearance | 2 | D020.02 | Heavy-lift spread | Offshore Manager | 2027-03-29 | 2027-03-30 | 148 | 150 | 148 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.01 | I030 | Offshore | ICG-ICP LD | Landing and interface readiness | 2 | L030;D020;J020 | Heavy-lift spread | Offshore Manager | 2027-03-31 | 2027-04-01 | 150 | 152 | 150 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.02 | I030 | Offshore | ICG-ICP LD | Approved lift and bridge landing | 5 | I030.01 | Heavy-lift spread | Offshore Manager | 2027-04-02 | 2027-04-06 | 152 | 157 | 152 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.03 | I030 | Offshore | ICG-ICP LD | Structural connections and access fittings | 6 | I030.02 | Heavy-lift spread | Offshore Manager | 2027-04-07 | 2027-04-12 | 157 | 163 | 157 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.04 | I030 | Offshore | ICG-ICP LD | Inspection and service checks | 3 | I030.03 | Heavy-lift spread | Offshore Manager | 2027-04-13 | 2027-04-15 | 163 | 166 | 163 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
I030.05 | I030 | Offshore | ICG-ICP LD | Package acceptance | 2 | I030.04 | Heavy-lift spread | Offshore Manager | 2027-04-16 | 2027-04-17 | 166 | 168 | 166 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D030.01 | D030 | Demolition | OTHER BRIDGES | Other-bridge demolition quantity and release check | 2 | I030;RA04;RB03;RA03 | Heavy-lift spread | Offshore Manager | 2027-04-18 | 2027-04-19 | 168 | 170 | 168 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D030.02 | D030 | Demolition | OTHER BRIDGES | Approved residual removal | 3 | D030.01 | Heavy-lift spread | Offshore Manager | 2027-04-20 | 2027-04-22 | 170 | 173 | 170 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
D030.03 | D030 | Demolition | OTHER BRIDGES | Waste/backload and records | 2 | D030.02 | Heavy-lift spread | Offshore Manager | 2027-04-23 | 2027-04-24 | 173 | 175 | 173 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
O090.01 | O090 | Offshore | ALL | Final offshore walkdowns | 3 | D030 | Support spread | Completions Manager | 2027-04-25 | 2027-04-27 | 175 | 178 | 175 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
O090.02 | O090 | Offshore | ALL | Acceptance-critical punch closure | 3 | O090.01 | Support spread | Completions Manager | 2027-04-28 | 2027-04-30 | 178 | 181 | 178 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
O090.03 | O090 | Offshore | ALL | Operational acceptance records | 1 | O090.02 | Support spread | Completions Manager | 2027-05-01 | 2027-05-01 | 181 | 182 | 181 | 0 | 3 | 0 | YES | PROPOSED / UNVERIFIED
C010.01 | C010 | Closeout | ALL | As-built and red-line consolidation | 10 | M100 | Completions team | QA / Completions | 2027-05-02 | 2027-05-11 | 182 | 192 | 182 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C010.02 | C010 | Closeout | ALL | Quality and commissioning dossiers | 10 | C010.01 | Completions team | QA / Completions | 2027-05-12 | 2027-05-21 | 192 | 202 | 192 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C010.03 | C010 | Closeout | ALL | Accepted measurement and e-MB records | 5 | C010.02 | Completions team | QA / Completions | 2027-05-22 | 2027-05-26 | 202 | 207 | 202 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C010.04 | C010 | Closeout | ALL | Handover submission | 5 | C010.03 | Completions team | QA / Completions | 2027-05-27 | 2027-05-31 | 207 | 212 | 207 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C020.01 | C020 | Closeout | ALL | Client review and comments | 7 | C010;O100 | Project team | Project Director | 2027-06-01 | 2027-06-07 | 212 | 219 | 212 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C020.02 | C020 | Closeout | ALL | Document and residual acceptance closure | 5 | C020.01 | Project team | Project Director | 2027-06-08 | 2027-06-12 | 219 | 224 | 219 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED
C020.03 | C020 | Closeout | ALL | Completion certificate processing | 2 | C020.02 | Project team | Project Director | 2027-06-13 | 2027-06-14 | 224 | 226 | 224 | 0 | 139 | 0 | YES | PROPOSED / UNVERIFIED

## Driving Chain
Sequence | ID | Bridge | Activity | Start | Finish | Duration | Float
1 | M000 | COMMON | Assumed NOA / commencement | 2026-11-01 | 2026-11-01 | 0 | 0
2 | G010.01 | COMMON | Contract kick-off and obligations | 2026-11-01 | 2026-11-02 | 2 | 0
3 | G010.02 | COMMON | Leadership and authority assignments | 2026-11-03 | 2026-11-04 | 2 | 0
4 | G010.03 | COMMON | Guarantee insurance and funding arrangements | 2026-11-05 | 2026-11-07 | 3 | 0
5 | G010 | COMMON | Kick-off, obligations, guarantees and funding arrangements - phase complete | 2026-11-08 | 2026-11-08 | 0 | 0
6 | S010.01 | COMMON | Survey scope and inspection plan | 2026-11-08 | 2026-11-09 | 2 | 0
7 | S010.02 | COMMON | Access permits and operational coordination | 2026-11-10 | 2026-11-12 | 3 | 0
8 | S010.03 | COMMON | Survey spread readiness | 2026-11-13 | 2026-11-14 | 2 | 0
9 | S010 | COMMON | Survey permits, mobilisation and access planning - phase complete | 2026-11-15 | 2026-11-15 | 0 | 0
10 | S020.01 | ALL | IC complex survey | 2026-11-15 | 2026-11-17 | 3 | 0
11 | S020.02 | ALL | BHS complex survey | 2026-11-18 | 2026-11-20 | 3 | 0
12 | S020.03 | ALL | Other bridge survey campaign | 2026-11-21 | 2026-11-24 | 4 | 0
13 | S020.04 | ALL | Survey data validation and accepted report | 2026-11-25 | 2026-11-28 | 4 | 0
14 | S020 | ALL | Bridge and platform verification survey campaign - phase complete | 2026-11-29 | 2026-11-29 | 0 | 0
15 | E020.01 | ALL | Preliminary checked quantities | 2026-11-29 | 2026-12-01 | 3 | 0
16 | E020.02 | ALL | Material requisitions and specifications | 2026-12-02 | 2026-12-04 | 3 | 0
17 | E020.03 | ALL | Technical procurement release | 2026-12-05 | 2026-12-08 | 4 | 0
18 | E020 | ALL | Checked material requisitions / early material release - phase complete | 2026-12-09 | 2026-12-09 | 0 | 0
19 | P010.01 | ALL | Vendor approval and purchase authorisation | 2026-12-09 | 2026-12-11 | 3 | 0
20 | P010.02 | ALL | Material manufacturing and expediting | 2026-12-12 | 2026-12-26 | 15 | 0
21 | P010.03 | ALL | Inspection and release documentation | 2026-12-27 | 2026-12-30 | 4 | 0
22 | P010.04 | ALL | Phased receipt and traceability | 2026-12-31 | 2027-01-02 | 3 | 0
23 | P010 | ALL | Vendor approval, steel purchase and phased yard delivery - phase complete | 2027-01-03 | 2027-01-03 | 0 | 0
24 | F020.01 | BHS-SLQ | Traceable material preparation | 2027-01-03 | 2027-01-07 | 5 | 0
25 | F020.02 | BHS-SLQ | Assembly and fit-up | 2027-01-08 | 2027-01-15 | 8 | 0
26 | F020.03 | BHS-SLQ | Welding and production | 2027-01-16 | 2027-02-09 | 25 | 0
27 | F020.04 | BHS-SLQ | NDT and repair closure | 2027-02-10 | 2027-02-16 | 7 | 0
28 | F020.05 | BHS-SLQ | Dimensional acceptance | 2027-02-17 | 2027-02-21 | 5 | 0
29 | F020.06 | BHS-SLQ | Coating preservation and yard release | 2027-02-22 | 2027-02-26 | 5 | 0
30 | F020 | BHS-SLQ | Fabricate, NDT, dimensional inspection and coating - phase complete | 2027-02-27 | 2027-02-27 | 0 | 0
31 | L020.01 | BHS-SLQ | Loadout and sea-fastening release | 2027-02-27 | 2027-02-28 | 2 | 0
32 | L020.02 | BHS-SLQ | Marine transport | 2027-03-01 | 2027-03-02 | 2 | 0
33 | L020.03 | BHS-SLQ | Site receipt and installation readiness | 2027-03-03 | 2027-03-03 | 1 | 0
34 | L020 | BHS-SLQ | Loadout, sea-fastening and transport - phase complete | 2027-03-04 | 2027-03-04 | 0 | 0
35 | I020.01 | BHS-SLQ | BHS landing and operational readiness | 2027-03-04 | 2027-03-05 | 2 | 0
36 | I020.02 | BHS-SLQ | Approved lift and new-bridge landing | 2027-03-06 | 2027-03-09 | 4 | 0
37 | I020.03 | BHS-SLQ | Structural connections and inspection | 2027-03-10 | 2027-03-13 | 4 | 0
38 | I020.04 | BHS-SLQ | Service transfer and commissioning | 2027-03-14 | 2027-03-19 | 6 | 0
39 | I020.05 | BHS-SLQ | Operational acceptance before demolition | 2027-03-20 | 2027-03-21 | 2 | 0
40 | I020.06 | BHS-SLQ | Package release | 2027-03-22 | 2027-03-23 | 2 | 0
41 | I020 | BHS-SLQ | Install new bridge, transfer services and commission - phase complete | 2027-03-24 | 2027-03-24 | 0 | 0
42 | D020.01 | BHS-SLQ | Demolition release and isolation confirmation | 2027-03-24 | 2027-03-24 | 1 | 0
43 | D020.02 | BHS-SLQ | Approved dismantling and controlled removal | 2027-03-25 | 2027-03-28 | 4 | 0
44 | D020.03 | BHS-SLQ | Backload and clearance | 2027-03-29 | 2027-03-30 | 2 | 0
45 | D020 | BHS-SLQ | Isolate, dismantle old bridge and remove to shore - phase complete | 2027-03-31 | 2027-03-31 | 0 | 0
46 | I030.01 | ICG-ICP LD | Landing and interface readiness | 2027-03-31 | 2027-04-01 | 2 | 0
47 | I030.02 | ICG-ICP LD | Approved lift and bridge landing | 2027-04-02 | 2027-04-06 | 5 | 0
48 | I030.03 | ICG-ICP LD | Structural connections and access fittings | 2027-04-07 | 2027-04-12 | 6 | 0
49 | I030.04 | ICG-ICP LD | Inspection and service checks | 2027-04-13 | 2027-04-15 | 3 | 0
50 | I030.05 | ICG-ICP LD | Package acceptance | 2027-04-16 | 2027-04-17 | 2 | 0
51 | I030 | ICG-ICP LD | Install, connect, inspect and accept replacement bridge - phase complete | 2027-04-18 | 2027-04-18 | 0 | 0
52 | D030.01 | OTHER BRIDGES | Other-bridge demolition quantity and release check | 2027-04-18 | 2027-04-19 | 2 | 0
53 | D030.02 | OTHER BRIDGES | Approved residual removal | 2027-04-20 | 2027-04-22 | 3 | 0
54 | D030.03 | OTHER BRIDGES | Waste/backload and records | 2027-04-23 | 2027-04-24 | 2 | 0
55 | D030 | OTHER BRIDGES | Other removal, waste backload and allocated demolition closure - phase complete | 2027-04-25 | 2027-04-25 | 0 | 0
56 | O090.01 | ALL | Final offshore walkdowns | 2027-04-25 | 2027-04-27 | 3 | 0
57 | O090.02 | ALL | Acceptance-critical punch closure | 2027-04-28 | 2027-04-30 | 3 | 0
58 | O090.03 | ALL | Operational acceptance records | 2027-05-01 | 2027-05-01 | 1 | 0
59 | O090 | ALL | Final offshore inspections, punch closure and operational acceptance - phase complete | 2027-05-02 | 2027-05-02 | 0 | 0
60 | M100 | ALL | Planned offshore works complete | 2027-05-02 | 2027-05-02 | 0 | 0
61 | C010.01 | ALL | As-built and red-line consolidation | 2027-05-02 | 2027-05-11 | 10 | 0
62 | C010.02 | ALL | Quality and commissioning dossiers | 2027-05-12 | 2027-05-21 | 10 | 0
63 | C010.03 | ALL | Accepted measurement and e-MB records | 2027-05-22 | 2027-05-26 | 5 | 0
64 | C010.04 | ALL | Handover submission | 2027-05-27 | 2027-05-31 | 5 | 0
65 | C010 | ALL | As-built dossiers, e-MB records, QA records and handover compilation - phase complete | 2027-06-01 | 2027-06-01 | 0 | 0
66 | C020.01 | ALL | Client review and comments | 2027-06-01 | 2027-06-07 | 7 | 0
67 | C020.02 | ALL | Document and residual acceptance closure | 2027-06-08 | 2027-06-12 | 5 | 0
68 | C020.03 | ALL | Completion certificate processing | 2027-06-13 | 2027-06-14 | 2 | 0
69 | C020 | ALL | Final document review and completion certificate processing - phase complete | 2027-06-15 | 2027-06-15 | 0 | 0
70 | M200 | ALL | Internal target: all works complete and handover accepted | 2027-06-15 | 2027-06-15 | 0 | 0

## Milestones
ID | Milestone boundary | Threecrewscenario | Twocrewscenario | Status
M000 | Assumed NOA / commencement | 2026-11-01 | 2026-11-01 | Conditionalscenario
E030 | Detailed design, AFC drawings and ITP approval - phase complete | 2026-12-24 | 2026-12-24 | Conditionalscenario
P010 | Vendor approval, steel purchase and phased yard delivery - phase complete | 2027-01-03 | 2027-01-03 | Conditionalscenario
F010 | Fabricate, NDT, dimensional inspection and coating - phase complete | 2027-02-07 | 2027-02-07 | Conditionalscenario
F020 | Fabricate, NDT, dimensional inspection and coating - phase complete | 2027-02-27 | 2027-02-27 | Conditionalscenario
F030 | Fabricate, NDT, dimensional inspection and coating - phase complete | 2027-03-19 | 2027-03-19 | Conditionalscenario
I010 | Install, connect, inspect and accept replacement bridge - phase complete | 2027-03-02 | 2027-03-02 | Conditionalscenario
I020 | Install new bridge, transfer services and commission - phase complete | 2027-03-24 | 2027-03-24 | Conditionalscenario
D020 | Isolate, dismantle old bridge and remove to shore - phase complete | 2027-03-31 | 2027-03-31 | Conditionalscenario
I030 | Install, connect, inspect and accept replacement bridge - phase complete | 2027-04-18 | 2027-04-18 | Conditionalscenario
M100 | Planned offshore works complete | 2027-05-02 | 2027-05-13 | Conditionalscenario
O100 | Offshore demobilisation - phase complete | 2027-05-15 | 2027-11-05 | Conditionalscenario
M200 | Internal target: all works complete and handover accepted | 2027-06-15 | 2027-11-19 | Conditionalscenario

## Delay Sensitivity
ExtraP 010.02 days | Offshoremilestone | Demobboundary | Overallmilestone | Calendaroverrundays
0 | 2027-05-02 | 2027-05-15 | 2027-06-15 | 0
1 | 2027-05-03 | 2027-05-16 | 2027-06-16 | 0
3 | 2027-05-05 | 2027-10-18 | 2027-11-01 | 1
4 | 2027-05-06 | 2027-10-19 | 2027-11-02 | 2
7 | 2027-05-09 | 2027-10-29 | 2027-11-12 | 12
14 | 2027-05-16 | 2027-10-29 | 2027-11-12 | 12

## Quality ITP Basis
ID | Stage | Verification | Sourcebasis | Responsibility | Release
Q01 | Materials | MTC/identity/grade/dimensions and specified tests | Applicable IRT/specification | QA / CA/TPI as applicable | HOLDpendingapproved ITP
Q02 | Weldingreadiness | WPS/PQR/welderqualifications/consumables | FS2009F Rev 8 | QA / Weldingengineer | Beforeproduction
Q03 | Fit-up | Geometry/gaps/alignment/preparation | Approveddrawings/WPS | FabricationQA | Beforewelding
Q04 | Weld/NDT | Method/extent/acceptance and repairclosure | FS2009F/approved ITP | QualifiedNDT/QA | Nopercentageinvented
Q05 | Dimensions | Coordinates/tolerances/interfacefit | Approveddrawings/procedure | Survey/QA | Beforecoating/loadout
Q06 | Coating | Surfaceprep/environment/DFT/repairs | FS2005/approvedsystem/IRT | Coatinginspector | Beforepreservation/release
Q07 | Loadout | Release/weight/COG/transportconfiguration | Approvedmarineengineering | Marine/QA/MWSasrequired | Sail-awaygate
Q08 | Offshoreconnections | Fit-up/weld/bolt/inspection/restoration | Approvedwork pack/ITP | OffshoreQA | Beforeacceptance
Q09 | Commissioning | Specifiedtests/operationalrecords | Approvedtestprocedures | Completions/ONGC | Beforehandover
Q10 | Turnover | Dossier/punch/quantities/as-builts | Contractacceptanceindex | QA/ONGC | Clientacceptance

## Commissioning
ID | Discipline | Scope | Requiredchecks | Procedurebasis | Owner | Status
C01 | Structural readiness | All | Acceptedconnections;dimensions;grating;handrails;access;coating | Approvedstructuralchecks/ITP | QA / Construction | Open
C02 | Bearings and movements | Newbridges | Position/guideclearance/setting and protection perapproved details | Approvedbearinginstallationrequirements | Engineering/QA | Open
C03 | Electrical | Applicablebridgecircuits | Continuity/insulation/earthing/lighting and other specifiedchecks | Approvedelectricalprocedures;valuesfromspecification | Electrical/ONGC | Open
C04 | Instrumentation | ApplicableBHSinterfaces | Loop/function/control verification and restoration | Approvedinstrumentprocedures | Instrumentation/ONGC | Open
C05 | Piping | ApplicableBHSsystems | Inspection;pressure/leaktest as specified;cleaning/reinstatement | Approvedline-specificprocedures;notassumedtestpressures | Piping/ONGC | Open
C06 | Service transfer | BHS-SLQ | Approvedisolations;tie-ins;functionalacceptance;contingency | ONGCoperational release | Commissioning/ONGC | Open
C07 | Demolition release | BHS-SLQ | Newbridgeandservicesaccepted;temporary-stabilityandisolationverified | Signeddemolitionreadinessgate | Technical Authority/ONGC | Hold
C08 | Safety/lifesaving interfaces | Applicablelandings | Muster/access/lifesavingrequirementsandsafetystudyactions | Approvedvendorandoperationalrequirements | HSE/Marine/ONGC | Open
C09 | Punch clearance | All | Closeacceptance-criticalitems;recordauthorisedresidualitems | Agreedpunch classification | Completions/ONGC | Open
C10 | Handover / e-MB | All | Acceptedquantities;as-builts;quality/test records;certificates | Contractualacceptanceandbillingrequirements | QA/Contracts/ONGC | Open

## Release Gates
Gate | Release | Evidence | Authority
G0 | Mobilisationauthority | Award/start/funding/leadership | Project Director/Contracts
G1 | Scope/surveybasis | Acceptedcoverage;quantityandinterfaceregister | Engineering
G2 | Engineeringrelease | Checkedcalculations;drawingreviews;resolvedcriticalqueries | Technical Authority/ONGCasrequired
G3 | Procurementrelease | Approvedrequisition/vendor/funding/inspection | Procurement/Engineering
G4 | Fabricationreadiness | AFCstatuswhere required;materials;procedures;ITP | Engineering/QA/Fabrication
G5 | Yardrelease | NDT/dimensions/coating/NCRclosure/traceability | QA
G6 | Marinereadiness | Suitablevessels;verifiedweights;lift/transportengineering;assurance | Marine/competentauthorities
G7 | Offshorework | Workpack;permits;SIMOPS;isolations;people/tools/access | Construction/ONGC
G8 | Demolition | Newbridge/servicesaccepted;stability/isolation/removalapproved | Technical Authority/ONGC
G9 | Handover | Acceptedwork/punch/dossiers/e-MB/certificates | ONGCacceptanceauthority

## Risks and Actions
ID | Risk | Priority | Owner | Action | Timing
R01 | ActualNOAunconfirmed | Critical | Contracts | Rebaseallcalendars/dates;do notshiftlinearlyacrossmonsoon | Beforebaseline
R02 | Threequantitydiscrepancies | High | Engineering/QS | Resolve 1 MTsteel,2 mhandrail,1 m 2 grating;preserveprintedandrows | Beforeprocurement
R03 | BHScriticalpath | Critical | Project Director | Protectmaterial/fabrication/service transfer/lift/demolitionchain | Weekly
R04 | Only 3 dayscalendarfloatforseveraloffshorecriticalactivitiesagainstunextended deadline | Critical | Planning/Marine | Do notinterpret 139 dayshandover headroomasoffshorefloat;weatherbarrierlimitsrecovery | Weekly
R05 | Thirdstrengtheningcrewuncommitted | High | Construction | Securecompletecrew/supportcapacityoradopttwo-seasonforecast | Beforemobilisation
R06 | Yard/QA/coatingcapacityunverified | High | Fabrication/QA | Auditbays/people/inspection/coating/loadout;validateallrates | Beforecommitment
R07 | Marinewindowandweightsunknown | Critical | Marine | Verifylift weights/COG/cranes/radii/vessels/availability | Beforecharter
R08 | EngineeringanddrawingsnotAFC | Critical | Engineering | Reconstructmodel;completechecking;resolveinputs;maintainrelease gates | Beforefabrication
R09 | Actualservice-loadsandmovementspending | Critical | Engineering | Reconcilepipingfutureallowance,LLareas,camber and supportrestraints | Beforedesignfreeze
R10 | Operationalaccess/SIMOPS | Critical | Offshore/ONGC | Agreeaccess,isolations,shutdowns,transferwindowsandemergencyarrangements | Six-weeklook-ahead
R11 | Cost/financeunpriced | High | Finance | Populatequotes,charters,bankmargins,billinglags,taxandfunding | Beforecommitment
R12 | Specialequipmentlead time | High | Procurement | Validatebearings/lifeboat/services;25 daybulklead timeisnotproof | Beforebaseline
R13 | Monsoonrelief/costexposure | High | Contracts | Compliantnotices;extensionreview;standby/remob/demobcosts | Beforeimpact
R14 | Other-projectscopecontamination | High | DocumentControl | UseBRRP-specificPart II;checkallimportedscope | Eachrelease
R15 | Second-seasoncomparator | High | Marine/Planning | 7 dayremobassumed;all capacity/cost/revalidationmustbeconfirmed | Beforeadoptingscenario

## Cost Input Register
Costcode | Category | ApprovedbudgetINR | CommittedINR | ActualINR | RemainingforecastINR | Status | ForecastcompletionINR
CST-01 | Engineering/surveys |  |  |  |  | UNPRICED; quotations and allocation required
CST-02 | Structuralmaterials |  |  |  |  | UNPRICED; quotations and allocation required
CST-03 | Fabrication |  |  |  |  | UNPRICED; quotations and allocation required
CST-04 | Coating |  |  |  |  | UNPRICED; quotations and allocation required
CST-05 | QA/NDT |  |  |  |  | UNPRICED; quotations and allocation required
CST-06 | Loadout/shorebase |  |  |  |  | UNPRICED; quotations and allocation required
CST-07 | Heavy-liftspread |  |  |  |  | UNPRICED; quotations and allocation required
CST-08 | Accommodation/support |  |  |  |  | UNPRICED; quotations and allocation required
CST-09 | Cargo/towage/supply |  |  |  |  | UNPRICED; quotations and allocation required
CST-10 | Offshorelabour |  |  |  |  | UNPRICED; quotations and allocation required
CST-11 | Services/commissioning |  |  |  |  | UNPRICED; quotations and allocation required
CST-12 | Demolition/disposal |  |  |  |  | UNPRICED; quotations and allocation required
CST-13 | Insurance/guarantees |  |  |  |  | UNPRICED; quotations and allocation required
CST-14 | Projectoverheads |  |  |  |  | UNPRICED; quotations and allocation required
CST-15 | Riskcontingency |  |  |  |  | UNPRICED; quotations and allocation required
CST-16 | Taxes/financing |  |  |  |  | UNPRICED; quotations and allocation required

## Overall Weekly Gantt
Phase | Bridge | Start | Lastworkday | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-06 | 2026-12-13 | 2026-12-20 | 2026-12-27 | 2027-01-03 | 2027-01-10 | 2027-01-17 | 2027-01-24 | 2027-01-31 | 2027-02-07 | 2027-02-14 | 2027-02-21 | 2027-02-28 | 2027-03-07 | 2027-03-14 | 2027-03-21 | 2027-03-28 | 2027-04-04 | 2027-04-11 | 2027-04-18 | 2027-04-25 | 2027-05-02 | 2027-05-09 | 2027-05-16 | 2027-05-23 | 2027-05-30 | 2027-06-06 | 2027-06-13 | 2027-06-20 | 2027-06-27 | 2027-07-04 | 2027-07-11 | 2027-07-18 | 2027-07-25 | 2027-08-01 | 2027-08-08 | 2027-08-15 | 2027-08-22 | 2027-08-29 | 2027-09-05 | 2027-09-12 | 2027-09-19 | 2027-09-26 | 2027-10-03 | 2027-10-10 | 2027-10-17 | 2027-10-24 | 2027-10-31 | 2027-11-07 | 2027-11-14 | 2027-11-21 | 2027-11-28 | 2027-12-05
G010 | COMMON | 2026-11-01 | 2026-11-07 | ■
E010 | COMMON | 2026-11-08 | 2026-11-21 |  | ■ | ■
G020 | COMMON | 2026-11-08 | 2026-11-21 |  | ■ | ■
MR10 | COMMON | 2026-11-08 | 2026-12-12 |  | ■ | ■ | ■ | ■ | ■
S010 | COMMON | 2026-11-08 | 2026-11-14 |  | ■
S020 | ALL | 2026-11-15 | 2026-11-28 |  |  | ■ | ■
E020 | ALL | 2026-11-29 | 2026-12-08 |  |  |  |  | ■ | ■
E030 | REPLACEMENTS | 2026-11-29 | 2026-12-23 |  |  |  |  | ■ | ■ | ■ | ■
E040 | REFURBISHMENTS | 2026-11-29 | 2026-12-23 |  |  |  |  | ■ | ■ | ■ | ■
E050 | BHS-SLQ | 2026-11-29 | 2027-01-02 |  |  |  |  | ■ | ■ | ■ | ■ | ■
MR20 | REPLACEMENTS | 2026-12-24 | 2027-01-27 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■
P010 | ALL | 2026-12-09 | 2027-01-02 | [5 empty] | ■ | ■ | ■ | ■
F010 | ICW-ICG LD | 2027-01-03 | 2027-02-06 | [9 empty] | ■ | ■ | ■ | ■ | ■
F020 | BHS-SLQ | 2027-01-03 | 2027-02-26 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
F030 | ICG-ICP LD | 2027-02-07 | 2027-03-18 | [14 empty] | ■ | ■ | ■ | ■ | ■ | ■
F040 | ALL STRENGTHENING | 2027-01-03 | 2027-02-06 | [9 empty] | ■ | ■ | ■ | ■ | ■
L010 | ICW-ICG LD | 2027-02-07 | 2027-02-11 | [14 empty] | ■
L020 | BHS-SLQ | 2027-02-27 | 2027-03-03 | [16 empty] | ■ | ■
L030 | ICG-ICP LD | 2027-03-19 | 2027-03-23 | [19 empty] | ■ | ■
O010 | ALL | 2027-01-23 | 2027-02-01 | [11 empty] | ■ | ■ | ■
H010 | COMMON | 2027-02-02 | 2027-02-08 | [13 empty] | ■ | ■
J010 | ICG / BHS | 2027-02-02 | 2027-02-13 | [13 empty] | ■ | ■
I010 | ICW-ICG LD | 2027-02-14 | 2027-03-01 | [15 empty] | ■ | ■ | ■
I020 | BHS-SLQ | 2027-03-04 | 2027-03-23 | [17 empty] | ■ | ■ | ■ | ■
D020 | BHS-SLQ | 2027-03-24 | 2027-03-30 | [20 empty] | ■ | ■
J020 | ICP | 2027-02-02 | 2027-02-11 | [13 empty] | ■ | ■
I030 | ICG-ICP LD | 2027-03-31 | 2027-04-17 | [21 empty] | ■ | ■ | ■
RA01 | ICW-ICG UD | 2027-02-14 | 2027-03-01 | [15 empty] | ■ | ■ | ■
RA02 | ICG-ICP UD | 2027-03-02 | 2027-03-23 | [17 empty] | ■ | ■ | ■ | ■
RA03 | SLQ-WIS | 2027-03-24 | 2027-04-10 | [20 empty] | ■ | ■ | ■
RA04 | NQO-NQD | 2027-02-07 | 2027-02-24 | [14 empty] | ■ | ■ | ■
RB01 | WIN-NC | 2027-02-12 | 2027-02-23 | [14 empty] | ■ | ■ | ■
RB02 | SCA-SC1 | 2027-02-24 | 2027-03-11 | [16 empty] | ■ | ■ | ■
RB03 | SCA-SCF | 2027-03-12 | 2027-04-04 | [18 empty] | ■ | ■ | ■ | ■ | ■
D030 | OTHER BRIDGES | 2027-04-18 | 2027-04-24 | [24 empty] | ■
O090 | ALL | 2027-04-25 | 2027-05-01 | [25 empty] | ■
C010 | ALL | 2027-05-02 | 2027-05-31 | [26 empty] | ■ | ■ | ■ | ■ | ■
W010 | ALL | 2027-05-02 | 2027-05-11 | [26 empty] | ■ | ■
O100 | ALL | 2027-05-12 | 2027-05-14 | [27 empty] | ■
C020 | ALL | 2027-06-01 | 2027-06-14 | [30 empty] | ■ | ■ | ■