## A-Z Closure Register
ID | Workstream | Outstanding action | Responsible role | Required basis | Need-by gate | Closure evidence | Current evidence status | Next control
A01 | A - Award, dates and contractual obligations | Confirm actual NOA, contractual commencement, milestones and completion convention. | Contracts Manager | GCC/SCC, executed contract and controlling amendments | Before baseline or binding commitment | Controlled award/date record and obligations register. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
A02 | A - Award, dates and contractual obligations | Confirm warranty, securities, insurance, payment, LD and notification provisions. | Contracts Manager | GCC/SCC, executed contract and controlling amendments | Before baseline or binding commitment | Clause-by-clause commercial obligations with owners and due dates. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
A03 | A - Award, dates and contractual obligations | Resolve document precedence and all applicable addenda; distinguish BRRP from other projects. | Contracts Manager | GCC/SCC, executed contract and controlling amendments | Before baseline or binding commitment | Approved contract/source hierarchy and amendment register. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
A04 | A - Award, dates and contractual obligations | Confirm project funding authority and limits for purchases, subcontracts and charters. | Contracts Manager | GCC/SCC, executed contract and controlling amendments | Before baseline or binding commitment | Named delegation of authority and funding authorisation. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
B01 | B - Bridge scope and quantity reconciliation | Freeze inclusions/exclusions for all 10 bridges, landings, services, temporary works and demolition. | Engineering Manager / Quantity Surveyor | B774 scope, MTO p 1, drawings and addenda | Before purchase quantities are frozen | Signed bridge scope/interface matrix. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
B02 | B - Bridge scope and quantity reconciliation | Reconcile structural row total 1141 MT with printed 1142 MT; landing-strengthening rows 216 versus 217 MT. | Engineering Manager / Quantity Surveyor | B774 scope, MTO p 1, drawings and addenda | Before purchase quantities are frozen | Traceable corrected or confirmed MTO revision; original retained. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
B03 | B - Bridge scope and quantity reconciliation | Reconcile handrail 1166 m versus 1168 m and grating 718 m 2 versus 719 m 2. | Engineering Manager / Quantity Surveyor | B774 scope, MTO p 1, drawings and addenda | Before purchase quantities are frozen | Drawing-based dimensional quantity reconciliation. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
B04 | B - Bridge scope and quantity reconciliation | Check whether ICG/ICP/BHS addendum wraps and other work are already included in tender quantities. | Engineering Manager / Quantity Surveyor | B774 scope, MTO p 1, drawings and addenda | Before purchase quantities are frozen | Inclusion map preventing omissions and double counting. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
C01 | C - Leadership, capability and resources | Assign named Project Director, discipline leads, deputies, checkers and package owners. | Project Director | P5 organisation, work packages and resource scenario | Before delivery commitments | Organisation/RACI with availability and authority. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
C02 | C - Leadership, capability and resources | Audit actual engineering, fabrication, QA/coating and offshore workforce capacity against competing work. | Project Director | P5 organisation, work packages and resource scenario | Before delivery commitments | Capacity audit and committed resource calendar. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
C03 | C - Leadership, capability and resources | Verify candidate vessels through ownership/charter status, particulars, certificates and project suitability. | Project Director | P5 organisation, work packages and resource scenario | Before delivery commitments | Asset-verification and commitment records; website claims alone insufficient. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
C04 | C - Leadership, capability and resources | Confirm third strengthening crew, installation team, support/inspection and peak POB/accommodation capacity. | Project Director | P5 organisation, work packages and resource scenario | Before delivery commitments | Resourced work-front plan and crew/support mobilisation commitments. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
D01 | D - Application of the supplied design criteria | Issue project application register for 25 yearlife, codes/editions, materials and design conditions. | Engineering Manager / Technical Authority | DC3.4 PartI Rev 14, BRRP PartII and specifications | Before design freeze | Approved design-basis application matrix; full criteria are already supplied. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
D02 | D - Application of the supplied design criteria | Apply 250 kg/m2 global walkway and 500 kg/m2 local grating loads to the correct elements. | Engineering Manager / Technical Authority | DC3.4 PartI Rev 14, BRRP PartII and specifications | Before design freeze | Load definition, area maps and local/global distinction. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
D03 | D - Application of the supplied design criteria | Reconcile wind gust duration and elevation:15 sec for 56/84 m studies and 3 sec for 42 m. | Engineering Manager / Technical Authority | DC3.4 PartI Rev 14, BRRP PartII and specifications | Before design freeze | Documented wind derivation from applicable MH environmental parameters. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
D04 | D - Application of the supplied design criteria | Confirm contingencies, corrosion zone treatment, fatigue/VIV, piping 20% future allowance and material requirements. | Engineering Manager / Technical Authority | DC3.4 PartI Rev 14, BRRP PartII and specifications | Before design freeze | Calculation assumptions showing which allowances are included; no double counting. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
E01 | E - Survey and existing condition | Verify bridge bearing centres, levels, skew, grid references and coordinate/datum system. | Survey Lead / Engineering | Source reports, tender drawings and approved survey scope | Before final dimensions or existing-capacity checks | Accepted survey coordinates;56/84/42 m remain study lengths until reconciled. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
E02 | E - Survey and existing condition | Verify existing members, wall thickness, connections, supports and corrosion using specified inspections. | Survey Lead / Engineering | Source reports, tender drawings and approved survey scope | Before final dimensions or existing-capacity checks | Condition/UT/NDT register with inaccessible areas identified. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
E03 | E - Survey and existing condition | Verify live piping/cables, clearances, access, adjacent bridge and lifeboat/muster interfaces. | Survey Lead / Engineering | Source reports, tender drawings and approved survey scope | Before final dimensions or existing-capacity checks | Coordinated existing-services and installation-clearance survey. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
E04 | E - Survey and existing condition | Resolve tender drawing references and update existing-condition markups for all work fronts. | Survey Lead / Engineering | Source reports, tender drawings and approved survey scope | Before final dimensions or existing-capacity checks | Controlled survey/as-built input pack with engineering acceptance. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
F01 | F - Global structural design | Obtain native source models or reconstruct models from verified coordinates, connectivity and section groups. | Structural Analysis Lead | Accepted geometry, criteria, loads and source studies | Before member schedules or reaction release | Documented reproducible model; native files are not the only possible route. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
F02 | F - Global structural design | Verify restraints, offsets, releases, stiffness, existing-platform movement and local/global axes. | Structural Analysis Lead | Accepted geometry, criteria, loads and source studies | Before member schedules or reaction release | Model-validation and support-philosophy record. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
F03 | F - Global structural design | Reconcile source gravity/live-load totals, load maps, allowances and all governing combinations. | Structural Analysis Lead | Accepted geometry, criteria, loads and source studies | Before member schedules or reaction release | Applied-load/reaction equilibrium checks and model revision log. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
F04 | F - Global structural design | Run and independently check strength, stability, deflection, vibration and applicable fatigue results. | Structural Analysis Lead | Accepted geometry, criteria, loads and source studies | Before member schedules or reaction release | Checked analysis report and complete signed result envelopes; source UC tables alone insufficient. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
G01 | G - Member, joint and connection engineering | Select and verify chords, braces, crossframes and walkway beams for applicable resistance and stability. | Structural Detail Lead / Checker | Checked global actions and material specifications | Before fabrication drawings | Member/group schedule with effective lengths, forces and code checks. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
G02 | G - Member, joint and connection engineering | Design tubular joints, gussets, stiffeners, end connections, bolts and welds for actual actions. | Structural Detail Lead / Checker | Checked global actions and material specifications | Before fabrication drawings | Local connection calculations and calculation-linked details. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
G03 | G - Member, joint and connection engineering | Verify fatigue-sensitive details, stress concentrations, inspectability and material toughness/weldability. | Structural Detail Lead / Checker | Checked global actions and material specifications | Before fabrication drawings | Detail-category and inspection provisions tied to design. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
G04 | G - Member, joint and connection engineering | Resolve camber from verified dead-load response and setting geometry; reconcile source 1:200 instruction. | Structural Detail Lead / Checker | Checked global actions and material specifications | Before fabrication drawings | Dimensioned camber profile, datum, tolerances and checking record. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
H01 | H - Bearings, landings, decks and jackets | Resolve hinged/pinned/sliding freedoms including contradictory SLQ wording; fixed intent is not moment-rigid. | Structural / Platform Engineer | Concurrent reactions, survey, movements and addendum | Before support procurement or modification | Approved support philosophy and consistent analysis/drawing terminology. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
H02 | H - Bearings, landings, decks and jackets | Calculate movement and axial thrust using specified 150% requirements; design guides, uplift and friction. | Structural / Platform Engineer | Concurrent reactions, survey, movements and addendum | Before support procurement or modification | Bearing travel/action envelopes, compatible rotations and bearing/guide calculations. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
H03 | H - Bearings, landings, decks and jackets | Check bearing seats, landing extensions, existing beams, joints, decks and jackets under concurrent load cases. | Structural / Platform Engineer | Concurrent reactions, survey, movements and addendum | Before support procurement or modification | Integrated existing-structure adequacy and strengthening report. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
H04 | H - Bearings, landings, decks and jackets | Engineer ICG/ICP/BHS wrap strengthening, fit-up, local load transfer, welds and temporary conditions. | Structural / Platform Engineer | Concurrent reactions, survey, movements and addendum | Before support procurement or modification | Checked strengthening drawings/MTO; ideal shell mass is not a capacity check. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
I01 | I - Detailed drawings and AFC control | Complete dimensioned GAs, framing, sections, connections, bearings, landings, access and service details. | Engineering Manager / Document Controller | Checked calculations and agreed interface reviews | Before construction release | Controlled drawing set with source survey/calculation references. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
I02 | I - Detailed drawings and AFC control | Complete missing 101/102 main arrangements and 0005 references and 103-series landing/demolition details. | Engineering Manager / Document Controller | Checked calculations and agreed interface reviews | Before construction release | Resolved drawing register; authorised reconstructed/new drawings where required. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
I03 | I - Detailed drawings and AFC control | Complete discipline checking, independent/technical review, interface clearance and applicable ONGC review. | Engineering Manager / Document Controller | Checked calculations and agreed interface reviews | Before construction release | Closed review comments and actual approval evidence. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
I04 | I - Detailed drawings and AFC control | Authorise issue purpose, signatures and controlled transmittals; withdraw superseded sheets. | Engineering Manager / Document Controller | Checked calculations and agreed interface reviews | Before construction release | Actual AFC release record when later authorised; no invented stamp/date/signature. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
J01 | J - Final MTO and material control | Prepare member/plate/component schedules with grade, size, cut length, finish and drawing revision. | Engineering / Procurement / QA | Released detailed drawings and measurement rules | Before final orders and throughout execution | Detailed bridge-specific purchasing MTO. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
J02 | J - Final MTO and material control | Develop grating/handrail/sheeting/service/bolt/weld/coating quantities from actual details. | Engineering / Procurement / QA | Released detailed drawings and measurement rules | Before final orders and throughout execution | Discipline MTOs; coating area and paint volume not inferred from tonnage. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
J03 | J - Final MTO and material control | Separate permanent steel, temporary works, rigging/sea-fastening and demolition; set justified allowances. | Engineering / Procurement / QA | Released detailed drawings and measurement rules | Before final orders and throughout execution | Reconciled take-off, inclusion map and approved wastage rules. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
J04 | J - Final MTO and material control | Implement receipt, heat/mark traceability, preservation, issue, installed quantity, surplus and returns. | Engineering / Procurement / QA | Released detailed drawings and measurement rules | Before final orders and throughout execution | Material ledger and certificates traceable to installed work. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
K01 | K - Procurement and subcontracts | Obtain compliant quotations and technical/commercial evaluations for all 25 packages. | Procurement / Commercial Manager | P5 procurement packages, approved requisitions and funding | Before supplier commitments | Approved bid comparisons, technical acceptance and actual lead times. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
K02 | K - Procurement and subcontracts | Verify vendor/yard/subcontract commitments and applicable client acceptance under amended provisions. | Procurement / Commercial Manager | P5 procurement packages, approved requisitions and funding | Before supplier commitments | Capacity commitments and required subcontractor letters/approvals. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
K03 | K - Procurement and subcontracts | Issue authorised orders/charters with specifications, inspection, documentation, schedule and change terms. | Procurement / Commercial Manager | P5 procurement packages, approved requisitions and funding | Before supplier commitments | Executed purchase/subcontract documents; no order has been evidenced here. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
K04 | K - Procurement and subcontracts | Expedite manufacture, inspections, dispatch and receipt; track bearings/lifesaving/services long leads. | Procurement / Commercial Manager | P5 procurement packages, approved requisitions and funding | Before supplier commitments | Supplier progress evidence and updated procurement dates integrated into schedule. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
L01 | L - Yard readiness and fabrication | Confirm bays, cranes, loadout access, workforce, coating and NDT capacity with competing jobs. | Fabrication Manager | Released shop work packs, accepted material, qualified procedures | Before production and module release | Audited production-capacity and yard logistics plan. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
L02 | L - Yard readiness and fabrication | Prepare and execute cutting, fit-up, assembly, welding and dimensional-control work packs. | Fabrication Manager | Released shop work packs, accepted material, qualified procedures | Before production and module release | Traceable production records and approved procedure compliance. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
L03 | L - Yard readiness and fabrication | Complete specified NDT, repair/retest, dimensional acceptance and suitable trial fit. | Fabrication Manager | Released shop work packs, accepted material, qualified procedures | Before production and module release | Accepted inspection records and release-critical NCR closure. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
L04 | L - Yard readiness and fabrication | Complete approved coating, preservation, marking and fabrication dossier. | Fabrication Manager | Released shop work packs, accepted material, qualified procedures | Before production and module release | QA module/kit release with accepted actual quantities and dimensions. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
M01 | M - Quality assurance and inspection | Approve item-specific ITP/QAP, hold/witness points, inspection responsibilities and notices. | QA/QC Manager | Specifications, source IRT and project ITP | Before manufacture and each release | Authorised inspection matrix; no generic NDT percentage substituted. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
M02 | M - Quality assurance and inspection | Verify personnel/procedures, welding qualifications, consumables, calibration and material certificates. | QA/QC Manager | Specifications, source IRT and project ITP | Before manufacture and each release | Competence, procedure and equipment evidence. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
M03 | M - Quality assurance and inspection | Complete inspections, nonconformances, concessions and corrective actions with competent review. | QA/QC Manager | Specifications, source IRT and project ITP | Before manufacture and each release | Accepted inspection/NCR/concession records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
M04 | M - Quality assurance and inspection | Compile material, weld/NDT, dimensional, coating and release dossiers progressively. | QA/QC Manager | Specifications, source IRT and project ITP | Before manufacture and each release | Complete traceable quality dossier for each bridge/module. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
N01 | N - Marine engineering and spread commitment | Select technically suitable heavy-lift, cargo, support, accommodation, towage and supply resources. | Marine Manager / Marine Engineer | Verified modules, route, field interfaces and vessel data | Before charter/loadout/sail-away | Suitability assessments and availability/charter commitments. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
N02 | N - Marine engineering and spread commitment | Complete loadout, grillage, sea-fastening, transport stability/motions and barge/deck checks. | Marine Manager / Marine Engineer | Verified modules, route, field interfaces and vessel data | Before charter/loadout/sail-away | Checked transport/loadout engineering and applicable marine assurance. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
N03 | N - Marine engineering and spread commitment | Define field positioning, moves, transfers, POB, logistics, operational limits and weather decisions. | Marine Manager / Marine Engineer | Verified modules, route, field interfaces and vessel data | Before charter/loadout/sail-away | Integrated marine campaign and emergency arrangements. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
N04 | N - Marine engineering and spread commitment | Secure required certification, port/statutory/field permissions and assurance releases as applicable. | Marine Manager / Marine Engineer | Verified modules, route, field interfaces and vessel data | Before charter/loadout/sail-away | Valid certificates/permissions and signed readiness records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
O01 | O - Lifting and temporary conditions | Verify module boundaries, actual weight/COG and crane capability at operating radius/configuration. | Lifting / Temporary-Works Engineer | Verified weight/COG, crane/radius and sequence | Before any lift or temporary load-path change | Weight control/weighing and lift-feasibility report. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
O02 | O - Lifting and temporary conditions | Analyse rigging geometry, skew/dynamics, adverse COG/weight and lift-point/local effects. | Lifting / Temporary-Works Engineer | Verified weight/COG, crane/radius and sequence | Before any lift or temporary load-path change | Checked lift model, lifting-point/spreader/rigging design. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
O03 | O - Lifting and temporary conditions | Engineer erection stability, temporary supports, guides, scaffolding/handling interfaces and removal stages. | Lifting / Temporary-Works Engineer | Verified weight/COG, crane/radius and sequence | Before any lift or temporary load-path change | Checked temporary-work drawings and authorised sequences. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
O04 | O - Lifting and temporary conditions | Approve operation-specific lift/landing method, weather window, communications and contingency. | Lifting / Temporary-Works Engineer | Verified weight/COG, crane/radius and sequence | Before any lift or temporary load-path change | Technical/operational go/no-go release; management schedule is not lift approval. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
P01 | P - Shore-base and offshore logistics | Establish storage, preservation, handling, manifests and required customs/transport arrangements. | Logistics / Marine Manager | Cargo schedule, release records and support capacity | Before sail-away and continuously | Shore-base procedure and traceable cargo register. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
P02 | P - Shore-base and offshore logistics | Deliver complete bridge kits, tools, consumables, inspection equipment and critical spares. | Logistics / Marine Manager | Cargo schedule, release records and support capacity | Before sail-away and continuously | Work-pack completeness and offshore receipt checks. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
P03 | P - Shore-base and offshore logistics | Coordinate personnel transfers, rotations, accommodation, supply and field moves with actual demand. | Logistics / Marine Manager | Cargo schedule, release records and support capacity | Before sail-away and continuously | Integrated POB/transfer/supply calendar. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
P04 | P - Shore-base and offshore logistics | Execute backload, waste segregation/disposal, equipment returns and surplus reconciliation. | Logistics / Marine Manager | Cargo schedule, release records and support capacity | Before sail-away and continuously | Accepted backload/disposal/return records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Q01 | Q - Replacement-bridge offshore installation | Close access, permits, isolations, SIMOPS, crew/tool/material and emergency prerequisites. | Offshore Construction Manager | Released work pack, landing/jacket readiness and marine approval | Before and during installation | Signed work-front readiness and applicable ONGC authorisation. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Q02 | Q - Replacement-bridge offshore installation | Execute approved loadout/transport/lift/landing and maintain engineered temporary stability. | Offshore Construction Manager | Released work pack, landing/jacket readiness and marine approval | Before and during installation | Operation records with inspections and deviations controlled. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Q03 | Q - Replacement-bridge offshore installation | Complete permanent connections, bearings/guides, access fittings, services and coating restoration. | Offshore Construction Manager | Released work pack, landing/jacket readiness and marine approval | Before and during installation | Accepted permanent-work inspection/test records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Q04 | Q - Replacement-bridge offshore installation | Verify final dimensions/settings, accepted quantities and package punch closure. | Offshore Construction Manager | Released work pack, landing/jacket readiness and marine approval | Before and during installation | Client/QA acceptance evidence and as-built markups. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
R01 | R - Seven-bridge strengthening execution | Validate repair locations/thicknesses and live-service restrictions before each work front. | Offshore Construction / Technical Authority | Accepted condition survey and bridge-specific repair design | Before and during strengthening | Accepted scope markups and actual condition records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
R02 | R - Seven-bridge strengthening execution | Provide approved access, protection, temporary support and complete strengthening kits. | Offshore Construction / Technical Authority | Accepted condition survey and bridge-specific repair design | Before and during strengthening | Work-pack readiness and temporary-work release. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
R03 | R - Seven-bridge strengthening execution | Execute authorised member/joint/landing modifications, fittings replacement and restoration. | Offshore Construction / Technical Authority | Accepted condition survey and bridge-specific repair design | Before and during strengthening | Production and inspection records without unapproved load-path changes. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
R04 | R - Seven-bridge strengthening execution | Accept weld/NDT/dimensions/coating, remove temporary arrangements and close package punch. | Offshore Construction / Technical Authority | Accepted condition survey and bridge-specific repair design | Before and during strengthening | Bridge-specific acceptance and measured quantities for all seven packages. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
S01 | S - BHS service transfer and demolition | Freeze line/cable/loop lists, support loads, isolations, tie-ins and operational contingency. | Commissioning / Offshore / ONGC Operations | New-bridge engineering plus live-service and demolition plans | Before service transfer or old-bridge removal | Approved multidisciplinary transfer/commissioning package. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
S02 | S - BHS service transfer and demolition | Install and test new piping/electrical/instrument interfaces and obtain operational acceptance. | Commissioning / Offshore / ONGC Operations | New-bridge engineering plus live-service and demolition plans | Before service transfer or old-bridge removal | Signed test/reinstatement and service-transfer records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
S03 | S - BHS service transfer and demolition | Confirm new bridge/services accepted, redundant services isolated and demolition stability verified. | Commissioning / Offshore / ONGC Operations | New-bridge engineering plus live-service and demolition plans | Before service transfer or old-bridge removal | Formal demolition release and checked removal method. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
S04 | S - BHS service transfer and demolition | Execute authorised dismantling, backload/disposal and remaining-platform restoration. | Commissioning / Offshore / ONGC Operations | New-bridge engineering plus live-service and demolition plans | Before service transfer or old-bridge removal | Demolition completion, waste records and post-work acceptance. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
T01 | T - Testing and commissioning | Prepare system/bridge test packs, prerequisites, witnessing and discipline-specific acceptance values. | Completions Manager / Discipline Leads | Accepted construction and approved test boundaries/procedures | Before operational acceptance | Approved procedures; no invented test pressure, torque or electrical threshold. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
T02 | T - Testing and commissioning | Complete structural/bearing/access checks and applicable electrical/earthing/lighting tests. | Completions Manager / Discipline Leads | Accepted construction and approved test boundaries/procedures | Before operational acceptance | Accepted structural and electrical records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
T03 | T - Testing and commissioning | Complete applicable piping pressure/leak/cleaning/reinstatement and instrument loop/function tests. | Completions Manager / Discipline Leads | Accepted construction and approved test boundaries/procedures | Before operational acceptance | Line/loop-specific accepted test and reinstatement records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
T04 | T - Testing and commissioning | Complete operational checks, safety/lifesaving interfaces, punch classification and acceptance. | Completions Manager / Discipline Leads | Accepted construction and approved test boundaries/procedures | Before operational acceptance | ONGC operational acceptance and authorised residual-item register. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
U01 | U - Schedule, critical path and recovery | Rebase the 205 activity scenario to actual contract dates and verified supplier/approval durations. | Project Controls / Project Director | P5 scenario, actual NOA, quantities, commitments and workability | Before baseline approval; update weekly | Approved schedule basis, logic and milestones. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
U02 | U - Schedule, critical path and recovery | Load measured quantities, demonstrated productivity, crews, QA/coating, vessels and POB; level conflicts. | Project Controls / Project Director | P5 scenario, actual NOA, quantities, commitments and workability | Before baseline approval; update weekly | Capacity-backed resource-loaded schedule and histograms. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
U03 | U - Schedule, critical path and recovery | Validate offshore workability, safe seasonal stopping/revalidation, reserve and demobilisation strategy. | Project Controls / Project Director | P5 scenario, actual NOA, quantities, commitments and workability | Before baseline approval; update weekly | Defensible seasonal margin and contingency/recovery plan. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
U04 | U - Schedule, critical path and recovery | Update actuals, remaining durations, critical/near-critical paths, look-ahead constraints and forecasts. | Project Controls / Project Director | P5 scenario, actual NOA, quantities, commitments and workability | Before baseline approval; update weekly | Weekly accepted-progress update and authorised recovery decisions. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
V01 | V - Cost, cash, guarantees and collections | Price the 16 cost categories with committed/actual/remaining costs and controlled shared allocations. | Finance / Cost / Commercial Manager | Actual quotations, contract payment terms and financing | Before financial sanction; update monthly | Approved cost baseline and forecast at completion; blanks are not zero. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
V02 | V - Cost, cash, guarantees and collections | Model supplier/charter payments, standby/remob, taxes, bank margins, financing and risk contingency. | Finance / Cost / Commercial Manager | Actual quotations, contract payment terms and financing | Before financial sanction; update monthly | Full-duration cost/cash model and funding requirement. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
V03 | V - Cost, cash, guarantees and collections | Map billing to amended milestones, accepted measurements/e-MB, certification and collection dates. | Finance / Cost / Commercial Manager | Actual quotations, contract payment terms and financing | Before financial sanction; update monthly | Auditable invoice/certification/receipts register. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
V04 | V - Cost, cash, guarantees and collections | Confirm funding and guarantee/insurance capacity; monitor cash runway and overdue collections. | Finance / Cost / Commercial Manager | Actual quotations, contract payment terms and financing | Before financial sanction; update monthly | Financial authorisations, valid securities and updated cash forecast. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
W01 | W - HSE, permits and emergency readiness | Complete hazard reviews and task controls for lifting, hot work, height, dropped objects and live services. | HSE / Construction / Marine / ONGC | Approved work methods, actual spreads and operational interfaces | Before mobilisation and every operation | Approved risk assessments and resolved critical actions. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
W02 | W - HSE, permits and emergency readiness | Verify training, medical/competence, fatigue/rotation and relevant certification. | HSE / Construction / Marine / ONGC | Approved work methods, actual spreads and operational interfaces | Before mobilisation and every operation | Personnel readiness and supervision records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
W03 | W - HSE, permits and emergency readiness | Agree PTW/SIMOPS/isolations, emergency communications, rescue, medical evacuation and weather actions. | HSE / Construction / Marine / ONGC | Approved work methods, actual spreads and operational interfaces | Before mobilisation and every operation | Operational permits, drills and emergency-readiness evidence. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
W04 | W - HSE, permits and emergency readiness | Implement environmental/waste/spill controls, leadership checks, incident reporting and action closure. | HSE / Construction / Marine / ONGC | Approved work methods, actual spreads and operational interfaces | Before mobilisation and every operation | HSE performance and corrective-action records throughout execution. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
X01 | X - Changes, notices and contractual entitlement | Record changed conditions, instructions, quantity changes and potential delay events immediately. | Contracts / Commercial Manager | Controlling contract, instructions and contemporaneous records | From first change/event through final account | Dated change/event register and evidence. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
X02 | X - Changes, notices and contractual entitlement | Issue required notices within actual contractual time limits; obtain authorised instructions. | Contracts / Commercial Manager | Controlling contract, instructions and contemporaneous records | From first change/event through final account | Compliant correspondence and instruction trail. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
X03 | X - Changes, notices and contractual entitlement | Substantiate time/cost effects, preserve delay/resource records and prevent duplicate recovery. | Contracts / Commercial Manager | Controlling contract, instructions and contemporaneous records | From first change/event through final account | Supported change submissions and entitlement assessment. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
X04 | X - Changes, notices and contractual entitlement | Agree approved changes and flow effects into drawings, MTO, schedule, subcontracts and billing. | Contracts / Commercial Manager | Controlling contract, instructions and contemporaneous records | From first change/event through final account | Controlled contract/baseline revisions and approved settlement records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Y01 | Y - Handover and operational documentation | Define bridge/system completion boundaries and agreed dossier/punch requirements. | Completions / QA / Contracts / ONGC | Accepted work, test evidence and agreed turnover requirements | Before contractual completion | Approved turnover index and acceptance checklist. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Y02 | Y - Handover and operational documentation | Complete as-builts, calculations/models as required, material/weld/NDT/coating/test and marine records. | Completions / QA / Contracts / ONGC | Accepted work, test evidence and agreed turnover requirements | Before contractual completion | Complete accepted engineering/manufacturing/construction dossiers. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Y03 | Y - Handover and operational documentation | Close acceptance-critical punch and document agreed residual items, measurements and e-MB evidence. | Completions / QA / Contracts / ONGC | Accepted work, test evidence and agreed turnover requirements | Before contractual completion | Signed punch/quantity/certification records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Y04 | Y - Handover and operational documentation | Obtain actual completion/handover acceptance and record commencement of warranty obligations. | Completions / QA / Contracts / ONGC | Accepted work, test evidence and agreed turnover requirements | Before contractual completion | Client certificates and actual package/overall acceptance dates. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Z01 | Z - Warranty, final account and closeout | Operate defect notification, response, rectification and verification during contractual warranty. | Project Director / Contracts / Warranty Coordinator | Actual handover dates and contractual release conditions | After acceptance through warranty/final closure | Closed defect register and accepted corrective work. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Z02 | Z - Warranty, final account and closeout | Maintain required securities/insurance and obtain releases only when contractual conditions are met. | Project Director / Contracts / Warranty Coordinator | Actual handover dates and contractual release conditions | After acceptance through warranty/final closure | Guarantee/insurance closeout and release records. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Z03 | Z - Warranty, final account and closeout | Settle final quantities, approved changes, subcontract accounts, surplus and outstanding payments. | Project Director / Contracts / Warranty Coordinator | Actual handover dates and contractual release conditions | After acceptance through warranty/final closure | Agreed final account and financial reconciliation. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date
Z04 | Z - Warranty, final account and closeout | Archive controlled records and capture productivity, cost, marine downtime and lessons learned. | Project Director / Contracts / Warranty Coordinator | Actual handover dates and contractual release conditions | After acceptance through warranty/final closure | Final project closure report and reusable verified data. | OPEN / COMPLETION NOT EVIDENCED IN THIS SESSION | Assign named owner and target date

## Already Supplied or Prepared
Subject | Status | Evidence/limit
Supplied design criteria | Received and indexed | DC3.4 PartI Rev 14;BRRP-specific PartII;methodology
Source drawings and IRT | Received and indexed;partialbridge drawing coverage | MTO Drawings IRT;reference models and landing sheets
Scope/work-package preparation | P5 drafted | 100 work packages across 10 bridges
Engineering review | P4 preliminary calculations and source sheets | Not independently solved global/member/connection/bearing design
AFC preparation | Register/forms prepared | No actualAFC approval
Quantity audit | P5 completed arithmetic | 1141/1142 MT;1166/1168 m;718/719 m 2
Procurement preparation | 25 packages registered | Quotes/orders/actual delivery not evidenced
Schedule/CPM | 205 activity conditional scenario computed | ActualNOA/resource/productivity/workabilityvalidation pending
Execution/commissioning/handover plans | P5 drafted | Physicalcompletion/clientacceptance not evidenced
Cost/cash controls | Unpricedinputregister prepared | No approvedcost/fundingforecast