# OVERALL PROJECT SCHEDULE

# SHIVANSH — ONGC Mumbai High
Bridge Refurbishment & Replacement Project

Revision 0 | Prepared 25 October 2026 | Provisional management planning

Planning scenario: commencement on 1 November 2026. Actual award / Notification of Award is unconfirmed. This document is a proposed overall schedule, subject to engineering, supplier, resource and ONGC review; it is not an approved contractual baseline.

# 1. Schedule basis

Contract basis: 12 months from Notification of Award under reviewed GCC 6.3.1.1 and Technical SCC 2.0. Use 31 October 2027 as the conservative last workday for this scenario, subject to confirmation of the contractual date convention. The 360-day assumption in earlier planning files has not been adopted.

Scope: ten bridge packages — three replacements and seven refurbishments — with surveys, engineering, procurement, fabrication, transport, marine support, offshore installation, jacket strengthening, service transfer, demolition, inspection and handover.

Calendar: durations are elapsed calendar days, assuming sufficient shifts and staffing. Offshore tasks conservatively avoid 16 May–15 October inclusive. An uninterrupted offshore activity that does not fit before the monsoon is deferred to 16 October. This planning rule does not establish contractual extension entitlement.

Logic: finish-to-start relationships, zero lag. A successor begins on the day after a predecessor’s last workday. Zero-duration milestones record the following date boundary. F041 is the first-batch release within F040 production; the two durations are not additive.

Durations: planner estimates requiring work-quantity, productivity, supplier-lead-time and review-turnaround verification. No actual progress or committed resource availability is inferred.

Recovery resources: two fabrication lines, one dedicated strengthening cell, three offshore strengthening crews, one sequential heavy-lift spread and one cargo spread. Supporting accommodation and logistics must be sized for simultaneous work; SCC minimum accommodation for 60 special personnel does not establish adequate total capacity.

Weather reserve: ten offshore days are reserved after planned offshore work, followed by three demobilisation days. This allowance must be validated against metocean history and vessel operating limits.

# 2. Executive milestones

| Milestone / deliverable | Recovery target | Two-crew comparison |
| --- | --- | --- |
| Assumed NOA / commencement | 2026-11-01 | 2026-11-01 |
| Detailed design, AFC drawings and ITP approval | 2026-12-23 | 2026-12-23 |
| Vendor approval, steel purchase and phased yard delivery | 2027-01-02 | 2027-01-02 |
| Fabricate, NDT, dimensional inspection and coating | 2027-03-18 | 2027-03-18 |
| Install, connect, inspect and accept replacement bridge | 2027-03-01 | 2027-03-16 |
| Install new bridge, transfer services and commission | 2027-03-23 | 2027-04-05 |
| Isolate, dismantle old bridge and remove to shore | 2027-03-30 | 2027-04-12 |
| Install, connect, inspect and accept replacement bridge | 2027-04-17 | 2027-04-30 |
| Planned offshore works complete | 2027-05-02 | 2027-10-30 |
| Offshore demobilisation | 2027-05-14 | 2027-11-11 |
| Internal target: all works complete and handover accepted | 2027-06-15 | 2027-12-13 |

The recovery option targets offshore work completion at the 2 May 2027 milestone, demobilisation by 14 May 2027 and overall handover at the 15 June 2027 milestone. The two-crew case forecasts overall completion on 13 December 2027, after the assumed unextended deadline. Its seasonal delay and associated cost exposure require resolution; no automatic time extension is assumed.

# 3. Mandatory sequence and management gates

Complete surveys and approved design before fabrication or modification. Procurement release requires checked material requisitions; early purchase release is not fabrication approval.

Complete specified ICG, ICP and BHS jacket strengthening before the corresponding new bridge installations.

Install the new BHS–SLQ bridge and accept transferred services before isolating and demolishing the existing bridge.

Release loadout and offshore lifts only after verified weight / centre of gravity, rigging, crane capability, transport, sea-fastening, permits and operational readiness approvals.

Resolve the structural quantity difference (1,142 MT summary versus 1,141 MT bridge rows) and bridge-specific allocation of approximately 357 MT demolition before baseline approval.

Secure the additional third strengthening crew and early first-kit QA release. Validate survey access, engineering review capacity, accommodation, simultaneous operations and vessel commitments.

# 4. Detailed overall schedule — proposed recovery option

Dates: YYYY-MM-DD. Duration: elapsed calendar days. Predecessors: finish-to-start, separated by semicolons. All activities are proposed / unverified.

| ID | Package / activity | Days | Start | Finish | Predecessors | Resource |
| --- | --- | --- | --- | --- | --- | --- |
| M000 | COMMON — Assumed NOA / commencement | 0 | 2026-11-01 | 2026-11-01 | — | Milestone |
| G010 | COMMON — Kick-off, obligations, guarantees and funding arrangements | 7 | 2026-11-01 | 2026-11-07 | M000 | Project team |
| G020 | COMMON — Controlled document / addendum and quantity reconciliation | 14 | 2026-11-08 | 2026-11-21 | G010 | Project team |
| S010 | COMMON — Survey permits, mobilisation and access planning | 7 | 2026-11-08 | 2026-11-14 | G010 | Survey team |
| S020 | ALL — Bridge and platform verification survey campaign | 14 | 2026-11-15 | 2026-11-28 | S010 | Survey spread |
| E010 | COMMON — Design basis and interface approval | 14 | 2026-11-08 | 2026-11-21 | G010 | Engineering |
| E020 | ALL — Checked material requisitions / early material release | 10 | 2026-11-29 | 2026-12-08 | S020; E010; G020 | Engineering |
| P010 | ALL — Vendor approval, steel purchase and phased yard delivery | 25 | 2026-12-09 | 2027-01-02 | E020 | Procurement |
| E030 | REPLACEMENTS — Detailed design, AFC drawings and ITP approval | 25 | 2026-11-29 | 2026-12-23 | S020; E010 | Design team A |
| E040 | REFURBISHMENTS — Bridge and jacket strengthening design / AFC work packs | 25 | 2026-11-29 | 2026-12-23 | S020; E010 | Design team B |
| E050 | BHS-SLQ — Utility transfer, temporary stability and demolition design | 35 | 2026-11-29 | 2027-01-02 | S020; E010 | Design team A |
| MR10 | COMMON — Vessel market enquiry, technical audit and conditional reservation | 35 | 2026-11-08 | 2026-12-12 | G010 | Marine engineering |
| MR20 | REPLACEMENTS — Lift, loadout, transport and sea-fastening engineering | 35 | 2026-12-24 | 2027-01-27 | E030; MR10 | Marine engineering |
| F010 | ICW-ICG LD — Fabricate, NDT, dimensional inspection and coating | 35 | 2027-01-03 | 2027-02-06 | P010; E030 | Fabrication line 1 |
| F020 | BHS-SLQ — Fabricate, NDT, dimensional inspection and coating | 55 | 2027-01-03 | 2027-02-26 | P010; E030 | Fabrication line 2 |
| F030 | ICG-ICP LD — Fabricate, NDT, dimensional inspection and coating | 40 | 2027-02-07 | 2027-03-18 | F010 | Fabrication line 1 |
| F041 | ALL STRENGTHENING — First approved strengthening kits: phased fabrication / QA release | 20 | 2027-01-03 | 2027-01-22 | P010; E040 | Milestone within strengthening cell production |
| F040 | ALL STRENGTHENING — Phased fabrication and release of strengthening kits | 35 | 2027-01-03 | 2027-02-06 | P010; E040 | Dedicated strengthening cell |
| O010 | ALL — Accommodation/support mobilisation, permits, SIMOPS and readiness | 10 | 2027-01-23 | 2027-02-01 | F041; MR10 | Support spread |
| J010 | ICG / BHS — Addendum jacket strengthening and acceptance | 12 | 2027-02-02 | 2027-02-13 | O010 | Strengthening crew A |
| J020 | ICP — Addendum jacket strengthening and acceptance | 10 | 2027-02-02 | 2027-02-11 | O010 | Strengthening crew B |
| RA01 | ICW-ICG UD — Strengthening, inspection and bridge acceptance | 16 | 2027-02-14 | 2027-03-01 | J010; F040 | Strengthening crew A |
| RA02 | ICG-ICP UD — Strengthening, inspection and bridge acceptance | 22 | 2027-03-02 | 2027-03-23 | RA01; F040 | Strengthening crew A |
| RA03 | SLQ-WIS — Strengthening, inspection and bridge acceptance | 18 | 2027-03-24 | 2027-04-10 | RA02; F040 | Strengthening crew A |
| RA04 | NQO-NQD — Strengthening, inspection and bridge acceptance | 18 | 2027-02-07 | 2027-02-24 | O010; F040 | Strengthening crew C (additional) |
| RB01 | WIN-NC — Strengthening, inspection and bridge acceptance | 12 | 2027-02-12 | 2027-02-23 | J020; F040 | Strengthening crew B |
| RB02 | SCA-SC1 — Strengthening, inspection and bridge acceptance | 16 | 2027-02-24 | 2027-03-11 | RB01; F040 | Strengthening crew B |
| RB03 | SCA-SCF — Strengthening, inspection and bridge acceptance | 24 | 2027-03-12 | 2027-04-04 | RB02; F040 | Strengthening crew B |
| H010 | COMMON — Heavy-lift spread mobilisation and operational readiness | 7 | 2027-02-02 | 2027-02-08 | MR20; O010 | Heavy-lift spread |
| L010 | ICW-ICG LD — Loadout, sea-fastening and transport | 5 | 2027-02-07 | 2027-02-11 | F010; MR20 | Cargo spread |
| I010 | ICW-ICG LD — Install, connect, inspect and accept replacement bridge | 16 | 2027-02-14 | 2027-03-01 | L010; H010; J010 | Heavy-lift spread |
| L020 | BHS-SLQ — Loadout, sea-fastening and transport | 5 | 2027-02-27 | 2027-03-03 | F020; MR20; L010 | Cargo spread |
| I020 | BHS-SLQ — Install new bridge, transfer services and commission | 20 | 2027-03-04 | 2027-03-23 | L020; I010; J010; E050 | Heavy-lift spread |
| D020 | BHS-SLQ — Isolate, dismantle old bridge and remove to shore | 7 | 2027-03-24 | 2027-03-30 | I020 | Heavy-lift spread |
| L030 | ICG-ICP LD — Loadout, sea-fastening and transport | 5 | 2027-03-19 | 2027-03-23 | F030; MR20; L020 | Cargo spread |
| I030 | ICG-ICP LD — Install, connect, inspect and accept replacement bridge | 18 | 2027-03-31 | 2027-04-17 | L030; D020; J020 | Heavy-lift spread |
| D030 | OTHER BRIDGES — Other removal, waste backload and allocated demolition closure | 7 | 2027-04-18 | 2027-04-24 | I030; RA04; RB03; RA03 | Heavy-lift spread |
| O090 | ALL — Final offshore inspections, punch closure and operational acceptance | 7 | 2027-04-25 | 2027-05-01 | D030 | Support spread |
| M100 | ALL — Planned offshore works complete | 0 | 2027-05-02 | 2027-05-02 | O090 | Milestone |
| W010 | ALL — Offshore weather / access allowance (not productive work) | 10 | 2027-05-02 | 2027-05-11 | M100 | Reserved marine capacity |
| O100 | ALL — Offshore demobilisation | 3 | 2027-05-12 | 2027-05-14 | W010 | Support spread |
| C010 | ALL — As-built dossiers, e-MB records, QA records and handover compilation | 30 | 2027-05-02 | 2027-05-31 | M100 | Completions team |
| C020 | ALL — Final document review and completion certificate processing | 14 | 2027-06-01 | 2027-06-14 | C010; O100 | Project team |
| M200 | ALL — Internal target: all works complete and handover accepted | 0 | 2027-06-15 | 2027-06-15 | C020 | Milestone |

# 5. Baseline approval and control

Before approval: confirm NOA, controlling documents, work quantities, supplier lead times, crew capacities, vessel suitability and availability, ONGC interfaces, weather workability, cost and funding.

Resource checks performed: exclusive fabrication-line, strengthening-crew, cargo-spread and heavy-lift sequencing. Full labour-loaded and resource-levelled P6 analysis remains outstanding.

Control rhythm: daily workfront and marine coordination; weekly six-week constraint look-ahead and integrated schedule update; monthly completion and cost forecast. Record actual dates and accepted quantities rather than subjective progress.

Warranty: twelve months after actual completion and handover, subject to the contract. Rebase warranty and security-release dates to actual acceptance; they are separate from the EPC execution duration.

Source basis: uploaded GCC 2.1.1 / 6.3.1.1; Technical SCC 2.0 / 3.0; SOW Section 1 including 1.3; structural scope addendum; Level3, Stage28 and 360-day scheduling workbooks; Stage34/35 control and mobilisation plans. This proposed schedule does not supersede the executed contract or controlling addenda.