# BRRP — Additional input and planning-model review

P10 |25 October2026 | Source screening and internal consistency audit

15 files supplied;14 transferred and opened;13 distinct accessible contents; four contents have no exact match among earlier local attachments. One PDF could not transfer because it exceeds32MiB. Section1/2/3 contain12/43/323 pages respectively. PDF title/scope screening, workbook data/formula inventory and CSV day-logic screening were performed. This is not an exhaustive numerical review of all378 PDF pages, formula recalculation, P6 scheduling run, structural analysis or AFC approval.

# Scope applicability

Source: Section1.pdf pp1,6-8; Section2.pdf p1; Section3.pdf p1

All three Sections identify S&SRP (Sump Caisson and SWLP Casing Replacement Project). Section1 describes SWLP casings, vent booms, heaters, PBIV, caissons and RS-21 repairs. Shared platform names do not prove BRRP scope.

Required update: Prepare an applicability matrix linking any adopted requirement to BRRP incorporation/contract reference. Retain these sources separately until applicability is established.

# New source contents

Source: inventory.json

Section1, the CSV, Stage4 and Stage5 are four distinct contents without exact prior local matches. Ten successfully transferred uploads match earlier local files; Stage10 variants are also identical to one another.

Required update: Do not assume no prior hash match proves a later revision; reconcile cell-level changes and issuance before superseding earlier plans.

# Network logic

Source: CSV BR0002, BR0003, BR0005, BR0007, BR0008; complete exceptions sheet

87 activity records. Screening finds54 FS-linked successors starting on or before their predecessor finish day, using the supplied day numbers and assuming no lag because no lag field is present. BR0002 starts day5 after BR0001 finishing day10; BR0007 starts76 after BR0006 finishing99. Same-day cases depend on timing convention.

Required update: Resolve intended FS/SS relations, lags and inclusive-day conventions; validate calendars and import mapping. Do not call these dates a calculated CPM baseline or change relations merely to preserve target dates.

# Resource feasibility

Source: Stage4 Resource Estimates C2:I11; Stage5 Yard Production C2:J11

Productivity and crew/vessel inputs are unfilled in the sampled resource tables. Stage5 yard allocations are TBD and release gates pending; Ready for loadout is NO.

Required update: Obtain yard outputs, working shifts, named crews, crane charts, vessel availability and shutdown windows; then calculate durations and resource-level the network.

# Spreadsheet calculation state

Source: Workbook sheet inventory

Some Stage4/5 formulas have no stored calculated value; many deliberately return blank for missing inputs. Stage25 also has uncached formula outputs. This does not establish an Excel error; Python inspection does not recalculate formulas.

Required update: Distinguish missing input, blank formula result and stale/missing cache. Recalculate an editable copy in Excel after verified inputs and perform checks; no recalculation claim is made here.

# Cost estimate completeness

Source: Stage25 READ ME B2:B9; Stage26 Commercial Inputs B3:B13 and Controls and Caveats

Financial models explicitly remain illustrative/unpriced. Zero contract value and zero cost inputs mean unknown, not zero exposure. Tonnage allocation is provisional.

Required update: Build priced WBS estimates from quotations, quantities, marine spread days, overheads, risk and taxes; reconcile to signed terms and actual commercial status.

# Funding horizon

Source: Stage26 Controls and Caveats rows5-9; CEO Decision Dashboard C5

29-week scenario excludes part of contract life. The workbook states retention is withheld but eventual release is not added; advance recovery needs verification; proposed certification/payment lags require confirmation.

Required update: Extend cash flow through completion, payment delays, retention/warranty/security release and final account. Add explicit advance recovery, BG margin release, tax and financing events and reconcile against milestones; then recalculate peak funding.

# Contract duration

Source: Stage25 READ ME B3:B4; earlier Technical SCC completion provision

1 November2026 and360 days are planning assumptions. Earlier reviewed SCC states12 months from NOA;360 days is not automatically equivalent to12 months.

Required update: Use controlled governing SCC/award, actual commencement evidence, monsoon rules and approved extensions; align all workbooks to one date/calendar basis.

# MTO reconciliation

Source: Stage25 READ ME B5:B7; Stage10 CEO Decisions row3

Printed structural total1142MT versus detailed rows1141MT remains acknowledged and unresolved. Labels such as Verified MTO are not approval evidence.

Required update: Maintain discrepancy register and obtain detailed engineering quantity reconciliation before procurement commitments; retain other prior handrail/grating discrepancies.

# Baseline gates

Source: Level3 P6 Preparation, Baseline Readiness rows2-13; Stage10 360D Logic

Workbooks identify award, survey, lift/COG, vessels, shutdowns, productivity, DCI/MCI and CPM as open. Target-day gates are proposals.

Required update: Connect each gate to an evidence owner, due date, document and acceptance; do not promote planned day360 completion or dashboard labels to proof of readiness.

# Newer tender amendments

Source: P9 impact report; C8 DCI/MCI previously reviewed

This upload does not itself demonstrate integration of revised security, steel-origin, vendor12.3, review-working-day, welding/coating and PPE requirements.

Required update: Cross-reference P9 findings into procurement, engineering review, QA, financing and schedule predecessors before the next consolidated baseline issue.

# Unreviewed large PDF

Source: SHIVANSH ONGC Offshore Bridges - PRELIMINARY.pdf

Transfer failed: file exceeds the executor32MiB limit. Its content was not opened or reviewed. The similarly named Excel was opened but equivalence cannot be assumed.

Required update: Keep PDF explicitly pending. The other14 successfully transferred files have been inventoried without requiring this PDF.

# Current disposition

Keep S&SRP applicability unresolved, repair and validate schedule logic, secure resource and commercial inputs, reconcile MTO and current amendments, extend financial horizons, then recalculate and obtain baseline approval. Preserve original uploaded files. This review has not changed source workbook formulas or overwritten the earlier planning scenario. Actual contract status remains unverified; text in the uploaded dashboards is source content, not independent confirmation.