## Findings
Topic | Source | Finding | Required action
Scope applicability | Section1.pdf pp1,6-8; Section2.pdf p1; Section3.pdf p1 | All three Sections identify S&SRP (Sump Caisson and SWLP Casing Replacement Project). Section1 describes SWLP casings, vent booms, heaters, PBIV, caissons and RS-21 repairs. Shared platform names do not prove BRRP scope. | Prepare an applicability matrix linking any adopted requirement to BRRP incorporation/contract reference. Retain these sources separately until applicability is established.
New source contents | inventory.json | Section1, the CSV, Stage4 and Stage5 are four distinct contents without exact prior local matches. Ten successfully transferred uploads match earlier local files; Stage10 variants are also identical to one another. | Do not assume no prior hash match proves a later revision; reconcile cell-level changes and issuance before superseding earlier plans.
Network logic | CSV BR0002, BR0003, BR0005, BR0007, BR0008; complete exceptions sheet | 87 activity records. Screening finds54 FS-linked successors starting on or before their predecessor finish day, using the supplied day numbers and assuming no lag because no lag field is present. BR0002 starts day5 after BR0001 finishing day10; BR0007 starts76 after BR0006 finishing99. Same-day cases depend on timing convention. | Resolve intended FS/SS relations, lags and inclusive-day conventions; validate calendars and import mapping. Do not call these dates a calculated CPM baseline or change relations merely to preserve target dates.
Resource feasibility | Stage4 Resource Estimates C2:I11; Stage5 Yard Production C2:J11 | Productivity and crew/vessel inputs are unfilled in the sampled resource tables. Stage5 yard allocations are TBD and release gates pending; Ready for loadout is NO. | Obtain yard outputs, working shifts, named crews, crane charts, vessel availability and shutdown windows; then calculate durations and resource-level the network.
Spreadsheet calculation state | Workbook sheet inventory | Some Stage4/5 formulas have no stored calculated value; many deliberately return blank for missing inputs. Stage25 also has uncached formula outputs. This does not establish an Excel error; Python inspection does not recalculate formulas. | Distinguish missing input, blank formula result and stale/missing cache. Recalculate an editable copy in Excel after verified inputs and perform checks; no recalculation claim is made here.
Cost estimate completeness | Stage25 READ ME B2:B9; Stage26 Commercial Inputs B3:B13 and Controls and Caveats | Financial models explicitly remain illustrative/unpriced. Zero contract value and zero cost inputs mean unknown, not zero exposure. Tonnage allocation is provisional. | Build priced WBS estimates from quotations, quantities, marine spread days, overheads, risk and taxes; reconcile to signed terms and actual commercial status.
Funding horizon | Stage26 Controls and Caveats rows5-9; CEO Decision Dashboard C5 | 29-week scenario excludes part of contract life. The workbook states retention is withheld but eventual release is not added; advance recovery needs verification; proposed certification/payment lags require confirmation. | Extend cash flow through completion, payment delays, retention/warranty/security release and final account. Add explicit advance recovery, BG margin release, tax and financing events and reconcile against milestones; then recalculate peak funding.
Contract duration | Stage25 READ ME B3:B4; earlier Technical SCC completion provision | 1 November2026 and360 days are planning assumptions. Earlier reviewed SCC states12 months from NOA;360 days is not automatically equivalent to12 months. | Use controlled governing SCC/award, actual commencement evidence, monsoon rules and approved extensions; align all workbooks to one date/calendar basis.
MTO reconciliation | Stage25 READ ME B5:B7; Stage10 CEO Decisions row3 | Printed structural total1142MT versus detailed rows1141MT remains acknowledged and unresolved. Labels such as Verified MTO are not approval evidence. | Maintain discrepancy register and obtain detailed engineering quantity reconciliation before procurement commitments; retain other prior handrail/grating discrepancies.
Baseline gates | Level3 P6 Preparation, Baseline Readiness rows2-13; Stage10 360D Logic | Workbooks identify award, survey, lift/COG, vessels, shutdowns, productivity, DCI/MCI and CPM as open. Target-day gates are proposals. | Connect each gate to an evidence owner, due date, document and acceptance; do not promote planned day360 completion or dashboard labels to proof of readiness.
Newer tender amendments | P9 impact report; C8 DCI/MCI previously reviewed | This upload does not itself demonstrate integration of revised security, steel-origin, vendor12.3, review-working-day, welding/coating and PPE requirements. | Cross-reference P9 findings into procurement, engineering review, QA, financing and schedule predecessors before the next consolidated baseline issue.
Unreviewed large PDF | SHIVANSH ONGC Offshore Bridges - PRELIMINARY.pdf | Transfer failed: file exceeds the executor32MiB limit. Its content was not opened or reviewed. The similarly named Excel was opened but equivalence cannot be assumed. | Keep PDF explicitly pending. The other14 successfully transferred files have been inventoried without requiring this PDF.

## Inventory
File | Bytes | SHA256 | Prior exact matches | Batch duplicate | PDF pages
Section 1.pdf | 891163 | 4396fb90c823805128145920d1348e69942a65e501773d80457a3b671e0f3641 | 0 |  | 12
Section 2.pdf | 1441383 | 1d6c9da72ce45156e95586056c6d96a06da9563a9a27817dc77935d6fa470a7f | 1 |  | 43
SHIVANSH ONGC Offshore Bridges - PRELIMINARY.xlsx | 11297 | caba714d2cc9b32ddf723228a57797a6e588463c0554ced81701982fcd7f7f20 | 1
Section 3.pdf | 6544792 | 64146db7c46ea30fc3e5161cea2ce94bdb3435e4aefe05a81cfac0174c141108 | 1 |  | 323
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | 71554 | a4545c34bc3bfdf771c5918e9335e6b288626e024a5f517e4eb0ca7f6fe870ee | 1
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | 22985 | 2c64809e2cbab409c9897e19ee5b46768287708a1adb9f923457d03177f24c36 | 1
Shivansh_BRRPP_Level3_P6_Preparation.xlsx | 15768 | 186a4f446d7691b5c726f32e8600482c7abde182ef9bbc7d11c07729e4706074 | 1
Shivansh_BRRPP_P6_Activity_Import.csv | 17737 | cd3865f25e6d42bccc800bd4344e38816fdcf68c6dbbe63c26a0e76096f358d7 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | 16487 | 88adcd75ff58317d0215801c0cee35b3f8aa03b024e8acbd45382e8138db56f0 | 0
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | 18952 | ac85c7dec0f9db25e971b0795623e465a92732bcc873ba6234bd21f485cc2036 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | 15553 | 44df6c84070a16804ad83487e7575ba1e99569a53e267c8e3da83ac9cfd59621 | 1
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | 15553 | 44df6c84070a16804ad83487e7575ba1e99569a53e267c8e3da83ac9cfd59621 | 1 | Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx
Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx | 10506 | a46229faa98cf1d94ebad3412394eda944398ea5f209b3da5b3fce3af1c0a7d6 | 1
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | 13114 | 9627644802f34de8ab9f44420ab6b7bad0437a6dbd5ea2a8dc0228d6f53bc422 | 1
SHIVANSH ONGC Offshore Bridges - PRELIMINARY.pdf | TRANSFER FAILED: over32MiB; not reviewed

## FS Date Exceptions
Activity | Start day | Predecessor | Predecessor finish day
BR0002 | 5 | BR0001 | 10
BR0003 | 10 | BR0001 | 10
BR0005 | 20 | BR0002 | 20
BR0007 | 76 | BR0006 | 99
BR0008 | 125 | BR0007 | 141
BR0009 | 190 | BR0008 | 205
BR0010 | 218 | BR0009 | 231
BR0011 | 242 | BR0010 | 246
BR0015 | 82 | BR0014 | 105
BR0016 | 131 | BR0015 | 147
BR0017 | 196 | BR0016 | 211
BR0018 | 224 | BR0017 | 237
BR0019 | 248 | BR0018 | 252
BR0023 | 88 | BR0022 | 111
BR0024 | 137 | BR0023 | 153
BR0025 | 202 | BR0024 | 217
BR0026 | 230 | BR0025 | 243
BR0027 | 254 | BR0026 | 258
BR0031 | 94 | BR0030 | 117
BR0032 | 143 | BR0031 | 159
BR0033 | 208 | BR0032 | 223
BR0034 | 236 | BR0033 | 249
BR0035 | 260 | BR0034 | 264
BR0039 | 100 | BR0038 | 123
BR0040 | 149 | BR0039 | 165
BR0041 | 214 | BR0040 | 229
BR0042 | 242 | BR0041 | 255
BR0043 | 266 | BR0042 | 270
BR0046 | 304 | BR0045 | 351
BR0049 | 106 | BR0048 | 129
BR0050 | 155 | BR0049 | 171
BR0051 | 220 | BR0050 | 235
BR0052 | 248 | BR0051 | 261
BR0053 | 272 | BR0052 | 276
BR0057 | 112 | BR0056 | 135
BR0058 | 161 | BR0057 | 177
BR0059 | 226 | BR0058 | 241
BR0060 | 254 | BR0059 | 267
BR0061 | 278 | BR0060 | 282
BR0065 | 118 | BR0064 | 141
BR0066 | 167 | BR0065 | 183
BR0067 | 232 | BR0066 | 247
BR0068 | 260 | BR0067 | 273
BR0069 | 284 | BR0068 | 288
BR0073 | 124 | BR0072 | 147
BR0074 | 173 | BR0073 | 189
BR0075 | 238 | BR0074 | 253
BR0076 | 266 | BR0075 | 279
BR0077 | 290 | BR0076 | 294
BR0081 | 130 | BR0080 | 153
BR0082 | 179 | BR0081 | 195
BR0083 | 244 | BR0082 | 259
BR0084 | 272 | BR0083 | 285
BR0085 | 296 | BR0084 | 300

## Workbook Sheet Audit
File | Sheet | Rows | Columns | Formula count | No cached value
SHIVANSH ONGC Offshore Bridges - PRELIMINARY.xlsx | SHIVANSH ONGC Offshore Bridges | 208 | 6 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | START HERE | 10 | 2 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Bridge Baseline | 11 | 10 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Master Activities | 208 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Engineering | 41 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Procurement | 21 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Fabrication | 31 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Quality | 21 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Logistics | 14 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Marine | 14 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Offshore | 49 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Demolition | 4 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Closeout | 21 | 20 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Resources | 11 | 10 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Daily Progress | 1 | 15 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | 6 Week Lookahead | 1 | 13 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Constraints Risks | 1 | 11 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Cost Cashflow | 13 | 9 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Marine Campaigns | 5 | 11 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | Milestones | 8 | 5 | 0 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | CEO Dashboard | 10 | 3 | 7 | 0
SHIVANSH_360_Day_EPC_Scheduling_Control_Workbook.xlsx | 360 Day Gantt | 101 | 18 | 1200 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | MTO Baseline | 12 | 12 | 19 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Bridge Execution | 11 | 9 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | 360 Day Plan | 14 | 9 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Engineering Register | 51 | 10 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Procurement | 71 | 11 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Fabrication | 11 | 12 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Lift COG Register | 11 | 13 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Marine Readiness | 6 | 11 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Hold Points | 61 | 7 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Risks | 5 | 10 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | CEO Dashboard | 11 | 5 | 0 | 0
Shivansh_BRRPP_Integrated_Execution_Control.xlsx | Assumptions | 6 | 4 | 0 | 0
Shivansh_BRRPP_Level3_P6_Preparation.xlsx | Activity Network | 88 | 18 | 0 | 0
Shivansh_BRRPP_Level3_P6_Preparation.xlsx | Bridge Resource Summary | 11 | 6 | 0 | 0
Shivansh_BRRPP_Level3_P6_Preparation.xlsx | Marine Vessel Allocation | 7 | 5 | 0 | 0
Shivansh_BRRPP_Level3_P6_Preparation.xlsx | Baseline Readiness | 13 | 3 | 0 | 0
Shivansh_BRRPP_Level3_P6_Preparation.xlsx | Instructions | 9 | 2 | 0 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | CEO Overview | 11 | 3 | 0 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Bridge Quantities | 12 | 9 | 16 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Work Packages | 11 | 8 | 0 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Schedule Windows | 11 | 7 | 10 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Resource Estimates | 11 | 10 | 30 | 20
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Lift COG Control | 11 | 12 | 10 | 10
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Marine Suitability | 7 | 9 | 0 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Inspection Gates | 9 | 5 | 0 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Risks & Decisions | 10 | 7 | 0 | 0
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Cost Inputs | 12 | 6 | 11 | 11
Shivansh_BRRPP_Stage4_Resource_Cost_Marine_Planning.xlsx | Basis and Sources | 8 | 3 | 0 | 0
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | CEO Decisions | 7 | 5 | 0 | 0
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | Package Baseline | 11 | 9 | 0 | 0
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | Yard Production | 11 | 10 | 10 | 10
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | Marine Campaign | 11 | 11 | 10 | 10
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | Cost Loading | 11 | 10 | 40 | 20
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | P6 Logic Review | 88 | 12 | 0 | 0
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | Lift Release Gates | 11 | 11 | 0 | 0
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | Risks and Controls | 7 | 5 | 0 | 0
Shivansh_BRRPP_Stage5_Integrated_Marine_Yard_Cost_P6.xlsx | Source and Limitations | 11 | 2 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Verified MTO | 14 | 12 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Workfronts | 5 | 5 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Yard Capacity | 5 | 8 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Resource Audit | 12 | 7 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Package Gate Matrix | 71 | 7 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Marine Campaigns | 11 | 13 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | 360D Logic | 7 | 6 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Weekly Lookahead | 1 | 10 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | CEO Decisions | 7 | 5 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility (1).xlsx | Basis and Limitations | 7 | 3 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Verified MTO | 14 | 12 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Workfronts | 5 | 5 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Yard Capacity | 5 | 8 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Resource Audit | 12 | 7 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Package Gate Matrix | 71 | 7 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Marine Campaigns | 11 | 13 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | 360D Logic | 7 | 6 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Weekly Lookahead | 1 | 10 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | CEO Decisions | 7 | 5 | 0 | 0
Shivansh_BRRPP_Stage10_Resource_Feasibility.xlsx | Basis and Limitations | 7 | 3 | 0 | 0
Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx | READ ME | 10 | 2 | 0 | 0
Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx | Bridge Cost Model | 16 | 16 | 36 | 20
Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx | Shared Resources | 17 | 6 | 13 | 12
Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx | 29 Week Cash Flow | 32 | 17 | 72 | 0
Shivansh_BRRPP_Stage25_Cost_Cashflow_Model.xlsx | CEO Gates | 10 | 4 | 0 | 0
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | Commercial Inputs | 25 | 3 | 0 | 0
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | Bridge Allocation | 14 | 7 | 44 | 0
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | Weekly Cash Flow | 31 | 16 | 388 | 0
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | CEO Decision Dashboard | 10 | 3 | 7 | 0
Shivansh_BRRPP_Stage26_Revenue_Cashflow_WorkingCapital (1).xlsx | Controls and Caveats | 13 | 2 | 0 | 0