## Actual Maturity
Area | Status | Meaning
Benchmark claim | NOT SUBSTANTIATED | No audited comparison withSaipem/McDermott; companyinternalprocedures and outcomes not verified.
Review independence | SELF-REVIEW | This supplement is not independentengineering or projectassurance sign-off.
Management documents | PRELIMINARY / DEVELOPING | P5/P6 provide scope,registers and workstreamplans; some procedures require project-specificpopulation/review.
Engineering | INCOMPLETE | P 4 source-basedsheets/arithmetic are not completedglobal/member/connection/bearing/fatigue/liftingdesign.
Schedule | ILLUSTRATIVE CONDITIONAL SCENARIO | Validconnectivity does not establish scopecoverage,resourcefeasibility or weatherconfidence.
Quantities | TENDER / UNRECONCILED | Three arithmeticdiscrepancies remainopen; nofinalpurchaseMTO.
Cost/cash | UNPRICED | Noapprovedbudget,margin,fundingadequacy or costconfidence.
AFC | NOT APPROVED | Register/forms are not actualapproved drawings.
Execution/acceptance | NOT EVIDENCED HERE | No suppliercommitment,physical completionorclientacceptance inferred.
Delivery | NOT CONFIRMED | Workspacefileintegrity does notprove recipientdownload/opening.

## Review Findings
ID | Control | Classification | Evidence-basedgap | Owner | Needby
PM01 | Contract-to-evidence requirements traceability | UNDERDEVELOPED | P5 source list and obligations are not a clause-by-clause verification matrix. | Contracts / Engineering | Before scope/design baseline
PM02 | Integrated WBS / CBS / OBS / control accounts | UNDERDEVELOPED | Package IDs exist but cost, responsibility, procurement and progress are not fully mapped. | Project Controls / Cost | Before cost/schedule baseline
PM03 | Execution-concept and constructability selection | UNDERDEVELOPED | Source concept is carried forward; project-specific alternatives and constraints are not decided. | Engineering / Marine / Construction | Before design freeze
PM04 | Engineering-model validation and checking plan | OPEN ENGINEERING | Source arithmetic and pictures do not reproduce the structural model. | Technical Authority / Checker | Before detailed design approval
PM05 | Long-lead procurement network | MATERIAL SCHEDULE GAP | P010 is one bulk-material placeholder; all 25 procurement packages lack separate validated logic. | Procurement / Planning | Before schedule baseline
PM06 | Schedule quality and full resource validation | UNDERDEVELOPED | Network connectivity checks pass; durations and full capacity constraints remain unverified. | Project Controls / Discipline Leads | Before baseline approval
PM07 | Activity-specific weather and operability model | CORRECTION REQUIRED | The 10-day hold after offshore work is not a validated weather-risk model. | Marine / Planning / Assurance | Before offshore campaign sanction
PM08 | Quantitative schedule and cost risk assessment | NOT PERFORMED | Deterministic delay tests exist; no calibrated probabilistic risk model or confidence dates exist. | Risk / Planning / Cost | Before management forecast commitment
PM09 | Progress measurement and earned-value rules | UNDERDEVELOPED | Accepted quantities are specified, but discipline weighting and credit rules are not approved. | Project Controls / QA / Cost | Before first progress report
PM10 | Weekly update and forecasting protocol | UNDERDEVELOPED | Reporting rhythm exists; data-date, actualisation and remaining-work rules need formal definition. | Project Controls | Before first controlled update
PM11 | Weight and centre-of-gravity control | UNDERDEVELOPED | Weight/COG is recognised but no live controlled register or change-trigger workflow exists. | Engineering / Fabrication / Marine | Before vessel commitment and each lift
PM12 | Technical interfaces and decision escalation | UNDERDEVELOPED | Interface and decision registers are described but not fully populated with closure deadlines. | Interface Manager / Project Director | Before design release and weekly
PM13 | Supplier and subcontract performance assurance | UNDERDEVELOPED | Procurement packages exist but supplier-specific surveillance and performance controls are not developed. | Supply Chain / QA / Contracts | Before placement and during supply
PM14 | Field change and configuration management | UNDERDEVELOPED | Change control is general; technical field-change routing and affected-document propagation need definition. | Engineering / Construction / Contracts | Before offshore execution
PM15 | Critical safety-barrier verification | UNDERDEVELOPED | HSE topics are covered; operation-specific critical controls and verification evidence are not established. | HSE / Operation Owners | Before each high-risk operation
PM16 | SIMOPS, shutdown and access integration | UNDERDEVELOPED | Access/permits are gates but operational windows are not fully scheduled and agreed. | ONGC Interface / Offshore / Marine | Before baseline and mobilisation
PM17 | Safe seasonal suspension and restart plan | UNDERDEVELOPED | Second-season comparator assumes safe stoppoints and 7-day remobilisation without operation-specific proof. | Marine / Construction / Engineering | Before adopting two-season strategy
PM18 | Systems-based completion and turnover | UNDERDEVELOPED | Test categories exist; detailed system boundaries and completion certificates are not mapped. | Completions / Discipline Leads / ONGC | Before construction work packs
PM19 | Operations, maintainability and asset-data handover | UNDERDEVELOPED | Dossiers are planned but operations/maintenance deliverables and asset-data requirements need agreement. | Engineering / Completions / ONGC Operations | Before detailed design freeze and handover
PM20 | Funding, contingency and financial risk governance | OPEN COMMERCIAL | Cost register is unpriced; no funding adequacy, margin or approved contingency can be claimed. | Finance / Cost / Commercial | Before financial sanction
PM21 | Communication and stakeholder engagement | UNDERDEVELOPED | Meeting rhythm exists but a stakeholder/communications responsibility plan is not explicit. | Project Director / Interface Manager | At project initiation
PM22 | Data, document and delivery assurance | UNDERDEVELOPED | Files exist, but successful recipient download/opening remains unverified. | Document Control / Project Controls | Before each formal issue
PM23 | Integrated assurance and independent review | NOT COMPLETED | Current audit is a self-review; there is no evidenced independent project/design assurance sign-off. | Project Director / Independent Review Authority | Before baseline, marine and construction release
PM24 | Package acceptance, lessons and closure criteria | UNDERDEVELOPED | A-to-Z actions exist; measurable package acceptance and evidence-based final closure need agreement. | Project Director / Contracts / QA | Before management package approval

## 96 Closure Actions
ID | Finding | Control | Class | Observedgap | Requiredaction | Owner | Needby | Status
PM01.01 | PM01 | Contract-to-evidence requirements traceability | UNDERDEVELOPED | P5 source list and obligations are not a clause-by-clause verification matrix. | Assign a unique requirement ID and exact source clause/revision. | Contracts / Engineering | Before scope/design baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM01.02 | PM01 | Contract-to-evidence requirements traceability | UNDERDEVELOPED | P5 source list and obligations are not a clause-by-clause verification matrix. | Link each requirement to applicable bridges, calculation/drawing, procurement and test evidence. | Contracts / Engineering | Before scope/design baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM01.03 | PM01 | Contract-to-evidence requirements traceability | UNDERDEVELOPED | P5 source list and obligations are not a clause-by-clause verification matrix. | Assign verification method, responsible owner and acceptance authority. | Contracts / Engineering | Before scope/design baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM01.04 | PM01 | Contract-to-evidence requirements traceability | UNDERDEVELOPED | P5 source list and obligations are not a clause-by-clause verification matrix. | Close only against actual approved evidence; retain exceptions and changes. | Contracts / Engineering | Before scope/design baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM02.01 | PM02 | Integrated WBS / CBS / OBS / control accounts | UNDERDEVELOPED | Package IDs exist but cost, responsibility, procurement and progress are not fully mapped. | Adopt one bridge/workstream coding dictionary across scope, schedule, cost and documentation. | Project Controls / Cost | Before cost/schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM02.02 | PM02 | Integrated WBS / CBS / OBS / control accounts | UNDERDEVELOPED | Package IDs exist but cost, responsibility, procurement and progress are not fully mapped. | Define control accounts with one accountable manager, budget, schedule and deliverable boundary. | Project Controls / Cost | Before cost/schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM02.03 | PM02 | Integrated WBS / CBS / OBS / control accounts | UNDERDEVELOPED | Package IDs exist but cost, responsibility, procurement and progress are not fully mapped. | Map procurement, material, invoice and accepted quantities to those control accounts. | Project Controls / Cost | Before cost/schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM02.04 | PM02 | Integrated WBS / CBS / OBS / control accounts | UNDERDEVELOPED | Package IDs exist but cost, responsibility, procurement and progress are not fully mapped. | Prevent shared marine/engineering cost duplication and cross-bridge quantity double counting. | Project Controls / Cost | Before cost/schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM03.01 | PM03 | Execution-concept and constructability selection | UNDERDEVELOPED | Source concept is carried forward; project-specific alternatives and constraints are not decided. | Compare practical module splits, lifting/transport strategies and fabrication routes. | Engineering / Marine / Construction | Before design freeze | OPEN / PROJECT EVIDENCE REQUIRED
PM03.02 | PM03 | Execution-concept and constructability selection | UNDERDEVELOPED | Source concept is carried forward; project-specific alternatives and constraints are not decided. | Assess live-service clearances, existing bridge interference, access and operational restrictions. | Engineering / Marine / Construction | Before design freeze | OPEN / PROJECT EVIDENCE REQUIRED
PM03.03 | PM03 | Execution-concept and constructability selection | UNDERDEVELOPED | Source concept is carried forward; project-specific alternatives and constraints are not decided. | Record cost, schedule, safety and interface consequences with qualified engineering input. | Engineering / Marine / Construction | Before design freeze | OPEN / PROJECT EVIDENCE REQUIRED
PM03.04 | PM03 | Execution-concept and constructability selection | UNDERDEVELOPED | Source concept is carried forward; project-specific alternatives and constraints are not decided. | Approve the selected concept and propagate it to model, MTO, vessel needs and schedule. | Engineering / Marine / Construction | Before design freeze | OPEN / PROJECT EVIDENCE REQUIRED
PM04.01 | PM04 | Engineering-model validation and checking plan | OPEN ENGINEERING | Source arithmetic and pictures do not reproduce the structural model. | Issue model/input/checking registers with calculation IDs and validation responsibility. | Technical Authority / Checker | Before detailed design approval | OPEN / PROJECT EVIDENCE REQUIRED
PM04.02 | PM04 | Engineering-model validation and checking plan | OPEN ENGINEERING | Source arithmetic and pictures do not reproduce the structural model. | Reproduce source load totals and gravity response or explain changes before new analyses. | Technical Authority / Checker | Before detailed design approval | OPEN / PROJECT EVIDENCE REQUIRED
PM04.03 | PM04 | Engineering-model validation and checking plan | OPEN ENGINEERING | Source arithmetic and pictures do not reproduce the structural model. | Check geometry, section groups, stiffness, releases, stability, units and load combinations. | Technical Authority / Checker | Before detailed design approval | OPEN / PROJECT EVIDENCE REQUIRED
PM04.04 | PM04 | Engineering-model validation and checking plan | OPEN ENGINEERING | Source arithmetic and pictures do not reproduce the structural model. | Document independent checking of members, joints, bearings, existing structures and temporary states. | Technical Authority / Checker | Before detailed design approval | OPEN / PROJECT EVIDENCE REQUIRED
PM05.01 | PM05 | Long-lead procurement network | MATERIAL SCHEDULE GAP | P010 is one bulk-material placeholder; all 25 procurement packages lack separate validated logic. | Create separate vendor-document, approval, manufacture, inspection, dispatch and receipt milestones where relevant. | Procurement / Planning | Before schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM05.02 | PM05 | Long-lead procurement network | MATERIAL SCHEDULE GAP | P010 is one bulk-material placeholder; all 25 procurement packages lack separate validated logic. | Obtain actual quotations and lead times for bearings, services, lifesaving equipment and specialist suppliers. | Procurement / Planning | Before schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM05.03 | PM05 | Long-lead procurement network | MATERIAL SCHEDULE GAP | P010 is one bulk-material placeholder; all 25 procurement packages lack separate validated logic. | Connect each package to its earliest genuine design/fabrication/installation/test need date. | Procurement / Planning | Before schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM05.04 | PM05 | Long-lead procurement network | MATERIAL SCHEDULE GAP | P010 is one bulk-material placeholder; all 25 procurement packages lack separate validated logic. | Recalculate critical paths after these links and commitments are entered; do not retain target dates by force. | Procurement / Planning | Before schedule baseline | OPEN / PROJECT EVIDENCE REQUIRED
PM06.01 | PM06 | Schedule quality and full resource validation | UNDERDEVELOPED | Network connectivity checks pass; durations and full capacity constraints remain unverified. | Validate every task duration against quantities, crew-hours, access and demonstrated productivity. | Project Controls / Discipline Leads | Before baseline approval | OPEN / PROJECT EVIDENCE REQUIRED
PM06.02 | PM06 | Schedule quality and full resource validation | UNDERDEVELOPED | Network connectivity checks pass; durations and full capacity constraints remain unverified. | Include review cycles, vendor data, port/field moves, inspection/coating, shutdowns and operational windows. | Project Controls / Discipline Leads | Before baseline approval | OPEN / PROJECT EVIDENCE REQUIRED
PM06.03 | PM06 | Schedule quality and full resource validation | UNDERDEVELOPED | Network connectivity checks pass; durations and full capacity constraints remain unverified. | Level labour, supervision, cranes, QA/NDT, coating bays, vessels, shifts, rotations and POB. | Project Controls / Discipline Leads | Before baseline approval | OPEN / PROJECT EVIDENCE REQUIRED
PM06.04 | PM06 | Schedule quality and full resource validation | UNDERDEVELOPED | Network connectivity checks pass; durations and full capacity constraints remain unverified. | Audit calendars, open ends, excessive constraints, lags, safe seasonal stoppoints and milestone definitions. | Project Controls / Discipline Leads | Before baseline approval | OPEN / PROJECT EVIDENCE REQUIRED
PM07.01 | PM07 | Activity-specific weather and operability model | CORRECTION REQUIRED | The 10-day hold after offshore work is not a validated weather-risk model. | Establish operation-specific wind/wave/current/visibility limits from actual vessels and approved methods. | Marine / Planning / Assurance | Before offshore campaign sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM07.02 | PM07 | Activity-specific weather and operability model | CORRECTION REQUIRED | The 10-day hold after offshore work is not a validated weather-risk model. | Use relevant seasonal/metocean evidence to estimate workable hours and continuous safe windows. | Marine / Planning / Assurance | Before offshore campaign sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM07.03 | PM07 | Activity-specific weather and operability model | CORRECTION REQUIRED | The 10-day hold after offshore work is not a validated weather-risk model. | Model interruption, recovery, safe suspension, standby and demobilisation where they occur. | Marine / Planning / Assurance | Before offshore campaign sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM07.04 | PM07 | Activity-specific weather and operability model | CORRECTION REQUIRED | The 10-day hold after offshore work is not a validated weather-risk model. | Replace the coarse hold with a documented weather/contingency basis; retain P5 only as an illustrative scenario. | Marine / Planning / Assurance | Before offshore campaign sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM08.01 | PM08 | Quantitative schedule and cost risk assessment | NOT PERFORMED | Deterministic delay tests exist; no calibrated probabilistic risk model or confidence dates exist. | Link risks to specific activities, costs, owners, triggers and responses. | Risk / Planning / Cost | Before management forecast commitment | OPEN / PROJECT EVIDENCE REQUIRED
PM08.02 | PM08 | Quantitative schedule and cost risk assessment | NOT PERFORMED | Deterministic delay tests exist; no calibrated probabilistic risk model or confidence dates exist. | Develop evidence-based duration/risk ranges and correlation assumptions. | Risk / Planning / Cost | Before management forecast commitment | OPEN / PROJECT EVIDENCE REQUIRED
PM08.03 | PM08 | Quantitative schedule and cost risk assessment | NOT PERFORMED | Deterministic delay tests exist; no calibrated probabilistic risk model or confidence dates exist. | Run quantitative scenarios/probabilistic assessment with documented inputs if confidence dates are required. | Risk / Planning / Cost | Before management forecast commitment | OPEN / PROJECT EVIDENCE REQUIRED
PM08.04 | PM08 | Quantitative schedule and cost risk assessment | NOT PERFORMED | Deterministic delay tests exist; no calibrated probabilistic risk model or confidence dates exist. | Report confidence levels and drivers only after analysis; do not invent P50/P80 dates or contingency percentages. | Risk / Planning / Cost | Before management forecast commitment | OPEN / PROJECT EVIDENCE REQUIRED
PM09.01 | PM09 | Progress measurement and earned-value rules | UNDERDEVELOPED | Accepted quantities are specified, but discipline weighting and credit rules are not approved. | Define units, denominator, milestone weights and acceptance evidence for each work type. | Project Controls / QA / Cost | Before first progress report | OPEN / PROJECT EVIDENCE REQUIRED
PM09.02 | PM09 | Progress measurement and earned-value rules | UNDERDEVELOPED | Accepted quantities are specified, but discipline weighting and credit rules are not approved. | Keep physical progress, commercial billing and cash receipts separate. | Project Controls / QA / Cost | Before first progress report | OPEN / PROJECT EVIDENCE REQUIRED
PM09.03 | PM09 | Progress measurement and earned-value rules | UNDERDEVELOPED | Accepted quantities are specified, but discipline weighting and credit rules are not approved. | Base project-level weighting on approved budgets/hours and control accounts; avoid arbitrary mixed-tonnage percentages. | Project Controls / QA / Cost | Before first progress report | OPEN / PROJECT EVIDENCE REQUIRED
PM09.04 | PM09 | Progress measurement and earned-value rules | UNDERDEVELOPED | Accepted quantities are specified, but discipline weighting and credit rules are not approved. | Use CPI/SPI only with compatible approved planned/earned/actual baselines and consistent units. | Project Controls / QA / Cost | Before first progress report | OPEN / PROJECT EVIDENCE REQUIRED
PM10.01 | PM10 | Weekly update and forecasting protocol | UNDERDEVELOPED | Reporting rhythm exists; data-date, actualisation and remaining-work rules need formal definition. | Fix reporting data date, responsible data owners and evidence deadlines. | Project Controls | Before first controlled update | OPEN / PROJECT EVIDENCE REQUIRED
PM10.02 | PM10 | Weekly update and forecasting protocol | UNDERDEVELOPED | Reporting rhythm exists; data-date, actualisation and remaining-work rules need formal definition. | Record accepted actual starts/finishes, remaining quantities and realistic remaining durations. | Project Controls | Before first controlled update | OPEN / PROJECT EVIDENCE REQUIRED
PM10.03 | PM10 | Weekly update and forecasting protocol | UNDERDEVELOPED | Reporting rhythm exists; data-date, actualisation and remaining-work rules need formal definition. | Reconcile out-of-sequence work through authorised logic updates with preserved baseline history. | Project Controls | Before first controlled update | OPEN / PROJECT EVIDENCE REQUIRED
PM10.04 | PM10 | Weekly update and forecasting protocol | UNDERDEVELOPED | Reporting rhythm exists; data-date, actualisation and remaining-work rules need formal definition. | Issue variance narrative, critical/near-critical changes, six-week constraints and decisions with owners. | Project Controls | Before first controlled update | OPEN / PROJECT EVIDENCE REQUIRED
PM11.01 | PM11 | Weight and centre-of-gravity control | UNDERDEVELOPED | Weight/COG is recognised but no live controlled register or change-trigger workflow exists. | Assign module IDs, weight categories, uncertainty, inclusions/exclusions and COG coordinates. | Engineering / Fabrication / Marine | Before vessel commitment and each lift | OPEN / PROJECT EVIDENCE REQUIRED
PM11.02 | PM11 | Weight and centre-of-gravity control | UNDERDEVELOPED | Weight/COG is recognised but no live controlled register or change-trigger workflow exists. | Reconcile theoretical and measured weights including temporary steel, rigging and loose-shipped items. | Engineering / Fabrication / Marine | Before vessel commitment and each lift | OPEN / PROJECT EVIDENCE REQUIRED
PM11.03 | PM11 | Weight and centre-of-gravity control | UNDERDEVELOPED | Weight/COG is recognised but no live controlled register or change-trigger workflow exists. | Apply the supplied criteria reanalysis triggers:weight increase over 5% or COG shift over 2% of corresponding dimension. | Engineering / Fabrication / Marine | Before vessel commitment and each lift | OPEN / PROJECT EVIDENCE REQUIRED
PM11.04 | PM11 | Weight and centre-of-gravity control | UNDERDEVELOPED | Weight/COG is recognised but no live controlled register or change-trigger workflow exists. | Release revised lift/transport calculations and communicate changes to vessel and installation authorities. | Engineering / Fabrication / Marine | Before vessel commitment and each lift | OPEN / PROJECT EVIDENCE REQUIRED
PM12.01 | PM12 | Technical interfaces and decision escalation | UNDERDEVELOPED | Interface and decision registers are described but not fully populated with closure deadlines. | Populate physical, functional, operational, organisational and document interfaces bridge by bridge. | Interface Manager / Project Director | Before design release and weekly | OPEN / PROJECT EVIDENCE REQUIRED
PM12.02 | PM12 | Technical interfaces and decision escalation | UNDERDEVELOPED | Interface and decision registers are described but not fully populated with closure deadlines. | Assign one interface owner, responding party, need-by date and objective closure evidence. | Interface Manager / Project Director | Before design release and weekly | OPEN / PROJECT EVIDENCE REQUIRED
PM12.03 | PM12 | Technical interfaces and decision escalation | UNDERDEVELOPED | Interface and decision registers are described but not fully populated with closure deadlines. | Escalate missed critical need dates and preserve decision rationale and authorised changes. | Interface Manager / Project Director | Before design release and weekly | OPEN / PROJECT EVIDENCE REQUIRED
PM12.04 | PM12 | Technical interfaces and decision escalation | UNDERDEVELOPED | Interface and decision registers are described but not fully populated with closure deadlines. | Separate information requests from deviations, nonconformances and commercial change requests. | Interface Manager / Project Director | Before design release and weekly | OPEN / PROJECT EVIDENCE REQUIRED
PM13.01 | PM13 | Supplier and subcontract performance assurance | UNDERDEVELOPED | Procurement packages exist but supplier-specific surveillance and performance controls are not developed. | Qualify capability, actual capacity, competence, financial exposure and subcontract interfaces as applicable. | Supply Chain / QA / Contracts | Before placement and during supply | OPEN / PROJECT EVIDENCE REQUIRED
PM13.02 | PM13 | Supplier and subcontract performance assurance | UNDERDEVELOPED | Procurement packages exist but supplier-specific surveillance and performance controls are not developed. | Flow down drawings/specifications, QA/HSE, documentation, schedule, change and completion obligations. | Supply Chain / QA / Contracts | Before placement and during supply | OPEN / PROJECT EVIDENCE REQUIRED
PM13.03 | PM13 | Supplier and subcontract performance assurance | UNDERDEVELOPED | Procurement packages exist but supplier-specific surveillance and performance controls are not developed. | Agree supplier deliverable registers, inspections, expediting milestones and evidence requirements. | Supply Chain / QA / Contracts | Before placement and during supply | OPEN / PROJECT EVIDENCE REQUIRED
PM13.04 | PM13 | Supplier and subcontract performance assurance | UNDERDEVELOPED | Procurement packages exist but supplier-specific surveillance and performance controls are not developed. | Review recovery, quality failures and counterparty risks; secure authorised remedies and alternative plans. | Supply Chain / QA / Contracts | Before placement and during supply | OPEN / PROJECT EVIDENCE REQUIRED
PM14.01 | PM14 | Field change and configuration management | UNDERDEVELOPED | Change control is general; technical field-change routing and affected-document propagation need definition. | Use distinct TQ/RFI, NCR, concession/deviation, field-change and commercial-change identifiers. | Engineering / Construction / Contracts | Before offshore execution | OPEN / PROJECT EVIDENCE REQUIRED
PM14.02 | PM14 | Field change and configuration management | UNDERDEVELOPED | Change control is general; technical field-change routing and affected-document propagation need definition. | Require technical evaluation before any design-affecting field modification. | Engineering / Construction / Contracts | Before offshore execution | OPEN / PROJECT EVIDENCE REQUIRED
PM14.03 | PM14 | Field change and configuration management | UNDERDEVELOPED | Change control is general; technical field-change routing and affected-document propagation need definition. | Update affected calculations, drawings, MTO, inspection, safety, schedule and cost records. | Engineering / Construction / Contracts | Before offshore execution | OPEN / PROJECT EVIDENCE REQUIRED
PM14.04 | PM14 | Field change and configuration management | UNDERDEVELOPED | Change control is general; technical field-change routing and affected-document propagation need definition. | Maintain red-lines and superseded-document control; verbal instructions are not a design release. | Engineering / Construction / Contracts | Before offshore execution | OPEN / PROJECT EVIDENCE REQUIRED
PM15.01 | PM15 | Critical safety-barrier verification | UNDERDEVELOPED | HSE topics are covered; operation-specific critical controls and verification evidence are not established. | Identify credible major hazards for the actual lifting, structural modification, marine and live-service tasks. | HSE / Operation Owners | Before each high-risk operation | OPEN / PROJECT EVIDENCE REQUIRED
PM15.02 | PM15 | Critical safety-barrier verification | UNDERDEVELOPED | HSE topics are covered; operation-specific critical controls and verification evidence are not established. | Assign each critical preventive/mitigating control an owner, standard and verification record. | HSE / Operation Owners | Before each high-risk operation | OPEN / PROJECT EVIDENCE REQUIRED
PM15.03 | PM15 | Critical safety-barrier verification | UNDERDEVELOPED | HSE topics are covered; operation-specific critical controls and verification evidence are not established. | Check controls at the work front; unresolved critical barriers hold the operation. | HSE / Operation Owners | Before each high-risk operation | OPEN / PROJECT EVIDENCE REQUIRED
PM15.04 | PM15 | Critical safety-barrier verification | UNDERDEVELOPED | HSE topics are covered; operation-specific critical controls and verification evidence are not established. | Include emergency, rescue, isolation, communication and simultaneous-operation responsibilities. | HSE / Operation Owners | Before each high-risk operation | OPEN / PROJECT EVIDENCE REQUIRED
PM16.01 | PM16 | SIMOPS, shutdown and access integration | UNDERDEVELOPED | Access/permits are gates but operational windows are not fully scheduled and agreed. | Build platform-specific access, hot-work, isolation, shutdown and simultaneous-operation calendars. | ONGC Interface / Offshore / Marine | Before baseline and mobilisation | OPEN / PROJECT EVIDENCE REQUIRED
PM16.02 | PM16 | SIMOPS, shutdown and access integration | UNDERDEVELOPED | Access/permits are gates but operational windows are not fully scheduled and agreed. | Coordinate vessels, transfers, cranes, service routes and emergency access in space and time. | ONGC Interface / Offshore / Marine | Before baseline and mobilisation | OPEN / PROJECT EVIDENCE REQUIRED
PM16.03 | PM16 | SIMOPS, shutdown and access integration | UNDERDEVELOPED | Access/permits are gates but operational windows are not fully scheduled and agreed. | Connect agreed windows to work packs and schedule logic; record operational restrictions. | ONGC Interface / Offshore / Marine | Before baseline and mobilisation | OPEN / PROJECT EVIDENCE REQUIRED
PM16.04 | PM16 | SIMOPS, shutdown and access integration | UNDERDEVELOPED | Access/permits are gates but operational windows are not fully scheduled and agreed. | Obtain renewed permissions after weather, configuration or seasonal changes. | ONGC Interface / Offshore / Marine | Before baseline and mobilisation | OPEN / PROJECT EVIDENCE REQUIRED
PM17.01 | PM17 | Safe seasonal suspension and restart plan | UNDERDEVELOPED | Second-season comparator assumes safe stoppoints and 7-day remobilisation without operation-specific proof. | Define structurally and operationally safe suspension states for every unfinished package. | Marine / Construction / Engineering | Before adopting two-season strategy | OPEN / PROJECT EVIDENCE REQUIRED
PM17.02 | PM17 | Safe seasonal suspension and restart plan | UNDERDEVELOPED | Second-season comparator assumes safe stoppoints and 7-day remobilisation without operation-specific proof. | Engineer temporary support, preservation, service continuity and protection through the gap. | Marine / Construction / Engineering | Before adopting two-season strategy | OPEN / PROJECT EVIDENCE REQUIRED
PM17.03 | PM17 | Safe seasonal suspension and restart plan | UNDERDEVELOPED | Second-season comparator assumes safe stoppoints and 7-day remobilisation without operation-specific proof. | Plan actual demobilisation/remobilisation, reinspection, revalidation, renewed permits and costs. | Marine / Construction / Engineering | Before adopting two-season strategy | OPEN / PROJECT EVIDENCE REQUIRED
PM17.04 | PM17 | Safe seasonal suspension and restart plan | UNDERDEVELOPED | Second-season comparator assumes safe stoppoints and 7-day remobilisation without operation-specific proof. | Recalculate restart dates and commitments; seven days is only a placeholder, not established readiness. | Marine / Construction / Engineering | Before adopting two-season strategy | OPEN / PROJECT EVIDENCE REQUIRED
PM18.01 | PM18 | Systems-based completion and turnover | UNDERDEVELOPED | Test categories exist; detailed system boundaries and completion certificates are not mapped. | Assign bridge/system/subsystem IDs and define structural, electrical, piping and instrument boundaries. | Completions / Discipline Leads / ONGC | Before construction work packs | OPEN / PROJECT EVIDENCE REQUIRED
PM18.02 | PM18 | Systems-based completion and turnover | UNDERDEVELOPED | Test categories exist; detailed system boundaries and completion certificates are not mapped. | Define agreed construction-complete, ready-for-test, ready-for-service and client-acceptance evidence. | Completions / Discipline Leads / ONGC | Before construction work packs | OPEN / PROJECT EVIDENCE REQUIRED
PM18.03 | PM18 | Systems-based completion and turnover | UNDERDEVELOPED | Test categories exist; detailed system boundaries and completion certificates are not mapped. | Link tests, punch categories, reinstatement, isolations and certificates to each boundary. | Completions / Discipline Leads / ONGC | Before construction work packs | OPEN / PROJECT EVIDENCE REQUIRED
PM18.04 | PM18 | Systems-based completion and turnover | UNDERDEVELOPED | Test categories exist; detailed system boundaries and completion certificates are not mapped. | For BHS require accepted new bridge/services before demolition release; do not substitute structural completion alone. | Completions / Discipline Leads / ONGC | Before construction work packs | OPEN / PROJECT EVIDENCE REQUIRED
PM19.01 | PM19 | Operations, maintainability and asset-data handover | UNDERDEVELOPED | Dossiers are planned but operations/maintenance deliverables and asset-data requirements need agreement. | Review bearing replacement, inspection access, drainage/coating maintenance and service access. | Engineering / Completions / ONGC Operations | Before detailed design freeze and handover | OPEN / PROJECT EVIDENCE REQUIRED
PM19.02 | PM19 | Operations, maintainability and asset-data handover | UNDERDEVELOPED | Dossiers are planned but operations/maintenance deliverables and asset-data requirements need agreement. | Agree applicable vendor manuals, preservation/maintenance requirements, spares and training. | Engineering / Completions / ONGC Operations | Before detailed design freeze and handover | OPEN / PROJECT EVIDENCE REQUIRED
PM19.03 | PM19 | Operations, maintainability and asset-data handover | UNDERDEVELOPED | Dossiers are planned but operations/maintenance deliverables and asset-data requirements need agreement. | Prepare asset/tag lists and agreed digital/as-built/model formats and ownership. | Engineering / Completions / ONGC Operations | Before detailed design freeze and handover | OPEN / PROJECT EVIDENCE REQUIRED
PM19.04 | PM19 | Operations, maintainability and asset-data handover | UNDERDEVELOPED | Dossiers are planned but operations/maintenance deliverables and asset-data requirements need agreement. | Obtain operations acceptance of maintainability actions and delivered asset data as applicable. | Engineering / Completions / ONGC Operations | Before detailed design freeze and handover | OPEN / PROJECT EVIDENCE REQUIRED
PM20.01 | PM20 | Funding, contingency and financial risk governance | OPEN COMMERCIAL | Cost register is unpriced; no funding adequacy, margin or approved contingency can be claimed. | Obtain quotations and actual charter terms, mobilisation, standby, tax, FX/import/local-content treatment. | Finance / Cost / Commercial | Before financial sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM20.02 | PM20 | Funding, contingency and financial risk governance | OPEN COMMERCIAL | Cost register is unpriced; no funding adequacy, margin or approved contingency can be claimed. | Build integrated cost, commitment, cash, certification, collections and bank-margin forecasts. | Finance / Cost / Commercial | Before financial sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM20.03 | PM20 | Funding, contingency and financial risk governance | OPEN COMMERCIAL | Cost register is unpriced; no funding adequacy, margin or approved contingency can be claimed. | Define risk contingency ownership, drawdown authority and change/budget thresholds. | Finance / Cost / Commercial | Before financial sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM20.04 | PM20 | Funding, contingency and financial risk governance | OPEN COMMERCIAL | Cost register is unpriced; no funding adequacy, margin or approved contingency can be claimed. | Test late payments, cost escalation and second-season exposures; confirm funded response options. | Finance / Cost / Commercial | Before financial sanction | OPEN / PROJECT EVIDENCE REQUIRED
PM21.01 | PM21 | Communication and stakeholder engagement | UNDERDEVELOPED | Meeting rhythm exists but a stakeholder/communications responsibility plan is not explicit. | Identify ONGC engineering/operations/SCM, vessel/yard/vendor, assurance and statutory stakeholders as applicable. | Project Director / Interface Manager | At project initiation | OPEN / PROJECT EVIDENCE REQUIRED
PM21.02 | PM21 | Communication and stakeholder engagement | UNDERDEVELOPED | Meeting rhythm exists but a stakeholder/communications responsibility plan is not explicit. | Define authorised channels, transmittals, meeting decisions and required approval notifications. | Project Director / Interface Manager | At project initiation | OPEN / PROJECT EVIDENCE REQUIRED
PM21.03 | PM21 | Communication and stakeholder engagement | UNDERDEVELOPED | Meeting rhythm exists but a stakeholder/communications responsibility plan is not explicit. | Assign escalation routes for engineering, quality, operational and commercial issues. | Project Director / Interface Manager | At project initiation | OPEN / PROJECT EVIDENCE REQUIRED
PM21.04 | PM21 | Communication and stakeholder engagement | UNDERDEVELOPED | Meeting rhythm exists but a stakeholder/communications responsibility plan is not explicit. | Control external commitments; minutes are not automatically contract amendments or technical approvals. | Project Director / Interface Manager | At project initiation | OPEN / PROJECT EVIDENCE REQUIRED
PM22.01 | PM22 | Data, document and delivery assurance | UNDERDEVELOPED | Files exist, but successful recipient download/opening remains unverified. | Use a controlled repository, permissions, revision history, backup and agreed file naming/formats. | Document Control / Project Controls | Before each formal issue | OPEN / PROJECT EVIDENCE REQUIRED
PM22.02 | PM22 | Data, document and delivery assurance | UNDERDEVELOPED | Files exist, but successful recipient download/opening remains unverified. | Maintain issued-file manifest, checksums, transmittal purpose and affected-document links. | Document Control / Project Controls | Before each formal issue | OPEN / PROJECT EVIDENCE REQUIRED
PM22.03 | PM22 | Data, document and delivery assurance | UNDERDEVELOPED | Files exist, but successful recipient download/opening remains unverified. | Test readability, units, formulas, print layouts and recipient access to the actual delivery route. | Document Control / Project Controls | Before each formal issue | OPEN / PROJECT EVIDENCE REQUIRED
PM22.04 | PM22 | Data, document and delivery assurance | UNDERDEVELOPED | Files exist, but successful recipient download/opening remains unverified. | Obtain recipient acknowledgement; local file integrity does not prove successful delivery. | Document Control / Project Controls | Before each formal issue | OPEN / PROJECT EVIDENCE REQUIRED
PM23.01 | PM23 | Integrated assurance and independent review | NOT COMPLETED | Current audit is a self-review; there is no evidenced independent project/design assurance sign-off. | Plan risk-based reviews of scope, engineering, schedule/cost, fabrication, marine and completion readiness. | Project Director / Independent Review Authority | Before baseline, marine and construction release | OPEN / PROJECT EVIDENCE REQUIRED
PM23.02 | PM23 | Integrated assurance and independent review | NOT COMPLETED | Current audit is a self-review; there is no evidenced independent project/design assurance sign-off. | Assign suitably competent reviewers with required independence and clear review scope. | Project Director / Independent Review Authority | Before baseline, marine and construction release | OPEN / PROJECT EVIDENCE REQUIRED
PM23.03 | PM23 | Integrated assurance and independent review | NOT COMPLETED | Current audit is a self-review; there is no evidenced independent project/design assurance sign-off. | Close review findings with accountable owners and objective evidence. | Project Director / Independent Review Authority | Before baseline, marine and construction release | OPEN / PROJECT EVIDENCE REQUIRED
PM23.04 | PM23 | Integrated assurance and independent review | NOT COMPLETED | Current audit is a self-review; there is no evidenced independent project/design assurance sign-off. | Record release decisions and residual risks; document count and checklist completion alone do not establish adequacy. | Project Director / Independent Review Authority | Before baseline, marine and construction release | OPEN / PROJECT EVIDENCE REQUIRED
PM24.01 | PM24 | Package acceptance, lessons and closure criteria | UNDERDEVELOPED | A-to-Z actions exist; measurable package acceptance and evidence-based final closure need agreement. | Agree a deliverable acceptance matrix distinguishing prepared, checked, approved, issued, executed and accepted states. | Project Director / Contracts / QA | Before management package approval | OPEN / PROJECT EVIDENCE REQUIRED
PM24.02 | PM24 | Package acceptance, lessons and closure criteria | UNDERDEVELOPED | A-to-Z actions exist; measurable package acceptance and evidence-based final closure need agreement. | Link remaining P6 actions and this supplement to named owners, dates and evidence. | Project Director / Contracts / QA | Before management package approval | OPEN / PROJECT EVIDENCE REQUIRED
PM24.03 | PM24 | Package acceptance, lessons and closure criteria | UNDERDEVELOPED | A-to-Z actions exist; measurable package acceptance and evidence-based final closure need agreement. | Capture actual productivity, rework and marine downtime and feed changes into forecasts. | Project Director / Contracts / QA | Before management package approval | OPEN / PROJECT EVIDENCE REQUIRED
PM24.04 | PM24 | Package acceptance, lessons and closure criteria | UNDERDEVELOPED | A-to-Z actions exist; measurable package acceptance and evidence-based final closure need agreement. | Close the management package only when it is internally consistent and the required project-specific reviews are evidenced. | Project Director / Contracts / QA | Before management package approval | OPEN / PROJECT EVIDENCE REQUIRED

## Requirements Traceability
RequirementID | Requirement | Source | Applicability | Deliverable/evidence | Verification | Acceptanceauthority | Status | Evidence/reference
REQ01 | Tenbridge EPC scope and interfaces | B774 structuralSOW RevC / GCC2.1.1 | All 10 bridges | Scope matrix + bridge work packs | Document/scope review | Project Director / ONGC as applicable | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ02 | 25 year design life | BRRP Part II p 119 | Newbridges | Design basis and calculations | Engineering check | Technical Authority | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ03 | Material elastic properties | Part I Annexure 2 p 66 | Structuralmodels | Model input record E210000 MPa and material properties | Model audit | Checker | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ04 | Globalwalkway 250 kg/m2;local grating 500 kg/m2 | Part I bridgeclausep 42;Annexure 4 p 70 | Applicablewalkways/grating | Load maps and element checks | Calculation review | Engineering/QA | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ05 | Minimum 1.20 m clearwalkway | Part I bridgeclausep 43 | Newbridgeaccess | GA/clearance details and survey | Drawing/field inspection | Engineering/ONGC | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ06 | Relative movement 150%;hinged thrust 150% | Part I bridgeclausep 43 | Bridge supports | Movement envelopes, bearing/connection calculations | Calculation review | Technical Authority | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ07 | Applicablefuturepiping 20% allowance | Part I bridgeclausep 42 | Piping-carrying bridges | Load register with included allowances | Calculation reconciliation | Engineering | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ08 | VerticalL/400;lateralwindL/500 | Part I p 43;Annexure 12 p 86 | Bridges | Serviceability calculations | Model/result review | Checker | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ09 | Camber compensates dead-load deflection | Part I bridgeclausep 43 | Newbridges | Camber profile and setting geometry | Calculation/drawing check | Technical Authority | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ10 | 15 secgust>50 m;3 secgust<50 m | Part I Annexure 5 p 73 | 56/84/42 m studyconcepts | Wind derivation and load cases | Calculation review | Checker | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ11 | TrussVIV displacement/fatigue | Part I bridgeclausep 42 | Applicabletrussmembers | VIV/fatigue report | Specialistcheck | Technical Authority | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ12 | Actualweight/COG change-trigger reanalysis | Part I liftingcriteriap 20 | Liftedmodules | Weight register and revised lift analysis | Weight/liftreview | Marine/Structural | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ13 | NewBHS bridge/services acceptedbefore demolition | SOW6.3.4;B 774 methodologyRevC | BHS-SLQ | Operationalacceptance + demolitionrelease | Operational/engineering review | ONGC/Technical Authority | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ14 | ICG/ICP/BHS strengthening addendum | Addendum_Structure_SOW p 1 | Applicableplatforms | Checkedwrap/landing/jacketdetails and records | Calculation/inspection | Engineering/QA | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ15 | Weld/NDT/material/coatingcontrols | Specifications 2009 F/6001 F/2005;MTO IRT | Applicablework | ApprovedITP and inspectionrecords | Inspection/audit | QA/CA/TPI as applicable | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ16 | Digitalmeasurement beforebilling | TechnicalSCC e-MBprovisions | Measured/invoicedwork | Acceptedquantity/e-MB/certification/invoicepack | Commercialrecordreview | Contracts/ONGC | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ17 | 12 months fromNOA;conditionalmonsoon relief | GCC6.3.1.1;TechnicalSCC 2 | Overallproject | Contractcalendar,notices and extensionrecords | Contractreview | Contracts/ONGC | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN
REQ18 | Contractorconstruction supportresources | B 774 methodologyRevC pp 137 onward | Offshoreexecution | Spread,accommodation,crane/logisticsplan | Readinessreview | Marine/Construction | REQUIREMENT LOCATED; IMPLEMENTATION/ACCEPTANCE OPEN

## Control Account Map
Bridge | Workstream | Proposedcontrolaccount | CBScategory | Accountablemanager | Budgetbasis | Application
ICW-ICG UD | Engineering | BRRP/ICW-ICG UD/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG UD | Materials | BRRP/ICW-ICG UD/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG UD | Fabrication | BRRP/ICW-ICG UD/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG UD | Marine | BRRP/ICW-ICG UD/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG UD | Offshore | BRRP/ICW-ICG UD/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG UD | Completions | BRRP/ICW-ICG UD/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG LD | Engineering | BRRP/ICW-ICG LD/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG LD | Materials | BRRP/ICW-ICG LD/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG LD | Fabrication | BRRP/ICW-ICG LD/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG LD | Marine | BRRP/ICW-ICG LD/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG LD | Offshore | BRRP/ICW-ICG LD/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICW-ICG LD | Completions | BRRP/ICW-ICG LD/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP UD | Engineering | BRRP/ICG-ICP UD/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP UD | Materials | BRRP/ICG-ICP UD/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP UD | Fabrication | BRRP/ICG-ICP UD/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP UD | Marine | BRRP/ICG-ICP UD/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP UD | Offshore | BRRP/ICG-ICP UD/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP UD | Completions | BRRP/ICG-ICP UD/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP LD | Engineering | BRRP/ICG-ICP LD/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP LD | Materials | BRRP/ICG-ICP LD/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP LD | Fabrication | BRRP/ICG-ICP LD/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP LD | Marine | BRRP/ICG-ICP LD/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP LD | Offshore | BRRP/ICG-ICP LD/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
ICG-ICP LD | Completions | BRRP/ICG-ICP LD/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
BHS-SLQ | Engineering | BRRP/BHS-SLQ/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
BHS-SLQ | Materials | BRRP/BHS-SLQ/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
BHS-SLQ | Fabrication | BRRP/BHS-SLQ/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
BHS-SLQ | Marine | BRRP/BHS-SLQ/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
BHS-SLQ | Offshore | BRRP/BHS-SLQ/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
BHS-SLQ | Completions | BRRP/BHS-SLQ/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SLQ-WIS | Engineering | BRRP/SLQ-WIS/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SLQ-WIS | Materials | BRRP/SLQ-WIS/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SLQ-WIS | Fabrication | BRRP/SLQ-WIS/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SLQ-WIS | Marine | BRRP/SLQ-WIS/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SLQ-WIS | Offshore | BRRP/SLQ-WIS/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SLQ-WIS | Completions | BRRP/SLQ-WIS/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
NQO-NQD | Engineering | BRRP/NQO-NQD/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
NQO-NQD | Materials | BRRP/NQO-NQD/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
NQO-NQD | Fabrication | BRRP/NQO-NQD/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
NQO-NQD | Marine | BRRP/NQO-NQD/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
NQO-NQD | Offshore | BRRP/NQO-NQD/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
NQO-NQD | Completions | BRRP/NQO-NQD/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
WIN-NC | Engineering | BRRP/WIN-NC/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
WIN-NC | Materials | BRRP/WIN-NC/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
WIN-NC | Fabrication | BRRP/WIN-NC/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
WIN-NC | Marine | BRRP/WIN-NC/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
WIN-NC | Offshore | BRRP/WIN-NC/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
WIN-NC | Completions | BRRP/WIN-NC/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SC1 | Engineering | BRRP/SCA-SC1/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SC1 | Materials | BRRP/SCA-SC1/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SC1 | Fabrication | BRRP/SCA-SC1/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SC1 | Marine | BRRP/SCA-SC1/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SC1 | Offshore | BRRP/SCA-SC1/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SC1 | Completions | BRRP/SCA-SC1/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SCF | Engineering | BRRP/SCA-SCF/ENG | ENG | Engineering Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SCF | Materials | BRRP/SCA-SCF/MAT | MAT | Procurement Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SCF | Fabrication | BRRP/SCA-SCF/FAB | FAB | Fabrication Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SCF | Marine | BRRP/SCA-SCF/MAR | MAR | Marine Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SCF | Offshore | BRRP/SCA-SCF/OFF | OFF | Offshore Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once
SCA-SCF | Completions | BRRP/SCA-SCF/COM | COM | Completions Manager | Budget/hours and resource profile pending | Use same code in schedule/cost/PO/progress/dossier; shared costs allocated once

## Progress Rules Proposal
Discipline | Milestone | Proposedweightpercent | Requiredevidence | Approvalstatus | Actualprogress
Engineering | Reviewed design-input/calculation scope | 15 | Accepted input/checking scope | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Engineering | Checked calculations and discipline drawings | 45 | Checker records | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Engineering | Applicable client/interface comments closed | 30 | Review/closure records | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Engineering | Authorised issue and complete records | 10 | Controlled transmittal | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Procurement | Technically accepted order placement | 10 | Authorised PO and technical acceptance | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Procurement | Verified manufacturing milestones | 30 | Agreed milestone/inspection evidence | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Procurement | Accepted inspection and dispatch | 30 | Release/dispatch records | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Procurement | Accepted site/yard receipt | 20 | Receipt/traceability | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Procurement | Complete supplier documentation | 10 | Accepted dossier | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Fabrication | Traceable prepared material | 10 | Accepted material/preparation records | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Fabrication | Accepted fit-up/assembly | 20 | Inspection record | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Fabrication | Completed weld production stage | 35 | Weld map/records; no defect closure implied | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Fabrication | Required NDT/repairs and dimensions accepted | 20 | QA acceptance | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Fabrication | Coating and preservation accepted | 10 | Coating record | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Fabrication | Final package release/dossier | 5 | QA release | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Installation | Accepted landing/placement stage | 25 | Approved installation record | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Installation | Permanent connections completed | 40 | Connection records; acceptance pending as applicable | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Installation | Required inspections/restoration accepted | 20 | QA acceptance | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Installation | Package acceptance and records | 15 | Accepted package closure | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Commissioning | Test readiness accepted | 20 | Approved prerequisites and boundary | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Commissioning | Applicable tests executed and accepted | 50 | Signed test records | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Commissioning | Reinstatement and critical punch closure | 20 | Operational/QA closure | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned
Commissioning | Operational acceptance and dossier | 10 | Client acceptance | PROPOSED INTERNAL RULE; approve before use; not A-10 billing weights | No current progress percentage assigned

## Procurement Network Gaps
PackageID | Package | Requiredneedpoint | Vendorlead time | Vendordocapprovaldate | Deliverydate | Status | Networkaction
P01 | Structural tubulars / sections | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P02 | Plates / gussets / stiffeners | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P03 | Jacket wrap steel | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P04 | Grating | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P05 | Handrails | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P06 | GI sheeting / roofing | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P07 | Bearings / PTFE / guides | Newbridge bearing/landing installation readiness (I010/I020/I030) |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P08 | Structural bolts / fasteners | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P09 | Welding consumables | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P10 | Coating system / abrasives | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P11 | Cables / cable trays / lighting | Applicable service installation/commissioning readiness; BHS I020 sequence where relevant |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P12 | BHS piping / fittings / valves | Applicable service installation/commissioning readiness; BHS I020 sequence where relevant |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P13 | Instrument / control interfaces | Applicable service installation/commissioning readiness; BHS I020 sequence where relevant |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P14 | Service supports / monorail | Applicable service installation/commissioning readiness; BHS I020 sequence where relevant |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P15 | Lifeboat / survival craft interfaces | Applicable service installation/commissioning readiness; BHS I020 sequence where relevant |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P16 | Scaffolding / access / temporary steel | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P17 | Lifting gear / spreader / rigging | Marine readiness before loadout/lifting/transport |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P18 | Sea-fastening / grillage | Marine readiness before loadout/lifting/transport |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P19 | Survey services | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P20 | Engineering specialist services | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P21 | NDT / dimensional / coating inspection | Each fabrication/offshore inspection holdpoint |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P22 | Fabrication yard slots | Applicable fabrication/work pack release |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P23 | Heavy-lift / cargo / support spreads | Marine readiness before loadout/lifting/transport |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P24 | Towage / anchorhandling / supply | Marine readiness before loadout/lifting/transport |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness
P25 | Waste handling / backload / disposal | Beforedemolition/backload(D020/D030) |  |  |  | VENDOR LEADTIME / DOCUMENT DATES UNKNOWN | Create separate detailed network; P010 bulk placeholder does not prove this package readiness

## Technical and Planning Issues
ID | Type | Issue | Evidence | Owner | Closure
TQ01 | Technical query | BHS SLQ support wording | SOWcontradiction vs report/methodology fixed intent | Engineering/ONGC | Approvedsupportphilosophy and drawing/modelupdate
TQ02 | Technical query | Camber rule versus source 1:200 | Suppliedcriteria requires dead-load compensation | Technical Authority | Checkedcamberprofile and instructions
TQ03 | Technical query | Live-load totals and actual areas | ICW156.25 vs 144.69 kN;otherrectangular screens differ | AnalysisLead | Reconciledload map and modelrevision
MTO01 | Quantity reconciliation | Structural 1141 vs 1142 MT | Landingstrengthening 216 vs 217 MT | Engineering/QS | ControlledMTOreconciliation
MTO02 | Quantity reconciliation | Handrail 1166 vs 1168 m | Source rows versus printedtotal | Engineering/QS | Drawing-basedtake-off
MTO03 | Quantity reconciliation | Grating 718 vs 719 m2 | Source rows versus printedtotal | Engineering/QS | Drawing-basedtake-off
SCH01 | Planning correction | Longlead packages not individually validated | P 010 generic 25 daymaterialsworkflow | Procurement/Planning | Vendor-backednetworkupdate
SCH02 | Planning correction | Weatherreserve model too coarse | 10 dayholdafterproductivework | Marine/Planning | Operation-specificweather/contingencymodel
DEL01 | Delivery issue | Recipientdownloadsnotconfirmed | User repeatedlyreportedfileaccessfailure | DocumentControl | Recipientopensactualissuedfiles

## Turnover Boundaries
SystemID | Boundary | Includedscope | Owner | Acceptanceevidence | Dependency
SYS-STR | Eachbridge permanentstructure | Connections,grating,handrails,coating,dimensions | Construction/QA | Acceptedinspections and punch status | Required for bridge acceptance
SYS-BRG | Newbridge bearings/guides | Settings,movementclearances,restraints,protection | Engineering/QA | Acceptedinstallation/setting records | Required before operational acceptance
SYS-ELE | Applicableelectricalcircuits | Cables,trays,lighting,earthing,isolations | Electrical/ONGC | Approvedtests and energisation/reinstatement | Boundaries/values to agree
SYS-PIP | ApplicableBHS pipe systems | Lines,tie-ins,supports,tests,isolation/reinstatement | Piping/ONGC | Line-specifictests and operatingacceptance | Required before relevantoldservice removal
SYS-INS | Applicableinstrument/controlloops | Loops,functions,isolations and restoration | Instrumentation/ONGC | Loop/functiontest records | Applicable scope to confirm
SYS-LSA | Applicablelifesaving/accessinterfaces | Muster,access,lifeboatinterfaces,safetystudyactions | HSE/ONGC | Approvedcommissioning/operationalrecords | Scope/vendorrequirements to confirm
SYS-DMO | BHS existingbridge removal | Isolation,stability,demolition/backload | Technical Authority/ONGC | Newbridge/servicesaccepted + demolitionrelease | No removal on structuralplacementalone

## Change Workflows
Type | Trigger | Process | Control
RFI/TQ | Clarify existing information/requirement | Engineeringresponse;recordsource;assessaffectedwork | No automaticdesignchangeauthorisation
NCR | Actualwork/materialdoesnotmeetrequirement | Contain;evaluate;approvedrepair/rework/disposition;verifyclosure | Concessionrequiresauthorisedtechnical/clientacceptancewhereapplicable
Deviation/concession | Proposeddeparturefromrequirement | Technical/commercialevaluation;approvalbeforeuse | Do not treatassilentscopechange
Fieldchange | Proposedchangeatsite | Technicalreviewandaffectedcalculation/drawing/MTO/safetyreview | Workhelduntilrequiredrelease
Commercialchange | Potentialcontractscope/time/costchange | Timelynotices;instruction;substantiation;authorisedsettlement | Noentitlementassumedfromtechnicalqueryalone