# BRRP — Review of latest uploaded documents

P9 | 25 October 2026 | Tender ZW1PC26002 | Source review and required package updates

All 19 uploaded files were downloaded, opened and hash-checked: 17 distinct contents in this batch; 9 new distinct contents versus prior local uploads, totalling 373 new pages. Nine uploaded files match earlier local sources exactly; two further files duplicate another new/batch source. Duplicate files are retained in the inventory.

This is an input and impact audit, not a claim that the entire engineering design, schedule or all historical documents have been fully validated. PDF page references below are one-based file pages. Bidder questions/proposals are distinguished from the reply column; no external messages, declarations, orders or approvals were issued.

# Most significant outcome

SVL Revision12.3 is now located in Combined Addendum3 pages261–341. This closes that specific previous missing-input finding. Commercial/security controls, steel-origin evidence, survey responsibility, PPE and discipline QA requirements require downstream updates. Earlier engineering and schedule deliverables remain development material, without AFC approval or a newly calculated critical path.

## P9-01 — Bid security

Source: Corrigendum.pdf p1

Any e-BG must be executed on NeSL before the tender closing deadline; later execution is liable to rejection.

Required update — Record portal execution timestamp and evidence; reconcile actual closing date with all extension notices.

Proposed owner: Treasury / Bid Manager. Completion evidence: not established by this source review.

## P9-02 — Bid validity

Source: Corrigendum_2.pdf pp1-2,5; Corrigendum_4.pdf p1; CQ_replies_BRRP.pdf pp2-3

Bid security extends 45 days beyond bid validity or extended validity. Bid validity is 120 days after opening of unpriced techno-contractual bids; do not anchor it to submission closing.

Required update — Use actual opening date; diarise bid and security expiry separately. Surety claim-period provisions remain distinct.

Proposed owner: Treasury / Contracts. Completion evidence: not established by this source review.

## P9-03 — Performance security

Source: Corrigendum_1_BRRP.pdf p1

The quoted ITB 28.1 option for 3% initial security plus 7% progressive deductions is deleted.

Required update — Remove that financing assumption; reconcile remaining ITB 28.1, IFB and B-3 for governing amounts, submission and validity. Do not infer replacement wording from deletion alone.

Proposed owner: Contracts / Finance. Completion evidence: not established by this source review.

## P9-04 — Supporting-company guarantees

Source: Corrigendum_2.pdf pp2-5

B-19/B-20/B-22 specified guarantee deadlines change from 15 to 30 days from NOA. Applicable supporting/JV guarantee provisions include delayed-submission recovery wording.

Required update — Set separate applicable-route milestones. Review 1.5% of performance-security amount per month or part-month recovery wording; do not apply indiscriminately to every guarantee.

Proposed owner: Contracts / Treasury. Completion evidence: not established by this source review.

## P9-05 — Setting out and changes

Source: Corrigendum_3.pdf p1, GCC 2.3.6

Modified column reinstates setting-out responsibility. Contractor corrects its positioning errors; company checking does not relieve it. Later company data/instructions after pre-engineering survey causing scope changes are dealt with under Clause 8.0.

Required update — Establish controlled datums, coordinates, survey acceptance and independent dimensional checks; preserve instruction/change evidence. This clause is not deleted.

Proposed owner: Survey / Engineering / Contracts. Completion evidence: not established by this source review.

## P9-06 — Domestic steel compliance

Source: Corrigendum_3.pdf pp1-8

DMI&SP policy reference changes to notification dated 17 December 2025, G.S.R.904(E). All bidders submit Form-1; item-specific Melt & Pour and domestic-value-addition provisions apply.

Required update — Classify items under policy Appendix A/B and HS code. Obtain heat/mill origin records, Form-1, authorisations and applicable auditor certificates; maintain traceability. Do not confuse these policy appendices with tender appendices.

Proposed owner: Procurement / QA / Contracts. Completion evidence: not established by this source review.

## P9-07 — MSE and local content

Source: CQ_replies_BRRP.pdf p5

ONGC reply says PPP-MSE exemption/purchase-preference benefits do not apply to this LSTK works tender. PP-MII is referred to ITB23.6.2(b).

Required update — Remove assumed MSE EMD exemption; verify PP-MII separately, including current amendments.

Proposed owner: Bid / Procurement. Completion evidence: not established by this source review.

## P9-08 — Bid content

Source: CQ_replies_BRRP.pdf p6

ONGC reply requires only BRS Part V-A with Quoted/Not Quoted confirmations in the unpriced bid; price manner follows the actual price format.

Required update — Keep prices in the correct cover; reconcile all A-3 line items and BRS. This reply does not waive separate subcontractor commitment requirements.

Proposed owner: Bid Manager. Completion evidence: not established by this source review.

## P9-09 — Tax and precedence

Source: CQ_replies_BRRP.pdf pp7-9

Beyond-12NM works are not declared tax-exempt: prevailing GST applies; offshore GSTIN may be used. SCC overrides GCC for conflicts; complete priority is referred to B-4. Liability reduction request was rejected.

Required update — Prepare transaction-specific GST, customs and withholding matrix; use B-4 for full hierarchy. Do not adopt the bidder-proposed document hierarchy or 15% liability cap.

Proposed owner: Tax / Contracts. Completion evidence: not established by this source review.

## P9-10 — Pre-bid and extension requests

Source: Corrigendum_1_BRRP.pdf p1; CQ_replies_BRRP.pdf pp7,9

Pre-bid conference was physical only, 8 April 2026. Six-week bid extension request was called premature at PBC stage.

Required update — Record historical event; use issued extension notices for actual deadline. This reply is not a six-week extension grant.

Proposed owner: Document Control / Bid. Completion evidence: not established by this source review.

## P9-11 — Integrity pact

Source: IP (1).pdf pp2,4-6; IP.pdf identical

Disclose intermediaries and relevant transgressions, obtain subcontractor adoption undertakings, retain records for IEM access. Contractor pact duration extends 12 months beyond last payment; other bidders six months after award, subject to outstanding claims.

Required update — Maintain signed pact, partner/consortium signatures as applicable, declarations and subcontract flow-down; extend compliance retention beyond physical completion. No signed compliance evidence established by blank form.

Proposed owner: Compliance / Contracts. Completion evidence: not established by this source review.

## P9-12 — PPE

Source: Kits PPE List-BRRP.pdf p1

Per person: 2 cotton overalls; 2 FR overalls; 2 pairs industrial shoes; 2 pairs electrical-hazard shoes for electrical personnel; 2 helmets; 2 clear goggles; 2 pairs ear muffs; 4 pairs impact/cut gloves; 2 pairs reusable ear plugs; 2 pairs rubber electrical gloves. Each construction season OR condition-based replacement.

Required update — Cost against actual personnel and seasons; certified BIS/EN/ANSI items; issue before work, track replacement. Add task-specific PPE from HIRA/JSA/PTW and OISD-STD-155. Do not use 60 accommodation places as total workforce.

Proposed owner: HSE / Procurement. Completion evidence: not established by this source review.

## P9-13 — Vendor revision gap closed

Source: Combined_Addendum_3.pdf pp261-341

Offshore Suggested Vendor List Rev12.3, as on 27 March 2026, now located. Prior missing-version finding is closed for this list.

Required update — Use Rev12.3 for revision reconciliation with the reference-only-list amendment. Product/location/status checks remain necessary; current external status not verified.

Proposed owner: Procurement / Document Control. Completion evidence: not established by this source review.

## P9-14 — Vendor restrictions

Source: Combined_Addendum_3.pdf p262

B1 quotation permitted subject to resolving hold reasons at PS submission; B3 and banned product entries prohibit order placement as stated. B2 rules and manufacturer-location undertakings also apply.

Required update — Record product, manufacturing location, hold category, evidence and disposition before PO release. Reference-only lists do not erase explicit bans.

Proposed owner: Procurement / QA. Completion evidence: not established by this source review.

## P9-15 — Piping material selection

Source: Combined_Addendum_3.pdf pp1-124; material specification 2008 Rev3

Piping material classes and component schedules are supplied. Index requires missing class sheets needed by approved P&IDs to be prepared using FS2004A for company approval.

Required update — Develop surveyed line list, fluid/design pressure-temperature, material class and corrosion allowance; approve PMS, stress/support loads, isometrics and MTO before purchase. Do not apply every class to BRRP.

Proposed owner: Piping / Procurement. Completion evidence: not established by this source review.

## P9-16 — Welding and NDT

Source: Combined_Addendum_3.pdf pp125-167; FS2009F Rev8 plus Duplex Annex1 Rev1

Welding/NDT specification and seven scanned duplex annex pages supplied; scanned annex OCR reviewed. Material- and joint-specific applicability is essential.

Required update — Prepare applicability matrix, approved WPS/PQR and welder qualifications, NDT procedures/personnel/calibration, weld maps, consumable traceability and repair controls. Duplex qualification/testing can be a procurement predecessor where applicable; no blanket structural NDT percentage asserted.

Proposed owner: Welding Engineer / QA. Completion evidence: not established by this source review.

## P9-17 — Protective coating

Source: Combined_Addendum_3.pdf pp168-245; FS2005 Rev9 dated12 December2022

Protective-coating specification is supplied. Selection depends on substrate, exposure, service temperature and approved system.

Required update — Prepare coating-system schedule, surface preparation/inspection, environmental logs, application/DFT/curing and repair records. Quantify areas from verified MTO; allow curing and inspection before transport. Full system-by-system numerical compliance review remains open.

Proposed owner: Coating / QA / Planning. Completion evidence: not established by this source review.

## P9-18 — Bridge piping flexibility

Source: Combined_Addendum_3.pdf pp246-260, piping criteria Rev4; clause5.3 p260

Bridge piping must account for differential platform movement under extreme storm conditions; assess temperature-range flexibility and required loops/supports.

Required update — Coordinate bearing movements, piping forces, support stiffness and bridge/platform analyses; close iterative reactions before design release. Generic fire-system text is not proof every system is additional bridge scope.

Proposed owner: Piping Stress / Structural. Completion evidence: not established by this source review.

## P9-19 — Schedule impact

Source: P9-03 to P9-18; Appendix C-8 previously reviewed

These inputs create real predecessors for security, material-origin evidence, PS/vendor disposition, qualification, coating and survey/change control. Prior illustrative network is not revalidated by this audit.

Required update — Update package-specific procurement and DCI/MCI review logic, working-day calendars and offshore windows; recalculate CPM only after durations/resources are evidenced. Do not reuse earlier float as an approved forecast.

Proposed owner: Planning Manager. Completion evidence: not established by this source review.

## P9-20 — Remaining version controls

Source: Combined_Addendum_1.pdf p1; P8 and P9 inventories

SVL12.3 found, but positive identification of the announced revised Technical SCC and revised A-3 still requires controlled-document reconciliation.

Required update — Link each governing revision to actual source and issue notice; preserve unresolved drawing revision conflicts and MTO discrepancies. Do not mark all historical inputs fully reconciled.

Proposed owner: Document Control / Contracts. Completion evidence: not established by this source review.

# Review boundaries and next controlled issue

Combined Addendum3 contains341 pages. Section boundaries and source revisions were checked. Fourteen selected pages were OCRed, including all seven low-text duplex annex pages and specification covers. Some piping/coating text has defective font encoding; no claim is made that every tabulated value has been verified. Numerical values must be read from the original relevant sheet during discipline design/QA review. SVL restrictions were screened, but every vendor/product entry was not individually evaluated.

Required next issue: controlled requirement matrix → bridge-by-bridge scope/design/MTO reconciliation → vendor and procurement/QA package updates → DCI/MCI and review-calendar updates → resource and marine-window validation → recalculated CPM/cash flow → independent design check and company approvals. Actual site verification, qualification tests, accepted vendors, signed commitments and construction release remain execution/approval gates; templates do not establish that these gates passed.