## Impact and Actions
ID | Topic | Source (PDF page) | Finding | Proposed owner | Required action | Status
P9-01 | Bid security | Corrigendum.pdf p1 | Any e-BG must be executed on NeSL before the tender closing deadline; later execution is liable to rejection. | Treasury / Bid Manager | Record portal execution timestamp and evidence; reconcile actual closing date with all extension notices. | Open / not execution evidence
P9-02 | Bid validity | Corrigendum_2.pdf pp1-2,5; Corrigendum_4.pdf p1; CQ_replies_BRRP.pdf pp2-3 | Bid security extends 45 days beyond bid validity or extended validity. Bid validity is 120 days after opening of unpriced techno-contractual bids; do not anchor it to submission closing. | Treasury / Contracts | Use actual opening date; diarise bid and security expiry separately. Surety claim-period provisions remain distinct. | Open / not execution evidence
P9-03 | Performance security | Corrigendum_1_BRRP.pdf p1 | The quoted ITB 28.1 option for 3% initial security plus 7% progressive deductions is deleted. | Contracts / Finance | Remove that financing assumption; reconcile remaining ITB 28.1, IFB and B-3 for governing amounts, submission and validity. Do not infer replacement wording from deletion alone. | Open / not execution evidence
P9-04 | Supporting-company guarantees | Corrigendum_2.pdf pp2-5 | B-19/B-20/B-22 specified guarantee deadlines change from 15 to 30 days from NOA. Applicable supporting/JV guarantee provisions include delayed-submission recovery wording. | Contracts / Treasury | Set separate applicable-route milestones. Review 1.5% of performance-security amount per month or part-month recovery wording; do not apply indiscriminately to every guarantee. | Open / not execution evidence
P9-05 | Setting out and changes | Corrigendum_3.pdf p1, GCC 2.3.6 | Modified column reinstates setting-out responsibility. Contractor corrects its positioning errors; company checking does not relieve it. Later company data/instructions after pre-engineering survey causing scope changes are dealt with under Clause 8.0. | Survey / Engineering / Contracts | Establish controlled datums, coordinates, survey acceptance and independent dimensional checks; preserve instruction/change evidence. This clause is not deleted. | Open / not execution evidence
P9-06 | Domestic steel compliance | Corrigendum_3.pdf pp1-8 | DMI&SP policy reference changes to notification dated 17 December 2025, G.S.R.904(E). All bidders submit Form-1; item-specific Melt & Pour and domestic-value-addition provisions apply. | Procurement / QA / Contracts | Classify items under policy Appendix A/B and HS code. Obtain heat/mill origin records, Form-1, authorisations and applicable auditor certificates; maintain traceability. Do not confuse these policy appendices with tender appendices. | Open / not execution evidence
P9-07 | MSE and local content | CQ_replies_BRRP.pdf p5 | ONGC reply says PPP-MSE exemption/purchase-preference benefits do not apply to this LSTK works tender. PP-MII is referred to ITB23.6.2(b). | Bid / Procurement | Remove assumed MSE EMD exemption; verify PP-MII separately, including current amendments. | Open / not execution evidence
P9-08 | Bid content | CQ_replies_BRRP.pdf p6 | ONGC reply requires only BRS Part V-A with Quoted/Not Quoted confirmations in the unpriced bid; price manner follows the actual price format. | Bid Manager | Keep prices in the correct cover; reconcile all A-3 line items and BRS. This reply does not waive separate subcontractor commitment requirements. | Open / not execution evidence
P9-09 | Tax and precedence | CQ_replies_BRRP.pdf pp7-9 | Beyond-12NM works are not declared tax-exempt: prevailing GST applies; offshore GSTIN may be used. SCC overrides GCC for conflicts; complete priority is referred to B-4. Liability reduction request was rejected. | Tax / Contracts | Prepare transaction-specific GST, customs and withholding matrix; use B-4 for full hierarchy. Do not adopt the bidder-proposed document hierarchy or 15% liability cap. | Open / not execution evidence
P9-10 | Pre-bid and extension requests | Corrigendum_1_BRRP.pdf p1; CQ_replies_BRRP.pdf pp7,9 | Pre-bid conference was physical only, 8 April 2026. Six-week bid extension request was called premature at PBC stage. | Document Control / Bid | Record historical event; use issued extension notices for actual deadline. This reply is not a six-week extension grant. | Open / not execution evidence
P9-11 | Integrity pact | IP (1).pdf pp2,4-6; IP.pdf identical | Disclose intermediaries and relevant transgressions, obtain subcontractor adoption undertakings, retain records for IEM access. Contractor pact duration extends 12 months beyond last payment; other bidders six months after award, subject to outstanding claims. | Compliance / Contracts | Maintain signed pact, partner/consortium signatures as applicable, declarations and subcontract flow-down; extend compliance retention beyond physical completion. No signed compliance evidence established by blank form. | Open / not execution evidence
P9-12 | PPE | Kits PPE List-BRRP.pdf p1 | Per person: 2 cotton overalls; 2 FR overalls; 2 pairs industrial shoes; 2 pairs electrical-hazard shoes for electrical personnel; 2 helmets; 2 clear goggles; 2 pairs ear muffs; 4 pairs impact/cut gloves; 2 pairs reusable ear plugs; 2 pairs rubber electrical gloves. Each construction season OR condition-based replacement. | HSE / Procurement | Cost against actual personnel and seasons; certified BIS/EN/ANSI items; issue before work, track replacement. Add task-specific PPE from HIRA/JSA/PTW and OISD-STD-155. Do not use 60 accommodation places as total workforce. | Open / not execution evidence
P9-13 | Vendor revision gap closed | Combined_Addendum_3.pdf pp261-341 | Offshore Suggested Vendor List Rev12.3, as on 27 March 2026, now located. Prior missing-version finding is closed for this list. | Procurement / Document Control | Use Rev12.3 for revision reconciliation with the reference-only-list amendment. Product/location/status checks remain necessary; current external status not verified. | Source version located; downstream checks open
P9-14 | Vendor restrictions | Combined_Addendum_3.pdf p262 | B1 quotation permitted subject to resolving hold reasons at PS submission; B3 and banned product entries prohibit order placement as stated. B2 rules and manufacturer-location undertakings also apply. | Procurement / QA | Record product, manufacturing location, hold category, evidence and disposition before PO release. Reference-only lists do not erase explicit bans. | Open / not execution evidence
P9-15 | Piping material selection | Combined_Addendum_3.pdf pp1-124; material specification 2008 Rev3 | Piping material classes and component schedules are supplied. Index requires missing class sheets needed by approved P&IDs to be prepared using FS2004A for company approval. | Piping / Procurement | Develop surveyed line list, fluid/design pressure-temperature, material class and corrosion allowance; approve PMS, stress/support loads, isometrics and MTO before purchase. Do not apply every class to BRRP. | Open / not execution evidence
P9-16 | Welding and NDT | Combined_Addendum_3.pdf pp125-167; FS2009F Rev8 plus Duplex Annex1 Rev1 | Welding/NDT specification and seven scanned duplex annex pages supplied; scanned annex OCR reviewed. Material- and joint-specific applicability is essential. | Welding Engineer / QA | Prepare applicability matrix, approved WPS/PQR and welder qualifications, NDT procedures/personnel/calibration, weld maps, consumable traceability and repair controls. Duplex qualification/testing can be a procurement predecessor where applicable; no blanket structural NDT percentage asserted. | Open / not execution evidence
P9-17 | Protective coating | Combined_Addendum_3.pdf pp168-245; FS2005 Rev9 dated12 December2022 | Protective-coating specification is supplied. Selection depends on substrate, exposure, service temperature and approved system. | Coating / QA / Planning | Prepare coating-system schedule, surface preparation/inspection, environmental logs, application/DFT/curing and repair records. Quantify areas from verified MTO; allow curing and inspection before transport. Full system-by-system numerical compliance review remains open. | Open / not execution evidence
P9-18 | Bridge piping flexibility | Combined_Addendum_3.pdf pp246-260, piping criteria Rev4; clause5.3 p260 | Bridge piping must account for differential platform movement under extreme storm conditions; assess temperature-range flexibility and required loops/supports. | Piping Stress / Structural | Coordinate bearing movements, piping forces, support stiffness and bridge/platform analyses; close iterative reactions before design release. Generic fire-system text is not proof every system is additional bridge scope. | Open / not execution evidence
P9-19 | Schedule impact | P9-03 to P9-18; Appendix C-8 previously reviewed | These inputs create real predecessors for security, material-origin evidence, PS/vendor disposition, qualification, coating and survey/change control. Prior illustrative network is not revalidated by this audit. | Planning Manager | Update package-specific procurement and DCI/MCI review logic, working-day calendars and offshore windows; recalculate CPM only after durations/resources are evidenced. Do not reuse earlier float as an approved forecast. | Open / not execution evidence
P9-20 | Remaining version controls | Combined_Addendum_1.pdf p1; P8 and P9 inventories | SVL12.3 found, but positive identification of the announced revised Technical SCC and revised A-3 still requires controlled-document reconciliation. | Document Control / Contracts | Link each governing revision to actual source and issue notice; preserve unresolved drawing revision conflicts and MTO discrepancies. Do not mark all historical inputs fully reconciled. | Open / not execution evidence

## File Inventory
File | Pages | SHA256 | Previously supplied exact copies | Duplicate in this batch | Path
Appendix B-6.pdf | 1 | dd4ce8688af1b3976c4fc752c9a19e4e14d43984c0e25733d11c6703d9919858 | 1 |  | /workspace/attachments/bca55dcd-b18e-471b-9279-825d78f7fe51/Appendix B-6.pdf
Appendix B-5.pdf | 1 | 82222c4cdca2f142d619e139280c264c68085cca7444ad0f1152204a91f1bf3e | 2 |  | /workspace/attachments/916f21ad-c459-47c8-8868-3e78975c473e/Appendix B-5.pdf
Appendix C-8 DCI MCI.pdf | 67 | 086b2f7837d09bc6320e2e0794f5b73fc7788b2cb9ecb5a08fa76836e2c97944 | 1 |  | /workspace/attachments/e57981f6-f4d1-4e45-a610-13896ccb632d/Appendix C-8 DCI MCI.pdf
Appendix C-9.pdf | 21 | f20a85ca3a13c08e62bb18a41838d9e32910cd4f0d7c6b0ab0623df4ca9aeec5 | 1 |  | /workspace/attachments/5e49cb26-313e-48e9-9660-187d29bee2c6/Appendix C-9.pdf
Appendix C-10.pdf | 19 | 8f0b1be35e96cc0e953e8614b751f08a987dca4a9060c54319b231f113d7d2d7 | 1 |  | /workspace/attachments/d9f51454-17f8-481e-8211-eb6719acb1b7/Appendix C-10.pdf
Combined_Addendum_2.pdf | 250 | f251ecb31a55528c700e82a095c36459b3b84610385d490fd492cc1ce1b9a6b4 | 1 |  | /workspace/attachments/8de59956-54d6-4669-bc36-000ccc82a6b9/Combined_Addendum_2.pdf
Combined_Addendum_1.pdf | 285 | dfda0877c74c0745763a6d8eb0e8894014d27b22ec72c8f44955c933cadf1d65 | 2 |  | /workspace/attachments/5eb9f6dc-7206-4584-bc8c-b40003aad345/Combined_Addendum_1.pdf
Combined_Addendum_1 (1).pdf | 285 | dfda0877c74c0745763a6d8eb0e8894014d27b22ec72c8f44955c933cadf1d65 | 2 | Combined_Addendum_1.pdf | /workspace/attachments/85a8f434-da1a-4c34-887c-6798ac0df182/Combined_Addendum_1 (1).pdf
Corrigendum.pdf | 1 | 02142550f5d609a6a2ffe4ed64d441eaa00540663cee661ed318446e6e19dea6 | 0 |  | /workspace/attachments/da11bafd-662a-4a74-8847-e64ff795185a/Corrigendum.pdf
Corrigendum_1_BRRP.pdf | 1 | 54977537e10a8249587ad2965eca04a057eaa45f932e6a229959bc3fa30ab7c4 | 0 |  | /workspace/attachments/9358f991-8462-41ff-8319-e51122d3cd94/Corrigendum_1_BRRP.pdf
Corrigendum_2.pdf | 5 | cb996ec5837ec4dcfab1a55e4ffcb56248919a73d70cd53492d64d39a2a7b435 | 0 |  | /workspace/attachments/5a0c29c4-054f-457b-8054-b58f9d62b702/Corrigendum_2.pdf
Corrigendum_3.pdf | 8 | e8a07f4059dcb9b81c1cc45b2ae60154c0c142999955b347d2c60133619656d7 | 0 |  | /workspace/attachments/91ee811c-0512-4a1e-af23-5cb249cdfd53/Corrigendum_3.pdf
Corrigendum_4.pdf | 1 | 623614acba28baadc68c22229c039399e9b4385c0945b787197b2dedaaa4acf4 | 0 |  | /workspace/attachments/520cb649-f91a-4a48-984a-acd0f69f8026/Corrigendum_4.pdf
CQ_replies_BRRP.pdf | 9 | b006f3d20e7ae10d9800b1b9fabfb3104091b09878fcd6bb83b2f328e926df4a | 0 |  | /workspace/attachments/54f82dbe-74a1-4e2a-be50-39de725d5ac7/CQ_replies_BRRP.pdf
IP (1).pdf | 6 | 8692fb4bca724408df3fe1ec8377faa678e6238f3fe14bb55fbc6ca4b8cdcf50 | 0 |  | /workspace/attachments/b6d3ed71-2d35-40b4-9288-0ff898ca6b55/IP (1).pdf
IP.pdf | 6 | 8692fb4bca724408df3fe1ec8377faa678e6238f3fe14bb55fbc6ca4b8cdcf50 | 0 | IP (1).pdf | /workspace/attachments/383c6caf-401a-4da0-b4da-55b890bc5ebc/IP.pdf
Design Criteria & Execution Methodology.pdf | 154 | 179b05dabdb90971b5132d38f2a1aa755ce091b640b4e844fa7b0c9cc4a7e706 | 1 |  | /workspace/attachments/c1b8bee7-6e2e-45ab-a245-f17c5183645c/Design Criteria & Execution Methodology.pdf
Kits PPE List-BRRP.pdf | 1 | 44e2e5f2214d741c15380702504a73ae00076ab5954bb6ce96011a1e06aed841 | 0 |  | /workspace/attachments/b91a8826-af38-4973-9961-d3ef91fd1a68/Kits PPE List-BRRP.pdf
Combined_Addendum_3.pdf | 341 | 6d6369b880718f0b84da0776adc723d99eae59b591c8b5d45f1f0b2596b9d5b6 | 0 |  | /workspace/attachments/a4d19aca-72c3-4d27-b5be-a84f2a5be0dc/Combined_Addendum_3.pdf

## Addendum 3 Map
PDF pages | Source | Review coverage
1-124 | Piping material specification2008 Rev3 | Section indexed; class-by-class selection remains engineering work
125-160 | Welding and NDT FS2009F Rev8 | Requirements screening; detailed applicability remains open
161-167 | Duplex welding Annex1 Rev1 | Scanned pages OCR reviewed; use original for numerical application
168-245 | Protective coating FS2005 Rev9 | Cover OCR verified; font encoding affects text; full numeric system review open
246-260 | Piping design criteria Rev4 | Requirements screening including movement clause5.3
261-341 | Offshore SVL12.3 | Revision and important notes checked; individual bid-vendor selection not performed