## READ ME
Topic | Basis / requirement
Status | PROVISIONAL MANAGEMENT SCHEDULE — Rev 0, 25 October 2026. Not ONGC approved; no actual progress inferred.
Start assumption | 1 November 2026 is a scenario from uploaded plans, NOT a confirmed award date. All relative days use this date as Day 1.
Contract deadline | 12 months from NOA under reviewed GCC 6.3.1.1 and SCC 2.0. For this scenario, use 31 October 2027 as conservative last workday; confirm legal date convention and actual NOA.
Calendar | Onshore durations are elapsed calendar days assuming adequate shifts and staffing; not 5-day working durations. Validate holidays and productivity. Offshore tasks conservatively avoid 16 May–15 October inclusive.
Weather treatment | An offshore activity that cannot fit wholly before 16 May is deferred wholly to 16 October; tasks are not split. This is a conservative planning rule, not a contractual automatic extension.
Contract relief | SCC provides conditional monsoon time relief for inability to work due to adverse weather; associated extra costs are not payable under that clause. Obtain ONGC agreement; no extension is assumed in deadline comparison.
Durations | All proposed durations are planner estimates, not measured quantity/productivity results or supplier commitments. Survey, approvals and procurement lead times require validation.
Logic | Finish-to-start, zero lag. Successor starts next day after predecessor working finish. Milestone date is next-day boundary. Offshore seasonal waits are separately visible.
Two-crew case | 2 fabrication lines + 1 dedicated strengthening cell; 2 offshore strengthening crews; 1 sequential heavy-lift spread and 1 cargo spread. Candidate capacity only.
Recovery option | Same fabrication lines and heavy-lift spread; first approved strengthening kits released after 20 rather than 35 days of cell production; ADDITIONAL crew C for NQO-NQD. Subject to package-specific release and availability.
Support capacity | Support spread / transfers / accommodation must support simultaneous crews and lifting. SCC minimum 60 special personnel is a floor, not proof capacity is adequate. Verify POB, vessels, access and operational interfaces.
Resource check | Exclusive fabrication-line, cargo, heavy-lift and strengthening-crew sequencing checked. This is NOT full quantity-loaded, labour-levelled P6 analysis. Survey/design teams and support capacities require validation.
Weather allowance | 10 reserved offshore days after planned offshore works, then 3 demobilisation days. This allowance is unvalidated; test against vessel weather limits and metocean history.
Scope | Ten bridges; ICG/ICP/BHS jacket strengthening included; BHS new bridge/service transfer precedes old-bridge demolition. Other demolition allowance is provisional pending bridge allocation and approved methods.
Quantities | Structural summary 1,142 MT vs bridge sum 1,141 MT unresolved. Demolition 357 MT allocation inconsistent across uploaded controls. No correction silently assumed.
Completion | Internal completion includes all offshore work, specified punch clearance, dossiers and acceptance processing. ONGC approval durations are estimates; planned certificate date is not an acceptance commitment.
Warranty | 12-month warranty after actual completion / handover; shown separately and excluded from EPC duration. Final warranty security release depends on contract terms.
Use | Recovery option is the proposed management target; two-crew case exposes seasonal risk. Neither is an approved baseline. Recalculate after actual NOA, supplier lead times, weather study and resource commitments.
Source priority | Executed contract and controlling addenda govern. This workbook supersedes no source document and is a newly proposed overall schedule.
Source references | GCC 2.1.1 / 6.3.1.1; Technical SCC 2.0 / 3.0; SOW Section 1 (including 1.3); Addendum_Structure_SOW; Stage28 / Level3 / 360-day workbook caveats; Stage34 and Stage35 planning assumptions.

## Recovery Schedule
ID | Phase | Package | Activity / milestone | Duration (calendar days) | FS predecessors | Planned start | Planned finish | Start day from NOA | Finish day from NOA | Seasonal wait days | Resource assumption | Accountable role | Release / acceptance condition | Status
M000 | Milestone | COMMON | Assumed NOA / commencement | 0 |  | 2026-11-01 | 2026-11-01 | 1 | 1 | 0 |  | Contracts |  | Proposed / unverified
G010 | Management | COMMON | Kick-off, obligations, guarantees and funding arrangements | 7 | M000 | 2026-11-01 | 2026-11-07 | 1 | 7 | 0 | Project team | Project Director |  | Proposed / unverified
G020 | Management | COMMON | Controlled document / addendum and quantity reconciliation | 14 | G010 | 2026-11-08 | 2026-11-21 | 8 | 21 | 0 | Project team | Engineering | Resolve 1 MT and demolition allocation | Proposed / unverified
S010 | Survey | COMMON | Survey permits, mobilisation and access planning | 7 | G010 | 2026-11-08 | 2026-11-14 | 8 | 14 | 0 | Survey team | Survey Manager |  | Proposed / unverified
S020 | Survey | ALL | Bridge and platform verification survey campaign | 14 | S010 | 2026-11-15 | 2026-11-28 | 15 | 28 | 0 | Survey spread | Survey Manager | Accepted survey / utility register | Proposed / unverified
E010 | Engineering | COMMON | Design basis and interface approval | 14 | G010 | 2026-11-08 | 2026-11-21 | 8 | 21 | 0 | Engineering | Engineering Manager |  | Proposed / unverified
E020 | Engineering | ALL | Checked material requisitions / early material release | 10 | S020, E010, G020 | 2026-11-29 | 2026-12-08 | 29 | 38 | 0 | Engineering | Engineering Manager | Approved procurement MTO; no fabrication release | Proposed / unverified
P010 | Procurement | ALL | Vendor approval, steel purchase and phased yard delivery | 25 | E020 | 2026-12-09 | 2027-01-02 | 39 | 63 | 0 | Procurement | Procurement Manager | Certificates, inspection and traceability | Proposed / unverified
E030 | Engineering | REPLACEMENTS | Detailed design, AFC drawings and ITP approval | 25 | S020, E010 | 2026-11-29 | 2026-12-23 | 29 | 53 | 0 | Design team A | Engineering Manager | Approved for construction | Proposed / unverified
E040 | Engineering | REFURBISHMENTS | Bridge and jacket strengthening design / AFC work packs | 25 | S020, E010 | 2026-11-29 | 2026-12-23 | 29 | 53 | 0 | Design team B | Engineering Manager | ICG / ICP / BHS addendum incorporated | Proposed / unverified
E050 | Engineering | BHS-SLQ | Utility transfer, temporary stability and demolition design | 35 | S020, E010 | 2026-11-29 | 2027-01-02 | 29 | 63 | 0 | Design team A | Technical Authority | ONGC operational interface approval | Proposed / unverified
MR10 | Marine | COMMON | Vessel market enquiry, technical audit and conditional reservation | 35 | G010 | 2026-11-08 | 2026-12-12 | 8 | 42 | 0 | Marine engineering | Marine Manager | Certified vessel data and availability | Proposed / unverified
MR20 | Marine | REPLACEMENTS | Lift, loadout, transport and sea-fastening engineering | 35 | E030, MR10 | 2026-12-24 | 2027-01-27 | 54 | 88 | 0 | Marine engineering | Marine Manager | Verified lift weights / COG; approved procedures | Proposed / unverified
F010 | Fabrication | ICW-ICG LD | Fabricate, NDT, dimensional inspection and coating | 35 | P010, E030 | 2027-01-03 | 2027-02-06 | 64 | 98 | 0 | Fabrication line 1 | Fabrication Manager | QA release | Proposed / unverified
F020 | Fabrication | BHS-SLQ | Fabricate, NDT, dimensional inspection and coating | 55 | P010, E030 | 2027-01-03 | 2027-02-26 | 64 | 118 | 0 | Fabrication line 2 | Fabrication Manager | QA release | Proposed / unverified
F030 | Fabrication | ICG-ICP LD | Fabricate, NDT, dimensional inspection and coating | 40 | F010 | 2027-02-07 | 2027-03-18 | 99 | 138 | 0 | Fabrication line 1 | Fabrication Manager | QA release | Proposed / unverified
F041 | Fabrication | ALL STRENGTHENING | First approved strengthening kits: phased fabrication / QA release | 20 | P010, E040 | 2027-01-03 | 2027-01-22 | 64 | 83 | 0 | Milestone within strengthening cell production | Fabrication Manager | Bridge-specific release required; remaining kits continue in same cell | Proposed / unverified
F040 | Fabrication | ALL STRENGTHENING | Phased fabrication and release of strengthening kits | 35 | P010, E040 | 2027-01-03 | 2027-02-06 | 64 | 98 | 0 | Dedicated strengthening cell | Fabrication Manager | All kits released at finish; earlier release only by QA | Proposed / unverified
O010 | Offshore readiness | ALL | Accommodation/support mobilisation, permits, SIMOPS and readiness | 10 | F041, MR10 | 2027-01-23 | 2027-02-01 | 84 | 93 | 0 | Support spread | Offshore Manager | Minimum 60 special-personnel accommodation per SCC | Proposed / unverified
J010 | Offshore | ICG / BHS | Addendum jacket strengthening and acceptance | 12 | O010 | 2027-02-02 | 2027-02-13 | 94 | 105 | 0 | Strengthening crew A | Offshore Manager | Before ICW-ICG LD and BHS replacement | Proposed / unverified
J020 | Offshore | ICP | Addendum jacket strengthening and acceptance | 10 | O010 | 2027-02-02 | 2027-02-11 | 94 | 103 | 0 | Strengthening crew B | Offshore Manager | Before ICG-ICP LD installation | Proposed / unverified
RA01 | Offshore | ICW-ICG UD | Strengthening, inspection and bridge acceptance | 16 | J010, F040 | 2027-02-14 | 2027-03-01 | 106 | 121 | 0 | Strengthening crew A | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RA02 | Offshore | ICG-ICP UD | Strengthening, inspection and bridge acceptance | 22 | RA01, F040 | 2027-03-02 | 2027-03-23 | 122 | 143 | 0 | Strengthening crew A | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RA03 | Offshore | SLQ-WIS | Strengthening, inspection and bridge acceptance | 18 | RA02, F040 | 2027-03-24 | 2027-04-10 | 144 | 161 | 0 | Strengthening crew A | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RA04 | Offshore | NQO-NQD | Strengthening, inspection and bridge acceptance | 18 | O010, F040 | 2027-02-07 | 2027-02-24 | 99 | 116 | 0 | Strengthening crew C (additional) | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RB01 | Offshore | WIN-NC | Strengthening, inspection and bridge acceptance | 12 | J020, F040 | 2027-02-12 | 2027-02-23 | 104 | 115 | 0 | Strengthening crew B | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RB02 | Offshore | SCA-SC1 | Strengthening, inspection and bridge acceptance | 16 | RB01, F040 | 2027-02-24 | 2027-03-11 | 116 | 131 | 0 | Strengthening crew B | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RB03 | Offshore | SCA-SCF | Strengthening, inspection and bridge acceptance | 24 | RB02, F040 | 2027-03-12 | 2027-04-04 | 132 | 155 | 0 | Strengthening crew B | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
H010 | Marine | COMMON | Heavy-lift spread mobilisation and operational readiness | 7 | MR20, O010 | 2027-02-02 | 2027-02-08 | 94 | 100 | 0 | Heavy-lift spread | Marine Manager | Survey/class, crane curves, permits and weather | Proposed / unverified
L010 | Marine | ICW-ICG LD | Loadout, sea-fastening and transport | 5 | F010, MR20 | 2027-02-07 | 2027-02-11 | 99 | 103 | 0 | Cargo spread | Marine Manager | Sail-away release | Proposed / unverified
I010 | Offshore | ICW-ICG LD | Install, connect, inspect and accept replacement bridge | 16 | L010, H010, J010 | 2027-02-14 | 2027-03-01 | 106 | 121 | 0 | Heavy-lift spread | Offshore Manager | Services / safe access accepted | Proposed / unverified
L020 | Marine | BHS-SLQ | Loadout, sea-fastening and transport | 5 | F020, MR20, L010 | 2027-02-27 | 2027-03-03 | 119 | 123 | 0 | Cargo spread | Marine Manager | Sail-away release | Proposed / unverified
I020 | Offshore | BHS-SLQ | Install new bridge, transfer services and commission | 20 | L020, I010, J010, E050 | 2027-03-04 | 2027-03-23 | 124 | 143 | 0 | Heavy-lift spread | Offshore Manager | New bridge and transferred services accepted BEFORE demolition | Proposed / unverified
D020 | Demolition | BHS-SLQ | Isolate, dismantle old bridge and remove to shore | 7 | I020 | 2027-03-24 | 2027-03-30 | 144 | 150 | 0 | Heavy-lift spread | Offshore Manager | Approved demolition sequence / service isolation | Proposed / unverified
L030 | Marine | ICG-ICP LD | Loadout, sea-fastening and transport | 5 | F030, MR20, L020 | 2027-03-19 | 2027-03-23 | 139 | 143 | 0 | Cargo spread | Marine Manager | Sail-away release | Proposed / unverified
I030 | Offshore | ICG-ICP LD | Install, connect, inspect and accept replacement bridge | 18 | L030, D020, J020 | 2027-03-31 | 2027-04-17 | 151 | 168 | 0 | Heavy-lift spread | Offshore Manager | Services / safe access accepted | Proposed / unverified
D030 | Demolition | OTHER BRIDGES | Other removal, waste backload and allocated demolition closure | 7 | I030, RA04, RB03, RA03 | 2027-04-18 | 2027-04-24 | 169 | 175 | 0 | Heavy-lift spread | Offshore Manager | Bridge-specific quantities and method to verify | Proposed / unverified
O090 | Offshore | ALL | Final offshore inspections, punch closure and operational acceptance | 7 | D030 | 2027-04-25 | 2027-05-01 | 176 | 182 | 0 | Support spread | Completions Manager | All work required for completion accepted | Proposed / unverified
M100 | Milestone | ALL | Planned offshore works complete | 0 | O090 | 2027-05-02 | 2027-05-02 | 183 | 183 | 0 |  | Project Director |  | Proposed / unverified
W010 | Allowance | ALL | Offshore weather / access allowance (not productive work) | 10 | M100 | 2027-05-02 | 2027-05-11 | 183 | 192 | 0 | Reserved marine capacity | Marine Manager | 10 days is a planning allowance; not a weather study | Proposed / unverified
O100 | Marine | ALL | Offshore demobilisation | 3 | W010 | 2027-05-12 | 2027-05-14 | 193 | 195 | 0 | Support spread | Marine Manager | Clearance / backload | Proposed / unverified
C010 | Closeout | ALL | As-built dossiers, e-MB records, QA records and handover compilation | 30 | M100 | 2027-05-02 | 2027-05-31 | 183 | 212 | 0 | Completions team | QA / Completions |  | Proposed / unverified
C020 | Closeout | ALL | Final document review and completion certificate processing | 14 | C010, O100 | 2027-06-01 | 2027-06-14 | 213 | 226 | 0 | Project team | Project Director | ONGC acceptance / contractual completion criteria | Proposed / unverified
M200 | Milestone | ALL | Internal target: all works complete and handover accepted | 0 | C020 | 2027-06-15 | 2027-06-15 | 227 | 227 | 0 |  | Project Director |  | Proposed / unverified

## Two Crew Schedule
ID | Phase | Package | Activity / milestone | Duration (calendar days) | FS predecessors | Planned start | Planned finish | Start day from NOA | Finish day from NOA | Seasonal wait days | Resource assumption | Accountable role | Release / acceptance condition | Status
M000 | Milestone | COMMON | Assumed NOA / commencement | 0 |  | 2026-11-01 | 2026-11-01 | 1 | 1 | 0 |  | Contracts |  | Proposed / unverified
G010 | Management | COMMON | Kick-off, obligations, guarantees and funding arrangements | 7 | M000 | 2026-11-01 | 2026-11-07 | 1 | 7 | 0 | Project team | Project Director |  | Proposed / unverified
G020 | Management | COMMON | Controlled document / addendum and quantity reconciliation | 14 | G010 | 2026-11-08 | 2026-11-21 | 8 | 21 | 0 | Project team | Engineering | Resolve 1 MT and demolition allocation | Proposed / unverified
S010 | Survey | COMMON | Survey permits, mobilisation and access planning | 7 | G010 | 2026-11-08 | 2026-11-14 | 8 | 14 | 0 | Survey team | Survey Manager |  | Proposed / unverified
S020 | Survey | ALL | Bridge and platform verification survey campaign | 14 | S010 | 2026-11-15 | 2026-11-28 | 15 | 28 | 0 | Survey spread | Survey Manager | Accepted survey / utility register | Proposed / unverified
E010 | Engineering | COMMON | Design basis and interface approval | 14 | G010 | 2026-11-08 | 2026-11-21 | 8 | 21 | 0 | Engineering | Engineering Manager |  | Proposed / unverified
E020 | Engineering | ALL | Checked material requisitions / early material release | 10 | S020, E010, G020 | 2026-11-29 | 2026-12-08 | 29 | 38 | 0 | Engineering | Engineering Manager | Approved procurement MTO; no fabrication release | Proposed / unverified
P010 | Procurement | ALL | Vendor approval, steel purchase and phased yard delivery | 25 | E020 | 2026-12-09 | 2027-01-02 | 39 | 63 | 0 | Procurement | Procurement Manager | Certificates, inspection and traceability | Proposed / unverified
E030 | Engineering | REPLACEMENTS | Detailed design, AFC drawings and ITP approval | 25 | S020, E010 | 2026-11-29 | 2026-12-23 | 29 | 53 | 0 | Design team A | Engineering Manager | Approved for construction | Proposed / unverified
E040 | Engineering | REFURBISHMENTS | Bridge and jacket strengthening design / AFC work packs | 25 | S020, E010 | 2026-11-29 | 2026-12-23 | 29 | 53 | 0 | Design team B | Engineering Manager | ICG / ICP / BHS addendum incorporated | Proposed / unverified
E050 | Engineering | BHS-SLQ | Utility transfer, temporary stability and demolition design | 35 | S020, E010 | 2026-11-29 | 2027-01-02 | 29 | 63 | 0 | Design team A | Technical Authority | ONGC operational interface approval | Proposed / unverified
MR10 | Marine | COMMON | Vessel market enquiry, technical audit and conditional reservation | 35 | G010 | 2026-11-08 | 2026-12-12 | 8 | 42 | 0 | Marine engineering | Marine Manager | Certified vessel data and availability | Proposed / unverified
MR20 | Marine | REPLACEMENTS | Lift, loadout, transport and sea-fastening engineering | 35 | E030, MR10 | 2026-12-24 | 2027-01-27 | 54 | 88 | 0 | Marine engineering | Marine Manager | Verified lift weights / COG; approved procedures | Proposed / unverified
F010 | Fabrication | ICW-ICG LD | Fabricate, NDT, dimensional inspection and coating | 35 | P010, E030 | 2027-01-03 | 2027-02-06 | 64 | 98 | 0 | Fabrication line 1 | Fabrication Manager | QA release | Proposed / unverified
F020 | Fabrication | BHS-SLQ | Fabricate, NDT, dimensional inspection and coating | 55 | P010, E030 | 2027-01-03 | 2027-02-26 | 64 | 118 | 0 | Fabrication line 2 | Fabrication Manager | QA release | Proposed / unverified
F030 | Fabrication | ICG-ICP LD | Fabricate, NDT, dimensional inspection and coating | 40 | F010 | 2027-02-07 | 2027-03-18 | 99 | 138 | 0 | Fabrication line 1 | Fabrication Manager | QA release | Proposed / unverified
F040 | Fabrication | ALL STRENGTHENING | Phased fabrication and release of strengthening kits | 35 | P010, E040 | 2027-01-03 | 2027-02-06 | 64 | 98 | 0 | Dedicated strengthening cell | Fabrication Manager | All kits released at finish; earlier release only by QA | Proposed / unverified
O010 | Offshore readiness | ALL | Accommodation/support mobilisation, permits, SIMOPS and readiness | 10 | F040, MR10 | 2027-02-07 | 2027-02-16 | 99 | 108 | 0 | Support spread | Offshore Manager | Minimum 60 special-personnel accommodation per SCC | Proposed / unverified
J010 | Offshore | ICG / BHS | Addendum jacket strengthening and acceptance | 12 | O010 | 2027-02-17 | 2027-02-28 | 109 | 120 | 0 | Strengthening crew A | Offshore Manager | Before ICW-ICG LD and BHS replacement | Proposed / unverified
J020 | Offshore | ICP | Addendum jacket strengthening and acceptance | 10 | O010 | 2027-02-17 | 2027-02-26 | 109 | 118 | 0 | Strengthening crew B | Offshore Manager | Before ICG-ICP LD installation | Proposed / unverified
RA01 | Offshore | ICW-ICG UD | Strengthening, inspection and bridge acceptance | 16 | J010 | 2027-03-01 | 2027-03-16 | 121 | 136 | 0 | Strengthening crew A | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RA02 | Offshore | ICG-ICP UD | Strengthening, inspection and bridge acceptance | 22 | RA01 | 2027-03-17 | 2027-04-07 | 137 | 158 | 0 | Strengthening crew A | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RA03 | Offshore | SLQ-WIS | Strengthening, inspection and bridge acceptance | 18 | RA02 | 2027-04-08 | 2027-04-25 | 159 | 176 | 0 | Strengthening crew A | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RA04 | Offshore | NQO-NQD | Strengthening, inspection and bridge acceptance | 18 | RA03 | 2027-04-26 | 2027-05-13 | 177 | 194 | 0 | Strengthening crew A | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RB01 | Offshore | WIN-NC | Strengthening, inspection and bridge acceptance | 12 | J020 | 2027-02-27 | 2027-03-10 | 119 | 130 | 0 | Strengthening crew B | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RB02 | Offshore | SCA-SC1 | Strengthening, inspection and bridge acceptance | 16 | RB01 | 2027-03-11 | 2027-03-26 | 131 | 146 | 0 | Strengthening crew B | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
RB03 | Offshore | SCA-SCF | Strengthening, inspection and bridge acceptance | 24 | RB02 | 2027-03-27 | 2027-04-19 | 147 | 170 | 0 | Strengthening crew B | Offshore Manager | PTW, stability, NDT and acceptance | Proposed / unverified
H010 | Marine | COMMON | Heavy-lift spread mobilisation and operational readiness | 7 | MR20, O010 | 2027-02-17 | 2027-02-23 | 109 | 115 | 0 | Heavy-lift spread | Marine Manager | Survey/class, crane curves, permits and weather | Proposed / unverified
L010 | Marine | ICW-ICG LD | Loadout, sea-fastening and transport | 5 | F010, MR20 | 2027-02-07 | 2027-02-11 | 99 | 103 | 0 | Cargo spread | Marine Manager | Sail-away release | Proposed / unverified
I010 | Offshore | ICW-ICG LD | Install, connect, inspect and accept replacement bridge | 16 | L010, H010, J010 | 2027-03-01 | 2027-03-16 | 121 | 136 | 0 | Heavy-lift spread | Offshore Manager | Services / safe access accepted | Proposed / unverified
L020 | Marine | BHS-SLQ | Loadout, sea-fastening and transport | 5 | F020, MR20, L010 | 2027-02-27 | 2027-03-03 | 119 | 123 | 0 | Cargo spread | Marine Manager | Sail-away release | Proposed / unverified
I020 | Offshore | BHS-SLQ | Install new bridge, transfer services and commission | 20 | L020, I010, J010, E050 | 2027-03-17 | 2027-04-05 | 137 | 156 | 0 | Heavy-lift spread | Offshore Manager | New bridge and transferred services accepted BEFORE demolition | Proposed / unverified
D020 | Demolition | BHS-SLQ | Isolate, dismantle old bridge and remove to shore | 7 | I020 | 2027-04-06 | 2027-04-12 | 157 | 163 | 0 | Heavy-lift spread | Offshore Manager | Approved demolition sequence / service isolation | Proposed / unverified
L030 | Marine | ICG-ICP LD | Loadout, sea-fastening and transport | 5 | F030, MR20, L020 | 2027-03-19 | 2027-03-23 | 139 | 143 | 0 | Cargo spread | Marine Manager | Sail-away release | Proposed / unverified
I030 | Offshore | ICG-ICP LD | Install, connect, inspect and accept replacement bridge | 18 | L030, D020, J020 | 2027-04-13 | 2027-04-30 | 164 | 181 | 0 | Heavy-lift spread | Offshore Manager | Services / safe access accepted | Proposed / unverified
D030 | Demolition | OTHER BRIDGES | Other removal, waste backload and allocated demolition closure | 7 | I030, RA04, RB03 | 2027-10-16 | 2027-10-22 | 350 | 356 | 155 | Heavy-lift spread | Offshore Manager | Bridge-specific quantities and method to verify | Proposed / unverified
O090 | Offshore | ALL | Final offshore inspections, punch closure and operational acceptance | 7 | D030 | 2027-10-23 | 2027-10-29 | 357 | 363 | 0 | Support spread | Completions Manager | All work required for completion accepted | Proposed / unverified
M100 | Milestone | ALL | Planned offshore works complete | 0 | O090 | 2027-10-30 | 2027-10-30 | 364 | 364 | 0 |  | Project Director |  | Proposed / unverified
W010 | Allowance | ALL | Offshore weather / access allowance (not productive work) | 10 | M100 | 2027-10-30 | 2027-11-08 | 364 | 373 | 0 | Reserved marine capacity | Marine Manager | 10 days is a planning allowance; not a weather study | Proposed / unverified
O100 | Marine | ALL | Offshore demobilisation | 3 | W010 | 2027-11-09 | 2027-11-11 | 374 | 376 | 0 | Support spread | Marine Manager | Clearance / backload | Proposed / unverified
C010 | Closeout | ALL | As-built dossiers, e-MB records, QA records and handover compilation | 30 | M100 | 2027-10-30 | 2027-11-28 | 364 | 393 | 0 | Completions team | QA / Completions |  | Proposed / unverified
C020 | Closeout | ALL | Final document review and completion certificate processing | 14 | C010, O100 | 2027-11-29 | 2027-12-12 | 394 | 407 | 0 | Project team | Project Director | ONGC acceptance / contractual completion criteria | Proposed / unverified
M200 | Milestone | ALL | Internal target: all works complete and handover accepted | 0 | C020 | 2027-12-13 | 2027-12-13 | 408 | 408 | 0 |  | Project Director |  | Proposed / unverified

## Milestone Comparison
ID | Milestone | Recovery option | Two-crew case | Recovery improvement days | Basis
M000 | Assumed NOA / commencement | 2026-11-01 | 2026-11-01 | 0 | Conditional target
E030 | Detailed design, AFC drawings and ITP approval | 2026-12-23 | 2026-12-23 | 0 | Conditional target
P010 | Vendor approval, steel purchase and phased yard delivery | 2027-01-02 | 2027-01-02 | 0 | Conditional target
F010 | Fabricate, NDT, dimensional inspection and coating | 2027-02-06 | 2027-02-06 | 0 | Conditional target
F020 | Fabricate, NDT, dimensional inspection and coating | 2027-02-26 | 2027-02-26 | 0 | Conditional target
F030 | Fabricate, NDT, dimensional inspection and coating | 2027-03-18 | 2027-03-18 | 0 | Conditional target
O010 | Accommodation/support mobilisation, permits, SIMOPS and readiness | 2027-02-01 | 2027-02-16 | 15 | Conditional target
J010 | Addendum jacket strengthening and acceptance | 2027-02-13 | 2027-02-28 | 15 | Conditional target
J020 | Addendum jacket strengthening and acceptance | 2027-02-11 | 2027-02-26 | 15 | Conditional target
I010 | Install, connect, inspect and accept replacement bridge | 2027-03-01 | 2027-03-16 | 15 | Conditional target
I020 | Install new bridge, transfer services and commission | 2027-03-23 | 2027-04-05 | 13 | Conditional target
D020 | Isolate, dismantle old bridge and remove to shore | 2027-03-30 | 2027-04-12 | 13 | Conditional target
I030 | Install, connect, inspect and accept replacement bridge | 2027-04-17 | 2027-04-30 | 13 | Conditional target
M100 | Planned offshore works complete | 2027-05-02 | 2027-10-30 | 181 | Conditional target
O100 | Offshore demobilisation | 2027-05-14 | 2027-11-11 | 181 | Conditional target
M200 | Internal target: all works complete and handover accepted | 2027-06-15 | 2027-12-13 | 181 | Conditional target
DEADLINE | Unextended contractual last workday (scenario) | 2027-10-31 | 2027-10-31 |  | Confirm actual NOA / contract convention
WARRANTY | Indicative warranty end: 12 months after actual handover | 2028-06-15 |  |  | Rebase to actual acceptance date

## Weekly Gantt
ID | Package / activity | Start | Finish | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-06 | 2026-12-13 | 2026-12-20 | 2026-12-27 | 2027-01-03 | 2027-01-10 | 2027-01-17 | 2027-01-24 | 2027-01-31 | 2027-02-07 | 2027-02-14 | 2027-02-21 | 2027-02-28 | 2027-03-07 | 2027-03-14 | 2027-03-21 | 2027-03-28 | 2027-04-04 | 2027-04-11 | 2027-04-18 | 2027-04-25 | 2027-05-02 | 2027-05-09 | 2027-05-16 | 2027-05-23 | 2027-05-30 | 2027-06-06 | 2027-06-13 | 2027-06-20 | 2027-06-27 | 2027-07-04 | 2027-07-11 | 2027-07-18 | 2027-07-25 | 2027-08-01 | 2027-08-08 | 2027-08-15 | 2027-08-22 | 2027-08-29 | 2027-09-05 | 2027-09-12 | 2027-09-19 | 2027-09-26 | 2027-10-03 | 2027-10-10 | 2027-10-17 | 2027-10-24 | 2027-10-31 | 2027-11-07 | 2027-11-14 | 2027-11-21 | 2027-11-28 | 2027-12-05 | 2027-12-12 | 2027-12-19
M000 | COMMON ¦ Assumed NOA / commencement | 2026-11-01 | 2026-11-01 | ◆
G010 | COMMON ¦ Kick-off, obligations, guarantees and funding arrangements | 2026-11-01 | 2026-11-07 | ■
G020 | COMMON ¦ Controlled document / addendum and quantity reconciliation | 2026-11-08 | 2026-11-21 |  | ■ | ■
S010 | COMMON ¦ Survey permits, mobilisation and access planning | 2026-11-08 | 2026-11-14 |  | ■
S020 | ALL ¦ Bridge and platform verification survey campaign | 2026-11-15 | 2026-11-28 |  |  | ■ | ■
E010 | COMMON ¦ Design basis and interface approval | 2026-11-08 | 2026-11-21 |  | ■ | ■
E020 | ALL ¦ Checked material requisitions / early material release | 2026-11-29 | 2026-12-08 |  |  |  |  | ■ | ■
P010 | ALL ¦ Vendor approval, steel purchase and phased yard delivery | 2026-12-09 | 2027-01-02 | [5 empty] | ■ | ■ | ■ | ■
E030 | REPLACEMENTS ¦ Detailed design, AFC drawings and ITP approval | 2026-11-29 | 2026-12-23 |  |  |  |  | ■ | ■ | ■ | ■
E040 | REFURBISHMENTS ¦ Bridge and jacket strengthening design / AFC work packs | 2026-11-29 | 2026-12-23 |  |  |  |  | ■ | ■ | ■ | ■
E050 | BHS-SLQ ¦ Utility transfer, temporary stability and demolition design | 2026-11-29 | 2027-01-02 |  |  |  |  | ■ | ■ | ■ | ■ | ■
MR10 | COMMON ¦ Vessel market enquiry, technical audit and conditional reservation | 2026-11-08 | 2026-12-12 |  | ■ | ■ | ■ | ■ | ■
MR20 | REPLACEMENTS ¦ Lift, loadout, transport and sea-fastening engineering | 2026-12-24 | 2027-01-27 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■
F010 | ICW-ICG LD ¦ Fabricate, NDT, dimensional inspection and coating | 2027-01-03 | 2027-02-06 | [9 empty] | ■ | ■ | ■ | ■ | ■
F020 | BHS-SLQ ¦ Fabricate, NDT, dimensional inspection and coating | 2027-01-03 | 2027-02-26 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
F030 | ICG-ICP LD ¦ Fabricate, NDT, dimensional inspection and coating | 2027-02-07 | 2027-03-18 | [14 empty] | ■ | ■ | ■ | ■ | ■ | ■
F041 | ALL STRENGTHENING ¦ First approved strengthening kits: phased fabrication / QA release | 2027-01-03 | 2027-01-22 | [9 empty] | ■ | ■ | ■
F040 | ALL STRENGTHENING ¦ Phased fabrication and release of strengthening kits | 2027-01-03 | 2027-02-06 | [9 empty] | ■ | ■ | ■ | ■ | ■
O010 | ALL ¦ Accommodation/support mobilisation, permits, SIMOPS and readiness | 2027-01-23 | 2027-02-01 | [11 empty] | ■ | ■ | ■
J010 | ICG / BHS ¦ Addendum jacket strengthening and acceptance | 2027-02-02 | 2027-02-13 | [13 empty] | ■ | ■
J020 | ICP ¦ Addendum jacket strengthening and acceptance | 2027-02-02 | 2027-02-11 | [13 empty] | ■ | ■
RA01 | ICW-ICG UD ¦ Strengthening, inspection and bridge acceptance | 2027-02-14 | 2027-03-01 | [15 empty] | ■ | ■ | ■
RA02 | ICG-ICP UD ¦ Strengthening, inspection and bridge acceptance | 2027-03-02 | 2027-03-23 | [17 empty] | ■ | ■ | ■ | ■
RA03 | SLQ-WIS ¦ Strengthening, inspection and bridge acceptance | 2027-03-24 | 2027-04-10 | [20 empty] | ■ | ■ | ■
RA04 | NQO-NQD ¦ Strengthening, inspection and bridge acceptance | 2027-02-07 | 2027-02-24 | [14 empty] | ■ | ■ | ■
RB01 | WIN-NC ¦ Strengthening, inspection and bridge acceptance | 2027-02-12 | 2027-02-23 | [14 empty] | ■ | ■ | ■
RB02 | SCA-SC1 ¦ Strengthening, inspection and bridge acceptance | 2027-02-24 | 2027-03-11 | [16 empty] | ■ | ■ | ■
RB03 | SCA-SCF ¦ Strengthening, inspection and bridge acceptance | 2027-03-12 | 2027-04-04 | [18 empty] | ■ | ■ | ■ | ■ | ■
H010 | COMMON ¦ Heavy-lift spread mobilisation and operational readiness | 2027-02-02 | 2027-02-08 | [13 empty] | ■ | ■
L010 | ICW-ICG LD ¦ Loadout, sea-fastening and transport | 2027-02-07 | 2027-02-11 | [14 empty] | ■
I010 | ICW-ICG LD ¦ Install, connect, inspect and accept replacement bridge | 2027-02-14 | 2027-03-01 | [15 empty] | ■ | ■ | ■
L020 | BHS-SLQ ¦ Loadout, sea-fastening and transport | 2027-02-27 | 2027-03-03 | [16 empty] | ■ | ■
I020 | BHS-SLQ ¦ Install new bridge, transfer services and commission | 2027-03-04 | 2027-03-23 | [17 empty] | ■ | ■ | ■ | ■
D020 | BHS-SLQ ¦ Isolate, dismantle old bridge and remove to shore | 2027-03-24 | 2027-03-30 | [20 empty] | ■ | ■
L030 | ICG-ICP LD ¦ Loadout, sea-fastening and transport | 2027-03-19 | 2027-03-23 | [19 empty] | ■ | ■
I030 | ICG-ICP LD ¦ Install, connect, inspect and accept replacement bridge | 2027-03-31 | 2027-04-17 | [21 empty] | ■ | ■ | ■
D030 | OTHER BRIDGES ¦ Other removal, waste backload and allocated demolition closure | 2027-04-18 | 2027-04-24 | [24 empty] | ■
O090 | ALL ¦ Final offshore inspections, punch closure and operational acceptance | 2027-04-25 | 2027-05-01 | [25 empty] | ■
M100 | ALL ¦ Planned offshore works complete | 2027-05-02 | 2027-05-02 | [26 empty] | ◆
W010 | ALL ¦ Offshore weather / access allowance (not productive work) | 2027-05-02 | 2027-05-11 | [26 empty] | ■ | ■
O100 | ALL ¦ Offshore demobilisation | 2027-05-12 | 2027-05-14 | [27 empty] | ■
C010 | ALL ¦ As-built dossiers, e-MB records, QA records and handover compilation | 2027-05-02 | 2027-05-31 | [26 empty] | ■ | ■ | ■ | ■ | ■
C020 | ALL ¦ Final document review and completion certificate processing | 2027-06-01 | 2027-06-14 | [30 empty] | ■ | ■ | ■
M200 | ALL ¦ Internal target: all works complete and handover accepted | 2027-06-15 | 2027-06-15 | [32 empty] | ◆

## Bridge Targets
Bridge | Work type | Recovery offshore package target | Two-crew offshore target | Acceptance scope / caveat
ICW-ICG LD | Replacement | 2027-03-01 | 2027-03-16 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
ICG-ICP LD | Replacement | 2027-04-17 | 2027-04-30 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
BHS-SLQ | Replacement | 2027-03-30 | 2027-04-12 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
ICW-ICG UD | Refurbishment | 2027-03-01 | 2027-03-16 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
ICG-ICP UD | Refurbishment | 2027-03-23 | 2027-04-07 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
SLQ-WIS | Refurbishment | 2027-04-10 | 2027-04-25 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
NQO-NQD | Refurbishment | 2027-02-24 | 2027-05-13 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
WIN-NC | Refurbishment | 2027-02-23 | 2027-03-10 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
SCA-SC1 | Refurbishment | 2027-03-11 | 2027-03-26 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance
SCA-SCF | Refurbishment | 2027-04-04 | 2027-04-19 | BHS includes old-bridge removal; other dates exclude later common residual demolition / final offshore punch, dossiers and overall acceptance

## Constraints and Actions
ID | Constraint | Required action | Owner | Decision point | Status
R01 | Actual NOA differs from 1 Nov | Recalculate the full network; date shift is not linear across monsoon. | Contracts | Before baseline | OPEN
R02 | Recovery requires third strengthening crew | Confirm competent crew C, supervision, accommodation and independent workfront. | Construction / Marine | Before commitment | OPEN
R03 | First-kit release after 20 days is unproven | Approve phased MTO, priority kits, inspection and transport; no work before QA release. | Engineering / Fabrication | Before production baseline | OPEN
R04 | Marine standby between campaigns | Cost reserved vessel days, accommodation, transfers and second-season remobilisation in base case. | Marine / Finance | Before charter | OPEN
R05 | Survey findings / demolition scope | Reconcile 1 MT; allocate 357 MT correctly; quantify other-bridge removal and engineered temporary works. | Engineering | Before procurement freeze | OPEN
R06 | Conditional monsoon relief | Submit compliant notices and obtain extension entitlement / dates; do not assume automatic relief or cost compensation. | Contracts | Before weather impact | OPEN
R07 | Support spread capacity | POB and simultaneous operations capacity may require multiple support vessels; minimum 60 does not establish adequacy. | Marine / ONGC | Before offshore release | OPEN
R08 | Durations and weather allowance not validated | Replace estimates with measured workpacks, rates, supplier delivery commitments and weather workability analysis. | Project Controls | Before baseline approval | OPEN
R09 | Approval turnaround / utility shutdown | Agree survey access, AFC review, service transfers, isolations, e-MB and acceptance windows. | Project Director / ONGC | Within first 30 days | OPEN
R10 | BHS removal sequence | New bridge and operational service transfer accepted before existing bridge demolition. | Technical Authority | Before demolition | HOLD
R11 | Shared engineering resources | Design team A requires structural, utility and temporary-works capacity concurrently; staffing numbers not established. | Engineering Manager | Before design start | OPEN
R12 | Unpriced project | Link dates to costs, charter terms, billing milestones and funding before commitment. | Finance / Commercial | Before sanction | OPEN

## Resource Basis
Resource | Planning quantity | Allocation | Qualification / limitation
Fabrication line 1 | 1 | ICW-ICG LD then ICG-ICP LD | Serial logic enforced; no throughput proven
Fabrication line 2 | 1 | BHS-SLQ | Dedicated candidate bay
Strengthening cell | 1 | All bridge and jacket kits | 20-day first batch + 35-day full release is recovery assumption
Strengthening crews | 3 | A: IC / SLQ; B: WIN / SCA; C: NQ | Recovery uses 3; comparator uses 2
Heavy-lift spread | 1 | ICW LD → BHS install → BHS demolition → ICP LD → residual removal | Sequential major operations; technical suitability unverified
Cargo spread | 1 | Sequential bridge transport | Voyage duration / deck suitability unverified
Support / accommodation spread | TBC | Survey, strengthening, heavy-lift and punch | Size for peak concurrent POB, logistics and ONGC operations
Engineering | 2 discipline groups + specialist support | Parallel design and marine / utility studies | Headcount and review capacity TBC
QA / NDT / coating | TBC | Support concurrent fabrication lines, kits and offshore | Independent coverage and inspection hold points TBC