# SHIVANSH / ONGC BRRP — Overall Project Schedule

Revision 0 | 25 October 2026 | Provisional management planning

Scenario commencement: 1 November 2026. Actual NOA / award is unconfirmed. Contract basis: 12 months from NOA, rather than a fixed 360-day limit. Dates and durations require approval and supplier / resource validation.

# Recommended recovery target

Two fabrication lines and one strengthening cell; three offshore strengthening crews, one sequential heavy-lift spread and one cargo spread. Earlier first-kit release is required. These are capacity assumptions, not confirmed commitments.

| Activity / milestone | Start | Finish |
| --- | --- | --- |
| Bridge and platform verification survey campaign | 15 Nov 2026 | 28 Nov 2026 |
| Detailed design, AFC drawings and ITP approval | 29 Nov 2026 | 23 Dec 2026 |
| Bridge and jacket strengthening design / AFC work packs | 29 Nov 2026 | 23 Dec 2026 |
| Vendor approval, steel purchase and phased yard delivery | 09 Dec 2026 | 02 Jan 2027 |
| Fabricate, NDT, dimensional inspection and coating | 03 Jan 2027 | 06 Feb 2027 |
| Fabricate, NDT, dimensional inspection and coating | 03 Jan 2027 | 26 Feb 2027 |
| Fabricate, NDT, dimensional inspection and coating | 07 Feb 2027 | 18 Mar 2027 |
| Phased fabrication and release of strengthening kits | 03 Jan 2027 | 06 Feb 2027 |
| Accommodation/support mobilisation, permits, SIMOPS and readiness | 23 Jan 2027 | 01 Feb 2027 |
| Addendum jacket strengthening and acceptance | 02 Feb 2027 | 13 Feb 2027 |
| Addendum jacket strengthening and acceptance | 02 Feb 2027 | 11 Feb 2027 |
| Install, connect, inspect and accept replacement bridge | 14 Feb 2027 | 01 Mar 2027 |
| Install new bridge, transfer services and commission | 04 Mar 2027 | 23 Mar 2027 |
| Isolate, dismantle old bridge and remove to shore | 24 Mar 2027 | 30 Mar 2027 |
| Install, connect, inspect and accept replacement bridge | 31 Mar 2027 | 17 Apr 2027 |
| Other removal, waste backload and allocated demolition closure | 18 Apr 2027 | 24 Apr 2027 |
| Final offshore inspections, punch closure and operational acceptance | 25 Apr 2027 | 01 May 2027 |
| Offshore weather / access allowance (not productive work) | 02 May 2027 | 11 May 2027 |
| Offshore demobilisation | 12 May 2027 | 14 May 2027 |
| As-built dossiers, e-MB records, QA records and handover compilation | 02 May 2027 | 31 May 2027 |
| Final document review and completion certificate processing | 01 Jun 2027 | 14 Jun 2027 |
| Internal target: all works complete and handover accepted | 15 Jun 2027 | 15 Jun 2027 |

# Seasonal and contractual assessment

Recovery option: offshore works complete 02 May 2027; demobilisation 14 May 2027; overall internal completion 15 Jun 2027.

Two-crew comparison: offshore works complete 30 Oct 2027; demobilisation 11 Nov 2027; overall internal completion 13 Dec 2027.

Conservative unextended contractual last workday for this scenario: 31 October 2027. Monsoon is excluded from planned offshore work, 16 May–15 October inclusive. Conditional contractual weather relief requires assessment and agreement; no extension or cost compensation is assumed.

# Management release conditions

Confirm actual NOA, contract date convention and controlling addenda.

Validate activity durations from work quantities, approval periods, supplier lead times and weather workability.

Secure third strengthening crew and phased first-kit QA release; confirm supporting accommodation, access and logistics.

Reconcile structural 1,142 / 1,141 MT discrepancy and bridge-specific demolition quantities.

Obtain approved jacket strengthening, lift and BHS service-transfer / demolition methods before offshore execution.

Approve integrated cost, cash and charter plan. Maintain weekly updates and a six-week constraint look-ahead.

Sources reviewed: GCC 2.1.1 / 6.3.1.1; Technical SCC 2.0 / 3.0; SOW Section 1 / 1.3; structural addendum; uploaded Level3, Stage28 and 360-day planning files; Stage34/35 management controls. Full resource-loaded P6 validation remains outstanding. All dates are proposed, not ONGC commitments.