## File Classification
File | Pages | Applicability | Findings
Design Criteria & Execution Methodology.pdf | 154 | PRIMARY BRRP SOURCE | Part I Rev14 pp1-116; BRRP PartII Rev0 pp117-120; PartIII Rev2 pp121-132; methodology RevC pp133-154
MTO Drawings IRT.pdf | 34 | BRRP SOURCE; PARTIAL DRAWING SET | MTO p1; six dimensioned landing / strengthening sheets pp2-7; standard details pp8-14; IRT pp15-34
Addendum_Structure_SOW.pdf | 1 | BRRP ADDENDUM | Two new uploads are identical to previously reviewed copy; ICG/ICP/BHS strengthening
Addendum (1).pdf |  | BRRP ADDENDUM | Identical to previously reviewed copy; apply controlling amendments
Specification Combined.pdf | 257 | BRRP SPECIFICATIONS | Identical to previously reviewed copies
Section 2.pdf | 43 | DIFFERENT PROJECT COVER | S&SRP: Sump Caisson and SWLP Casing Replacement Project; do not add its scope to BRRP by default
Section 3.pdf | 323 | MIXED / OTHER-PROJECT PACKAGE | General PartI Rev14 repeated; pp150-152 PartII names WSSRP-2; cover names S&SRP; use BRRP-specific PartII instead

## Input Gap Review
ID | Requirement | Revised status | File | PDF pages | Clause / document | Finding / next action
B01 | Complete general structural criteria | SUPPLIED | Design Criteria & Execution Methodology.pdf | 1-116 | DC3.4 PartI Rev14 | Remove earlier full-criteria missing flag
B02 | BRRP-specific design criteria | SUPPLIED | Design Criteria & Execution Methodology.pdf | 117-120 | PartII Rev0 | Apply 25-year bridge design life and MH Annexure13A
B03 | Bridge design provisions | SUPPLIED | Design Criteria & Execution Methodology.pdf | 42-43 | 3.4.16.4.17 | Pinned/hinged plus sliding; live load;20%future piping; movements; camber; roof
B04 | Material elastic constants | SUPPLIED | Design Criteria & Execution Methodology.pdf | 66 | Annexure2 | E210000MPa; G80770MPa; nu0.3; density7850kg/m3; alpha12e-6/C;g9.81
B05 | Global and local live loads | SUPPLIED | Design Criteria & Execution Methodology.pdf | 42;70;72 | Bridge clause and Annexure4 | Bridge walkway250kg/m2; local grating500kg/m2; apply to correct element/loadcase
B06 | Wind gust duration | EXPLAINED | Design Criteria & Execution Methodology.pdf | 73 | Annexure5 | Bridges>50m:15sec; bridges<50m:3sec. Explains study duration difference; speed/height calculation still to verify
B07 | Bridge deflection limits | SUPPLIED | Design Criteria & Execution Methodology.pdf | 43;85-86 | Bridge clause / Annexure12 | VerticalL/400; lateral due to windL/500; required camber compensates dead-load deflection
B08 | Environmental input | SUPPLIED | Design Criteria & Execution Methodology.pdf | 87-89;119 | Annexure13A / BRRP PartII | MH North/South parameters; use elevations/gust adjustment per criteria
B09 | Execution methodology | SUPPLIED AT TENDER LEVEL | Design Criteria & Execution Methodology.pdf | 133-154 | B774-000-83-43-EM-0001 RevC | Develop operation-specific engineered procedures
B10 | MTO | SUPPLIED; DISCREPANCY OPEN | MTO Drawings IRT.pdf | 1 | B774 MTO | Existing landing-strengthening column rows216MT versus total217MT; total structural1141vs1142MT
B11 | ICW/ICG landing drawings | PARTIAL | MTO Drawings IRT.pdf | 2-4 | B774-101-83-43-0002/0003/0004 RevA | Dimensioned tender sheets found; main0001 and extension0005 not located in this pack
B12 | ICP/ICG landing drawings | PARTIAL | MTO Drawings IRT.pdf | 5-7 | B774-102-83-43-0004/0002/0003 RevA | Dimensioned tender sheets found; main0001 and extension0005 not located in this pack
B13 | BHS-SLQ drawings | NOT LOCATED IN NEW PACK | MTO Drawings IRT.pdf | 2-14 | B774-103 series | Prior report model/crosssections remain available; detailed103-series sheets not located
B14 | Standard fittings drawings | SUPPLIED | MTO Drawings IRT.pdf | 8-14 | 7111-OD-STR-5001 through5006 | Grating handrails stairs jumping-rope D-shackle tie-up chain references; use applicability checks
B15 | Inspection requirements | SUPPLIED | MTO Drawings IRT.pdf | 15-34 | IRT and legends | Material / fittings / coating inspection responsibilities and releases
B16 | Native structural model | NOT LOCATED | Uploaded set | N/A | SACS native files | Printed models/results available; cannot reproduce full native connectivity/load map from figures alone
B17 | Final survey geometry and current condition | NOT ESTABLISHED | Uploaded reports and new criteria | 120 | PartII section13 | Tender drawings require survey update; confirm current bearing centres/levels/condition
B18 | Final lift/transport vessel data | CONTRACTOR INPUT | Design Criteria & Execution Methodology.pdf | 119 | PartII section6 | Lift list and vessel/de-rated capacity to be furnished; no actual spread confirmed
B19 | Camber profile | RULE SUPPLIED; DETAIL OPEN | Design Criteria & Execution Methodology.pdf | 43 | 3.4.16.4.17(c) | Use dead-load compensation rule; reconcile report1:200 statement and define profile
B20 | Concurrent reactions and existing capacity | VERIFICATION OPEN | Earlier bridge reports | 123;153;208-209 | Study reaction summaries | Obtain/reconstruct signed loadcase envelopes and support/deck/jacket checks

## Priority Design Changes
Item | Required adoption
Design life | 25 years for new bridges under BRRP PartII
Modulus | Use criteria E210000MPa; do not retain generic200000MPa assumption
Support model | Pinned/hinged and sliding; fixed intent does not mean moment-rigid
Translation | 150% total predicted relative translation; calculate platform movements
Axial thrust | Hinged connection designed for150% expected axial thrust
Future piping | 20% increment on planned including future piping operating loads; reconcile existing allowances to avoid double-counting
Camber | Compensate dead-load deflection; do not automatically use L/200
Wind duration | 15-second for56/84m;3-second for42m; validate wind-speed derivation
Local grating | 500kg/m2 local check distinct from250kg/m2 global bridge walkway
Scope segregation | BRRP-specific PartII controls applicability; unrelated S&SRP/WSSRP-2 scope not imported