## Basis
Topic | Statement
Status | PRELIMINARY DESIGN DEVELOPMENT / INDEPENDENT ARITHMETIC AUDIT ONLY. Not a completed design, checked FE model or AFC release.
Sources | SOW & Bridge Report Combined.pdf, 506 pages; structural SOW Rev C; reports BPR-0003/0004/0005; structural scope addendum; Specification Combined.pdf.
Scope | Three replacement bridges and associated supports / landings / platform-jacket interfaces. BHS includes service supports, operational transfer and demolition engineering.
Geometry | Reported SACS lengths 56/84/42 m are preliminary model lengths, NOT verified fabrication lengths or bearing-centre coordinates.
Loads | Load extents, source model and combinations require reconciliation; do not size members from the arithmetic review.
Limits | L/400 vertical and L/500 lateral are source-study criteria used for arithmetic reproduction, not independently approved project acceptance criteria.
Sections | Tubular dimensions in Section Geometry are transcribed only from ICP report VIV table. They are NOT mapped to chords/braces or selected for construction.
Support | SOW fixed/sliding terminology must be implemented using verified global/local directions, support coordinates, movements and actual restraints. Fixed is not automatically a moment-fixed member end.
Model status | Native analysis model, member groups, load distribution, stiffness assumptions, connectivity, combinations and full result envelopes have not been independently reproduced.
Release | Final fabrication, bearing, connection, lifting and temporary-work details require checked project-specific calculations and applicable ONGC approval.
Spreadsheet | Excel formula fields are recalculated on opening. Audit Snapshot contains independently computed static values for immediate reading.
SUPERSEDED INPUT STATUS | Full design criteria and partial drawings now supplied. Refer BRRP_Engineering_Input_Check_RevP3.xlsx; P2 query statuses are historical.

## Source Inputs
Bridge | Source report | Model length m | Approx gap m | Walkway loading width m | Reported vertical mm | Reported lateral mm | Highest listed member UC | Highest listed joint UC | Reported DL deflection mm | Combined PDF pages
ICW-ICG LD | B774-000-83-43-BPR-0004 Rev 0 | 56 | 54.5 | 1.2 | 105 | 87 | 0.557 | 0.509 | 85 | 133-135;152-153
ICP-ICG LD | B774-000-83-43-BPR-0003 Rev 0 | 84 | 80.5 | 1.2 | 177 | 123 | 0.61 | 0.625 | 143 | 196-199;207-209
BHS-SLQ LD | B774-000-83-43-BPR-0005 Rev A | 42 | 40 | 2.324 | 32 | 76 | 0.916 | 0.859 | 32 | 97-100;122-123

## Serviceability Arithmetic
Bridge | Model L m | Source L/400 mm | Reported vertical mm | Vertical ratio | Source L/500 mm | Reported lateral mm | Lateral ratio | L/200 arithmetic mm | Reported DL deflection mm | L/200 divided by DL deflection | Interpretation
ICW-ICG LD | [10 empty] | SOURCE LIMIT ARITHMETIC ONLY; not independent structural adequacy
ICP-ICG LD | [10 empty] | SOURCE LIMIT ARITHMETIC ONLY; not independent structural adequacy
BHS-SLQ LD | [10 empty] | SOURCE LIMIT ARITHMETIC ONLY; not independent structural adequacy

## Audit Snapshot
Bridge | Source vertical limit mm | Reported vertical mm | Ratio vertical | Source lateral limit mm | Reported lateral mm | Ratio lateral | L/200 arithmetic mm | Reported DL deflection mm | Camber arithmetic / DL
ICW-ICG LD | 140 | 105 | 0.75 | 112 | 87 | 0.77679 | 280 | 85 | 3.2941
ICP-ICG LD | 210 | 177 | 0.84286 | 168 | 123 | 0.73214 | 420 | 143 | 2.9371
BHS-SLQ LD | 105 | 32 | 0.30476 | 84 | 76 | 0.90476 | 210 | 32 | 6.5625

## Live Load Reconciliation
Bridge | Study L m | Loading width m | Source loading kg/m2 | Converted kN/m2 | Simple rectangular load kN | Report table LL kN | Output LL magnitude kN | Table minus rectangle kN | Required interpretation
ICW-ICG LD | 56 | 1.2 | 250 | 2.4517 | 164.7517 | 156.25 | 144.69 | -8.5017 | Screen uses full rectangular L x width; source may include/exclude other areas. Obtain actual load map. No discrepancy correction assumed.
ICP-ICG LD | 84 | 1.2 | 250 | 2.4517 | 247.1276 | 288 | 288 | 40.8724 | Screen uses full rectangular L x width; source may include/exclude other areas. Obtain actual load map. No discrepancy correction assumed.
BHS-SLQ LD | 42 | 2.324 | 250 | 2.4517 | 239.3019 | 268.42 | 268.42 | 29.1181 | Screen uses full rectangular L x width; source may include/exclude other areas. Obtain actual load map. No discrepancy correction assumed.

## Section Geometry
Source OD mm | Source wall mm | Calculated ID mm | Area mm2 | I mm4 | Elastic Z mm3 | Radius gyration mm | Nominal mass kg/m | Source VIV length m | Status
406 | 15.9 | 374.2 | 19486.0112 | 371283582.7843 | 1828983.1664 | 138.0357 | 152.9652 | 4 | ICP VIV table, combined PDF p.208; member role / grade / corrosion / effective length not adopted
406 | 12.7 | 380.6 | 15691.9726 | 303730250.9736 | 1496208.1329 | 139.125 | 123.182 | 4 | ICP VIV table, combined PDF p.208; member role / grade / corrosion / effective length not adopted
168 | 9.5 | 149 | 4730.4531 | 14908318.7182 | 177479.9847 | 56.1388 | 37.1341 | 4.98 | ICP VIV table, combined PDF p.208; member role / grade / corrosion / effective length not adopted
114 | 7.9 | 98.2 | 2633.2515 | 3725925.8586 | 65367.1203 | 37.6159 | 20.671 | 4.71 | ICP VIV table, combined PDF p.208; member role / grade / corrosion / effective length not adopted

## Design Queries
ID | Discipline | Bridge | Issue | Required closure | Status | Owner
Q01 | Geometry | All | Model length versus final span | Survey coordinates, datums, skew, landing offsets and actual bearing centres | HOLD | Engineering
Q02 | Analysis | All | Source model unavailable for reproduction | Native SACS model, connectivity, groups, loads, combinations, stiffness and envelopes | HOLD | Analysis lead
Q03 | Loads | All | Rectangular LL screen does not reproduce all totals | Actual loaded areas, extensions, units, distribution and load-generation records | HOLD | Analysis lead
Q04 | Loads | ICW | Report LL156.25kN vs output144.69kN | Identify controlling model revision and corresponding load map | HOLD | Analysis lead
Q05 | Camber | All | Report instruction 1:200 differs from reported DL deflection | Define camber meaning/profile, reference line, support levels and tolerances | HOLD | Technical Authority
Q06 | Support | BHS-SLQ | Report says SLQ fixed; SOW also contains sliding wording | Resolve support philosophy and exact freedoms / restraints | HOLD | ONGC / Engineering
Q07 | Wind | All | 15-second gust in IC reports vs 3-second gust in BHS | Approved metocean/design basis and compatible averaging/conversion method | HOLD | Analysis lead
Q08 | Existing structure | All | Bridge reports refer to separate support/deck/jacket adequacy | Obtain checks/models and integrate reactions with addendum strengthening | HOLD | Platform engineer
Q09 | Reactions | All | Summary does not identify complete concurrent signed envelopes | Provide units, axes, governing combinations, minima, maxima, uplift and moments | HOLD | Analysis lead
Q10 | Members | All | Pictures/VIV list do not establish member schedule | Obtain complete section-group mapping, effective lengths and material specifications | HOLD | Analysis lead
Q11 | Dynamic/fatigue | All | Source summary does not establish full project coverage | Verify vibration, wind response, fatigue and movement criteria with full calculations | HOLD | Specialist engineer
Q12 | Temporary conditions | All | Operating study is not lifting / transport approval | Check actual modules, transport supports, accelerations, lifting and installation states | HOLD | Marine / Structural
Q13 | References | All | 83-41 / 83-43 and landing/demolition reference conflicts | Issue corrected controlling drawing register and revisions | HOLD | Document control / ONGC
Q14 | Durability | All | 50ksi yield is not a complete procurement grade | Approve grade, toughness, thickness tolerances, corrosion basis, welding and coatings | HOLD | Materials / QA

## Calculation and Detail Plan
Workstream | Scope | Required analysis | Release deliverable
Global model | Permanent framing | Coordinates, member connectivity, releases, eccentricity, torsion and lateral stability | Checked model and independent review
Members | Strength and buckling | Axial, bending, shear, interaction, local slenderness and effective lengths | Member group schedule and full utilisation envelopes
Connections | Joints and end connections | Tubular joint checks, local stresses, bolts, welds, gussets and fatigue details | Joint calculations and fabrication detail drawings
Serviceability | Deflection and vibration | Agreed load cases, vertical/lateral limits, walkway vibration and service movement | Serviceability report and camber profile
Bearings | Restraints and movements | Thermal and relative platform motion, friction, guides, travel and uplift | Bearing data sheets and reactions
Existing steel | Landings / decks / jackets | Actual corrosion and load paths plus new reaction envelopes | Integrated existing-structure adequacy report
Marine | Temporary conditions | Loadout, transport, seafastening, lifting, landing and temporary support | Checked operation-specific engineering
Fabrication | Detailed engineering | Approved geometry and sections, connections, tolerances, inspection and traceability | AFC drawings and manufacturing dossier

## Design Basis Source Index
ID | Subject | Document | Uploaded file | PDF pages | Evidence status | Application
DB01 | Structural standards register | B774-000-83-43-ST-01 Rev A | Specification Combined.pdf | 1-2 | Located | Defines listed standards and specifications
DB02 | Welding and NDT | 2009F Rev 8 | Specification Combined.pdf | 3-38 | Located | Apply applicable procedures and inspection requirements
DB03 | Fabrication and assembly | 6-60-0013 Rev 3 | Specification Combined.pdf | 55-81 | Located | Fabrication and assembly requirements
DB04 | Protective coating | 2005 Rev 9 | Specification Combined.pdf | 91-168 | Located | Select applicable coating systems by exposure and service
DB05 | Material fabrication installation | 6001F Rev 14 | Specification Combined.pdf | 169-243 | Located | Includes material and construction requirements; apply relevant clauses
DB06 | Design-code references | API RP 2A WSD / AWS / AISC within 6001F | Specification Combined.pdf | 172-175 | Located | Confirm governing editions and hierarchy; listed standards are not all applicable to every item
DB07 | ICW-ICG study basis | BPR-0004 Rev 0 | SOW & Bridge Report Combined.pdf | 133-135 | Located | 56m model;54.5m approximate gap; material/wind/loading/support study inputs
DB08 | ICP-ICG study basis | BPR-0003 Rev 0 | SOW & Bridge Report Combined.pdf | 196-199 | Located | 84m model;80.5m approximate gap; material/wind/loading/support study inputs
DB09 | BHS-SLQ study basis | BPR-0005 Rev A | SOW & Bridge Report Combined.pdf | 97-100 | Located | 42m model;40m approximate gap; material/wind/loading/support study inputs
DB10 | Structural project scope | B774-000-83-43-SOW-0001 Rev C | SOW & Bridge Report Combined.pdf | 15-53 | Located | Replacement scope, landings and drawing references
DB11 | Jacket strengthening addendum | Addendum_Structure_SOW | Addendum_Structure_SOW.pdf | 1 | Located | ICG ICP BHS enabling strengthening
DB12 | Referenced structural design criteria | DC-3.4-Part-1-Rev.14 | Referenced in bridge reports | 98;133;197 | Reference located; complete text not identified | Do not mark entire design basis missing; distinguish source excerpts from standalone criteria