# SHIVANSH OFFSHORE EPC

# PROJECT EXECUTION MASTER PLAN

# VOLUME 6 — COMMERCIAL, QUALITY, HSE, RISK AND HANDOVER

ONGC Bridge Refurbishment & Replacement Project | Pre-award planning draft | 17 October 2026

DOCUMENT STATUS: For management planning and verification only. Not issued for construction. Technical and marine procedures require competent engineering review and ONGC approvals.

## Document control

| Item | Entry |
| --- | --- |
| Document code | SHV-BRRP-PEP-V06-R0 |
| Revision | 0 — Pre-award planning |
| Prepared for | Shivansh management / Project Director |
| Contract award | Not confirmed |
| Governing duration | 360 days subject to contract |
| Approval | Pending CEO and discipline review |

## Basis, sources and limitations

The ONGC SOW & Bridge Report Combined.pdf, Section 1 Background and General Requirement, contains the ten-bridge B774 scope and quantity table. Previous project-stage assumptions are incorporated as planning hypotheses, not as verified commitments. Latest addenda, detailed drawings and MTO must be reconciled before procurement, fabrication, lifting or offshore work.

External EPC benchmarks: Saipem offshore engineering and construction; McDermott offshore EPCI. Marine reference for applicability review: DNV-ST-N001 (December 2023). Contract documents and approved ONGC requirements govern.

## Master bridge and quantity register

| Bridge | New/replace MT | Existing bridge strengthen MT | New landing/deck MT | Existing landing/deck strengthen MT | Demolition MT |
| --- | --- | --- | --- | --- | --- |
| ICW–ICG UD | 0 | 19 | 0 | 30 | 25 |
| ICW–ICG LD | 57 | 0 | 65 | 0 | 1 |
| ICG–ICP UD | 0 | 86 | 0 | 30 | 25 |
| ICG–ICP LD | 115 | 0 | 45 | 0 | 1 |
| BHS–SLQ | 195 | 0 | 87 | 0 | 210 |
| SLQ–WIS | 0 | 61 | 0 | 30 | 15 |
| NQO–NQD | 0 | 63 | 0 | 30 | 25 |
| WIN–NC | 0 | 6 | 0 | 40 | 10 |
| SCA–SC1 | 0 | 35 | 0 | 28 | 15 |
| SCA–SCF | 0 | 91 | 0 | 28 | 30 |

Printed SOW column totals: 367 / 361 / 197 / 217 / 357 MT. Structural column total = 1,142 MT. Sum of printed bridge-row structural entries = 1,141 MT. Open discrepancy: 1 MT. Handrail 1,168 m; grating 719 m²; GI sheeting 1,274 m². No correction made pending source reconciliation.

# Management procedures and control requirements

## 6.1 Cost baseline

Code engineering, steel, fabrication, NDT, coating, logistics, marine, offshore labour, demolition, service interfaces, management, insurance, finance, risk and handover by bridge and common package.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.2 Commercial contract review

Verify ONGC invoice measurement, certification periods, retention, guarantees, advances, variation notices, tax treatment, insurance, payment terms and subcontracting permission before making assumptions.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.3 Working capital

Forecast cash-out from dated POs, subcontract milestones, wages, charters and overhead; cash-in from contract-specific billing and expected collection; peak cash gap is maximum cumulative payments minus receipts.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.4 Cost and earned value

Track budget, commitment, accrual, actual, earned value, forecast ETC and EAC. Reconcile physical progress, certified progress, invoicing and cash collected separately.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.5 Quality management

Issue project quality plan, ITP matrix, welding qualifications, material traceability, NDT/coating procedures, calibration, NCR and corrective action, turnover dossiers. ONGC/third-party hold points as contract requires.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.6 HSE and SIMOPS

Site-specific risk assessments, permit-to-work, isolations, working at height, lifting, dropped objects, hot work, marine transfers, emergency response, personnel competence and simultaneous operations must follow approved ONGC and vessel systems.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.7 Emergency response

Integrate platform emergency authority, vessel master, contractor personnel accountability, communications, evacuation, medical response, incident management and restart checks. Run tabletop and relevant joint drills.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.8 Risk and contingency

Maintain probability/impact register with named owner, early-warning indicator, mitigation, cost and schedule consequence; quantify contingency separately from hidden budget allowances.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.9 Claims and changes

Maintain change register, written instructions, contemporaneous records, delay event logs, notices within contractual time bars and approved variation valuation. Do not assume entitlement.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.10 Completion and turnover

Bridge-wise mechanical/structural completion records, punch lists, NDT/coating reports, material certificates, as-builts, removal/disposal records, service reinstatement and ONGC acceptance.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

## 6.11 Financial and execution gate

CEO receives cost-to-complete, 13-week cash forecast, marine exposure, unresolved NCRs, critical-path risk and acceptance forecast; no unapproved spending or safety-gate waiver.

Required evidence / deliverable: controlled register or signed record, responsible manager, planned date, verification status, and escalation of any open technical, resource, commercial or operational constraint.

# Bridge-wise implementation matrix

| Bridge | Work type | Planning quantity MT | Required bridge-specific output |
| --- | --- | --- | --- |
| ICW–ICG UD | Strengthening | 49 | Approved drawings + MTO + work pack + QA release + accepted handover |
| ICW–ICG LD | New lower deck | 122 | Approved drawings + MTO + work pack + QA release + accepted handover |
| ICG–ICP UD | Strengthening | 116 | Approved drawings + MTO + work pack + QA release + accepted handover |
| ICG–ICP LD | New lower deck | 160 | Approved drawings + MTO + work pack + QA release + accepted handover |
| BHS–SLQ | Replacement | 282 | Approved drawings + MTO + work pack + QA release + accepted handover |
| SLQ–WIS | Strengthening | 91 | Approved drawings + MTO + work pack + QA release + accepted handover |
| NQO–NQD | Strengthening | 93 | Approved drawings + MTO + work pack + QA release + accepted handover |
| WIN–NC | Strengthening | 46 | Approved drawings + MTO + work pack + QA release + accepted handover |
| SCA–SC1 | Strengthening | 63 | Approved drawings + MTO + work pack + QA release + accepted handover |
| SCA–SCF | Strengthening | 119 | Approved drawings + MTO + work pack + QA release + accepted handover |

# Control register template

| ID | Deliverable / action | Accountable owner | Due date | Status / evidence |
| --- | --- | --- | --- | --- |
| V6-01 | Cost baseline | To assign | To confirm | Open — verify |
| V6-02 | Commercial contract review | To assign | To confirm | Open — verify |
| V6-03 | Working capital | To assign | To confirm | Open — verify |
| V6-04 | Cost and earned value | To assign | To confirm | Open — verify |
| V6-05 | Quality management | To assign | To confirm | Open — verify |
| V6-06 | HSE and SIMOPS | To assign | To confirm | Open — verify |
| V6-07 | Emergency response | To assign | To confirm | Open — verify |
| V6-08 | Risk and contingency | To assign | To confirm | Open — verify |
| V6-09 | Claims and changes | To assign | To confirm | Open — verify |
| V6-10 | Completion and turnover | To assign | To confirm | Open — verify |
| V6-11 | Financial and execution gate | To assign | To confirm | Open — verify |

# Formal review and release criteria

Before release, discipline leads must verify: (1) controlling contract and drawing revision; (2) reconciled quantity and scope; (3) qualified resources and documented capacity; (4) schedule and cost impact; (5) inspection and safety hold points; (6) ONGC and marine operational authorisations where applicable. CEO approval of a planning volume does not authorise offshore operations.

# Reference sources

SOW & Bridge Report Combined.pdf — Section 1, Background and General Requirement; B774 MTO table

MTO Drawings IRT.pdf — drawing collection; detailed checking outstanding

https://www.saipem.com/en/solutions-energy-transition/offshore

https://www.mcdermott.com/solutions/offshore

https://www.dnv.com/energy/standards-guidelines/dnv-st-n001-marine-operations-and-marine-warranty/