## CEO Overview
Metric | Value | Status / basis
Project | ONGC Mumbai High BRRP | Tender / MTO baseline
Period (days) | 360 | Provisional relative-day planning horizon
New bridge steel (MT) | 367 | Uploaded MTO
Bridge strengthening steel (MT) | 361 | Uploaded MTO
New landing and deck steel (MT) | 197 | Uploaded MTO
Landing strengthening steel (MT) | 217 | Uploaded MTO
Demolition (MT) | 357 | Uploaded MTO
Heavy lift vessel | TBD | Requires module weights and lift study
Actual project start | TBD | Confirm notification of award / SCC
Cost and rates | TBD | No invented costs or production rates

## Bridge Quantities
Package | New bridge MT | Bridge strengthening MT | New landing MT | Landing strengthening MT | Demolition MT | Construction MT | Module count TBD | Status
ICW-ICG UD | 0 | 19 | 0 | 30 | 25 | 49 |  | Survey/engineering pending
ICW-ICG LD | 57 | 0 | 65 | 0 | 1 | 122 |  | Survey/engineering pending
ICG-ICP UD | 0 | 86 | 0 | 30 | 25 | 116 |  | Survey/engineering pending
ICG-ICP LD | 115 | 0 | 45 | 0 | 1 | 160 |  | Survey/engineering pending
BHS-SLQ | 195 | 0 | 87 | 0 | 210 | 282 |  | Survey/engineering pending
SLQ-WIS | 0 | 61 | 0 | 30 | 15 | 91 |  | Survey/engineering pending
NQO-NQD | 0 | 63 | 0 | 30 | 25 | 93 |  | Survey/engineering pending
WIN-NC | 0 | 6 | 0 | 40 | 10 | 46 |  | Survey/engineering pending
SCA-SC1 | 0 | 35 | 0 | 28 | 15 | 63 |  | Survey/engineering pending
SCA-SCF | 0 | 91 | 0 | 28 | 30 | 119 |  | Survey/engineering pending
TOTAL | 367 | 361 | 197 | 216 | 357 | 1141

## Work Packages
Package | Design release gate | Procurement gate | Fabrication gate | Loadout gate | Offshore gate | Closeout gate | Accountable lead
ICW-ICG UD | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
ICW-ICG LD | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
ICG-ICP UD | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
ICG-ICP LD | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
BHS-SLQ | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
SLQ-WIS | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
NQO-NQD | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
WIN-NC | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
SCA-SC1 | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD
SCA-SCF | Approved survey + AFC | Approved MTO + PO | NDT + dimensional + coating | Weight/COG + seafastening | Vessel + permit + lift approval | Inspection + as-builts | TBD

## Schedule Windows
Activity | Start Day | Finish Day | Duration calendar days | Lead | Predecessor / release condition | Validated?
Mobilisation / execution baseline | 1 | 30 | 30 | PMO | To be logic-linked in P6 | NO
Offshore surveys | 10 | 75 | 66 | Engineering | To be logic-linked in P6 | NO
Engineering / ONGC review | 25 | 135 | 111 | Engineering | To be logic-linked in P6 | NO
Steel and consumables procurement | 55 | 190 | 136 | Procurement | To be logic-linked in P6 | NO
Fabrication and QA | 95 | 245 | 151 | Fabrication | To be logic-linked in P6 | NO
Marine studies and readiness | 90 | 240 | 151 | Marine | To be logic-linked in P6 | NO
Strengthening campaign | 165 | 310 | 146 | Offshore | To be logic-linked in P6 | NO
New bridge installation | 220 | 315 | 96 | Offshore | To be logic-linked in P6 | NO
BHS-SLQ installation/service transfer/demolition | 245 | 335 | 91 | Offshore | To be logic-linked in P6 | NO
Completion and turnover | 315 | 360 | 46 | Completion | To be logic-linked in P6 | NO

## Resource Estimates
Package | Construction MT | Shop productivity MT/day INPUT | Fabrication working days CALC | Offshore crew INPUT | Offshore workdays INPUT | Crew person-days CALC | Heavy-lift vessel days INPUT | Accommodation vessel days INPUT | Basis / verification
ICW-ICG UD | 49 | [7 empty] | Enter approved rates, workpacks and marine method
ICW-ICG LD | 122 | [7 empty] | Enter approved rates, workpacks and marine method
ICG-ICP UD | 116 | [7 empty] | Enter approved rates, workpacks and marine method
ICG-ICP LD | 160 | [7 empty] | Enter approved rates, workpacks and marine method
BHS-SLQ | 282 | [7 empty] | Enter approved rates, workpacks and marine method
SLQ-WIS | 91 | [7 empty] | Enter approved rates, workpacks and marine method
NQO-NQD | 93 | [7 empty] | Enter approved rates, workpacks and marine method
WIN-NC | 46 | [7 empty] | Enter approved rates, workpacks and marine method
SCA-SC1 | 63 | [7 empty] | Enter approved rates, workpacks and marine method
SCA-SCF | 119 | [7 empty] | Enter approved rates, workpacks and marine method

## Lift COG Control
Package | Module ID | Net module MT | Attachments MT | Rigging MT | Gross suspended MT | COG X m | COG Y m | COG Z m | Crane radius m | Crane capacity MT | Engineered lift approved?
ICW-ICG UD | TBD | [9 empty] | NO
ICW-ICG LD | TBD | [9 empty] | NO
ICG-ICP UD | TBD | [9 empty] | NO
ICG-ICP LD | TBD | [9 empty] | NO
BHS-SLQ | TBD | [9 empty] | NO
SLQ-WIS | TBD | [9 empty] | NO
NQO-NQD | TBD | [9 empty] | NO
WIN-NC | TBD | [9 empty] | NO
SCA-SC1 | TBD | [9 empty] | NO
SCA-SCF | TBD | [9 empty] | NO

## Marine Suitability
Vessel / asset | Website-listed role | Proposed BRRP role | Available dates | Class / certificates | Crane curve verified | Deck load / stability | ONGC marine audit | Decision
Shivansh Shambhavi | Accommodation barge | Accommodation / support |  |  | N/A |  |  | Pending
AHTS Garnet | AHTS | Towing / anchor handling |  |  | N/A |  |  | Pending
AHTS Shivansh | AHTS | Towing / anchor handling |  |  | N/A |  |  | Pending
Shivansh Aryan | Workboat | Support / personnel transfers | [5 empty] | Pending
DSV Shivansh Priya | Diving support vessel | Survey / subsea if required | [5 empty] | Pending
Heavy-lift vessel TBD | Not verified on website | Engineered module lifting |  |  | NO |  |  | Sourcing required

## Inspection Gates
Gate | Applies to | Required evidence | Approver | Release status
Survey freeze | All relevant bridge packages | Signed survey and interfaces | Qualified lead / ONGC as required | NOT RELEASED
AFC design | All relevant bridge packages | Independent checks and accepted drawings | Qualified lead / ONGC as required | NOT RELEASED
Material traceability | All relevant bridge packages | MTC and heat-number reconciliation | Qualified lead / ONGC as required | NOT RELEASED
Welding release | All relevant bridge packages | WPS/PQR and welder qualification | Qualified lead / ONGC as required | NOT RELEASED
Fabrication acceptance | All relevant bridge packages | NDT / dimensional / coating reports | Qualified lead / ONGC as required | NOT RELEASED
Lift release | All relevant bridge packages | Weight COG padeyes rigging crane vessel approvals | Qualified lead / ONGC as required | NOT RELEASED
Demolition release | All relevant bridge packages | Isolation / staged stability / PTW / SIMOPS | Qualified lead / ONGC as required | NOT RELEASED
Final turnover | All relevant bridge packages | Punch list closure and as-builts | Qualified lead / ONGC as required | NOT RELEASED

## Risks & Decisions
ID | Risk / decision | Priority | Mitigation / action | Owner | Due date | Status
R01 | Award/start date unknown | HIGH | Confirm contractual date and milestone obligations | TBD |  | OPEN
R02 | Offshore weather window | HIGH | Calendarise seasonal limits and standby assumptions | TBD |  | OPEN
R03 | Survey/as-built mismatch | HIGH | Verify all support and service interfaces | TBD |  | OPEN
R04 | BHS-SLQ service continuity | HIGH | New bridge and services transfer before old bridge demolition | TBD |  | OPEN
R05 | Crane lift weights unknown | HIGH | Define segmentation and verified weight/COG | TBD |  | OPEN
R06 | Fabrication yard capacity unknown | HIGH | Audit yard and qualify capacity | TBD |  | OPEN
R07 | Vessel availability unknown | HIGH | Reserve audited suitable marine spread | TBD |  | OPEN
R08 | Commercial rate uncertainty | HIGH | Secure vendor / vessel quotations | TBD |  | OPEN
R09 | ONGC approvals on critical path | HIGH | Build DCI and resubmission cycles into schedule | TBD |  | OPEN

## Cost Inputs
Cost category | Quantity / basis | Unit rate INR INPUT | Budget INR CALC | Quotation / source | Status
Structural steel supply |  |  |  |  | Unpriced
Shop fabrication |  |  |  |  | Unpriced
NDT and coating |  |  |  |  | Unpriced
Engineering and survey |  |  |  |  | Unpriced
Marine vessel charter |  |  |  |  | Unpriced
Loadout and seafastening |  |  |  |  | Unpriced
Offshore installation |  |  |  |  | Unpriced
Offshore strengthening |  |  |  |  | Unpriced
Demolition and disposal |  |  |  |  | Unpriced
HSE QA/QC and insurance |  |  |  |  | Unpriced
Contingency |  |  |  |  | Unpriced

## Basis and Sources
Category | Basis | Limitations / next verification
MTO | ONGC B774 tender summary, ten bridge packages | Quantities subject to AFC design and survey
Schedule | Previous Stage-3 proposed 360-day windows | Not a resource-levelled or CPM-approved schedule
Shivansh fleet | Company website shivanshoffshore.in | Company claims; vessel particulars/availability unverified
Marine safety | IMCA lifting and operational planning guidance | Applicable revision and contract requirements to be confirmed
P6 | Oracle Primavera activity relationship guidance | Import format and calendars to be validated
Contract | ONGC SCC / project tender documents | Award, dates, approved procedures and subcontract restrictions govern
Engineering | No module weights or crane radii provided | Do not use for lift or demolition authorization