## CEO Decisions
Priority | Decision | Owner | Evidence required | Status
1 | Confirm award and Day 1 / contract calendar | CEO | Signed contract and SCC | OPEN
2 | Appoint PMO and engineering authority | CEO | Organisation and authority matrix | OPEN
3 | Select audited fabrication yard(s) | Project Director | Capacity, QA, welding approvals | OPEN
4 | Confirm heavy lift partner and vessel | Marine Manager | Crane curves, class, stability, availability | OPEN
5 | Approve package-specific survey mobilisation | Engineering Manager | Permits and scope | OPEN
6 | Approve baseline only after CPM and leveling | Project Director | P6 report and resource histogram | OPEN

## Package Baseline
Package | Work type | Steel MT | Demolition MT | Fabrication split count (INPUT) | Module gross weight MT (INPUT) | Verified COG (INPUT) | Engineering status | Marine strategy
ICW-ICG UD | Strengthening | 49 | 25 |  |  |  | NOT APPROVED | Survey / lift study required
ICW-ICG LD | New | 122 | 1 |  |  |  | NOT APPROVED | Survey / lift study required
ICG-ICP UD | Strengthening | 116 | 25 |  |  |  | NOT APPROVED | Survey / lift study required
ICG-ICP LD | New | 160 | 1 |  |  |  | NOT APPROVED | Survey / lift study required
BHS-SLQ | Replacement | 282 | 210 |  |  |  | NOT APPROVED | Survey / lift study required
SLQ-WIS | Strengthening | 91 | 15 |  |  |  | NOT APPROVED | Survey / lift study required
NQO-NQD | Strengthening | 93 | 25 |  |  |  | NOT APPROVED | Survey / lift study required
WIN-NC | Strengthening | 46 | 10 |  |  |  | NOT APPROVED | Survey / lift study required
SCA-SC1 | Strengthening | 63 | 15 |  |  |  | NOT APPROVED | Survey / lift study required
SCA-SCF | Strengthening | 119 | 30 |  |  |  | NOT APPROVED | Survey / lift study required

## Yard Production
Package | Steel MT | Yard MT per working day (INPUT) | Fabrication working days (CALC) | Yard allocation | WPS/PQR | NDT release | Coating release | Trial fit | Ready for loadout
ICW-ICG UD | 49 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
ICW-ICG LD | 122 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
ICG-ICP UD | 116 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
ICG-ICP LD | 160 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
BHS-SLQ | 282 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
SLQ-WIS | 91 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
NQO-NQD | 93 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
WIN-NC | 46 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
SCA-SC1 | 63 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO
SCA-SCF | 119 |  |  | TBD | PENDING | PENDING | PENDING | PENDING | NO

## Marine Campaign
Package | Marine role | Candidate vessel | Vessel confirmed? | Crane capacity verified? | Lift study approved? | Loadout readiness | Weather window | Offshore days (INPUT) | Daily rate INR (INPUT) | Budget INR (CALC)
ICW-ICG UD | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
ICW-ICG LD | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
ICG-ICP UD | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
ICG-ICP LD | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
BHS-SLQ | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
SLQ-WIS | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
NQO-NQD | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
WIN-NC | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
SCA-SC1 | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD
SCA-SCF | Heavy lift / transport / support | TBD | NO | NO | NO | NO | TBD

## Cost Loading
Package | Steel MT | Steel installed INR per MT (INPUT) | Steel subtotal INR | Demolition MT | Demolition INR per MT (INPUT) | Demolition subtotal INR | Marine INR (linked) | Other INR (INPUT) | Total INR
ICW-ICG UD | 49 |  |  | 25 |  |  | 0 |  | 0
ICW-ICG LD | 122 |  |  | 1 |  |  | 0 |  | 0
ICG-ICP UD | 116 |  |  | 25 |  |  | 0 |  | 0
ICG-ICP LD | 160 |  |  | 1 |  |  | 0 |  | 0
BHS-SLQ | 282 |  |  | 210 |  |  | 0 |  | 0
SLQ-WIS | 91 |  |  | 15 |  |  | 0 |  | 0
NQO-NQD | 93 |  |  | 25 |  |  | 0 |  | 0
WIN-NC | 46 |  |  | 10 |  |  | 0 |  | 0
SCA-SC1 | 63 |  |  | 15 |  |  | 0 |  | 0
SCA-SCF | 119 |  |  | 30 |  |  | 0 |  | 0

## P6 Logic Review
Activity ID | Package | Discipline | Activity | Start Day | Finish Day | Duration | Predecessor | Relationship | Accountable Role | Crew assumption | Marine Resource
BR0001 | COMMON | Management | Kickoff / contract review | 1 | 10 | 10 |  |  | Project Director | 6
BR0002 | COMMON | Survey | Offshore survey campaign planning and permits | 5 | 20 | 16 | BR0001 | FS | Survey Manager | 8 | Workboat
BR0003 | COMMON | Engineering | Design basis and engineering register approval | 10 | 30 | 21 | BR0001 | FS | Engineering Manager | 7
BR0004 | COMMON | Marine | Marine spread capability audit and charter strategy | 15 | 45 | 31 | BR0001 | FS | Marine Manager | 4
BR0005 | ICW-ICG UD | Survey | Site survey and as-built interface verification | 20 | 43 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0006 | ICW-ICG UD | Engineering | Structural assessment / detailed engineering / AFC | 44 | 99 | 56 | BR0005 | FS | Engineering Lead | 6
BR0007 | ICW-ICG UD | Procurement | Material requisition, vendor review and steel receipt | 76 | 141 | 66 | BR0006 | FS | Procurement Lead | 3
BR0008 | ICW-ICG UD | Fabrication | Fabricate / weld / inspect / coat assemblies | 125 | 205 | 81 | BR0007 | FS | Fabrication Lead | 18
BR0009 | ICW-ICG UD | Marine | Weigh, COG, lifting, seafastening and marine approval | 190 | 231 | 42 | BR0008 | FS | Marine Engineer | 5
BR0010 | ICW-ICG UD | Offshore | Offshore mobilisation, access and enabling works | 218 | 246 | 29 | BR0009 | FS | Offshore Manager | 20 | Accommodation barge
BR0011 | ICW-ICG UD | Offshore | Install bridge / strengthening assemblies | 242 | 278 | 37 | BR0010 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0012 | ICW-ICG UD | Completion | Inspection, punch clearance and turnover dossier | 280 | 298 | 19 | BR0011 | FS | QAQC Lead | 6
BR0013 | ICW-ICG LD | Survey | Site survey and as-built interface verification | 26 | 49 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0014 | ICW-ICG LD | Engineering | Structural assessment / detailed engineering / AFC | 50 | 105 | 56 | BR0013 | FS | Engineering Lead | 6
BR0015 | ICW-ICG LD | Procurement | Material requisition, vendor review and steel receipt | 82 | 147 | 66 | BR0014 | FS | Procurement Lead | 3
BR0016 | ICW-ICG LD | Fabrication | Fabricate / weld / inspect / coat assemblies | 131 | 211 | 81 | BR0015 | FS | Fabrication Lead | 18
BR0017 | ICW-ICG LD | Marine | Weigh, COG, lifting, seafastening and marine approval | 196 | 237 | 42 | BR0016 | FS | Marine Engineer | 5
BR0018 | ICW-ICG LD | Offshore | Offshore mobilisation, access and enabling works | 224 | 252 | 29 | BR0017 | FS | Offshore Manager | 20 | Accommodation barge
BR0019 | ICW-ICG LD | Offshore | Install bridge / strengthening assemblies | 248 | 284 | 37 | BR0018 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0020 | ICW-ICG LD | Completion | Inspection, punch clearance and turnover dossier | 286 | 304 | 19 | BR0019 | FS | QAQC Lead | 6
BR0021 | ICG-ICP UD | Survey | Site survey and as-built interface verification | 32 | 55 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0022 | ICG-ICP UD | Engineering | Structural assessment / detailed engineering / AFC | 56 | 111 | 56 | BR0021 | FS | Engineering Lead | 6
BR0023 | ICG-ICP UD | Procurement | Material requisition, vendor review and steel receipt | 88 | 153 | 66 | BR0022 | FS | Procurement Lead | 3
BR0024 | ICG-ICP UD | Fabrication | Fabricate / weld / inspect / coat assemblies | 137 | 217 | 81 | BR0023 | FS | Fabrication Lead | 18
BR0025 | ICG-ICP UD | Marine | Weigh, COG, lifting, seafastening and marine approval | 202 | 243 | 42 | BR0024 | FS | Marine Engineer | 5
BR0026 | ICG-ICP UD | Offshore | Offshore mobilisation, access and enabling works | 230 | 258 | 29 | BR0025 | FS | Offshore Manager | 20 | Accommodation barge
BR0027 | ICG-ICP UD | Offshore | Install bridge / strengthening assemblies | 254 | 290 | 37 | BR0026 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0028 | ICG-ICP UD | Completion | Inspection, punch clearance and turnover dossier | 292 | 310 | 19 | BR0027 | FS | QAQC Lead | 6
BR0029 | ICG-ICP LD | Survey | Site survey and as-built interface verification | 38 | 61 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0030 | ICG-ICP LD | Engineering | Structural assessment / detailed engineering / AFC | 62 | 117 | 56 | BR0029 | FS | Engineering Lead | 6
BR0031 | ICG-ICP LD | Procurement | Material requisition, vendor review and steel receipt | 94 | 159 | 66 | BR0030 | FS | Procurement Lead | 3
BR0032 | ICG-ICP LD | Fabrication | Fabricate / weld / inspect / coat assemblies | 143 | 223 | 81 | BR0031 | FS | Fabrication Lead | 18
BR0033 | ICG-ICP LD | Marine | Weigh, COG, lifting, seafastening and marine approval | 208 | 249 | 42 | BR0032 | FS | Marine Engineer | 5
BR0034 | ICG-ICP LD | Offshore | Offshore mobilisation, access and enabling works | 236 | 264 | 29 | BR0033 | FS | Offshore Manager | 20 | Accommodation barge
BR0035 | ICG-ICP LD | Offshore | Install bridge / strengthening assemblies | 260 | 296 | 37 | BR0034 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0036 | ICG-ICP LD | Completion | Inspection, punch clearance and turnover dossier | 298 | 316 | 19 | BR0035 | FS | QAQC Lead | 6
BR0037 | BHS-SLQ | Survey | Site survey and as-built interface verification | 44 | 67 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0038 | BHS-SLQ | Engineering | Structural assessment / detailed engineering / AFC | 68 | 123 | 56 | BR0037 | FS | Engineering Lead | 6
BR0039 | BHS-SLQ | Procurement | Material requisition, vendor review and steel receipt | 100 | 165 | 66 | BR0038 | FS | Procurement Lead | 3
BR0040 | BHS-SLQ | Fabrication | Fabricate / weld / inspect / coat assemblies | 149 | 229 | 81 | BR0039 | FS | Fabrication Lead | 18
BR0041 | BHS-SLQ | Marine | Weigh, COG, lifting, seafastening and marine approval | 214 | 255 | 42 | BR0040 | FS | Marine Engineer | 5
BR0042 | BHS-SLQ | Offshore | Offshore mobilisation, access and enabling works | 242 | 270 | 29 | BR0041 | FS | Offshore Manager | 20 | Accommodation barge
BR0043 | BHS-SLQ | Offshore | Install bridge / strengthening assemblies | 266 | 302 | 37 | BR0042 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0044 | BHS-SLQ | Offshore | Transfer services, test and obtain ONGC acceptance | 303 | 326 | 24 | BR0043 | FS | Interface Manager | 16
BR0045 | BHS-SLQ | Offshore | Engineered demolition of existing bridge | 327 | 351 | 25 | BR0044 | FS | Construction Manager | 20 | Crane vessel (verify)
BR0046 | BHS-SLQ | Completion | Inspection, punch clearance and turnover dossier | 304 | 322 | 19 | BR0045 | FS | QAQC Lead | 6
BR0047 | SLQ-WIS | Survey | Site survey and as-built interface verification | 50 | 73 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0048 | SLQ-WIS | Engineering | Structural assessment / detailed engineering / AFC | 74 | 129 | 56 | BR0047 | FS | Engineering Lead | 6
BR0049 | SLQ-WIS | Procurement | Material requisition, vendor review and steel receipt | 106 | 171 | 66 | BR0048 | FS | Procurement Lead | 3
BR0050 | SLQ-WIS | Fabrication | Fabricate / weld / inspect / coat assemblies | 155 | 235 | 81 | BR0049 | FS | Fabrication Lead | 18
BR0051 | SLQ-WIS | Marine | Weigh, COG, lifting, seafastening and marine approval | 220 | 261 | 42 | BR0050 | FS | Marine Engineer | 5
BR0052 | SLQ-WIS | Offshore | Offshore mobilisation, access and enabling works | 248 | 276 | 29 | BR0051 | FS | Offshore Manager | 20 | Accommodation barge
BR0053 | SLQ-WIS | Offshore | Install bridge / strengthening assemblies | 272 | 308 | 37 | BR0052 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0054 | SLQ-WIS | Completion | Inspection, punch clearance and turnover dossier | 310 | 328 | 19 | BR0053 | FS | QAQC Lead | 6
BR0055 | NQO-NQD | Survey | Site survey and as-built interface verification | 56 | 79 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0056 | NQO-NQD | Engineering | Structural assessment / detailed engineering / AFC | 80 | 135 | 56 | BR0055 | FS | Engineering Lead | 6
BR0057 | NQO-NQD | Procurement | Material requisition, vendor review and steel receipt | 112 | 177 | 66 | BR0056 | FS | Procurement Lead | 3
BR0058 | NQO-NQD | Fabrication | Fabricate / weld / inspect / coat assemblies | 161 | 241 | 81 | BR0057 | FS | Fabrication Lead | 18
BR0059 | NQO-NQD | Marine | Weigh, COG, lifting, seafastening and marine approval | 226 | 267 | 42 | BR0058 | FS | Marine Engineer | 5
BR0060 | NQO-NQD | Offshore | Offshore mobilisation, access and enabling works | 254 | 282 | 29 | BR0059 | FS | Offshore Manager | 20 | Accommodation barge
BR0061 | NQO-NQD | Offshore | Install bridge / strengthening assemblies | 278 | 314 | 37 | BR0060 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0062 | NQO-NQD | Completion | Inspection, punch clearance and turnover dossier | 316 | 334 | 19 | BR0061 | FS | QAQC Lead | 6
BR0063 | WIN-NC | Survey | Site survey and as-built interface verification | 62 | 85 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0064 | WIN-NC | Engineering | Structural assessment / detailed engineering / AFC | 86 | 141 | 56 | BR0063 | FS | Engineering Lead | 6
BR0065 | WIN-NC | Procurement | Material requisition, vendor review and steel receipt | 118 | 183 | 66 | BR0064 | FS | Procurement Lead | 3
BR0066 | WIN-NC | Fabrication | Fabricate / weld / inspect / coat assemblies | 167 | 247 | 81 | BR0065 | FS | Fabrication Lead | 18
BR0067 | WIN-NC | Marine | Weigh, COG, lifting, seafastening and marine approval | 232 | 273 | 42 | BR0066 | FS | Marine Engineer | 5
BR0068 | WIN-NC | Offshore | Offshore mobilisation, access and enabling works | 260 | 288 | 29 | BR0067 | FS | Offshore Manager | 20 | Accommodation barge
BR0069 | WIN-NC | Offshore | Install bridge / strengthening assemblies | 284 | 320 | 37 | BR0068 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0070 | WIN-NC | Completion | Inspection, punch clearance and turnover dossier | 322 | 340 | 19 | BR0069 | FS | QAQC Lead | 6
BR0071 | SCA-SC1 | Survey | Site survey and as-built interface verification | 68 | 91 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0072 | SCA-SC1 | Engineering | Structural assessment / detailed engineering / AFC | 92 | 147 | 56 | BR0071 | FS | Engineering Lead | 6
BR0073 | SCA-SC1 | Procurement | Material requisition, vendor review and steel receipt | 124 | 189 | 66 | BR0072 | FS | Procurement Lead | 3
BR0074 | SCA-SC1 | Fabrication | Fabricate / weld / inspect / coat assemblies | 173 | 253 | 81 | BR0073 | FS | Fabrication Lead | 18
BR0075 | SCA-SC1 | Marine | Weigh, COG, lifting, seafastening and marine approval | 238 | 279 | 42 | BR0074 | FS | Marine Engineer | 5
BR0076 | SCA-SC1 | Offshore | Offshore mobilisation, access and enabling works | 266 | 294 | 29 | BR0075 | FS | Offshore Manager | 20 | Accommodation barge
BR0077 | SCA-SC1 | Offshore | Install bridge / strengthening assemblies | 290 | 326 | 37 | BR0076 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0078 | SCA-SC1 | Completion | Inspection, punch clearance and turnover dossier | 328 | 346 | 19 | BR0077 | FS | QAQC Lead | 6
BR0079 | SCA-SCF | Survey | Site survey and as-built interface verification | 74 | 97 | 24 | BR0002 | FS | Survey Lead | 8 | Workboat
BR0080 | SCA-SCF | Engineering | Structural assessment / detailed engineering / AFC | 98 | 153 | 56 | BR0079 | FS | Engineering Lead | 6
BR0081 | SCA-SCF | Procurement | Material requisition, vendor review and steel receipt | 130 | 195 | 66 | BR0080 | FS | Procurement Lead | 3
BR0082 | SCA-SCF | Fabrication | Fabricate / weld / inspect / coat assemblies | 179 | 259 | 81 | BR0081 | FS | Fabrication Lead | 18
BR0083 | SCA-SCF | Marine | Weigh, COG, lifting, seafastening and marine approval | 244 | 285 | 42 | BR0082 | FS | Marine Engineer | 5
BR0084 | SCA-SCF | Offshore | Offshore mobilisation, access and enabling works | 272 | 300 | 29 | BR0083 | FS | Offshore Manager | 20 | Accommodation barge
BR0085 | SCA-SCF | Offshore | Install bridge / strengthening assemblies | 296 | 332 | 37 | BR0084 | FS | Construction Manager | 26 | Crane vessel (verify)
BR0086 | SCA-SCF | Completion | Inspection, punch clearance and turnover dossier | 334 | 349 | 16 | BR0085 | FS | QAQC Lead | 6
BR0087 | COMMON | Completion | Consolidated completion and handover | 350 | 360 | 11 | BR0086 | FS | Project Director | 8

## Lift Release Gates
Package | Survey verified | Weight control | COG | Padeyes / local design | Rigging calculation | Crane radius / load chart | Marine stability | Weather criteria | Independent review | ONGC release
ICW-ICG UD | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
ICW-ICG LD | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
ICG-ICP UD | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
ICG-ICP LD | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
BHS-SLQ | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
SLQ-WIS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
NQO-NQD | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
WIN-NC | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
SCA-SC1 | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
SCA-SCF | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO

## Risks and Controls
ID | Risk | Mitigation | Owner | Status
R01 | Marine window lost | Seasonal calendar, vessel standby strategy | Marine Manager | OPEN
R02 | Existing dimensions differ | Early survey and interface freeze | Engineering Manager | OPEN
R03 | BHS-SLQ services affected | New bridge + tested transfer before demolition | Construction Manager | OPEN
R04 | Heavy lift infeasible | Segmentation and certified vessel feasibility | Marine Manager | OPEN
R05 | Shared yard bottleneck | Resource leveling and dual-yard assessment | Fabrication Manager | OPEN
R06 | Lump-sum cost growth | Variation register and forecast at completion | Commercial Manager | OPEN

## Source and Limitations
Item | Status / source
Bridge quantities | ONGC uploaded MTO summary, preliminary and subject to survey
87 activity network | Stage-3 user project CSV; not validated CPM
Shivansh fleet | Official company website; suitability not independently verified
Marine guidance | IMCA Guidelines for lifting operations, IMCA M 187 / LR 006
Scheduling | Oracle Primavera P6 relationship and resource leveling documentation
Project start | Not provided; no actual calendar dates claimed
Commercial rates | Unknown, intentionally blank
Productivity | Unknown, intentionally blank
Heavy lift weights / COG | Unknown, require engineered calculation and verification
Safety | No field execution without approved engineered procedures and ONGC permits