## SHIVANSH ONGC Offshore Bridges
ID | Name | Duration | Start | Finish | % Complete
1 | ICW-ICG-LD-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
2 | ICW-ICG-LD-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
3 | ICW-ICG-LD-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
4 | ICW-ICG-LD-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
5 | ICW-ICG-LD-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
6 | ICW-ICG-LD-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
7 | ICW-ICG-LD-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
8 | ICW-ICG-LD-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
9 | ICW-ICG-LD-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
10 | ICW-ICG-LD-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
11 | ICW-ICG-LD-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
12 | ICW-ICG-LD-12 ¦ Module weight COG and loadout engineering | 73d | 11/2/26 | 2/10/27 | 0.0
13 | ICW-ICG-LD-13 ¦ Cargo manifest and shore base transfer | 41d | 2/11/27 | 4/8/27 | 0.0
14 | ICW-ICG-LD-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
15 | ICW-ICG-LD-15 ¦ Marine mobilisation and readiness | 41d | 3/9/27 | 5/4/27 | 0.0
16 | ICW-ICG-LD-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
17 | ICW-ICG-LD-18 ¦ Structural fit-up or landing | 91d | 2/23/27 | 6/29/27 | 0.0
18 | ICW-ICG-LD-19 ¦ Connection welding and bolting | 91d | 6/30/27 | 11/3/27 | 0.0
19 | ICW-ICG-LD-20 ¦ Inspection and coating restoration | 91d | 11/4/27 | 3/9/28 | 0.0
20 | ICW-ICG-LD-21 ¦ Punch closure and dossier | 86d | 11/2/26 | 3/1/27 | 0.0
21 | ICW-ICG-LD-22 ¦ Client acceptance and final handover | 51d | 3/2/27 | 5/11/27 | 0.0
22 | ICG-ICP-LD-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
23 | ICG-ICP-LD-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
24 | ICG-ICP-LD-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
25 | ICG-ICP-LD-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
26 | ICG-ICP-LD-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
27 | ICG-ICP-LD-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
28 | ICG-ICP-LD-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
29 | ICG-ICP-LD-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
30 | ICG-ICP-LD-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
31 | ICG-ICP-LD-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
32 | ICG-ICP-LD-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
33 | ICG-ICP-LD-12 ¦ Module weight COG and loadout engineering | 73d | 11/2/26 | 2/10/27 | 0.0
34 | ICG-ICP-LD-13 ¦ Cargo manifest and shore base transfer | 41d | 2/11/27 | 4/8/27 | 0.0
35 | ICG-ICP-LD-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
36 | ICG-ICP-LD-15 ¦ Marine mobilisation and readiness | 41d | 3/9/27 | 5/4/27 | 0.0
37 | ICG-ICP-LD-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
38 | ICG-ICP-LD-18 ¦ Structural fit-up or landing | 91d | 2/23/27 | 6/29/27 | 0.0
39 | ICG-ICP-LD-19 ¦ Connection welding and bolting | 91d | 6/30/27 | 11/3/27 | 0.0
40 | ICG-ICP-LD-20 ¦ Inspection and coating restoration | 91d | 11/4/27 | 3/9/28 | 0.0
41 | ICG-ICP-LD-21 ¦ Punch closure and dossier | 86d | 11/2/26 | 3/1/27 | 0.0
42 | ICG-ICP-LD-22 ¦ Client acceptance and final handover | 28d | 3/2/27 | 4/8/27 | 0.0
43 | BHS-SLQ-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
44 | BHS-SLQ-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
45 | BHS-SLQ-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
46 | BHS-SLQ-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
47 | BHS-SLQ-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
48 | BHS-SLQ-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
49 | BHS-SLQ-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
50 | BHS-SLQ-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
51 | BHS-SLQ-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
52 | BHS-SLQ-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
53 | BHS-SLQ-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
54 | BHS-SLQ-12 ¦ Module weight COG and loadout engineering | 73d | 11/2/26 | 2/10/27 | 0.0
55 | BHS-SLQ-13 ¦ Cargo manifest and shore base transfer | 41d | 2/11/27 | 4/8/27 | 0.0
56 | BHS-SLQ-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
57 | BHS-SLQ-15 ¦ Marine mobilisation and readiness | 41d | 3/9/27 | 5/4/27 | 0.0
58 | BHS-SLQ-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
59 | BHS-SLQ-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
60 | BHS-SLQ-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
61 | BHS-SLQ-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
62 | BHS-SLQ-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
63 | BHS-SLQ-21 ¦ Punch closure and dossier | 61d | 11/2/26 | 1/25/27 | 0.0
64 | BHS-SLQ-22 ¦ Client acceptance and final handover | 11d | 1/26/27 | 2/9/27 | 0.0
65 | BHS-SLQ-SP64 ¦ Operational isolation and service transfer | 28d | 11/2/26 | 12/9/26 | 0.0
66 | BHS-SLQ-SP65 ¦ Engineered demolition and removal | 31d | 11/2/26 | 12/14/26 | 0.0
67 | BHS-SLQ-SP66 ¦ Backload and disposal | 36d | 11/2/26 | 12/21/26 | 0.0
68 | ICW-ICG-UD-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
69 | ICW-ICG-UD-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
70 | ICW-ICG-UD-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
71 | ICW-ICG-UD-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
72 | ICW-ICG-UD-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
73 | ICW-ICG-UD-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
74 | ICW-ICG-UD-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
75 | ICW-ICG-UD-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
76 | ICW-ICG-UD-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
77 | ICW-ICG-UD-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
78 | ICW-ICG-UD-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
79 | ICW-ICG-UD-13 ¦ Cargo manifest and shore base transfer | 41d | 11/2/26 | 12/28/26 | 0.0
80 | ICW-ICG-UD-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
81 | ICW-ICG-UD-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
82 | ICW-ICG-UD-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
83 | ICW-ICG-UD-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
84 | ICW-ICG-UD-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
85 | ICW-ICG-UD-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
86 | ICW-ICG-UD-21 ¦ Punch closure and dossier | 86d | 11/2/26 | 3/1/27 | 0.0
87 | ICW-ICG-UD-22 ¦ Client acceptance and final handover | 51d | 3/2/27 | 5/11/27 | 0.0
88 | ICG-ICP-UD-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
89 | ICG-ICP-UD-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
90 | ICG-ICP-UD-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
91 | ICG-ICP-UD-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
92 | ICG-ICP-UD-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
93 | ICG-ICP-UD-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
94 | ICG-ICP-UD-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
95 | ICG-ICP-UD-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
96 | ICG-ICP-UD-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
97 | ICG-ICP-UD-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
98 | ICG-ICP-UD-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
99 | ICG-ICP-UD-13 ¦ Cargo manifest and shore base transfer | 41d | 11/2/26 | 12/28/26 | 0.0
100 | ICG-ICP-UD-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
101 | ICG-ICP-UD-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
102 | ICG-ICP-UD-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
103 | ICG-ICP-UD-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
104 | ICG-ICP-UD-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
105 | ICG-ICP-UD-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
106 | ICG-ICP-UD-21 ¦ Punch closure and dossier | 86d | 11/2/26 | 3/1/27 | 0.0
107 | ICG-ICP-UD-22 ¦ Client acceptance and final handover | 44d | 3/2/27 | 4/30/27 | 0.0
108 | SLQ-WIS-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
109 | SLQ-WIS-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
110 | SLQ-WIS-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
111 | SLQ-WIS-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
112 | SLQ-WIS-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
113 | SLQ-WIS-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
114 | SLQ-WIS-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
115 | SLQ-WIS-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
116 | SLQ-WIS-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
117 | SLQ-WIS-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
118 | SLQ-WIS-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
119 | SLQ-WIS-13 ¦ Cargo manifest and shore base transfer | 41d | 11/2/26 | 12/28/26 | 0.0
120 | SLQ-WIS-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
121 | SLQ-WIS-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
122 | SLQ-WIS-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
123 | SLQ-WIS-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
124 | SLQ-WIS-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
125 | SLQ-WIS-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
126 | SLQ-WIS-21 ¦ Punch closure and dossier | 86d | 11/2/26 | 3/1/27 | 0.0
127 | SLQ-WIS-22 ¦ Client acceptance and final handover | 32d | 3/2/27 | 4/14/27 | 0.0
128 | NQO-NQD-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
129 | NQO-NQD-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
130 | NQO-NQD-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
131 | NQO-NQD-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
132 | NQO-NQD-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
133 | NQO-NQD-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
134 | NQO-NQD-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
135 | NQO-NQD-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
136 | NQO-NQD-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
137 | NQO-NQD-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
138 | NQO-NQD-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
139 | NQO-NQD-13 ¦ Cargo manifest and shore base transfer | 41d | 11/2/26 | 12/28/26 | 0.0
140 | NQO-NQD-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
141 | NQO-NQD-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
142 | NQO-NQD-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
143 | NQO-NQD-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
144 | NQO-NQD-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
145 | NQO-NQD-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
146 | NQO-NQD-21 ¦ Punch closure and dossier | 85d | 11/2/26 | 2/26/27 | 0.0
147 | NQO-NQD-22 ¦ Client acceptance and final handover | 20d | 3/1/27 | 3/26/27 | 0.0
148 | WIN-NC-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
149 | WIN-NC-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
150 | WIN-NC-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
151 | WIN-NC-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
152 | WIN-NC-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
153 | WIN-NC-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
154 | WIN-NC-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
155 | WIN-NC-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
156 | WIN-NC-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
157 | WIN-NC-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
158 | WIN-NC-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
159 | WIN-NC-13 ¦ Cargo manifest and shore base transfer | 41d | 11/2/26 | 12/28/26 | 0.0
160 | WIN-NC-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
161 | WIN-NC-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
162 | WIN-NC-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
163 | WIN-NC-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
164 | WIN-NC-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
165 | WIN-NC-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
166 | WIN-NC-21 ¦ Punch closure and dossier | 73d | 11/2/26 | 2/10/27 | 0.0
167 | WIN-NC-22 ¦ Client acceptance and final handover | 11d | 2/11/27 | 2/25/27 | 0.0
168 | SCA-SC1-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
169 | SCA-SC1-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
170 | SCA-SC1-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
171 | SCA-SC1-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
172 | SCA-SC1-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
173 | SCA-SC1-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
174 | SCA-SC1-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
175 | SCA-SC1-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
176 | SCA-SC1-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
177 | SCA-SC1-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
178 | SCA-SC1-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
179 | SCA-SC1-13 ¦ Cargo manifest and shore base transfer | 41d | 11/2/26 | 12/28/26 | 0.0
180 | SCA-SC1-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
181 | SCA-SC1-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
182 | SCA-SC1-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
183 | SCA-SC1-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
184 | SCA-SC1-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
185 | SCA-SC1-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
186 | SCA-SC1-21 ¦ Punch closure and dossier | 61d | 11/2/26 | 1/25/27 | 0.0
187 | SCA-SC1-22 ¦ Client acceptance and final handover | 11d | 1/26/27 | 2/9/27 | 0.0
188 | SCA-SCF-01 ¦ Existing-condition survey | 28d | 11/2/26 | 12/9/26 | 0.0
189 | SCA-SCF-02 ¦ Design basis and interface verification | 24d | 12/10/26 | 1/12/27 | 0.0
190 | SCA-SCF-03 ¦ Detailed structural and temporary works engineering | 65d | 1/13/27 | 4/13/27 | 0.0
191 | SCA-SCF-04 ¦ Fabrication drawing release | 58d | 4/14/27 | 7/2/27 | 0.0
192 | SCA-SCF-05 ¦ Material requisitions and vendor approval | 28d | 11/2/26 | 12/9/26 | 0.0
193 | SCA-SCF-06 ¦ Steel purchasing and delivery | 63d | 12/10/26 | 3/8/27 | 0.0
194 | SCA-SCF-07 ¦ Cutting and material preparation | 31d | 11/2/26 | 12/14/26 | 0.0
195 | SCA-SCF-08 ¦ Assembly and fit-up | 46d | 12/15/26 | 2/16/27 | 0.0
196 | SCA-SCF-09 ¦ Shop welding | 46d | 2/17/27 | 4/21/27 | 0.0
197 | SCA-SCF-10 ¦ NDT and dimensional acceptance | 38d | 11/2/26 | 12/23/26 | 0.0
198 | SCA-SCF-11 ¦ Blast, coat and preserve | 31d | 12/24/26 | 2/4/27 | 0.0
199 | SCA-SCF-13 ¦ Cargo manifest and shore base transfer | 41d | 11/2/26 | 12/28/26 | 0.0
200 | SCA-SCF-14 ¦ Vessel technical selection and assurance | 91d | 11/2/26 | 3/8/27 | 0.0
201 | SCA-SCF-16 ¦ Access and permit readiness | 81d | 11/2/26 | 2/22/27 | 0.0
202 | SCA-SCF-17 ¦ Temporary access and works | 91d | 2/23/27 | 6/29/27 | 0.0
203 | SCA-SCF-18 ¦ Structural fit-up or landing | 91d | 6/30/27 | 11/3/27 | 0.0
204 | SCA-SCF-19 ¦ Connection welding and bolting | 91d | 11/4/27 | 3/9/28 | 0.0
205 | SCA-SCF-20 ¦ Inspection and coating restoration | 91d | 3/10/28 | 7/14/28 | 0.0
206 | SCA-SCF-21 ¦ Punch closure and dossier | 49d | 11/2/26 | 1/7/27 | 0.0
207 | SCA-SCF-22 ¦ Client acceptance and final handover | 11d | 1/8/27 | 1/22/27 | 0.0